## Slide 1: Status report for FS_EnergySys Phase 2
Konstantinos Samdanis (Lenovo)
Zhuoyi Chen (China Telecom)

## Slide 2: FS_EnergySys_Ph2 Status at SA2#171
  Progress – 3 pCRs Agreed
  Approved 3 contributions for each agreed principle related to each KI
  Approved 1 LS to SA5 related to the support of renewable energy
  Impacts and dependencies on other WGs
  Dependency on SA5 related to renewable energy and interaction with CHF.
  Contentious issues
  Support of new measurements including renewable energy
  Support of energy consumption when an NF handle no traffic
  Support of interaction with CHF for keeping statistics
  Support of Energy Saving states and related schedule when selection and NF from NRF
  Support Energy Information for N3IWFs and TNGF profiles in NRF.
Next steps:
  Try to update principles and conclusions based on consensus.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070058 | New SID on Energy Efficiency and Energy Saving Phase 2 | FS_EnergySys_Ph2 | 12/12/2025 | 85% | SP-250417 | 95% | 

## Slide 3: FS_EnergySys_Ph2 Work Plan
Meeting | Date | Planned TUs | Actual Used TUs | Action plan
SA2#168 | Apr. 2025 | 1 | 1 | TR skeleton, scope, Terms, Architectural assumptions & Requirements Key Issues for all WTs.
SA2#169 | May 2025 | 2 | 2 | Key Issue updates (if necessary), New solutions for approved Key Issues.
SA2#170 | Aug. 2025 | 1 | 1 | New solutions and solution updates. Last meeting for new solutions.
SA#109 | Sep. 2025 | - | - | For information
SA2#171 | Oct. 2025 | 1 | 1 | Solution updates. Evaluation and conclusion.
SA2#172 | Nov.2025 | 1 |  | Conclusion.
SA#110 | Dec 2025 | - | - | For Approval
 | Total | 6 | 5 |