## Slide 1: FS_5GSAT_Ph4_ARC Status Report Study on integration of satellite components in the 5G architecture Phase 4
Hucheng Wang (CATT),
Relja Djapic (TNO)

## Slide 2
FS_5GSAT_Ph4_ARC status after SA#109
Progress since SA#109
  In SA2#171 meeting, 14 pCRs are approved, including:
    8 pCRs for KI#1 (Support of IMS voice call over NB-IoT NTN via GEO satellite connecting to EPC) are approved, including 7 pCRs for new/update solutions and 1 pCR for Interim Agreement;
    5 pCRs for KI#3 (Support of IMS emergency call over NB-IoT NTN via GEO satellite connecting to EPC) are approved;
    1 pCR for KI#4 (Location service for IMS emergency call and regulatory services over NB-IoT NTN) is approved.
  In SA2#172 meeting, 5 pCRs are approved, including:
    5 pCRs for KI#1 are approved, including 1 pCR for update solution and 4 pCRs for Conclusions;
  RAN impacts and dependencies
  Yes, KI#1 and KI#3 have RAN impact, KI#2 may have dependency on RAN conclusion.
Contentious issues
  KI#2: Whether and how to support text based and/or binary based IMS signaling during call setup procedure?
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070011 | Study on Integration of satellite components in the 5G architecture Phase 4 | FS_5GSAT_Ph4_ARC | 12/12/2025 | 60 | SP-250400 | 85 | In progress
Notes: Conclusions for Key Issue #1：
S2-2510861
- The IMS signalling shall be transported over the NB-IoT (GEO) user plane, i.e. using DRB and S1-U；

## Slide 3
FS_5GSAT_Ph4_ARC status after SA#109
Next Steps (for SA2#173)
  One TU for completing the study
  One TU for Normative work
    Start normative work for KI#1

## Slide 4
Progress since SA2#172
  5 pCRs for KI#1(Support of IMS voice call over NB-IoT NTN via GEO satellite connecting to EPC) are approved, including 1 pCR for update solution and 4 pCRs for Conclusions;
  RAN impacts and dependencies
  Yes, KI#1 and KI#3 have RAN impact, KI#2 may have dependency on RAN conclusion.
Contentious issues
  KI#2: Whether and how to support text based and/or binary based IMS signaling during call setup procedure?
FS_5GSAT_Ph4_ARC status after SA2#172
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070011 | Study on Integration of satellite components in the 5G architecture Phase 4 | FS_5GSAT_Ph4_ARC | 12/12/2025 | 80 | SP-250400 | 85 | In progress

## Slide 5
Next Steps (for SA2#173)
  One TU for completing the study
  One TU for Normative work
    Start normative work for KI#1
FS_5GSAT_Ph4_ARC status after SA2#172

## Slide 6
FS_5GSAT_Ph4_ARCH status after SA2#172
Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#168 | Apr. 2025 | 1 | 1 | 1 TU for TR scope, TR skeleton, Assumption, KI definition. Start solution discussion
SA2#169 | May. 2025 | 2 | 2 | Last chance for KI update, continue solution discussion Conclude KI#5
SA2#170 | Aug. 2025 | 1.5 | 1.5 | continue solution discussion
SA2#171 | Qct. 2025 | 1 | 1 | Last meeting for new solution (solutions for KI#3 and 4 focusing on general aspects will be prioritized) Solution evaluation and try to conclude topics with common understanding
SA2#172 | Nov. 2025 | 1 | 1 | Last meeting for solution update, KI#1 and 2 will be prioritized Conclude the study as much as possible (feedback from RAN WGs, SA4, CT1, SA3, SA1 need to be considered) WI is approved in this meeting.
SA2#173 | Feb. 2026 | 2 |  | 1 TU for concluding the study: KI#1-5, some unofficial CC may be needed to converge the discussion. 1 TU for normative work: KI#1
SA2#174 | Apr. 2026 | 2 |  | 
SA2#175 | May. 2026 | 1.5 |  | 
SA2#176 | Aug. 2026 | 1 |  | 
Total TU’s |  | 13 | 6.5 |