## Slide 1: Status Report of FS_Sensing_ARC
Jianning LIU (Xiaomi), Rapporteur David Gutierrez (Apple), Rapporteur

## Slide 2: Rel-20 FS_Sensing_ARC status in SA2#172 (1/2)
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070012 | Study on Stage 2 for Integrated Sensing and Communication | FS_Sensing_ARC | Dec/2025 | 80% | SP-250833 | 93% | 
  Progress since SA2#172
  116 papers were submitted, including 6 pCRs agreed, 1 LS OUT agreed, 1 LS OUT Noted, 20 pCRs not treated, 88 pCRs merged.
    Conclusion for KI#2/3/4/5/6 agreed
    Conclusion for KI#1 agreed but with one open issue “Whether Sensing control signalling exchanged between SE and SF directly without AMF involvement or with AMF involvement”
    1 LS OUT to RAN WGs agreed
    1 LS OUT to SA3 Noted
  The new WID for Sensing was Noted due to the open issue of KI#1.
  1 TU used in this meeting (total 7 TUs used) and no TU for study left.
Notes: KI#1 : 11 agreed, 1 approved, 2 merged, 3 postponed
KI#2: 12 agreed, 0 approved, 5 merged, 1 postponed
KI#3: 2 agreed, 1 merged
KI#4: 1 agreed, 0 merged
Total: 26 agreed, 1 approved, 8 merged, 4 postponed

## Slide 3: Rel-20 FS_Sensing_ARC status in SA2#172 (2/2)
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070012 | Study on Stage 2 for Integrated Sensing and Communication | FS_Sensing_ARC | Dec/2025 | 80% | SP-250833 | 93% | 
  Impacts and dependence with other WGs:
  Impact on SA3: Privacy protection and other security aspects will be coordinated with SA3, and the related impact to architecture enhancement will be based on SA3 conclusion.
  Impact on SA5: Charging and OAM aspects will be coordinated with SA5, and the related impact to architecture enhancement will be based on SA5 conclusion.
  Dependency with RAN WGs: SE selection, Sensing data collection, and Sensing parameters provided from SF to SE will be coordinated with RAN WGs during the normative work
  Controversial issues
  Whether Sensing control signalling is exchanged between SE and SF directly without AMF involvement, or with AMF involvement, is FFS and will be resolved in the next meeting.
  Next Steps
  Complete conclusion for KI#1 (will use 0.5 TU from normative TU)
  Approval for WID.
  Start the normative work.
Notes: KI#1 : 11 agreed, 1 approved, 2 merged, 3 postponed
KI#2: 12 agreed, 0 approved, 5 merged, 1 postponed
KI#3: 2 agreed, 1 merged
KI#4: 1 agreed, 0 merged
Total: 26 agreed, 1 approved, 8 merged, 4 postponed

## Slide 4: Substantial Issues
Issue # | Description | Identified in | Resolution | Resolved in

## Slide 5: Work plan for Rel-20 FS_Sensing_ARC
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #168 | April 2025 | 1 | 1 | TR 23.700-14 Skeleton/scope, Terms, Arch Assumptions and requirements, key issues #1/2/3/4/5/6.
SA2 #169 | May 2025 | 2 | 2 | Key issues updates if need New solutions (only common aspect)
SA2#170 | Aug 2025 | 2 | 2 | New solutions (KI#4, KI#5, KI#6, in priority), (KI#1, KI#2, KI#3) Solution updates Interim agreements if any (7.1 interim principles, 7.2 topics for further consideration)
SA2 #171 | Oct 2025 | 1 | 1 | Solution updates interim agreements and conclusion
SA2 #172 | Nov 2025 | 1 | 1 | Complete conclusion LSouts to RAN3 and SA3. WID discussion/approval
SA2#173 | Feb 2026 | 1.5 |  | Complete the conclusion of KI#1 (0.5 TU) WID approval Normative work (1 TU)
SA2#174 | April 2026 | 1.5 |  | Normative
SA2#175 | May 2026 | 1.5 |  | Normative
SA2#176 | Aug 2026 | 1 |  | Normative
Total: 12.5 TUs
  7 TUs for Study Work
  5.5 TUs for Normative Work
(after TSG#108)

## Slide 6: Annex

## Slide 7: Rel-20 FS_Sensing_ARC status in SA2#168 (1/2)
  Progress since SA2#168
  TR 23.700-14 v0.1.0 is available;
  90 papers were submitted (88 pCR, 2 DP): 11 pCR agreed, 66 pCR merged, 13 papers not handled (including 5 new solutions).
  11 agreed pCR includes:
    TR skeleton and scope
    Terms and definitions
    Architectural assumptions
    Architectural requirements
    KI#1: System Architecture to Support Sensing
    KI#2: Authorization and Revocation to Support Sensing Service
    KI#3: Sensing entity and Sensing Function discovery and (re-)selection
    KI#4: Sensing data and the associated information collection and transport
    KI#5: Sensing result exposure
    KI#6: Configuration parameter provisioning of sensing entities.
  1 TU was used.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070012 | Study on Stage 2 for Integrated Sensing and Communication | FS_Sensing_ARC | Dec/2025 | 0% | SP-250401 | 15% | 
Notes: KI#1 : 11 agreed, 1 approved, 2 merged, 3 postponed
KI#2: 12 agreed, 0 approved, 5 merged, 1 postponed
KI#3: 2 agreed, 1 merged
KI#4: 1 agreed, 0 merged
Total: 26 agreed, 1 approved, 8 merged, 4 postponed

## Slide 8: Rel-20 FS_Sensing_ARC status in SA2#168 (2/2)
  Impacts and dependence with other WGs:
  Impact on SA3: Privacy protection and other security aspects will be coordinated with SA3, and the related impact to architecture enhancement will be based on SA3 conclusion.
  Impact on SA5: Charging and OAM aspects will be coordinated with SA5, and the related impact to architecture enhancement will be based on SA5 conclusion.
  Dependency on RAN TSG/WG: The scope of the sensing study (incl. TUs) will be further aligned in plenary TSG#108 together with RAN TSG.
  Controversial issues
  N/A
  Next Steps
  Update key issues if required
  New solutions (only common aspect)
    Any study work on Sensing in Q2 should be limited to common aspects for the study without any RAN specific or UE specific sensing modes. Any UE/RAN aspects will be aligned with RAN after TSG#108 (Guidance from SA#107, SP-250418)
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070012 | Study on Stage 2 for Integrated Sensing and Communication | FS_Sensing_ARC | Dec/2025 | 0% | SP-250401 | 15% | 
Notes: KI#1 : 11 agreed, 1 approved, 2 merged, 3 postponed
KI#2: 12 agreed, 0 approved, 5 merged, 1 postponed
KI#3: 2 agreed, 1 merged
KI#4: 1 agreed, 0 merged
Total: 26 agreed, 1 approved, 8 merged, 4 postponed

## Slide 9: Rel-20 FS_Sensing_ARC status in SA2#169 (1/2)
  Progress since SA2#169
  The revised Sensing SID was approved to fill TR number, title correction and rapporteur info.
  78 papers were submitted, including 23 pCRs approved, 1 pCRs merged, 52 pCRs not treated, 2 pCRs noted.
  23 pCR were approved including:
    For general, 1 pCR skeleton update, 1 pCR editorial correction, 1 pCR for architectural requirement approved
    For KI#1: 7 new solutions approved, 1 solutions merged, 10 solutions not treated
    For KI#2: 5 new solutions approved, 10 solutions not treated
    For KI#3: 5 new solutions approved, 10 solutions not treated
    For KI#4: 1 new solutions approved, 7 solutions not treated
    For KI#5: 1 new solutions approved, 11 solutions not treated
    For KI#6: 1 new solutions approved, 1 solutions not treated
  2 TUs were used in this meeting
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070012 | Study on Stage 2 for Integrated Sensing and Communication | FS_Sensing_ARC | Dec/2025 | 15% | SP-250401 | 35% (NOTE: the exact completion rate will be updated based on the outcome of TSG#108) | 
Notes: KI#1 : 11 agreed, 1 approved, 2 merged, 3 postponed
KI#2: 12 agreed, 0 approved, 5 merged, 1 postponed
KI#3: 2 agreed, 1 merged
KI#4: 1 agreed, 0 merged
Total: 26 agreed, 1 approved, 8 merged, 4 postponed

## Slide 10: Rel-20 FS_Sensing_ARC status in SA2#169 (2/2)
  Impacts and dependence with other WGs:
  Impact on SA3: Privacy protection and other security aspects will be coordinated with SA3, and the related impact to architecture enhancement will be based on SA3 conclusion.
  Impact on SA5: Charging and OAM aspects will be coordinated with SA5, and the related impact to architecture enhancement will be based on SA5 conclusion.
  Dependency on RAN TSG/WG: The scope of the sensing study (incl. TUs) will be further aligned in plenary TSG#108 together with RAN TSG.
  Solutions proposing exposure of sensing results to the UE need to be coordinated / checked with SA1 and SA3
  Controversial issues
  N/A
  Next Steps
  To update the contents in TR 23.700-14 if necessary, based on the study scope alignment at TGS#108
  Continue discussing solutions for all the key issues based on updated SID scope
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070012 | Study on Stage 2 for Integrated Sensing and Communication | FS_Sensing_ARC | Dec/2025 | 15% | SP-250401 | 35% (NOTE: the exact completion rate will be updated based on the outcome of TSG#108) | 
Notes: KI#1 : 11 agreed, 1 approved, 2 merged, 3 postponed
KI#2: 12 agreed, 0 approved, 5 merged, 1 postponed
KI#3: 2 agreed, 1 merged
KI#4: 1 agreed, 0 merged
Total: 26 agreed, 1 approved, 8 merged, 4 postponed

## Slide 11: FS_Sensing_ARC status after SA2#170 (1/2)
  Progress since SA2#170
  75 papers were submitted, 24 pCRs agreed, 3pCRs merged, 4 pCRs noted, 44 pCRs not treated, including:
    For general, 4 pCR approved for TR scope alignment, terms update, architectural requirement update and KI#6 update.
    For KI#4: 6 new solutions approved, 7 solutions not treated
    For KI#5: 7 new solutions approved, 3 solutions not treated
    For KI#6: 2 new solutions approved, 1 solutions not treated
    For KI#1: 1 new solutions NOTED, 6 solutions not treated
    For KI#2: 4 new solutions approved, 3 solutions not treated
    For KI#3: 1 new solutions approved, 1 new solution NOTED, 3 solutions not treated
  One LS out to SA1 on UE as Sensing Service consumer was NOTED.
  2 TUs were used in this meeting (2 TUs left for the study);
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070012 | Study on Stage 2 for Integrated Sensing and Communication | FS_Sensing_ARC | Dec/2025 | 35% | SP-250833 | 65% | 
Notes: KI#1 : 11 agreed, 1 approved, 2 merged, 3 postponed
KI#2: 12 agreed, 0 approved, 5 merged, 1 postponed
KI#3: 2 agreed, 1 merged
KI#4: 1 agreed, 0 merged
Total: 26 agreed, 1 approved, 8 merged, 4 postponed

## Slide 12: FS_Sensing_ARC status after SA2#170 (2/2)
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070012 | Study on Stage 2 for Integrated Sensing and Communication | FS_Sensing_ARC | Dec/2025 | 35% | SP-250833 | 65% | 
  Impacts and dependence with other WGs:
  Impact on SA3: Privacy protection and other security aspects will be coordinated with SA3, and the related impact to architecture enhancement will be based on SA3 conclusion.
  Impact on SA5: Charging and OAM aspects will be coordinated with SA5, and the related impact to architecture enhancement will be based on SA5 conclusion.
  Controversial issues
  N/A
  Next Steps
  Update the solutions agreed in TR 23.700-14.
  Start interim agreement and conclusion.
Notes: KI#1 : 11 agreed, 1 approved, 2 merged, 3 postponed
KI#2: 12 agreed, 0 approved, 5 merged, 1 postponed
KI#3: 2 agreed, 1 merged
KI#4: 1 agreed, 0 merged
Total: 26 agreed, 1 approved, 8 merged, 4 postponed

## Slide 13: Rel-20 FS_Sensing_ARC status in SA2#171 (1/2)
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070012 | Study on Stage 2 for Integrated Sensing and Communication | FS_Sensing_ARC | Dec/2025 | 65% | SP-250833 | 80% | 
  Progress since SA2#171
  110 papers were submitted, including 4 pCRs agreed, 1 LS OUT postponed, 52 pCRs not treated, 53 pCRs merged.
  4 pCR were agreed, including Interim agreement/conclusion for KI#1/2/3/4;
  1 TU used in this meeting (total 6 TUs used), and 1 TU left.
  Impacts and dependence with other WGs:
  Impact on SA3: Privacy protection and other security aspects will be coordinated with SA3, and the related impact to architecture enhancement will be based on SA3 conclusion.
  Impact on SA5: Charging and OAM aspects will be coordinated with SA5, and the related impact to architecture enhancement will be based on SA5 conclusion.
  Dependency with RAN WGs: determination of Sensing data collected from SE (i.e. gNB) will be coordinated with RAN WGs; Configuration parameters to SE will be coordinated with RAN WGs.
Notes: KI#1 : 11 agreed, 1 approved, 2 merged, 3 postponed
KI#2: 12 agreed, 0 approved, 5 merged, 1 postponed
KI#3: 2 agreed, 1 merged
KI#4: 1 agreed, 0 merged
Total: 26 agreed, 1 approved, 8 merged, 4 postponed

## Slide 14: Rel-20 FS_Sensing_ARC status in SA2#171 (2/2)
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1070012 | Study on Stage 2 for Integrated Sensing and Communication | FS_Sensing_ARC | Dec/2025 | 65% | SP-250833 | 80% | 
  Controversial issues
  Whether to involve AMF for delivering the Sensing control signaling and/or Sensing data between SE and SF.
  Whether to introduce one new Gateway Sensing function to support for, e.g., authorization of sensing service, discovery and selection of SF, or exposure of sensing result, etc.
  Next Steps
  Complete Conclusions for KI#1/2/3/4/5/6.
  LS OUTs to RAN WGs and SA3.
  Discussion and approval for WID if possible.
Notes: KI#1 : 11 agreed, 1 approved, 2 merged, 3 postponed
KI#2: 12 agreed, 0 approved, 5 merged, 1 postponed
KI#3: 2 agreed, 1 merged
KI#4: 1 agreed, 0 merged
Total: 26 agreed, 1 approved, 8 merged, 4 postponed