## Sheet1
WT# | Topic | Time units | Dependencies | NOTE: Covers meeting sessions during 2026 (Feb-Nov). Meeting time already consumed for the 6G study is not included. Conference calls and drafting sessions not included.
| Miscellaneous (Arch assumption, requirements, 5G features Day 1) | 2
WT#1.1 | Overall system procedures | 3
| UE-CN control signalling specific aspects | 3 |  | NOTE: Energy-efficient WT is under discussion. If approved, we estimate that 2 TUs will be required. This can be considered as part of WT1.2 as an additional topic.
WT#1.2 | SBA | 1
| Slicing | 2
| User Plane | 2
| QoS | 4
| Policy | 4
| Network exposure | 2
| Network sharing | 1
| Localized network | 2
| FWA | 1
WT#1.3 | non-3GPP | 2
WT#1.4 | Voice services | 2
| Emergency voice | 2
| Location services | 2
| Messaging services | 2
| Other essential/regulatory services | 2
WT#2 | Migration | 2
| Interworking | 4
WT#3 | #3.1: AI for 6G NW | 4
| #3.2: 6G NW for AI | 4
WT#4 | Sensing | 6
WT#5 | Data architecture | 5
WT#6 | Compute | 5
WT#7 | NTN | 3
WT#8 | IoT | 3
Cross-WT handling |  | 5
Total |  | 80