## Slide 1: Time Plan Overview for SA4#111-e
Frédéric Gabin, SA4 Chairman, Dolby Laboratories Inc., ETSI
SA4#111-e, 11-20 November 2020, Electronic Meeting.
with rapporteurs
Tdoc: S4-20xxxx

## Slide 2: Timeline
9/19
12/19
3/20
6/20
9/20
12/20
3/21
9/21
6/21
6/19
12/21
SA#84
Q2/2019
SA#85
Q3/2019
SA#86
Q4/2019
SA#87
Q1/2020
SA#88
Q2/2020
SA#89
Q3/2020
SA#90
Q4/2020
SA#91
Q1/2021
R16 stage 2
freeze
R16 stage 3 & code
freeze
R17 stage 1
freeze
R17 stage 2
freeze
R17
stage 1
~ 80%
SA#92
Q2/2021
SA Rel-17 Schedule
Rel-16 Schedule
R18
stage 1
Initial input
Rel-18
(unknown)
exceptions
start/ ongoing:
S1 normative
S2 studies
SA#93
Q3/2021
SA#94
Q4/2021
R17 stage 3
freeze
R17 code
freeze
exceptions
R18
stage 1
Freeze TBD
Shift 3+ months TBD
R18
stage 1
~ 80%
TBD

## Slide 3: SA4 calendar
Meeting 2020 | Dates | Venue and Host
SA4#111-e | 11-20 November 2020 | E-Meeting
Meetings 2021 | Dates | Venue and Host
SA4#112-e | [27 January TBD] 1 – 5 or [3-12 TBD] February 2021 | Host: MCC, Electronic meeting* Dolby, Venue: San Francisco, CA, USA
SA4#113-e | [7 TBD] 12 – 16 April 2021 | Host: MCC, Electronic meeting* [EF3], Venue: [Fully electronic?]
SA4#114-e | [19 TBD] 24 – 28 May 2021 | Host: MCC, Electronic meeting* Samsung, Venue: TBD
SA4#115 | 23 – 27 August 2021 | Host: Samsung, Venue: TBD
SA4#116 | 15 – 19 November 2021 | Host: EF3, Venue: Marbella, Spain
*Note that the e-meeting may be converted back to Face-to-face meeting if COVID-19 situation allows and a host is identified.

## Slide 4: FS_5GVideo
Question | Answer
Name of study | “Feasibility Study on 5G Video Codec Characteristics”
Work Item Description | SP-200052
Rapporteur | Thomas Stockhammer (Qualcomm)
Latest Time Plan | V0.7: S4-201391
Completion Status before SA4#111-e | 30%
Expected Completion Status after SA4#111-e | 45%
Dependencies to other work | none
Other work depending on us | none
Send for information | TR 26.955 1.0.0 for SA#91-e (March 21)
Send for approval | TR 26.955 2.0.0 for SA#92-e (June 21)
Expected normative work in Rel-17 | Unclear, but possible with the addition of new codecs

## Slide 5: FS_XRTraffic
Question | Answer
Name of study | Feasibility Study on Extensions to Typical Traffic Characteristics
Work Item Description | SP-200054
Rapporteur | Thomas Stockhammer (Qualcomm)
Latest Time Plan | V0.5: S4-201398
Completion Status before SA4#111-e | 25%
Expected Completion Status after SA4#111-e | 40%
Dependencies to other work | None
Other work depending on us | RAN1 Study: XR Evaluations for NR in RP-193241.zip
Send for information | CR 26.925 (XR) for RAN1#104-e (January 21)
Send for approval | CR 26.925 (XR) for SA#91-e (03/21) and (other) for SA#92-e (06/21)
Expected normative work in Rel-17 | Not in SA4

## Slide 6: Thank You!
Frédéric Gabin
3GPP SA4 Chairman
mail: frederic.gabin@dolby.com
phone: +33 678448575