Source:	Editor*

Title:	IVAS Permanent Document IVAS-8a: Test Plan for Selection Phase

Version:	v.0.7.4

Agenda Item:	7.5

Document History:

| v.0.1.0 | 27 August 2021 | Initial Skeleton, Example Test Designs |
| --- | --- | --- |
| v.0.1.1 | 04 November 2021 | Consolidation of references, editorial changes |
| v.0.2.0 | 19 November 2021 | Editorial corrections |
| v.0.2.1 | 8 February 2022 | Editorial corrections |
| v.0.3.0 | 22 February 2022 | Editorial corrections |
| v.0.3.1 | 5 May 2022 | Port of text from EVS-8b, conclusions from S4aA220004, inclusion of candidate laboratories from S4-211523, S4-220152 |
| v.0.4.0 | 20 May 2022 | Integration of Experiment overview template from S4-220666, editorial corrections |
| v.0.4.1 | 12 August 2022 | Integration of agreed text from S4a220005, editorial corrections |
| v.0.5.0 | 25 August 2022 | Integration of agreed text from S4-220921 |
| v.0.5.1 | 13 January 2023 | Integration in brackets agreed text from S4aA230003, S4aA230004, editorial changes |
| v.0.6.0 | 3 February 2023 | As agreed at the Jan 13 Audio SWG call |
| v.0.6.1 | 20 February 2023 | Integration of text agreed at Feb 3 Audio SWG call from S4aA230016, S4aA230018 (to put in brackets), and S4aA230019 (to put in brackets) |
| v.0.7.0 | 24 February 2023 | As agreed at the Feb 2023 SA4 #122 plenary. Integration of agreed text from s4-230245, Test Plan related remaining work from S4-230254, and edits during the meeting. |
| v.0.7.1 | 17 March 2023 | Integration of agreed text from S4aA230024, completed responsibilities, Selection Time plan skeleton, editorial changes |
| v.0.7.2 | 3 April 2023 | Integration o agreed text and proposals from S4aA230028, S4aA230030, and S4aA230032. |
| v.0.7.3 | 3 April 2023 | Integration of LL pricing indication |
| v.0.7.4 | 17 April 2023 | Integration of agreed text from S4aA230048, changes to allocation of experiments to LLs and Selection Time Plan following discussion and agreement on S4aA230036 and S4aA230052, editorial changes. |

Editor’s note: The following test was originally copied from S4-230254 for further reference. It was further edited to take into account progress achieved at and after the SA4 meeting #122:

The following remaining work was identified:

Complete various open aspects wrt sound material

Complete definition of test material, incl.

    - Speech material

    - Background material

    - Captured Music and Mixed Content Material

Define method for test item generation for the immersive conversation use-case using P.SUPPL800. This might include

    - Definition of scenes

    - Selection of method for scene composition

    - Collection of required scene data, e.g. FB stereo and spatial impulse responses – see e.g. discussion in [9]

    - Collection of corresponding background audio

Initiate the call for test material collection, e.g. for background and critical generic audio items; this might likely involve

    - setup of a legal framework on non-disclosure of the collected material

    - clearance on publicly available material

    - set up of infrastructure to collect submitted material

Add detailed list of experiments, incl.

Definition of references, anchors, CuTs

Background levels

FER

Level

Loudspeaker or headphone listening

…

Annexes A – D need to be reviewed, completed and agreed. This includes:

Sample Instructions to Subjects and Data Collection

Presentation Orders

Data to be Provided by LL

Selection Testing Timeline needs to be completed

In addition, many sections of the permanent document are populated but not formally agreed.

Introduction

This document contains the Test Plan for the Selection Phase of the Codec (IVAS).

References, Conventions, and Contacts

Permanent Documents

The following documents provide additional information on the IVAS codec development project.

| P-doc | Title |
| --- | --- |
| IVAS-1 | IVAS Codec Development Overview |
| IVAS-2 | IVAS Project Plan |
| IVAS-3 | IVAS Performance Requirements |
| IVAS-4 | EVS Design Constraints |
| IVAS-5 | Selection Rules for Selection Phase |
| IVAS-6 | Deliverables for Selection Phase |
| IVAS-7a | Processing Plan for Selection Phase |
| IVAS-7b | Processing Plan for Characterization Phase |
| IVAS-8a | Test Plan for Selection Phase |
| IVAS-8b | Test Plan for Characterization Phase |
| IVAS-9 | IVAS Usage Scenarios |

The latest version of these documents can be found in the following link.

https://www.3gpp.org/ftp/tsg_sa/WG4_CODEC/IVAS_Permanent_Documents

Reference Documents

S4-211523: MESAQIN.com and FORCE Technology - SenseLab expression of interest to participate in IVAS codec selection and characterization work

S4-220152: Interest in participation in IVAS codec selection and characterisation phase

Recommendation ITU-R BS.2051-1 (06/2017): Advanced sound system for programme production

S4-211155: On IVAS example test designs, Source: Nokia Corporation

S4-210848: IVAS MASA spatial speech quality evaluation, Source: Nokia Corporation

S4-191167: Description of the IVAS MASA C Reference Software, Source: Nokia Corporation

S4-210840: Updates to IVAS MASA C Reference Software, Source: Nokia Corporation

Recommendation ITU-T P.800 (08/1996): Methods for subjective determination of transmission quality,

Recommendation ITU-T P.811 (01/2019): Subjective test methodology for evaluating Speech oriented stereo communication systems over headphones,

S4-211151: Example designs for IVAS codec tests, Source: Dolby Laboratories Inc.

S4-210836: On reference designs for IVAS codec tests, Source: Dolby Laboratories Inc.

Recommendation ITU-R BS.1770-4 (10/2015): Algorithms to measure audio programme loudness and true-peak audio level

ITU-T Handbook of subjective testing practical procedures, 2011

S4-200158: A Reference Audio Renderer for Qualification, Source: Dolby Laboratories Inc.

S4-211160: Experience of P.800 for stereo testing, Source: Ericsson LM

S4-130155: EVS Permanent Document EVS-7a: Processing functions for qualification phase

AFsp Programs and Routines: http://www-mmsp.ece.mcgill.ca/Documents/Software/Packages/AFsp/audio/html/AFsp.html

S4aA220005: On reference designs for IVAS codec tests - Update, Source: Dolby Laboratories Inc.

S4aA220007 - DCR test experiments for FOA and HOA3 input in 7.0+4 and binaural listening setup.

F. Zotter and M. Frank, “All-Round Ambisonic Panning and Decoding,” in J. Audio Eng. Soc., Vol. 60, No. 10, 2012.

T22-SG12-220607-TD-GEN-0138!!MSW-E: Draft new ITU-T P.800-series – Supplement P.SUPPL800: ITU-T Rec. P.800 use case examples.

Recommendation ITU-R BS.1534 (10/2015): Method for the subjective assessment of intermediate quality level of audio systems.

3GPP TR 26.952: Codec for Enhanced Voice Services (EVS); Performance characterization.

S4-030821: PSS/MMS High-Rate Audio Selection Test and Processing Plan, Version 2.2

Audio File Format Specifications: WAVE, https://www-mmsp.ece.mcgill.ca/Documents/AudioFormats/WAVE/WAVE.html

AFsp Package https://www-mmsp.ece.mcgill.ca/Documents/Downloads/AFsp/

Key Acronyms

BIT		Beijing Institute of Technology

CL		Cross-check Laboratory

CuT		Codec under Test

DCR		Degradation Category Rating

DTX		Discontinuous transmission

ESDRU		Energy-based Spatial Distortion Reference Unit

EVS		Enhanced Voice Services

FB		Full Band

FE		Frame Erasure

FOA		First-Order Ambisonics

GAL		Global Analysis Laboratory

HL		Host Laboratory

HOA3		Higher-Order Ambisonics, 3rd order

IVAS		Immersive Voice and Audio Services

LKFS		Loudness, K-weighted, relative to Full Scale

LL		Listening Laboratory

MASA		Metadata-Assisted Spatial Audio

MNRU		Modulated Noise Reference Unit

MUSHRA	Multi Stimulus test with Hidden Reference and Anchor

PC		Proponent Company

SDRU		Spatial Distortion Reference Unit

SNR		Signal-to-Noise Ratio

SPL 		Sound Pressure Level

SWB		Super Wide Band

WB		Wide Band

Roles and Responsibilities

Overview of the Selection Test Process

The execution of the IVAS codec Selection subjective testing is under the responsibility of the LLs participating in the Selection Phase.

The execution of the IVAS codec Selection objective testing is under the responsibility of the PC participating in the Selection Phase.

SA4 selects and ETSI will contract the LLs to perform the subjective listening tests described in this document. SA4 selects the languages used in each experiment conducted by each LL.  SA4 further selects the HL, the CL, and the GAL to perform respective tasks defined in this document, and ETSI will contract the GAL.

[The LLs and volunteering contributors (SA4 companies) shall provide unprocessed 48 kHz sampled clean speech, background material, music and mixed content, and critical generic audio content samples to the MC. The format of the material is WAVE [25], 16-bit little endian format. For multi-track audio, the audio tracks are ordered according to Error! Reference source not found. of IVAS Processing Plan (IVAS-7a).

The material collection entity (MC) shall control that the unprocessed raw material (both artificially created and real recorded) meets the requirements defined by SA4, collect a pool of model parameters and sound materials and choose the model parameters and sound materials to be used in the experiments in a randomized blind process.]

The PC shall deliver a CuT executable to the HL and ETSI.

The CL shall perform cross-check of the HL processing.

The LLs shall insert the raw voting data into the workbook provided by the GAL and forward the workbook directly to the GAL. In addition, each LL must provide a report of experiments to SA4 no later than the document submission deadline for the selection meeting.

Allocation of Additional Roles

LLs: [Mesaqin.com, FORCE Technology [1], HEAD acoustics GmbH/IKS [2], Macquarie University]

HL: Contributors of the Public Collaboration

CL: Contributors of the Public Collaboration

MC: Contributors of the Public Collaboration

GAL: [HEAD acoustics GmbH/IKS]

Responsibilities

Many of the procedures to be followed are defined in this test plan, with further information being given in IVAS Processing Plan (IVAS-7a).

Editor’s note: Possibly integrating Annexes with laboratory tasks here if there is no particular reason for keeping it in annexes

Proponent Companies

The specific responsibilities of each PC are:

Delivery to the HL of a preliminary CuT executable

Delivery to the HL and ETSI of a final CuT executable

Interaction with the HL to cross-check the HL’s implementation of its CuT executable

Listening Laboratories

[

Requirements for the Listening Laboratories

Provide a listening environment that conforms to the requirements in [8] including:

Having a background noise level of less than NR-25.

For each listening test, use subjects that are native speakers of the tested language.

Provide a person during the training session of each test that is able to answer questions from the subjects in their native language.

Provide to SA4 the instructions for subjects in each of the languages to be tested by the LL for the Selection Testing.

Tasks for the Listening Laboratories

LLs shall record or obtain, if not otherwise available, original clean mono speech material (unprocessed 48 kHz sampled speech) for the tests allocated to them and provide it to the MC.

For any tests, LLs may record or obtain original clean mono speech or stereo/immersive material (unprocessed 48 kHz sampled signals) and provide it to the MC.

LLs shall have the option to declare their material provided to the MC as not available for use by other LLs.

Delivery to the HL of the unprocessed speech and music and mixed content material for all tests to be conducted by the LL. Speech and music and mixed content shall conform to restrictions indicated in[13].

Obtain from the HL the processed test materials for all tests to be conducted by the LL.

Perform the listening tests in accordance with this document.

Delivery to the GAL of all raw voting data using the data delivery file provided by the GAL for all tests to be conducted by the LL.

Delivery of a LL report to the IVAS Selection Meeting which includes:

Confirmation that the LL testing environment conforms to the requirements of the Selection test for all tests conducted by the LL.

Provision of listening test instructions for subjects in each of the languages tested by the LL.

Age and gender information for the set of subjects used in each listening test, and over all listening tests in each tested language tested by the LL.

Discussion of any problems encountered during testing and the solution used to address the problem.

]

Host Laboratory

[

E.1	Included tasks

The following list defines the tasks expected to be carried out by the Host Laboratory (HL). The tasks have to be conducted and completed following the schedule for the IVAS Selection phase defined in IVAS-2.

Cross-checking activities:

Preliminary cross-check with the PC using the preliminary CuT executables from the PC and the common corpus to identify potential problems.

Interaction with the PC in order to identify and resolve potential problems. A cross-check is successful when all MD5 hashes produced by the HL and the PC agree.  All MD5 hashes will be based on concatenated processed source files.

Preliminary cross-check with the CL using the preliminary CuT executables from the PC,  the reference executables, and the common corpus (or a subset thereof) to identify potential problems.

Interaction with the CL in order to identify and resolve potential problems. A cross-check is successful when all MD5 hashes produced by the HL and the CL agree.

Final cross-check with the PC using the final CuT executables from the PC and the common corpus to identify potential problems.

Interaction with the PC in order to identify and resolve potential problems. A cross-check is successful when all MD5 hashes produced by the HL and the PC agree.

Final cross-check with the CL using the final CuT executables, reference executables, and the speech and music and mixed materials provided by the LLs for each experiment.  A cross-check is successful when all MD5 hashes produce by the HL and the CL agree.

Processing and Delivery activities:

Receive preliminary CuT executables from the PC for use in developing an independent set of processing scripts.

Develop the processing scripts using the condition lists defined in this document and the processing steps defined in IVAS-7a.

Interact with the CL and the PC to resolve any problems.

Modify the processing scripts as needed to account for any changes in IVAS-7a and this document.

Deliver the cross-checked processing scripts to SA4.

Receive common corpus from the PC (including speech, music and mixed materials, and noise materials)

Receive preliminary CuT executables and MD5 files on common corpus from the PC.

Receive final CuT executables and MD5 files on common corpus from the PC.

Receive all source databases from the LLs.

Processing and delivery of all test files per experiment for 2 x 23 experiments to the LLs in phases to meet testing schedules after completion of final cross-check.

Reporting activities:

Delivery and Presentation of HL report. The report should include a discussion of any problems encountered during the cross-check and processing efforts. The dates for final test material delivery to the LLs should be included.

E.2	Excluded tasks

The following list defines the tasks that are explicitly excluded from the HL activities.

Provision or validation of reference executables.

Selection, verification, or validation of speech, music and mixed content, or noise materials.

]

Cross-check Laboratory

[

Included tasks

The following list defines the tasks expected to be carried out by the Cross-check Laboratory (CL). The tasks have to be carried out following the schedule for the IVAS Selection phase defined in IVAS-2.

Cross-checking activities:

Preliminary cross-check with the HL using the preliminary CuT executables from the HL, the reference executables and the common corpus database (or a subset thereof) to identify potential problems.

Interaction with the HL in order to identify and resolve potential problems. A cross-check is successful when all MD5 hashes produced by the HL and the CL agree.

Final cross-check with the HL using the final CuT executables from the HL, reference executables, and the speech and music and mixed materials provided by the LLs for each experiment and available from the HL. A cross-check is successful when all MD5 hashes produce by the HL and the CL agree.

Processing and Delivery activities:

Receive processing scripts and all associated executables and parameter files for the experiments from the PC.

Receive common corpus from the PC (including speech, music and mixed content, and noise materials).

Receive the preliminary and final CuT executables from the HL.

Receive all source materials from the HL.

Processing and cross-check of all test files per experiment for 2 x 23 experiments in phases as needed for the LLs to meet testing schedules.

Reporting activities:

Delivery and presentation of CL report. The report should include a discussion of any problems encountered during cross-check.

F.2	Excluded tasks

The following list defines the tasks that are explicitly excluded from the CL activities.

Development of processing scripts

Provision or validation of reference codec executables.

Selection, verification, or validation of speech, music and, mixed content, or noise materials.

Material Collection Entity (MC)

MC shall collect the clean mono speech, real recorded stereo/immersive signals, and a pool of parameters for artificially created stereo/immersive sound material (e.g., impulse responses).

MC shall control that the unprocessed material (for both artificially created and real recorded content) and parameters for artificially created stereo/immersive sound material meet the requirements defined by SA4.

MC shall choose the parameters and sound materials to be used in the experiments by a randomized blind process.

]

Global Analysis Laboratory

[

Tasks

The following list defines the tasks expected to be carried out by the Global Analysis Laboratory (GAL). The tasks have to be carried out following the schedule for the IVAS Selection phase defined in IVAS-2.

Provide the randomization playlists for 9 P.SUPPL800 subjective experiments to be described in this document. The playlists will be the same for the two tests of the same experiment conducted in different languages. Each LL will receive the randomization playlists only for the experiments to be conducted by that LL. The playlists will be delivered in Excel spreadsheet format.

Provide the raw voting data delivery worksheets for the 46 subjective tests (i.e., 23 experiments, each in two LLs) to the appropriate LLs. Each LL will receive the data delivery only for the experiments to be conducted by that LL. The worksheets will be delivered in Excel spreadsheet format.

Receive the raw voting data from the LLs in the appropriate data delivery worksheets.

Conduct statistical Terms of Reference (ToR) tests as specified in clause 3.3.6.2. The ToR tests compare the subjective scores of the CuT against the scores for specified reference conditions. Each subjective experiment contains a number of ToR tests to be computed by the GAL.

Prepare a GAL report to be presented at the Selection meeting as scheduled in the IVAS Project Plan IVAS-2.

Statistical analysis of results

The GAL report will present the results of the Terms of Reference (ToR) tests using Student's Dependent Groups t-test (single-sided at 95% confidence level). Results of the Requirement ToR tests for each experiment will be presented in a table as illustrated Table 1.

In the example below for Requirement ToR tests:

Requirement ToR tests that are passed, (i.e., CuT "not worse than" Requirement) are indicated by CuT NWT Ref.

Requirement ToR tests that are exceeded, (i.e., CuT "better than" Requirement) are indicated by  CuT BT Ref.

Requirement ToR tests that are failed (i.e., CuT "worse than" Requirement) are indicated by  CuT WT Ref.

Table 1: Example of Requirement ToR test results

Results of the Objective ToR tests for each experiment will be presented in a table as illustrated Table 2.

In the example below for Objective ToR tests:

Objective ToR tests where CuT "not worse than" Objective are indicated by  CuT NWT Ref.

Objective ToR tests where CuT "better than" Objective are indicated by  CuT BT Ref.

Table 2: Example of Objective ToR test results

SA4

SA4 defines the methods and models for artificial creation of sound material based on original (mono) sound material.

SA4 defines the stereo/immersive scenes including, e.g., environments/rooms, relative placement of talkers to capture point, and overtalk by talkers.

SA4 (volunteering members) shall provide the parameter sets for models/methods for artificial creation of sound material based on original (mono) sound material.

SA4 defines the set of requirements for original sound material (e.g., sampling frequency, formats).

SA4 (volunteering members) shall record or obtain original stereo/immersive material (unprocessed 48 kHz sampled signals).

SA4 (volunteering members) may record or obtain original clean mono speech material (unprocessed 48 kHz sampled speech).

]

Information relevant to all Experiments

General Technical Notes

Any and all deviations from the specifications contained in this document and the IVAS Processing Plan (IVAS-7a) must be documented and submitted to SA4 along with the experimental report.

General Consideration of Experiments

[

IVAS Selection Test is separated into two main use case scenarios, namely speech centric Immersive conversation, and Generic immersive audio. The Immersive conversation use case targets lower bitrates and the evaluation is done by naïve listeners. The Generic immersive audio assumes higher bitrates and the evaluation is done by experienced listeners.

Each experiment is performed twice and is tested in two different LLs. Each P.SUPPL800 experiment is run in two different languages with native listeners.

Immersive conversation

Source material:

Clean speech

Speech with background

Music and mixed content

Input formats:

Stereo, including binaural

FOA

Object-based audio

MASA

Lower bitrates, up to approximately the bitrate having as reference multi-mono EVS at 24.4 kbps per channel, as specified in IVAS Performance  Requirements (IVAS-3).

Including DTX conditions

Including FE conditions

Listening environment: headphones, including simulated headtracking

Test methodology: P.SUPPL800 [21]

Generic immersive audio

Source material: Generic audio

Higher bitrates

No DTX conditions

FE conditions

Input formats:

Stereo, including binaural

FOA

HOA3

Object-based audio

MASA

Channel-based audio

Listening environment:

Headphones, including simulated headtracking (?)

7.1 + 4 loudspeaker setup

Test methodology: BS.1534 (MUSHRA) [22]

Methodology

The following test methodologies shall be used in the IVAS Selection test: P.SUPPL800 [21] will be used in experiments designed to evaluate the Immersive conversation use case scenario, and BS.1534 [22] will be used in experiments designed to evaluate the Generic immersive audio use case scenario. High-level configuration of experiments for both methodologies is outlined below.

]

P.SUPPL800

Test duration should not exceed 2 hours per listening panel. Typical value of voting period was used for estimation of test durations, but actual voting period is not specified.

- [

Randomizations constructed under “partially-balanced/randomized blocks” experimental design described in [13].

- ]

6 categories for each test. Categories are defined for each experiment separately.

6 samples/category (1 for each listening panel) plus 1 sample/category for preliminaries.

30 naïve listeners, 6 listening panels (5 listeners per panel), each panel with an independent randomization

180 votes for each condition.

Total number of conditions: Maximum 36 test conditions x 6 talkers/categories = 216 DCR trials.

- [

Number of anchor conditions: 11

Direct

5 MNRUs [9]

5 (E)SDRUs [9]

Number of reference conditions: approx.10

Number of CuT conditions: approx. 10

BS.1534

Number of items per experiment: 12

[12 - 16] experienced listeners

Maximum total number of conditions: 8

Number of anchor conditions: 2

Direct

1 low-pass anchor

Maximum number of reference conditions: 4

Number of CuT conditions: 2

Note: As a rough preliminary approximation, approximately the same cost per listener per experiment is assumed both for BS.1534 and P.SUPPL800. Assuming 15 listeners for BS.1534, this would imply that the cost of one P.SUPPL800 experiment is approximately equivalent to the cost of two BS.1534 experiments. This further implies that the cost to evaluate 10 conditions of a Codec under Test (CuT) using P.SUPPL800 is approximately equivalent to the cost to evaluate 4 CuT conditions using BS.1534.

Note: the exact number of listeners, conditions, anchors, etc. may vary depending on actual experiment.

]

Opinion Scales

[

Table 3 defines opinion scale used for ITU-T P.SUPPL800 DCR test. Instructions in English for the P.SUPPL800 test are provided in Annex A.

Table 3: Opinion scale for ITU-T P.SUPPL800 DCR test

| Degradation | Scale |
| --- | --- |
| Degradation is inaudible | 5 |
| Degradation is audible but not annoying | 4 |
| Degradation is slightly annoying | 3 |
| Degradation is annoying | 2 |
| Degradation is very annoying | 1 |

Editor’s note: Scale and instructions to be still discussed.

]

Material

All audio material shall be sampled at 48 kHz with Full Band (FB) content. The audio material is to be delivered to the HL as 16-bit  little endian WAVE format files [25] following the naming convention provided in the IVAS Processing Plan (IVAS-7a). For multi-track audio, the audio tracks are ordered according to Error! Reference source not found. of IVAS Processing Plan (IVAS-7a). Additionally, it should be verified that the audio material can be processed with the AFsp package tools [26].

[The following categories of audio content will be used in IVAS Selection Test using P.SUPPL800:

Clean speech: Except for experiment P800-6 (1 object), each sample contains two (or more) different talkers in conversation scenario. The talkers transition from one to another as in natural conversation, i.e. without a pause, possibly with partial overlap.

Speech with background: the background comprises car, street, and office noise.

Music and Mixed content

The following category of audio content will be used in IVAS Selection Test using BS.1534:

Generic audio – critical generic audio items including speech with and/or without background, music, mixed.

]

- Editor’s note: What each category comprises is for further discussion

Speech Material for P.SUPPL800 testing

P.SUPPL800 test experiments will use artificially created immersive audio. LLs shall provide clean speech mono audio samples. SA4 would provide scene descriptions and scripts to create the immersive audio.

[

Talker Scenarios for Immersive Speech Experiments

Example scenarios for object-based audio testing of 2 objects:

2 talkers sitting at a table, at different azimuth angles with respect to the microphone.

2 standing talkers, at different azimuth angles with respect to the microphone.

1 talker sitting at a table, second talker standing beside the table.

1 talker sitting at a table, second talker walking around the table.

2 talkers walking side-by-side around the table.

2 talkers walking around the table in opposite directions, starting at the same position.

- ]

Editor’s note: This needs to be reflected in the Processing Plan

Background Material

Immersive conversation use case scenario (P.SUPPL800 testing): A mix-based approach using separate background recordings will be used. Identical background noise types as were used for EVS testing, i.e. car, office and street noise, will be used. Testing with DTX will be restricted to these background noise types.

[

The following guideline is applied to the noise types used.

Car noise is intended to test the performance of the codec under steady state background noise and should be recorded in a moving car. A constant speed between 80km/h (50mph) and 110km/h (70mph) is recommended. The make and model of the car should be reasonably common in the country of the recording. Typically, the windows of the car should be closed, and the radio turned off.

Office noise is intended to represent a typical office environment. This noise type should also contain typical office sounds, such as keyboard noise, computer fans, telephones ringing, printers, air conditioner, etc.

Street noise is intended to represent a typical street environment. It should contain unsteady traffic noise for example recorded at traffic lights where cars stop, human noise such as steps. It should not contain speech, but baby cries are allowed.

Editor’s note: This text was copied from EVS testing and needs to be updated

]

Generic immersive audio use case scenario (BS.1534 testing): Primarily, full recordings of complete immersive scenes including background will be used. A mix-based approach might be used in addition.

Music and Mixed Content Material for P.SUPPL800 testing

[

Classical music

Modern instrumental music

Modern vocal music

Radio Jingle

Movie Trailer

Advertisement

]

[

Critical Generic Audio Items for BS.1534 testing

Steps of Critical Test Item Selection

The following steps are based on [24]:

Call for test material according to the generic audio signal categories described below.

MC collects candidate material submitted in response to the call and selects a number of critical items to be used in the Selection test.

MC selects a limited set of training items to be used in a training phase.

Test Material

First, a call will be sent out for test material according to a number of generic audio signal categories as specified below. All 3GPP members are invited to submit test material to MC. The submitting organization shall assign the items to the below-mentioned audio signal categories. Then, MC will identify 12 critical items per experiment, plus four items for training, which are representative for assumed typical IVAS application scenarios.

Generic audio signal categories:

Stereo – generic stereo audio signals with a focus on music categories:

Pop, with and/or without vocals

Classic, with and/or without vocals

Single instruments

a capella vocals, solo and/or choir

Mixed speech and music

Speech with and/or without background noise

Multi-Channel (5.1 and 7.1.4) – generic channel-based audio signals from produced content:

Music including concerts with live audience

Film soundtracks with and/or without speech dialogue

Effects (e,g, nature, city/transport sounds)

Scene-Based Audio / MASA – generic immersive audio signals in the form of complex scenes, captured and/or produced content which may or may not include speech:

Nature sounds (e.g. forest, water, wind)

City sounds (e.g. traffic, bus, train)

Music including concerts with live audience

Babble-like sound (e.g. market, restaurant, conference)

Event/Sport-like sound

Conferencing scene with and/or without background noise/music

Object-Based Audio:

Conferencing scene with and/or without background noise/music

Tbd

The length in time of the items will be 10s at a maximum.

MC will further maintain and report to SA4 a list indicating the number of proposed items per submitting organization.

In case the submitted material is insufficient/inadequate to conduct the tests, MC will add the missing test items.

Training material

Limited material will be used in the training phase in which the subjects familiarize with the testing methodology and environment.

The training will be conducted with four sound items. These items will be identified by MC and shall not be re-used in the blind grading phase. The training phase shall be executed as a separate short MUSHRA session.

]

Listening Systems and Listening Environments

The IVAS Selection Test will use the following listening systems:

Stereo headphones, both for static binaural listening and binaural listening with simulated head-tracking (scene rotation is predefined)

Loudspeaker listening system – 7.1+4 loudspeaker setup [3].

Experimental Procedure

Experimental Procedure for P.SUPPL800 experiments

Initially the experimenter should provide a written copy of the experiment instructions to the listeners. When the listeners have acknowledged that they understand the instructions, they will be presented with a practice session to rate the preliminary conditions. After the practice session has been completed, the experimenter should ask if there are any questions. Only questions about the rating procedures or the meaning of the instructions should be answered. Any technical questions on matters such as the experimental methodology or details of the types of distortions they are rating must not be answered.

Results and Analysis

On completion of the experiments, the LLs must provide the raw voting data to the GAL for the purpose of performing a global analysis. The raw voting data for each experiment shall be delivered in the spreadsheet provided by the GAL for that purpose.

Subjective Experiments

[

The purpose of the 23 experiments (Experiments P800-1 – P800-9, and BS1534-1a – BS1534-7b) is to evaluate the performances of the IVAS codec candidate algorithm with respect to the performance requirements and objectives where possible defined in (IVAS-3).

The details provided in this section and in corresponding Annexes are those that are specific to each particular experiment. Generic information can be found in Section 4. Therefore, the LLs should use the information in Section 4 in conjunction with the information given in this section and Annexes.

Table 4 shows high-level overview of P.SUPPL800 experiments. Table 5 shows high-level overview of BS.1534 experiments. Table 6 shows LLs’ proposal of number of experiments they can ran and languages they can provide for P.SUPPL800 experiments.  Finally, Table 7 shows [preliminary] allocation of experiments to LLs and languages proposed by LLs for each P.SUPPL800 experiment.

Detail conditions for each subjective experiment are defined in Annex [X] for P.SUPPL800 experiments and in Annex [Y] for BS.1534 experiments.

Table 4: High-level overview of P.SUPPL800 experiments

| Exp | Input format | Source material | Listening environment | Bitrates kbps | FER/jitter | DTX | Headtracking |
| --- | --- | --- | --- | --- | --- | --- | --- |
| P800-1 | Stereo | Clean speech | Headphones | ≤ 48 | ≤ 3% | Y | No |
| P800-2 | Stereo | Speech+Background | Headphones | ≤ 48 | ≤ 3% | Y | No |
| P800-3 | Stereo | Mixed & Music | Headphones | ≤ 48 | ≤ 3% | N | No |
| P800-4 | FOA | Clean speech | Headphones | ≤ 96 | ≤ 3% | Y |  |
| P800-5 | FOA | Speech+Background | Headphones | ≤ 96 | ≤ 3% | Y |  |
| P800-6 | 1 Object | Clean speech | Headphones | ≤ 24 | ≤ 3% | Y |  |
| P800-7 | 2 Objects | Clean speech | Headphones | ≤ 48 | ≤ 3% | Y |  |
| P800-8 | MASA | Clean speech | Headphones | ≤ 96 | ≤ 3% | Y |  |
| P800-9 | MASA | Speech+Background | Headphones | ≤ 96 | ≤ 3% | Y |  |

Table 5: High-level overview of BS.1534 experiments

| Exp | Input format | Source material | Listening environment | Bitrates kbps | FER/jitter | DTX | Headtracking |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BS1534-1a | Stereo | Generic Audio | Headphones |  | ≤ x% | N | No |
| BS1534-1b | Stereo | Generic Audio | Headphones |  | ≤ x% | N | No |
| BS1534-2a | 5.1 | Generic Audio | 5.1 |  | ≤ x% | N | No |
| BS1534-2b | 5.1 | Generic Audio | 5.1 |  | ≤ x% | N | No |
| BS1534-3a | 7.1.4 | Generic Audio | 7.1 + 4 |  | ≤ x% | N | No |
| BS1534-3b | 7.1.4 | Generic Audio | 7.1 + 4 |  | ≤ x% | N | No |
| BS1534-4a | FOA | Generic Audio | Headphones |  | ≤ x% | N |  |
| BS1534-4b | FOA | Generic Audio | Headphones |  | ≤ x% | N |  |
| BS1534-5a | HOA3 | Generic Audio | Headphones |  | ≤ x% | N |  |
| BS1534-5b | HOA3 | Generic Audio | 7.1 + 4 |  | ≤ x% | N | No |
| BS1534-6a | Objects | Generic Audio | Headphones |  | ≤ x% | N |  |
| BS1534-6b | Objects | Generic Audio | Headphones |  | ≤ x% | N |  |
| BS1534-7a | MASA | Generic Audio | Headphones |  | ≤ x% | N |  |
| BS1534-7b | MASA | Generic Audio | Headphones |  | ≤ x% | N |  |

Notes:

Stereo may include binauralized samples (without head tracking).

For inputs 7.1+4, FOA, HOA3, Objects & MASA vertical dimension is assumed in the samples.

If listening is done with headphones, headtracking might be used, and is assumed simulated.

Maximum Frame Error Rate (FER) x% depends on whether channel error conditions are mixed with clean channel conditions in the same experiment (as assumed in the above table), or whether separate experiments are designed specifically for testing channel errors. In the former case, x should not be too high to prevent compressing results for clean channel conditions, e.g. x=3.

DTX on/off is assumed within the same experiment, where DTX on is used for relevant conditions.

All experiments are assumed Full Band experiments, i.e., the direct reference condition is always FB.

]

Note: the assumption is to have at least 6 weeks for subjective testing, from receiving the processed samples to delivering the listening results, assuming a dry run could be available a week before.

Editors’ note: EVS Selection P.800 configuration: 6 talkers, 5 double sentences (10 single-sentences) per talker.

Note: The databases are not assumed pristine.

SA4 minimum requirements for P.SUPPL800 experiments: 6 talkers (3 male + 3 female) per experiment, 14 single sentences per talker.

Editor’s note: still to be clarified for the music & mixed experiment (P800-3).

[

Table 6: LLs’ proposal of number of experiments and P.SUPPL800 languages

|  | Force Technology | Head Acoustics/ IKS | MQ University | Mesaqin.com |
| --- | --- | --- | --- | --- |
| Max nb. Of P.SUPPL800 exps | 9 | 4 | 2 | 2 tests /week1 (12) |
| Language and nb of P.SUPPL800 exps | Japanese (4) Danish (3) English (2) | German (4) | English Mandarin | French Mandarin Slovak |
| Nb of binaural BS.1534 exps | 3 | 5+ | 0 | 3 tests /week1 (18) |
| Nb of LS BS.1534 exps | 5 | 5 | 0 | 0 |

1Mesaqin’s indication about the number of P.SUPPL800 tests and BS.1534 tests correspond to the total number of experiments Mesaqin is able to perform, i.e. 12 P.SUPPL800 experiments OR 18 BS.1534 experiments.

Editor’s note:Table 6 can be removed once Table 7 is agreed

Table 7: Preliminary allocation of experiments to LLs and proposed P.SUPPL800 languages) shows allocation of LLs so that each experiment is conducted twice, each time by a different LL. For P.SUPPL800 experiments, each experiment is run twice with different languages.

Table 7: Preliminary allocation of experiments to LLs and proposed P.SUPPL800 languages

| Exp | Source material | Listening environment | Languages |  |  |  | Pricing |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Force Technology | Head Acoustics/ IKS | MQ University | Mesaqin | Euros |
| P800-1 | Clean speech | Headphones | JAP |  |  | FR | 36000 |
| P800-2 | Speech+Background | Headphones |  | GER |  | MAN | 36000 |
| P800-3 | Mixed & Music | Headphones | DAN |  |  | MAN | 36000 |
| P800-4 | Clean speech | Headphones | JAP |  | ENG |  | 36000 |
| P800-5 | Speech+Background | Headphones | DAN | GER |  |  | 36000 |
| P800-6 | Clean speech | Headphones | JAP |  | ENG |  | 36000 |
| P800-7 | Clean speech | Headphones | DAN |  |  | MAN | 36000 |
| P800-8 | Clean speech | Headphones | DAN | GER |  |  | 36000 |
| P800-9 | Speech+Background | Headphones | JAP |  |  | FR | 36000 |
| BS1534-1a | Generic Audio | Headphones | x |  |  | x | 20000 |
| BS1534-1b | Generic Audio | Headphones |  | x |  | x | 20000 |
| BS1534-2a | Generic Audio | 5.1 | x | x |  |  | 26000 |
| BS1534-2b | Generic Audio | 5.1 | x | x |  |  | 26000 |
| BS1534-3a | Generic Audio | 7.1 + 4 | x | x |  |  | 26000 |
| BS1534-3b | Generic Audio | 7.1 + 4 | x | x |  |  | 26000 |
| BS1534-4a | Generic Audio | Headphones | x |  |  | x | 20000 |
| BS1534-4b | Generic Audio | Headphones |  | x |  | x | 20000 |
| BS1534-5a | Generic Audio | Headphones | x |  |  | x | 20000 |
| BS1534-5b | Generic Audio | 7.1+4 | x | x |  |  | 26000 |
| BS1534-6a | Generic Audio | Headphones |  | x |  | x | 20000 |
| BS1534-6b | Generic Audio | Headphones |  | x |  | x | 20000 |
| BS1534-7a | Generic Audio | Headphones |  | x |  | x | 20000 |
| BS1534-7b | Generic Audio | Headphones |  | x |  | x | 20000 |
| Total |  |  |  |  |  |  | 634000 |

]

Editor’s note: A this stage the attribution of experiments is just an indicative example.

Sample Instructions to Subjects and Data Collection

[

These instructions shall be translated properly to the LL’s language and be given to the listeners. The instructions given to the listeners shall be provided for information in the LL report.

SAMPLE INSTRUCTIONS TO SUBJECTS FOR P.SUPPL800 TEST In this experiment you will be evaluating systems that might be used for future immersive telecommunication services using spatial audio. Spatial audio means that you can locate various sound sources around yourself. For example, a first talker may appear to talk from the left-hand side and a second talker from the right-hand side, a talker can be moving, etc. In each trial, you will hear a reference audio sample followed by a test sample. The test sample has the same content as the reference sample, but it was possibly degraded after it has passed through a telecommunication system. The reference audio sample defines the expected quality. Any alteration to this expected quality shall be considered as a degradation, even if you personally would prefer the test sample over the reference sample. Your task is to evaluate the overall degradation of the second sample compared to the first sample, comprising both degradation of the sound quality (e.g., due to additional noise, roughness, clicks or other distortions), and degradation of the spatial representation (e.g., sound source location, distance, spatial width, movement, etc.). You should listen carefully to both samples within a trial. When they have finished, please record your overall opinion about the amount of any degradation you can perceive in the second sample relative to the first sample using the following rating scale: 5 - Degradation is inaudible 4 - Degradation is audible but not annoying 3 - Degradation is slightly annoying 2 - Degradation is annoying 1 - Degradation is very annoying Note that the level of degradation present in different test samples is expected to span the complete range of the rating scale during the experiment. Please do not discuss your opinions with other listeners participating in the experiment. If you have any questions, please ask the test administrator.

Editor’s note: The instructions are for further discussion, in particular in view of any additional information from listening tests concerning appropriateness of the proposed scale.

Editor’s note: The text above was agreed as basis for further work assuming that the same renderer will be used for all conditions.

]

P.SUPPL800 Presentation Orders

[

The GAL will provide the Presentation Order for each P.SUPPL800 experiment to the Listening Lab assigned to conduct the test. The presentation order for each experiment has been developed by the GAL using a partially-balanced randomized-blocks experimental design and sample allocation for conducting Dependent Groups Student T-tests for the specified Terms of Reference tests. Each Presentation Order includes six blocks, corresponding to six categories and includes a separate presentation sequence for each of 6 panels of subjects. The Presentation Orders will be delivered to the Listening Labs in the form of Data Delivery Excel spreadsheets described in Annex C. Presentation Orders will be cross-checked before the actual listening tests start.

]

Editor’s note: The text was copied from EVS Selection and needs a review.

Data to be Provided by LL

[

The GAL will provide a Data Delivery spreadsheet for each experiment to the Listening Lab assigned to conduct the test. Attached to this Annex is an Excel file containing an example data delivery spreadsheet for a single experiment - a Music and Mixed content DCR test including 36 conditions (c01,c02, ... ,c36) and 6 categories (a1,a2,a3,a4,a5,a6) for each of 6 panels of subjects. For each panel, the data delivery spreadsheet includes 6 blocks of 36 trials each. The table below illustrates the data delivery spreadsheet for the 36 trials in Block-1 for Panel-1. For each trial, the table shows both the Reference file (condition c01) and the Test file (conditions c01-c36) followed by 5 data cells, one per subject, to be filled by the Listening Lab with the raw voting data provided by the subjects. In the table and in the attached file, the file naming convention is as follows:

cw5a1s1.c01	c = Listening Lab, w5 = Experiment, a1 = Category, s1 = Sample, c01 = Condition

]

Editor’s note: Text and the table copied from EVS Selection and need to be updated.

Selection Testing Timeline

Table H.1: Testing Timeline

| Month | Meeting/date | Task | Active Parties |
| --- | --- | --- | --- |
| April-2023 | April 17-21 | 3GPP SA4 e-meeting #123 |  |
| May-2023 | May 19 | All payments of the Funding Agreement (FA), including the second payment, are expected to be received by ETSI at the latest by May 19. ETSI will ensure that invoices for the payments are sent out in time, in accordance with the FA. | ETSI |
| May-2023 | May 22-26 | 3GPP SA4 meeting #124 – Version 1.0 of Test Plan, Processing Plan completed |  |
| June-2023 | Exact date tbd | Proper legal framework exists (signed) among proponent companies, ETSI, host lab, cross-check lab, listening labs, GAL to cover use of executables, source codes, audio test material (unprocessed and processed), and test results (raw voting data). |  |
| June-2023 | June 16, 17:00 CEST | Submission of preliminary IVAS codec candidate executable ready for Selection processing dry run |  |
| June-2023 | June 27, 17:00 CEST | Submission of IVAS codec candidate executable (floating-point code) to ETSI for selection testing. |  |
| 21-Aug |  | 3GPP SA4 meeting #124 - IVAS codec Selection meeting |  |

Editor’s note: Only agreed text copied from IVAS-2 in the table that needs to be completed.

Examples of test designs potentially relevant for IVAS codec testing

Introduction

This Appendix contains a collection of experimental designs that are deemed potentially relevant for IVAS codec testing. When creating the IVAS codec selection and characterizations test plans SA4 may decide to resort to concepts of these designs.

Example 1: Modified P.800 DCR test of parametric spatial speech [4], [5]

Test purpose

The main purposes for the experiment were: to evaluate the updated IVAS MASA C Reference Software package [6], [7]; to study the suitability of modified ITU-T P.800 [8] DCR and P.811 [9] methodologies for experiments using real spatial speech recordings; to evaluate quality of potential reference conditions for MASA format with degradation anchors spanning both signal and spatial quality dimensions.

Test outline

The listening test experiment was designed for evaluation of potential reference conditions for the parametric metadata-assisted spatial audio (MASA) format with degradation anchors spanning both signal and spatial quality dimensions.

Content types and material generation:

Realistic spatial speech items in real environments and controlled environments where background was generated using loudspeakers

The audio capture use cases can be described as “realistic spatial audio communications and user-generated content capture scenarios”

Audio was recorded in various indoor and outdoor environments using Eigenmike, Eigenmike + external microphone pair, Ambisonic + external cardioid pair, and (for a single category) a multi-microphone smartphone mockup

Majority of the captured signals were analyzed with the updated IVAS MASA C Reference Software [S4-210840] with the sole exception of the smartphone mockup samples that were analyzed using an in-house parametric analysis method

Binaural rendering was performed with IVAS MASA C Reference Software [6], [7] package for all conditions.

Evaluation and listening system/environment:

Modified P.800 DCR test method using real spatial speech recordings with parametric representation

Anchor conditions based on P.50 MNRU and P.811 ESDRU

Binaural listening was conducted using Sennheiser HD650 headphones in quiet booths

Detailed test description

Following provides detailed description of the test:

16 test subjects

Eight sample categories

Four randomizations for each 4-listener set

Four samples per category (one for each listening panel)

128 votes casted for each condition

Total of 24 conditions: 7 Reference conditions, 8 coded reference 2xEVS conditions (with unquantized (UQ) spatial metadata), 9 CuTs

5-scale DCR test methodology with updated instructions and revised voting scale

Degradation references: P.50 MNRU and ESDRU

P.50 MNRU Q values of 30, 24, and 18 dB were used

ESDRU values of 0.85, 0.70, and 0.55 were used

Average trial duration: 20 s

8 s reference sample + 0.5 s silence + 8 s test sample + 3.5 s voting period

Test duration: ~1.8 h per listening panel including instructions, preliminaries, and rest breaks

| Main Codec Conditions |  |  |
| --- | --- | --- |
| Codec under Test (CuT) | 9 | Nokia-internal IVAS MASA coding system |
| Codec references |  |  |
| Codec references | 8 | Dual-mono EVS (2xEVS) with unquantized MASA metadata operated at 2*8(WB), 2*9.6, 2*13.2, 2*16.4, 2*24.4, 2*32, 2*48, 2*64 kbps. Rendering with IVAS MASA C Reference binaural renderer [6], [7]. |
| Other references |  |  |
| Direct | 1 | Analysed with the updated IVAS MASA C Reference software [S4-210840]. No transport stream nor MASA spatial metadata compression. Rendering done with IVAS MASA C Reference binaural renderer [6], [7]. |
| P.50 MNRU (applied to MASA transport streams) | 3 | Q = 18, 24, 30 dB (output loudness set to nominal level) |
| ESDRU (applied to binaural rendering) | 3 | α = 0.55, 0.7, 0.85 (output loudness set to nominal level) |
| Common Conditions |  |  |
| Test item generation | 4 | Multi-channel recordings in real environments analysed with the updated IVAS MASA C Reference Software [7] in various configurations or (for single category) using an in-house system. |
| Binaural rendering | 1 | Rendering done with IVAS MASA C Reference renderer [6], [7]. |
| Audio sampling frequency / bandwidth | 2 | 48 kHz/SWB except for reference condition 2xEVS@2*8kbps which used 48 kHz/WB |
| Rating Scale | 1 | DCR with modified instructions and scale considered more suitable for binaural/spatial telephony (see “Instructions to listeners”) |
| Languages | 1 | Finnish |
| Listening System | 1 | Sennheiser HD650 headphones for binaural presentation |
| Listening Environment | 1 | No room noise |

Instructions to listeners

The following set of instructions were given to all listeners as printouts. Note that the instructions were in Finnish, and they are here translated into English to aid the reader.

Listening instructions: You will hear through stereo headphones pairs of binaural speech samples. Binaural means that you can locate various sound sources around yourself while listening with headphones. For example, a first talker may appear to talk from the left-hand side and a second talker from the right-hand side. This may also be called spatial audio. In traditional mono audio you cannot hear the direction of the talkers like in spatial audio. Instead, both talkers appear to talk from the same position inside your head. The samples you are about to hear were recorded in real environments and may contain in addition to main talkers’ speech various ambient noises, music, and distant chatter by other people. The first speech sample of each pair is the original. Right after the first sample you will hear the sample again. For the second sample there may have been used some future mobile phone technology. Your task is to evaluate the second speech sample compared to the first speech sample. Your task is to evaluate both the voice quality and the spatial representation of the second speech sample compared to the first speech sample. We can call this combination of voice quality and the spatial quality the Overall quality of the sample. The Overall quality degradation of the second speech sample compared to the first speech sample is evaluated using the following scale: 5 Degradation is inaudible 4 Degradation is barely audible 3 Degradation is audible but not annoying 2 Degradation is slightly annoying 1 Degradation is annoying ---------------------- Do not take refreshments with you to the booth (you can have refreshments during the breaks) Leave your mobile phone on the table outside the listening booths Do not discuss about the speech samples with other people during the comfort breaks

Compared to standard P.800 instructions, the listeners are guided to consider the overall quality, including any degradation of the speech or other sound, and any change in the spatial presentation quality before casting their vote. For degradation scale, a more sensitive wording is used. Instead of “1 Degradation is very annoying” we use here “1 Degradation is annoying” for lowest quality and an additional step is inserted between original scores of 4 and 5. This score is “4 Degradation is barely audible”. This sensitivity adjustment of the scale can reduce the effect of quality saturation at the upper end of the voting scale when conditions are close to transparency. This modification also increases usage of the lowest score of 1, particularly in case of relatively high-quality samples thus providing additional separation between conditions.

In addition to the textual instructions, verbal instructions were given prior to listening to all listeners. Before the listening test, several introductory samples were played back covering the full range of degradations appearing in the actual test.

Example 2: Example P.800 DCR test of spatial (FOA) speech [10]

Introduction

Below is a P.800 DCR [8] test design example for subjective testing of spatial (FOA) speech quality. The example has been imported from Tdoc S4-210836 [11]. Results obtained from the test execution are not provided here but are available in the original documents [11] for Experiment 1 and [18] for Experiment 2.

Test Purpose

Build an opinion about suitability of modified P.800 DCR test methodology for quality assessments of immersive conversational speech.

Test Outline

2 Experiments

Exp1: use case ‘immersive conferencing’ with Ambisonics (FOA) spatial speech, 6 content type categories constructed as follows:

Model-based relying on convolution of raw mono clean speech sentences convolved with (FOA) Spatial Room Impulse Responses respective various talker positions relative to a capture point. The Spatial Room Impulse Responses were recorded in the respective conference rooms.

Spatialized sentences are combined to sentence pairs and mixed with spatial (FOA) ambient noise.

2 relatively low background noise levels (30, 40 dB SNR, based on level normalization according to ITU-R BS.1770-4 [12])

Reverberance typical for 2 conference rooms (large and small)

2 talker interactions types: sentence pairs with and without ‘overtalking’ (1s overtalk)

Language: Polish

Lab: Dolby Wroclaw (Poland)

Exp2: Immersive telephony while on the move (outside) with Ambisonics (FOA) spatial speech, 6 content type categories constructed as follows:

Model-based relying on convolution of raw mono clean speech sentences convolved with (FOA) Spatial Room Impulse Responses respective various talker positions relative to a capture point. The Spatial Room Impulse Responses were recorded in the respective test environments (car) or a low-echoic room approximating the other environments.

Spatialized sentences are combined to sentence pairs and mixed with spatial (FOA) ambient noise.

Moderate to high background noise levels (15, 20, 25dB SNR, based on level normalization according to ITU-R BS.1770-4 [12])

Various environments: street, car, public indoor (shopping mall, subway station)

No talker interactions (no ‘overtalking’): sentence pairs without ‘overtalking’ (1s gap)

Language: American English

Lab: Dolby San Francisco (USA)/remote (home environment)

General Consideration of Experiments

Six categories of content types.

30 subjects, five listening panels (six subjects per panel), each panel with an independent randomization.

Five samples per category (one for each listening panel).

Randomizations constructed under “partially-balanced/randomized blocks” experimental design described in “Practical procedures for subjective testing”, [13].

Every condition has 30 different samples passed through it (6 categories x 5 panels). Each of these are voted on by the 6 subjects in the panel, giving: (30 samples x 6 subjects/panel) = 180 (150) votes per condition.

30 test conditions x 6 categories = 180 DCR trials.

Average trial duration: 16 s (6.5 s reference sample +0.5 s silence + 6.5 s test sample + 2.5 s voting period).

Test duration: ~1.6 h per listening panel. Test duration comprises 50% of actual listening/voting time (48 min) and 50% test overhead including orientation, instructions, preliminaries, and rest breaks

The listening sessions were split into a number of sub-sessions with breaks in between to allow for the subject to relax. This was to avoid listener fatigue.

Test platform: Dolby-internal

Degradation references (anchors)

According to ITU-T Rec. P.811 Appendix II, P.811 [9] overall quality scores strongly correlate with P.800 DCR scores if the latter is run with modified instructions and degradation references that span both signal and spatial quality dimensions. P.811 suggests using P.50 MNRU for signal degradation anchors and SDRU/ESDRU for spatial degradation anchors. P.50 MNRU is a modulated noise reference unit with P.50-artificial voice weighting. SDRU/ESDRU are spatial degradation reference units defined for stereo signals that gradually, depending on a degradation parameter α, impair the stereo image without substantially causing signal distortions. A random process additionally introduces temporal fluctuations ranging from the original to the maximally degraded stereo image. The ESDRU applies a more sophisticated random process.

We followed this recommendation and adapted the P.50 MNRU and the ESDRU to derive degradation anchors for our P.800 experiments with binauralized FOA content.

For the P.50 MNRU the adaptation is that it is coherently applied (same seed) to all 4 FOA signals. This has the perceptual effect that the spatial direction of the introduced signal distortion coincides with the spatial signal direction. Thus, the introduced signal distortion does not significantly affect the spatial image.

The ESDRU on the other hand is directly applied to the two binaural channels after binaural rendering of the FOA signal.

A limited subjective experiment was carried out to

verify the suitability of these degradation anchors,

to verify the basic assumption that the P.50 MNRU has little impact on spatial distortion and vice-versa that the ESDRU has little impact on perceived signal distortion, and

to find suitable P.50 MNRU and ESDRU degradation parameters Q and, respectively, α.

In the experiment 6 FOA voice vectors were degraded either with P.50 MNRU values of Q=30, 25, and 20 dB or with ESDRU parameter values of α = 0.8, 0.55, and 0.3. These vectors were evaluated in a Mushra test (with 3 expert listeners) with the three quality attributes overall quality (Overall), signal quality (SIG), and spatial quality (SPA).

The results are displayed in the following plots:

From the plots, the following observations can be made:

The P.50 MNRU degradation affects mainly signal (SIG) and Overall quality while spatial quality (SPA) is less impacted.

The ESDRU degradation affects mainly spatial (SPA) and Overall quality while signal quality (SIG) is less impacted.

The P.50 MNRU induced signal degradation appears a bit too strong and should be softened for the P.800 tests.

The ESDRU induced degradation is too strong, which results in that spatial and overall quality start to saturate at the lower end. Consequently, for the P.800 tests, it was decided to increase the α parameters.

Factors and conditions

| Main Codec Conditions |  |  |
| --- | --- | --- |
| Codec under Test (CuT) | 11 | Dolby-internal FOA coding system |
| Codec references |  |  |
| Codec references | 12 | Multi-mono 4xEVS operated at 4*8, 4*9.6, 4*13.2, 4*16.4, 4*24.4, 4*32, 4*48, 4*64, 4*96 kbps with DTX off and 4*13.2, 4*16.4, 4*24.4 kbps with DTX on |
| Other references |  |  |
| Direct | 1 | Nominal input level |
| P.50 MNRU (applied to all FOA components) | 3 | Q=22, 27, 32 dB (all: nominal level) |
| ESDRU [9] | 3 | α = 0.55, 0.7, 0.85 (output loudness forced to nominal level) |
| Common Conditions |  |  |
| Test item generation: pre-processing incl. spatialization | 1 | Model-based relying on convolution of raw mono clean speech sentences convolved with (FOA) Spatial Room Impulse Responses respective various talker positions relative to a capture point and spatial (FOA) ambient noise mixing |
| Binaural renderer | 1 | FOA to binaural rendering according to [14] |
| Audio sampling frequency/bandwidth | 2 | 48 kHz/SWB except for 4xEVS@4*8kbps which is 48 kHz/WB |
| Content types (categories) | 6 | Exp1: 6 Different conference rooms and talker interactions Exp2: 6 Different background noise types and levels |
| Kind of samples | 1 | Sentence pair uttered by different talkers and genders (3 male and 3 female) |
| Number of samples | 5 | per content type |
| Input frequency mask | 1 | Flat |
| Nominal output loudness | 1 | -26 LKFS (ITU-R BS.1770-4 [12]) |
| Listening Level | 1 | 73 dB SPL |
| Listeners | 30 | Naïve Listeners |
| Randomizations | 5 | 5 panels of 6 listeners |
| Rating Scale | 1 | DCR with modified instructions |
| Replications | 1 |  |
| Languages | 1 | Exp1: Polish, Exp2: American English |
| Listening System | 1 | High-quality headphone for diotic presentation |
| Listening Environment | 1 | No room noise |

Preliminaries (familiarization of listeners)

| Main Codec Conditions |  |  |
| --- | --- | --- |
| Codec under Test (CuT) | 0 |  |
| Codec references | 5 | Multi-mono 4xEVS operated at 4*8, 4*13.2, 4*24.4, 4*48, 4*64, with DTX off |
| Other references |  |  |
| Direct | 1 | Nominal input level |
| P.50 MNRU (applied to all FOA components) | 3 | Q=22, 27, 32 dB (all: nominal level) |
| ESDRU [9] | 3 | α = 0.55, 0.7, 0.85 (output loudness forced to nominal level) |
| Common Conditions |  |  |
| Test item generation: pre-processing incl. spatialization | 1 | Model-based relying on convolution of raw mono clean speech sentences convolved with (FOA) Spatial Room Impulse Responses respective various talker positions relative to a capture point and spatial (FOA) ambient noise mixing |
| Audio sampling frequency/bandwidth | 1 | 48 kHz/SWB except for 4xEVS@4*8kbps which is 48 kHz/WB |
| Content types (categories) | 6 | Exp1: 6 Different conference rooms and talker interactions Exp2: 6 Different background noise types and levels |
| Number of samples | 1 | per content type |
| Input frequency mask | 1 | Flat |
| Nominal output loudness | 1 | -26 LKFS (ITU-R BS.1770-4 [12]) |
| Listening Level | 1 | 73 dB SPL |
| Listeners | 30 | Naïve Listeners |
| Randomizations | 1 | Same randomization for the 5 panels of 6 listeners |
| Rating Scale | 1 | DCR with modified instructions |
| Replications | 1 |  |
| Languages | 1 | Exp1: Polish, Exp2: American English |
| Listening System | 1 | High-quality headphone for diotic presentation |
| Listening Environment | 1 | No room noise |

Instructions to listeners and Degradation Scale

The following presents the modified DCR test instructions given to the subjects and the five-point degradation category scale used in the test:

"Evaluation of the quality of future 3D audio telephony and conferencing systems"

In this experiment you will hear pairs of speech samples that have been recorded through various experimental 3D audio telephone and conferencing equipment. You will listen to these samples through a set of stereo headphones.

What you will hear is a first sample containing one pair of sentences from two talkers, a short period of silence, and a second sample. You will evaluate the OVERALL quality of the second sample compared to the quality of the first sample.

You should listen carefully to each pair of samples. As soon as a sample pair has been completely played back, you should register your opinion on ANY kind of degradation of the second sample compared to the first sample. Please consider in your vote, besides, e.g., the quality of the speech or other sounds, also any change in the perceived location of voices or sounds or changes in spatial width.

Then, when the system requests your vote, please record your opinion on the OVERALL quality using the following scale:

The OVERALL quality DEGRADATION of the Second Compared to the First is:

5: Inaudible

4: Audible but not annoying

3: Slightly annoying

2: Annoying

1: Very annoying

You will have five seconds to record your answer by pushing the button corresponding to your choice. There will be a short pause before the presentation of next pair of sentences.

We will begin with a short practice session to familiarize you with the test procedure. The actual tests will take place during multiple sessions with short breaks in between.

Degradation Scale

The OVERALL quality DEGRADATION of the Second Compared to the First is:

5: Inaudible

4: Audible but not annoying

3: Slightly annoying

2: Annoying

1: Very annoying

Example 3: Experience of P.800 for stereo testing [15]

Test description

As a part of Ericsson’s involvement in the development of P.811 [9] standard, a listening test according to the draft P.811 specification was done in a collaboration between Ericsson and Beijing Institute of Technology (BIT). The test was conducted in October 2018 and was done in conjunction with a P.800 [8] DCR test on the same test material. The purpose was to evaluate the proposed P.811 standard (called P.SOSH at the time) and to compare the overall score of the P.811 test with a P.800 DCR test which requires shorter test time. These tests were performed:

Experiment 1: P.800 Degradation category rating (DCR) with spatial distortion reference units and listener instructions similar to the P.811 instructions, see appendix A

Experiment 2: Subjective test methodology for evaluating speech oriented stereo communication systems over headphones (P.811)

The test design and processing were carried out by Ericsson, while BIT handled recording of the test material and execution of the test itself.

Test material

The test was conducted using stereo speech samples in Mandarin Chinese recorded at BIT. The talkers were 4 female and 4 male talkers recruited from the BIT students. The talkers were all native Mandarin Chinese speakers and were selected to have a rather neutral dialect. The stereo capture was done using a Sabinetek® SMIC Panoramic Microphone and the recordings were made using 48 kHz sampling rate.

Out of the 20 test items in total, 10 items contained one talker with a split of 5 female and 5 male talkers. The remaining 10 items contained two concatenated talkers at different positions, where each item contained one male and one female talker. The concatenation of the talkers was done with a short pause between each talker, i.e. no overlapping talk. The talkers were positioned at the angles of -90, -45, 0, 45 and 90 degrees relative to the front pickup of the microphone.

Listener subjects

Each of the experiments was performed with 32 naïve listeners (balanced between male and female). All of them were BIT adult students between 20-24 years old. In total, 64 different native listeners of Chinese were selected as test subjects.

The listeners were selected randomly from native Chinese persons in the BIT campus. After the pre-tests, the staff checked the subjects' scores to make sure they understood the rating criterion. If the listener gave inconsistent or confusing votes, they were asked to do the pre-test session again. If the inconsistencies were not resolved in the second pre-test session, the listener was excluded from the main test session.

Experiments Procedure

For both the P.800 and P.811 tests, the subjects were divided into 4 listening panels of 8 persons each. Each panel used its own randomization sequence files.

Preliminary tests (pre-tests) were held before the main tests. In the pre-test, 4 trials were run to make the subjects familiar with test methodology. The main test was divided into 4 sessions of 20 trials each. A break was inserted between each test session, of 5, 10 and 5 minutes respectively.

The processed speech material was presented to groups of listeners, who were seated in separate listening stations in an acoustically conditioned sound room meeting the requirements recommended in ITU-T P.800. A photo of the test room is shown in Figure 1.

Figure 1: Listening laboratory

All test stimuli were presented to the subjects using Sennheiser® HD 280 Pro headphones. Tablets were used to collect votes during the two experiments. The voting table interfaces are shown in Figure 2 and Figure 3.

Figure 2: Voting interface on a tablet with spreadsheet for collecting votes in the P.800 test.

Figure 3: Spreadsheet for collecting votes in the P.811 test. The three rows for votes of a specific test file were marked with the same color to minimize the risk of confusion.

The voting time was 5 seconds after the completed presentation of each new stimulus. All seated listeners were required to vote prior to the subsequent presentation of a new stimulus. Comments, experiences and suggestions from listeners were collected at the end of each experiment.

The average test time per session was 18 minutes for the P.811 test and 6 minutes for the P.800 test.

Scoring

Both experiments used the Degradation Category Rating (DCR) method where the reference is played first followed by a test sample to be judged in comparison to the reference.

In the P.800 DCR test, listeners gave their opinion on any degradation in Overall Quality they could perceive on the second sample compared to the first one (the reference). The instructions for the P.800 test with P.811 inspired instructions can be found in appendix A.

In the P.811 test, listeners gave their opinion of any signal degradation, difference in spatial localization and overall quality degradation they could perceive on the second sample compared to the reference, according to the instruction below:

Signal (SIG) degradation

Attending ONLY to the SIGNAL (SPEECH and BACKGROUND NOISE or MUSIC), select the category that best describes the DEGRADATION in the second sample compared to the first sample.

Signal degradation in this sample was,

5   INAUDIBLE

4   AUDIBLE BUT NOT ANNOYING

3   SLIGHTLY ANNOYING

2   ANNOYING

1   VERY ANNOYING

Spatial localization (SPA)

Attending ONLY to the TALKER/SOURCE LOCATIONS, select the category that best describes the DIFFERENCE in the second sample compared to the first sample.

There was

5   NO DIFFERENCE

4   SMALL DIFFERENCE

3   MODERATE DIFFERENCE

2   LARGE DIFFERENCE

1   VERY LARGE DIFFERENCE

Overall (OVRL) quality degradation

Attending to the OVERALL impression, including but not limited to signal quality and spatial localization, select the category that best describes the OVERALL Quality degradation of the sample compared to the reference.

Overall quality degradation was,

5   INAUDIBLE

4   AUDIBLE BUT NOT ANNOYING

3   SLIGHTLY ANNOYING

2   ANNOYING

1   VERY ANNOYING

Anchors used in the test

To span the signal degradation dimension, MNRU anchors at Q-levels 16, 23 and 30 were used. The Direct signal and Direct-Downmix to mono were also used in the test. In addition, there were two versions of spatial anchors, SDRU and ESDRU.

SDRU and ESDRU

The effect of the SDRU can be summarized as:

a down-mix (collapse) of the stereo image for α≈0.5 and a full reversal of the channels for α≈1.

an amplitude modulation (panning) of the signal with a triangle wave with a period of 1 second.

The second dimension of this distortion reference unit creates a “ping-pong” effect between the channels which was regarded a bit unnatural in relation to the typical distortions introduced by stereo codecs. In addition, some listeners reported the effect induced dizziness. While dizziness may be an unavoidable side-effect of spatial distortion, it was found relevant to try a different variant of the modulation function. The formulation of the ESDRU, an alternative spatial distortion reference unit, is the same as the SDRU apart from the definition of the modulation function. Instead of a periodic triangle wave, a random stepwise pattern was introduced. The idea behind this was that the random deviation would be more similar to a stereo codec which may introduce quantization errors on a parametric description of the stereo image. It would also avoid the periodic panning which may give the illusion that the listener’s head is spinning.

Test conditions

The input speech items were processed for the 20 conditions listed in Table 8 below. The same test material was used in both the P.800 DCR test and the P.811 test. The processing bandwidth in the test was Super Wideband (SWB) sampled at 32 kHz. The SDRU in conditions c06 - c08 operate on 48 kHz, which means a sampling rate change was necessary. All sampling rate changes were implemented using the ITU-T STL filter tool with SHQ2 and SHQ3 resampling filters and delay compensation as described in Table 6 of [16].

Table 9: Processed conditions

| Label | Condition |
| --- | --- |
| c01 | DIRECT |
| c02 | DIRECT downmix (L+R)/2 |
| c03 | MNRU Q=16 |
| c04 | MNRU Q=23 |
| c05 | MNRU Q=30 |
| c06 | SDRU 0.0 |
| c07 | SDRU 0.3 |
| c08 | SDRU 0.6 |
| c09 | ESDRU 0.0 |
| c10 | ESDRU 0.3 |
| c11 | ESDRU 0.6 |
| c12-c20 | Stereo codec conditions |

Preprocessing

The stereo signals were split using

stereoop.exe -split <input> <outputL> <outputR>

Each channel was then high-pass filtered using filter, followed by a delay compensation of 839 samples

filter.exe HP50_48KHZ <input> <output> 960

The sampling rate was then changed from 48 kHz to 32 kHz and the level was normalized to 
-26 dBov using the following procedure:

stereoop -maxenval <input> maxenval32

sv56demo -log log.txt -lev -26 -sf 32000 maxenval32 dummy 640

scale=`cat log.txt | grep "Norm factor" | awk '{print $6}'`

scaldemo -gain $scale <input> <output>

DIRECT

Preprocessed input signal without further modification.

DIRECT downmix (L+R)/2
The passive downmix realized as L+R2, using the tool CopyAudio [17]:

CopyAudio.exe --chanA="0.5*A+0.5*B" -P integer16,,32000,,2 -F noheader <stereo> <output>

MNRU
The MNRU conditions were generated using the SDRU tool [9], where the modulated noise generators are synchronized between left and right channels:

BG_MNR07.exe <input> <output> <Q-value> H 1

SDRU
The SDRU conditions were generated using SDRU tool [9]:

BG_MNR07.exe <input> <output> 100 H <alpha-value>

ESDRU
ESDRU conditions generated using the ESDRU tool [9]. The random seed may be set to get deterministic results for each processing run:

matlab /minimize /nosplash /nodesktop /r "esdru('<input>', '<output>', 32000, <alpha-value>, 0.5, <random seed>);exit"

Post-processing level normalization

While the stereo coding normally preserves the level of the signal, the signal levels of SDRU, ESDRU and the DIRECT downmix often deviates from the input level. For this reason, the level was normalized for the SDRU and ESDRU conditions following the same normalization procedure as in the preprocessing:

stereoop -maxenval <input> maxenval32

sv56demo -log log.txt -lev -26 -sf 32000 maxenval32 dummy 640

scale=`cat log.txt | grep "Norm factor" | awk '{print $6}'`

scaldemo -gain $scale <input> <output>

The DIRECT downmix condition results in a dual mono representation, which tends to get a too high level with the described procedure. For this condition a separate normalization procedure was used. The procedure matches the energy of the down-mix signal with half the energy of left and right channels combined.

sv56demo -rms -sf 32000 -blk 1280 -log tmp.log <stereo input> dummy.raw

A=`cat tmp.log | grep "Norm factor" | gawk '{print $6}'`

sv56demo -rms -sf 32000 -blk 640 -log tmp.log <downmix input> dummy.raw

B=`cat tmp.log | grep "Norm factor" | gawk '{print $6}'`

fac=`echo "$B/$A" | bc -l`

scaldemo -gain $fac <downmix input> <downmix output>

Test results

The results of the listening tests are illustrated in Figure 4 and Figure 5 below. As seen in Figure 4, the signal distortion induced by the MNRU has the main impact on the SIG dimension (a) while keeping a fairly constant rating in the SPA dimension (b). Conversely, the spatial distortion of the SDRU and ESDRU has a strong effect on the SPA dimension (b) while it the showing less impact on the SIG dimension (b).

(b)

(a)

Figure 4: The scores of the signal degradation (a) and spatial localization (b) of the P.811 test.

(b)

(a)

Figure 5: The scores of the overall dimension (a) of the P.811 test and the P.800 DCR scores (b).

Turning to Figure 5, the overall scores of the P.811 test in the OVRL dimension (a) show a high degree of similarity with the P.800 DCR scores (b). The correlation coefficient between these scores is 0.966. As a comparison, the correlation between the scores of the two listening labs for each experiment in the EVS selection SWB conditions tests [23] are shown in Table 10. Here the two labs used the same test configuration and processing scripts but carried out their tests in different labs and in different languages.

Table 11: Correlation between scores from lab (a) and lab (b) in SWB experiments of the EVS selection tests.

| Experiment | Corrcoef |
| --- | --- |
| s1 | 0.985 |
| s2 | 0.972 |
| s3 | 0.956 |
| s4 | 0.960 |
| s5 | 0.959 |
| s6 | 0.888 |
| s7 | 0.977 |

The relations between the scores may also be illustrated in the form of scatter plots. The relation between the SIG and SPA dimensions is shown in Figure 6. The scores of the MNRUs remains fairly stable for varying SIG scores, while the SDRU and ESDRU show a robustness in the SPA dimension.

Figure 6: The scores of the SIG dimension on the x-axis versus the scores of the SPA dimension on the y-axis.

The relation between the OVRL dimension and the SIG and SPA dimension is illustrated in Figure 7 (a) and (b) respectively.

(a)

(b)

Figure 7: Scores in the OVRL dimension (y-axis) compared to the scores of the SIG dimension (a) and the SPA dimension (b).

The relation between the P.811 overall score and the P.800 DCR scores is illustrated in Figure 8, indicating that the scores are highly correlated.

Figure 8: Scores of the P.811 OVRL dimension (x-axis) versus the scores of the P.800 DCR test (y-axis).

Focusing on the scores of the anchor conditions in Figure 9, one can see that the MNRU remains stable in the SPA dimension while declining in the SIG dimension (a). Conversely, the SDRU and ESDRU are stably in the SIG dimension while declining in the SPA dimension for increasing levels of distortion.

Figure 9: P.811 results for the MNRU (a), SDRU (b) and ESDRU (c).

Additional small test about dizziness

The test participants were encouraged to write comments after the tests about how they perceived the test methodology and the test material. These comments revealed that 8 out of the 64 test participants in the P.800 DCR and P.811 tests felt somewhat dizzy or uncomfortable during the test when the voices changed position between left and right channel. This behavior can be found for the spatial anchors. To examine if the SDRU and ESDRU anchors were perceived differently the test participant that had commented that they felt dizzy were invited to an extra test with only the SDRU and ESDRU conditions.

The 8 students were divided into two groups, A and B with 4 persons in each group. All 20 speech files used in the P.800 and P.811 tests were also used in this test. Group A listened to sentence pairs 1-10 and Group B listened to speech examples 11-20. Each group listened to 5 samples with one speaker and 5 samples with two speakers.

The processed samples were presented after the reference samples as in the main tests, but in this test the test subjects should quantify how dizzy they felt while listening to the test samples according to this scale:

5 Not dizzy.

4 The degree of dizziness is very small

3 The degree of dizziness is moderate

2 The degree of dizziness is large

1 The degree of dizziness is very large

The results in Figure 10 reveal that the ESDRUs made the test subjects less dizzy than the SDRUs. This test was done only with persons that had reported that they got dizzy during the main tests. Most persons will however probably not get dizzy during a test as only 8 persons out of the 64 test participants commented that they became dizzy during the main tests.

4.5

2.5

1.5

3.5

Figure 10: Mean scores for the degree of dizziness in the test with only the spatial anchor conditions. In this additional test, higher scores indicated lower degree of dizziness. The confidence intervals (95%) are indicated using black lines.

Comments and suggestions

The main comment from test participants regarding the P.811 test methodology was that it was boring with so many repetitions. They suggested that the test material should be more enriched and varying. Some commented that the test was too long and monotonous and that they felt tired and thought it was hard to focus at the end of the test.

As this can be a problem there should be a careful selection of conditions to keep the test as short as possible.

A suggestion from two listeners was that it would be enough to listen to each speech sample two times instead of three times. After hearing the speech sample, the first time they could judge the signal degradation and after hearing the sample the second time they could vote for both the spatial and the overall quality. This suggestion would of course shorten the total test time but might lead to less focus on each of the spatial and overall dimensions and possibly less accurate results.

Another suggestion was that it would be better to use a more automatic collection of the votes as that would certify that the vote is connected to the correct speech example. Then it would also be possible to hide the previous votes, so that the judgments are not so easily influenced by previous votes.

Conclusions and proposal

The listening experiments shows that the P.811 method does give a relevant rating in the different dimensions specified by the test, but the prolonged test time from asking three questions may result in listener fatigue and puts limitations on the test size (e.g., number of conditions). Further, the results for the overall quality in the P.811 and P.800 DCR tests were highly correlated which indicates that P.800 DCR with adapted instructions and spatial anchors is an attractive alternative to P.811 for tests where the main interest is the overall score.

The spatial anchor ESDRU received similar quality ratings as the SDRU while inducing less dizziness. Hence, the ESDRU is considered a good alternative to the SDRU.

Example 4: DCR test experiments for FOA and HOA3 input in 7.0+4 and binaural listening setup [19]

Test Purpose

The purpose of the experiments was to evaluate suitability of P.800 DCR test [8] for immersive listening using naïve listeners, and to compare test results of 7.0+4 loudspeaker-rendered listening with test results of binaurally rendered listening via headphones.

Audio database

Artificially created spatial samples from phonetically balanced mono recordings adjusted to -26 dBOvl.

Language: North American French

Two mono recordings with similar meaning were combined in HOA3 domain to create spatially separated sentence pairs.

4 male and 4 female talkers, always a male and a female talker in a sentence pair.

Sentence pairs simulating a conversation with natural transition from one talker to another. Half of the samples partially overlapped.

Length of the samples - 6 s.

48 kHz sampling rate.

HOA3 and FOA input format.

All talkers were placed at the nominal height at different configurations using regular pattern using:

3 different speaker separations: 60, 90, 135

24 different combinations:

| Separation [°] | 1st talker position [°] |
| --- | --- |
| 60 | -15 : 45: 300 |
| -90 | 30 : 45 : 345 |
| 135 | -15 : 45 : 300 |

Background

Mono recordings of instrumental music at 15 dB SNR.

Different music sample and position used for each speech sentence pair.

The mono samples were encoded into HOA3 domain using elevation of 20°, 40°, and 60°. Exact azimuths and elevations were distributed as follows:

Azimuth = [15, 60, 115, 155, -155, -115, -60, -15, 15, 60, 115, 155, -155, -115, -60, -15, 15, 60, 115, 155, -155, -115, -60, -15]

Elevation = [20, 20, 20, 20, 20, 20, 20, 20, 40, 40, 40, 40, 40, 40, 40, 40, 60, 60, 60, 60, 60, 60, 60, 60]

Test Setup

P.800 DCR test, instructions mentioning spatial aspect.

4 categories, each category corresponding to the different talker pair.

6 panels, each using different audio samples and randomizations.

Naïve listeners.

4 listeners per panel

One listener at a time in the loudspeaker setup.

Four listeners at a time in the binaural setup.

24 listeners in total.

29 conditions. The randomization was done using a flexible algorithm, selecting conditions randomly with some constraints to balance distribution of conditions within each panel.

Each condition was evaluated 24 x 4 = 96 times.

Anchors - P.50 MNRUs (Modulated Noise Reference Units) [9] – applied coherently (using the same seed) to all ambisonic channels. 4 MNRU levels were used – 34, 29, 24, and 19 dB.

No SDRUs (Spatial Distortion Reference Unit) or ESDRUs spatial anchors were used as they are not defined for loudspeaker listening.

CuT – multi-mono EVS applied on FOA and HOA3 channels.

Rendering

All conditions rendered to 7.0+4 loudspeaker system or to binaural representation using All-Round Ambisonic Decoding (AllRAD) [20].

Rendering was done on concatenated files.

Level adjustment

The level was adjusted to -26 LKFS.

The direct signal level was first measured on the signal rendered to 7.0+4 loudspeaker system using B.1770 [12] and level difference was computed with -26 LKFS (Loudness, K-weighted, relative to Full Scale). The corresponding gain was then applied to the original HOA3 input channels. No level readjustment was done on the coded signals.

Listening laboratory - Immersive listening laboratory at the University of Sherbrooke.

Loudspeaker listening setup - 7.0+4 Genelec SAM 3031 speaker setup in the following configuration:

| Speakers | Azimuth | Elevation |
| --- | --- | --- |
| Left front | 30 | 0 |
| Right front | -30 | 0 |
| Centre front | 0 | 0 |
| LFE | - | - |
| Left rear surround | 135 | 0 |
| Right rear surround | -135 | 0 |
| Left side surround | 90 | 0 |
| Right side surround | -90 | 0 |
| Left front height | 30 | 35 |
| Right front height | -30 | 35 |
| Left rear surround height | 135 | 35 |
| Right rear surround height | -135 | 35 |

Binaural listening setup used Beyer Dynamic DT 770  Pro headphones.

Screening of listeners

Listeners were post-screened as follows. In order to be considered, a listener had:

To use the whole voting scale during the session. In other words, he must have voted at least once “1” and at least once “5”.

To vote, in average, the direct condition better than or equal to the MNRU 29 dB condition. To reflect the fact that the perceptual quality of MNRU 29 dB is close to Direct, the listener was still kept if the median of his votes for all anchor conditions was below 4.

To vote, in average, the MNRU 29 dB condition better than the MNRU 24 dB condition.

To vote, in average, the MNRU 24 dB condition better than the MNRU 19 dB condition.

To vote, in average, the MNRU 19 dB condition better than the MNRU 14 dB condition.

Comments

The tests took about 2 weeks.

Overall, naïve listeners could reliably detect coding deficiencies.

When coding ambisonic channels with EVS at low bitrates (below 24.4 kb/s), more ambisonic channels seem to degrade the perceptual experience rather than improve it.

Naïve listeners do not seem to be too sensitive to the spatial aspect, e.g., differentiating between FOA and HOA3. Nevertheless, they were still able to discriminate the direct HOA3 from FOA with statistical significance in both tests.

Despite clear and explicit instructions, and standard DCR voting labels used in the listening software interface, some listeners still did not understand the task.

Comparisons of results between the loudspeaker rendering and binaural rendering

Good correlation between the binaural listening test results and the loudspeaker listening test results.

In binaural listening, the listeners were able to distinguish HOA3 and FOA direct conditions better than in the loudspeaker listening.

Larger dynamics of results are observed for binaural listening than for loudspeaker listening.

Overall, the multi-mono EVS processing conditions were voted noticeably lower in binaural listening than in the loudspeaker listening.

For multi-mono EVS processing, at 24.4 kbps/channel, an advantage for FOA over HOA3 input is observed in binaural listening, but the opposite tendency is observed for loudspeaker listening

Conclusions

With some adjustments, the DCR test with naïve listeners seems to be a good trade-off between accuracy and efficiency.

EVS multi-mono seems to be a good reference, able to cover practically the whole range of perceptual quality.

More explicit initiation of naïve listeners to spatial aspects would be beneficial, e.g., an extended training session at the very least. Also, some discussion on listeners’ perception after the training session might help.

Agreed methodology for systematic post-screening of listeners would be useful.

* Milan Jelinek, VoiceAge Corporation; Milan.Jelinek@USherbrooke.ca