## 3GPP SA4 Rel-19 Planning
Date of SA4 meeting | 2024-08-24 | 2024-11-01 | 2025-02-01 | 2025-04-01 | 2025-05-01 | 2025-07-01 | 2025-11-01
SA meeting -> | SA#105 | SA#106 Rel-19 Stage 2 | SA#107 |  | SA#108 | SA#109 Rel-19 stage 3 | SA#110
SA4 Meeting-> | SA4#129 | SA4#130 | SA4#131 | SA4#131bis-e | SA4#132 | SA4#133 | SA4#134
Audio SWG | IVAS_Codec_Ph2 | IVAS_Codec_Ph2 | IVAS_Codec_Ph2 | IVAS_Codec_Ph2 | IVAS_Codec_Ph2
Audio SWG |  | ATIAS_Ph2 | ATIAS_Ph2 | ATIAS_Ph2 | ATIAS_Ph2 | ATIAS_Ph2
Audio SWG | 2024-08-24: FS_ACAPI; 2024-11-01: FS_ACAPI; 2025-02-01: FS_ACAPI
Audio SWG | FS_DaCED | DaCAS | DaCAS | DaCAS | DaCAS | DaCAS
MBS SWG | FS_MeMe | FS_MeMe | FS_MeMe | MeMe_Stage 3 | MeMe_Stage 3 | MeMe_Stage 3
MBS SWG | FS_AMD | FS_AMD | AMD Stage 2/3 | AMD Stage 2/3 | AMD Stage 2/3 | AMD Stage 2/3
MBS SWG | 2024-08-24: FS_MediaEnergyGREEN; 2024-11-01: FS_MediaEnergyGREEN; 2025-02-01: FS_MediaEnergyGREEN
Video SWG | 2024-08-24: FS_AI4Media; 2024-11-01: FS_AI4Media; 2025-02-01: FS_AI4Media
Video SWG | 2024-08-24: VOPS; 2024-11-01: VOPS; 2025-02-01: VOPS
Video SWG | FS_AVATAR | FS_AVATAR | FS_AVATAR | AVATAR Stage 3 | AVATAR Stage 3 | AVATAR Stage 3
Video SWG | 2024-08-24: FS_FGS
Video SWG | FS_Beyond2D | FS_Beyond2D | FS_Beyond2D | FS_Beyond2D | FS_Beyond2D
Video SWG | FS_ARSpatial | FS_ARSpatial | FS_ARSpatial | FS_ARSpatial | FS_ARSpatial
SA4 | 2024-08-24: FS_HapticMed
RTC SWG | 2024-11-01: FS_HapticMedia; 2025-02-01: FS_HapticMedia
RTC SWG | 2024-11-01: FS_iRTCW_Ph2; 2025-02-01: FS_iRTCW_Ph2; 2025-04-01: FS_iRTCW_Ph2; 2025-05-01: FS_iRTCW_Ph2
RTC SWG | FS_5G_RTP_Ph2 | FS_5G_RTP_Ph2 | 5G_RTP_Ph2 Stg. 3 | 5G_RTP_Ph2 Stg. 3 | 5G_RTP_Ph2 Stg. 3 | 5G_RTP_Ph2 Stg. 3
RTC SWG | 2024-08-24: SR_IMS; 2024-11-01: SR_IMS; 2025-02-01: SR_IMS
Total # SID/WID | 15 | 16 | 16 | 10 | 10 | 6 | 0
Endorsed
Agreed
Exception request
TBD
Completed
* this SI/WI is duplicated to reflect extra load