## Slide 1: TSG SA WG4 (SA4) Status Report at TSG SA#105
Frédéric Gabin
SA4 Chair (Dolby France SAS)
(Agenda Item 4.4)

## Slide 2: Outline
General
  Leadership and subgroups
  Meeting calendar and statistics
  Progress highlights
Work progress
  CRs to features in Release 18 and earlier
  Rel-19 Work Items
  Study Items
  New Work and Study Item(s)
SA4 Planning
IETF Dependencies
Summary of action items

## Slide 3: SA4 leadership and subgroups (1/2)
SA4 officials:
  Chair: Frédéric Gabin (Dolby France SAS, ETSI)
  Vice Chairs:
    Gilles Teniou (Tencent, CCSA)
    Jaeyeon Song (Samsung Electronics Co., Ltd, TTA)
  Secretary: Andrijana Brekalo (MCC Support)
Action from SA#104
Action: SA3, SA4, and SA5 WG should assess whether their current SWG should continue in its current form, or whether the work should be performed in the WG using relevant breakout session(s).
  The WG agreed proposal should be submitted to TSG#105 for approval.
  SA4#129-e Working Agreement: “The SA WG4 Chair declared that based on the discussion of Tdoc S4-241568 on SA assigned action with regards to SWG, “SA4 have assessed that their current SWG should continue in their current form. Compliance with Working procedures requires that ToRs submitted at SA#104 be re-submitted to SA#105 for approval. Also, the Audio SWG structure will be such that current “co-chairs” will become respectively Chair and Vice-Chair.” is a Working Agreement.” (https://www.3gpp.org/delegates-corner/3gpp-working-procedures/tsg-working-agreements)

## Slide 4: SA4 leadership and subgroups (2/2)
Sub Working Groups and their Chairs
  SWG ToRs agreed at SA4#128, postponed at SA#104 and for approval at SA#105: SP-241126:
  Audio SWG reports: SP-241292
  MBS SWG reports: SP-241293
  Video SWG reports: SP-241294
  RTC SWG reports: SP-241295
Audio SWG | Multicast-Broadcast-Streaming (MBS) SWG | Real Time Communications (RTC) SWG | Video SWG
Chair: Tomas Toftgård (Ericsson LM, ETSI) Vice-Chair: Stéphane Ragot (Orange, ETSI) Note: Chair and Vice-Chair positions agreed at SA4#129-e | Frédéric Gabin (Dolby France SAS, ETSI) | Saba Ahsan (Nokia corporation, ETSI) | Gilles Teniou (Tencent, CCSA)

## Slide 5: Meetings held since SA#104
SWG AH conference calls (2 to 3 hours each)
  Audio SWG: 28 June, 2nd September
  MBS SWG: 27 June, 11 July, 25 July
  Video SWG: 25 June, 9 July, 23 July
  RTC SWG: 26 June
SA4 plenary meetings
SA4 meeting(s) since last SA | Dates | Venue and Host
SA4#129-e | E-meeting: 19-23 August 2024 | Host: MCC, Electronic meeting

## Slide 6: Calendar of future meetings - 1
SWG AH conference calls
  Audio SWG: 2 Sep., 13 Sep., 18 Oct., 4 Nov.
  MBS SWG: 26 Sep., 10 Oct., 16-18 Oct. (e-meeting), 24 Oct.
  Video SWG: 8 Oct., 22 Oct., 29 Oct.
  RTC SWG: 25 Sep., 9 Oct., 23 Oct.
SA4 plenary meetings in next quarter
Meetings in 2024 | Dates | Venue and Host
SA4#130 | F2F: 18-22 November 2024 | Host: ATIS, Venue: Orlando, Florida, USA

## Slide 7: Calendar of future meetings - 2
SA4 plenary meetings (2025): 3 F2F and 2 e-meetings
Meetings in 2025 | Dates | Venue and Host
SA4#131 | F2F: 17-21 Feb. 2025 | Host: EBU, Venue: Geneva, Switzerland
SA4#131e-bis | E-meeting: 11-17 April 2025 | Host: MCC, Electronic meeting
SA4#132 | F2F: 19-23 May 2025 | Host: TBD, Venue: Japan
SA4#133e | E-meeting: 21-25 Jul. 2025 | Host: MCC, Electronic meeting
SA4#134 | F2F: 17-21 Nov. 2025 | Host: TBD, Venue: North-America

## Slide 8: Calendar of future meetings - 3
SA4 plenary meetings (2026): 3 F2F and 2 e-meetings
  * Only one of April or October bis meeting is expected to be needed.
Meetings in 2025 | Dates | Venue and Host
SA4#135 | F2F: 9-13 Feb. 2026 | Host: TBD, Venue: TBD
SA4#135e-bis* | E-meeting: 13-17 Apr. 2026 Note: dates TBC depending on MPEG#154 exact dates. | Host: MCC, Electronic meeting
SA4#136 | F2F: 11-15 May 2026 | Host: Interdigital, Venue: Montreal (confirmed)
SA4#137e | E-meeting: 24-28 Aug. 2026 | Host: MCC, Electronic meeting
SA4#137e-bis* | E-meeting: 12-16 Oct. 2026 Note: dates TBC depending on MPEG#156 exact dates. | Host: MCC, Electronic meeting
SA4#138 | F2F: 16-20 Nov. 2026 | Host: TBD, Venue: TBD

## Slide 9: SA4 meeting statistics
Note 1: the number of F2F participants at SA4#127 (88) is representative of a regular standalone SA4 F2F meeting.
Note 2: the number of Tdocs (533) per meeting at SA4#128 is at a record high

## Slide 10: SA4 progress highlights
A couple of Rel-17 corrections to 5G Multicast-Broadcast related to radio parameters
Several Rel-18 Corrections on completed features.
Rel-19:
  3 ongoing Work Items progressing as planned.
  12 ongoing Studies progressing:
    FS_DaCED planned completion delayed to SA#106
    FS_FGS completed with a reduced scope while JVET (Joint effort between ISO/IEC and ITU-T) progresses a similar study
    FS_AMD progressing slower than expected. An MBS SWG Ad hoc e-meeting is planned 16-18 October to accelerate progress.
    FS_Beyond2D progressing slower than expected.
    While the FS_ACAPI TR wasn’t progressed, SA4 agreed a proposal on 3GPP Codecs registration as Web Codecs.
    Other 7 studies progressing as planned
New work
  New Study on immersive Real-Time Communication for WebRTC, Phase 2 (FS_iRTCW_Ph2)
  New Work Item on Terminal Audio quality performance and Test methods for Immersive Audio Services, Phase 2 (ATIAS_Ph2)
SA4 IVAS codec real-time communication demo at TSG SA#105 (Room M14)

## Slide 11: CRs to features in Release 17 and earlier
TDoc | Title | TDoc Status | Release | Spec | Version | Related WIs | CR | CR revision | CR category | TSG CR Pack
S4-241399 | [5MBUSA] Radio parameters alignment | agreed | Rel-17 | 26.502 | 17.7.0 | 5MBUSA | 0032 | 2 | F | SP-241110
S4-241400 | [5MBUSA, TEI18] Radio parameters alignment | agreed | Rel-18 | 26.502 | 18.1.0 | 5MBUSA, TEI18 | 0031 | 1 | A | SP-241110
TDoc | Title | TDoc Status | Release | Spec | Version | Related WIs | CR | CR revision | CR category | TSG CR Pack
S4-241401 | [5MBP3] Make radio parameters optional | agreed | Rel-17 | 26.517 | 17.6.0 | 5MBP3 | 0022 | 1 | F | SP-241109
S4-241402 | [5MBP3, TEI18] Make radio parameters optional | agreed | Rel-18 | 26.517 | 18.1.0 | 5MBP3 | 0021 | 1 | A | SP-241109

## Slide 12: CRs to Release 18
TDoc | Title | Source | Agenda item | Agenda item description
SP-241106 | CR Pack on WIs 5G_MEDIA_MTSI_ext, TEI18 | SA WG4 | 18.4 | SA WG4 Rel-18 CRs
SP-241107 | CR Pack on WI 5GMS_Ph2 | SA WG4 | 18.4 | SA WG4 Rel-18 CRs
SP-241111 | CR Pack on WI GA4RTAR | SA WG4 | 18.4 | SA WG4 Rel-18 CRs
SP-241113 | CR Pack on WI iRTCW | SA WG4 | 18.4 | SA WG4 Rel-18 CRs
SP-241114 | CR Pack on WI ISAR | SA WG4 | 18.4 | SA WG4 Rel-18 CRs
SP-241115 | CR Pack on IVAS_Codec | SA WG4 | 18.4 | SA WG4 Rel-18 CRs
SP-241116 | CR Pack on WIs PSS_MBMS_OMTV, TEI18 | SA WG4 | 18.4 | SA WG4 Rel-18 CRs
SP-241117 | CR Pack on WI SR_MSE | SA WG4 | 18.4 | SA WG4 Rel-18 CRs
SP-241118 | CR Pack on WIs TEI18, EVEX | SA WG4 | 18.4 | SA WG4 Rel-18 CRs
SP-241119 | CR Pack on WIs TEI18, IBACS | SA WG4 | 18.4 | SA WG4 Rel-18 CRs
SP-241108 | CR Pack on WI 5GMS_Pro_Ph2 | SA WG4 | 18.5 | SA WG5 Rel-18 CRs

## Slide 13: Overview of work progress Rel-19 Work Items
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1030002 | Video Operating Points - Harmonization and Stereo MV-HEVC | VOPS | 3/3/2025 | 10% | SP-240060 | 20% | 
1030003 | Split Rendering over IMS | SR_IMS | 3/3/2025 | 15% | SP-240492 | 25% | 
1040021 | EVS Codec Extension for Immersive Voice and Audio Services, Phase 2 | IVAS_Codec_Ph2 | 6/6/2025 | - | SP-241000 | 5% | 

## Slide 14: Video Operating Points - Harmonization and Stereo MV-HEVC (VOPS)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030002 | Video Operating Points - Harmonization and Stereo MV-HEVC | VOPS | 3/3/2025 | 10% | SP-240060 | 20% | 
Purpose
Harmonize and include as needed all the SA4 video operating points into a new specification that will be home to all such video operating points and upgrade HEVC-based levels based on industry practices.
Define the MV-HEVC capability in this new specification.
Then add and harmonize stereoscopic MV-HEVC operating points and capabilities for TS 26.511, TS 26.119 and TS 26.143
Progress in the last quarter
Decided not to rely anymore on 3GP file format but rather on ISO BMFF
For messaging services pay attention to MeMAF and what is being done in FS_MeMe
CR endorsed on the inclusion of MV-HEVC into 5G Media Streaming.
Draft TS 26.265 Media Delivery: Video Capabilities and Operation Points, progressed to v0.3.0 with video representation formats, and updates to existing video capabilities
Next steps
Progressing pCR on draft TS 26.265
Endorse CRs to TS 26.118, TS 26.511
Endorse CRs to TS 26.143, TS 26.119

## Slide 15: Split Rendering over IMS (SR_IMS)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030003 | Split Rendering over IMS | SR_IMS | 3/3/2025 | 15% | SP-240492 | 25% | 
Purpose
Identify functional entities for IMS-based split rendering and introduce a mapping to the IMS architecture. Identify interfaces and define network APIs for delivering media from 3GPP and non-3GPP services for split rendering of XR services. Define protocols, procedures, and codecs for delivery of split-rendered media and metadata for support of split rendered content including uplink (e.g., pose), and downlink (e.g., rendered pose) as part of a new specification.
Progress in the last quarter
Progressed draft TS 26.567 Split rendering over IMS to v0.3.0 with the following items:
  Metadata formats
  General procedures for split rendering session modification
  Network centric procedures for adaption of split rendering
  Correction in the procedures for session establishment and editorial updates
Next steps
Progress format of split-rendered media, signaling protocols to enable split rendering over IMS, metadata formats, detailed procedures of rendering session management.

## Slide 16: EVS Codec Extension for Immersive Voice and Audio Services, Phase 2 (IVAS_Codec_Ph2)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1040021 | EVS Codec Extension for Immersive Voice and Audio Services, Phase 2 | IVAS_Codec_Ph2 | 6/6/2025 | - | SP-241000 | 5% | 
Purpose
The overall objective of this work item is to provide an improved set of IVAS specifications with a fixed-point C-code to be part of TS 26.251; characterization of the IVAS codec based on the floating-point and fixed-point C-codes, and documentation of characterization results into TR 26.997; Enhancements to codec conformance test procedures and criteria; definition of relevant tiers of functionality to be implementable on a wide range of UEs with different capabilities, balancing user experience and implementation complexity/cost; enhancements to the RTP payload format and SDP negotiation, including split rendering operation; update relevant system and service specifications.
Progress in the last quarter
An initial time plan was agreed
A proposal on IVAS negotiation and call setup was discussed and noted
Next steps
Review progress of the fixed-point code conversion
  fixed-point Decoder and Renderer
  fixed-point Encoder with following operation modes: Mono (EVS), ISM (core coder), Stereo, MCT, MASA, SBA, Parametric modes
Verification and Agreement by SA4 of the IVAS fixed-point Decoder and Renderer, fulfilling the FL-to-FX requirements

## Slide 17: Overview of work progress Study Items targeting Rel-19
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950011 | Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media | FS_AI4Media | 3/3/2025 | 75% | SP-220328 | 78% | 
980008 | Study on Diverse audio Capturing system for End-user Devices | FS_DaCED | 9/9/2024 ->12/12/2024 | 85% | SP-221330 | 90% | 
1000016 | Feasibility Study on Film Grain synthesis | FS_FGS | 3/3/2025 ->9/9/2024 | 30% | SP-230539 -> SP-241120 | 100% | SID revised and complete !
1000019 | Feasibility Study on Avatars for Real-Time Communication | FS_AVATAR | 12/12/2024 | 50% | SP-230544 | 55% | 
1030004 | Study on Media enerGy consumption exposuRE and EvaluatioN framework | FS_MediaEnergyGREEN | 3/3/2025 | 15% | SP-240481 | 30% | 
1030005 | Study on Media Messaging | FS_MeMe | 3/3/2025 | 10% | SP-240477 | 30% | 
1030006 | Study on Advanced Media Delivery | FS_AMD | 12/12/2024 | 15% | SP-241011 | 30% | 
1030007 | Study of 5G Real-time Transport Protocol Configurations, Phase 2 | FS_5G_RTP_Ph2 | 12/12/2024 | 40% | SP-240482 | 65% | 
1030008 | Study on Beyond 2D Video | FS_Beyond2D | 3/3/2025 | 10% | SP-240479 | 17% | 
1030009 | Study on Audio Codec APIs | FS_ACAPI | 3/3/2025 | 10% | SP-240480 | 10% | 
1030002 | Study on Haptics in 5G Media Services | FS_HapticsMed -> FS_HapticsMedia | 3/3/2025 | 0% | SP-240979 -> SP-241121 | 15% | Revised SID
1040022 | Study on Spatial Computing for AR Services | FS_ARSpatial | 6/6/2025 | 0% | SP-240927 | 10% | 

## Slide 18: Feasibility Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media (FS_AI4Media)
Purpose
The objectives of the study item are primarily to identify relevant interoperability requirements and implementation constraints of AI/ML in 5G media services.
Progress in the last quarter
The draft TR 26.927 is updated with a few agreements on the description of sign language translation scenario and NLP on speech in RTC, some updates on MPEG FCM, various approaches on the architecture mapping to IMS, some updates on metadata and a few descriptions of architectures for collaboration scenarios and their mapping to the UC.
On the evaluation side TR 26.847 is updated with NNC results in the context of automatic speech recognition.
Next steps
Complete analysis of collaboration scenarios. Review and refine TR 26.927; Agree on TR 26.927 v1.0.0 to be sent to SA plenary for information
Progress AI/ML evaluation; Agree on TR 26.847 v1.0.0 to be sent to SA plenary for information
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950011 | Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media | FS_AI4Media | 3/3/2025 | 75% | SP-220328 | 78% | 

## Slide 19: Study on Diverse audio Capturing system for End-user Devices (FS_DaCED)
Purpose
This study item considers codec-independent immersive voice and audio capturing configurations for end-user devices. The outcome of the studies can be used as guidelines for the manufacturers to deploy immersive voice and audio services.
Progress in the last quarter
An Editor update of TR 26.933 (v1.0.2) was reviewed and revised during the meeting. Several updates were discussed, agreeable parts were integrated. The updated TR could not be fully reviewed and edited online during the SA4#129-e meeting. Two offline sessions were scheduled to progress the TR. TR 26.933 (v1.1) was agreed as basis for further work and the Audio SWG telco of the 2nd September was granted SA4 power to agree on TR 26.933 to be sent to SA for approval. On the 2nd September Audio SWG telco the TR could not be completed. Hence the work completion is rescheduled to SA4#130.
Next steps
Complete TR 26.933 and its conclusions.
Send TR 26.933 for approval at SA#106
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
980008 | Study on Diverse audio Capturing system for End-user Devices | FS_DaCED | 9/9/2024 ->12/12/2024 | 85% | SP-221330 | 90% | 

## Slide 20: Feasibility Study on Film Grain synthesis (FS_FGS) – complete !
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1000016 | Feasibility Study on Film Grain synthesis | FS_FGS | 3/3/2025 ->9/9/2024 | 30% | SP-230539 | 100% | SID revised and complete!
Purpose
This study aims to evaluate use of Film Grain Synthesis (FGS) in 5G video services.
Progress in the last quarter
During the study, it was observed a dependency with a similar ongoing work happening in the Joint Video Exploratory Team - JVET (Joint effort between ISO/IEC and ITU-T) on performance evaluation aspects. It was then decided to document the work done so far into a technical report and close the study until significant progress is shown.
Study Item revised (SP-241120) to create a new internal TR 26.8xx Film Grain Synthesis (SP-241299) to document findings to this date. The report provides a preliminary analysis of the performance and the potential benefits of film grain synthesis technologies for video compression. This TR is ready for approval.
Next steps
n/a

## Slide 21: Feasibility Study on Avatars for Real-Time Communication (FS_AVATAR)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1000019 | Feasibility Study on Avatars for Real-Time Communication | FS_AVATAR | 12/12/2024 | 50% | SP-230544 | 55% | 
Purpose
Based on relevant TR 22.856 use cases, the study item aims, among other objectives, to collect and document Avatar animation and representation approaches, document the requirements for an interoperable base Avatar format.
Progress in the last quarter
agreed a description of the 3D-gaussian-splatting-based representation, even if acknowledged as a format not mature.
documented some mesh-based avatar protection approaches into the TR.
started to consider a mapping to IMS and noted a dependency with SA2
agreed a reference architecture for non-IMS services
agreed to rely on OpenXR API as the reference implementation, similarly to what we did with Media capabilities for AR.
TR 26.813 progressed to version 0.6.0
Next steps
Finalize list of potential requirements for the selection of the Avatar representation format,
Study the integration of Avatars into the RTC services (including WebRTC and IMS).
Study the cross-operation with split rendering.
Investigate the QoS, processing, and storage requirements for Avatars.
In collaboration with SA3, investigate security aspects of Avatars, including authentication, privacy, DRM, …
Document the network procedures and the impact on the 5G-RTC architecture.

## Slide 22: Study on Media enerGy consumption exposuRE and EvaluatioN framework (FS_MediaEnergyGREEN)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030004 | Study on Media enerGy consumption exposuRE and EvaluatioN framework | FS_MediaEnergyGREEN | 3/3/2025 | 15% | SP-240481 | 30% | 
Purpose
The study aims to identify sustainable media metrics, architectural impacts (APIs), functional extensions required for SA4 service enablers and evaluate the feasibility of an evaluation framework to facilitate efficient energy use and energy saving for media services.
Progress in the last quarter
Progressed TR 26.942 with:
  Related work in ITU-R
  Energy-related information amendment
  Additional use cases defined by SA4
  Description of the existing collection and exposure of energy consumption information at NF
  Key Issue #3: Evaluation framework
Next steps
Progress ongoing items
Initiate work on Conclusions and proposed next steps
Agree on TR 26.942 v1.0.0 to be sent to SA plenary for information.

## Slide 23: Study on Media Messaging (FS_MeMe)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030005 | Study on Media Messaging | FS_MeMe | 3/3/2025 | 10% | SP-240477 | 30% | 
Purpose
Key topics to be studied: A) Integration of TS 26.143 Capabilities and Profiles into IETF MIMI, B) Support of advanced file format, C) Support of external body content and late binding, D) DRM and encrypted content, E) Additional media experiences. In particular how they relate to the system and data models in TS 26.143 and collect additional industry requirements according to F) Additional industry requirements as above. Identify gaps and recommend potential normative work to enhance interoperability in Messaging Services.
Progress in the last quarter
Progress the study the integration of TS 26.143 capabilities and profiles into IETF MIMI content formats
TR 26.841 progressed to v0.2.0 including 3 agreed pCRS: IETF MIMI and 3GPP Messaging; Media Messaging Format; 3D Video Messaging Format
Next steps
Progress the study the integration of TS 26.143 capabilities and profiles into IETF MIMI content formats
Progress the study the suitability to enhance the specification of the MMBP Generator and MMBP Player in TS 26.143 by using the Media Service Enabler principles
Collaborate with MPEG to study the needs and functionalities for an advanced file format to be added to TS 26.143 based on bullet B above taking into account the key topics identified in objective 1.
Progress identifying gaps and recommend potential normative work to enhance interoperability in Messaging Services.
Present TR 26.841 v1.0.0 for information

## Slide 24: Advanced Media Delivery (FS_AMD)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030006 | Study on Advanced Media Delivery | FS_AMD | 12/12/2024 | 15% | SP-241011 | 30% | 
Purpose
Study the following topics
Progress in the last quarter
16 endorsed CRS to progress items 1, 2, 3, 4, 5, 6, 7, 8, 9, 12, 13 and new topic 14 (Inband Signaling of QoS for 5G Media Streaming) and 15 (Multi AS dynamic content generation and a sample solution). Several CRS noted for which we expect revisions.
0 | Specification Structure
1 | Common Client Metadata
2 | Common Server-and Network-Assisted Streaming.
3a | Multi-CDN and Multi-Access Media Delivery.
3b | Multi-Access with ATSSS
4 | Modem Usage Optimized Media Streaming.
5 | DRM and Conditional Access.
6 | In-session Unicast Repair for MBS Object Distribution.
7 | MBS User Service and Delivery Protocols for eMBMS.
8 | Selected MBMS Functionalities not supported in MBS.
9 | DASH/HLS Interoperability.
10 | Further harmonization of RTC and Streaming for Advanced Media Delivery.
11 | Issues identified by Market Representation Partners.
12 | Improved QoS support
13 | Impacts and opportunities of QUIC for segmented content delivery
Next steps
MBS SWG ad hoc e-meeting scheduled 16-18 October in addition to 3 telcos.
Progress candidate solutions including call flows, protocols and APIs for each of the identified issues.
Progress identifying gaps for stage-3 for relevant work topics.
Progress CRs relevant for potential issues related to stage-3
Communicate with other 3GPP working groups and external organizations, in particular 5G-MAG, on need basis
For October 17, 2024, a joint session with 5G-MAG from 15:00 to 16:30 is planned.

## Slide 25: 5G Real-time Transport Protocol Configurations, Phase 2 (FS_5G_RTP_Ph2)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030007 | Study of 5G Real-time Transport Protocol Configurations, Phase 2 | FS_5G_RTP_Ph2 | 12/12/2024 | 40% | SP-240482 | 65% | 
Purpose
Study the following Key Issues in more detail, and in particular how they relate to RTP and RTCP for WebRTC and IMS-based XR services: Inaccuracy of the PDU Set Size (PSSize) information, Issues around "lonely” PDU, as identified by SA2, Enhancements for application-layer FEC support (e.g., for split rendering); Application-layer FEC awareness for PDU Set handling; RTP transport of XR metadata; PDU Set marking for XR streams with RTP end-to-end encryption; RTCP messages to better support XR services in 5G; RTP retransmission for supporting XR services in 5G; Feasibility of RTP multiplexing options for transport of XR media streams; Document use cases and intended deployment scenarios of enhancements for RTP header extension for PDU Set marking; Enhancements of RTP header extension for PDU Set marking; End of Data Burst Marking.
Progress in the last quarter
Agreed inputs to TR 26.822 v1.0.0 on
Terms and abbreviations
MID packet filtering
PDU Set size
Lonely PDUs
RTP multiplexing
Delivery over multiple sessions
Data burst marking
RTP retransmission
Application Layer FEC
Support of XR services in 5G
TR 26.822 presented to SA for information (SP-241298)
Next steps
Identify gaps that require solutions for each of the key issues.
Discuss and agree on candidate solutions for the key issues requiring solutions.
Send TR 26.822 to SA for information

## Slide 26: Beyond 2D Video (FS_Beyond2D)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030008 | Study on Beyond 2D Video | FS_Beyond2D | 3/3/2025 | 10% | SP-240479 | 17% | 
Purpose
Identify and document beyond 2D formats, that are market-relevant within the next years, generated from established and emerging capturing systems (including cameras for spatial video capturing), contribution, and usable on display technologies (smartphones, VR HMDs, AR glasses, autostereoscopic and multiscopic displays). Establish and document a set of beyond 2D video end-to-end reference scenarios; Define concrete evaluation framework per scenario; Identify potential areas for normative work as the next phase and communicate with other 3GPP WGs regarding relevant aspects related to the study to the extent needed.
Progress in the last quarter
TR 26.956 progressed to version 0.1.0
Good progress made on the representation formats for stereoscopic video and point cloud representations.
Agreed to document NERF and 3D gaussian splats as more advanced formats, unlikely to be considered in release 19.
Reviewed quality example for the point cloud representations documented into the PD and considered quality metrics for stereoscopic video and candidate source sequences.
Next steps
For each agreed scenario:
  Define test conditions and evaluation framework per scenario.
  Collect and review test material, including test sequences, reference software tools and etc.
  Define performance metrics for each scenarios, communication with external groups, e.g., MPEG, to ask for potential metrics may be done.
  Evaluate the feasibility and performance of existing 3GPP codecs (H.265/HEVC) as well as potentially new codecs to support the scenarios.

## Slide 27: Audio Codec APIs (FS_ACAPI)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030009 | Study on Audio Codec APIs | FS_ACAPI | 3/3/2025 | 10% | SP-240480 | 10% | 
Purpose
The overall objective of this study item is to study APIs to provide support for 3GPP's speech and audio codecs in TS 26.114 and TS 26.117 for enhanced Web-based applications over 3GPP networks.
Progress in the last quarter
While the TR wasn’t progressed, SA4 agreed proposal on 3GPP Codecs registration as W3C WebCodecs.
  To register relevant 3GPP audio codecs as web codecs
  To support registration of relevant 3GPP video codecs (including AVC, HEVC, MV-HEVC) together with MPEG as web codecs including
  Consider to document codecs with MSE principles and support testing of codecs.
Such information will be added to the TR.
A registry will be created as part of 3GPP githubs.
Next steps
Identify relevant interfaces on hardware/firmware platforms to the (supported) relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, and characterize signal (including control signal and metadata) flows on these interfaces.
Continue to identify potential gaps in the 3GPP and W3C specifications to enable and simplify the use of the codecs in TS 26.114 and TS 26.117 in WebCodecs and WebRTC. Continue to identify common APIs for the relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, that are useable to expose the identified interfaces.

## Slide 28: Study on Haptics in 5G Media Services (FS_HapticsMedia)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030002 | Study on Haptics in 5G Media Services | FS_HapticsMed -> FS_HapticsMedia | 3/3/2025 | 0% | SP-240979 -> SP-241121 | 15% | Revised SID
Purpose (updated)
The study aims to investigate and identify the integration of haptics media in 3GPP communication and streaming services, including the identification of haptics input and representation formats, potential compression formats of haptics media, the integration into delivery systems, as well as QoE aspects.
Progress in the last quarter
Revised Study item to correct the acronym and adjust justification and objectives: SP-241121
TR 26.854 Study on Haptics in 5G Media Services was initiated and progressed with agreed inputs on : UseCase Immersive multi-modal XR and metaverse; Use case on haptic enhanced communication; Use case immersive entertainment; Haptic input formats; haptic device types.
Next steps
Identify and describe the candidate input formats for haptic experience, relevant to the above use-cases.
Identify relevant device types with support for haptic playback and/or capture.
Send TR 26.854 for information to SA#106

## Slide 29: Study on Spatial Computing for AR Services (FS_ARSpatial)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1040022 | Study on Spatial Computing for AR Services | FS_ARSpatial | 6/6/2025 | 0% | SP-240927 | 10% | 
Purpose
Study how spatial computing functions such as relocalization, mapping, and semantic perception are realized and identify the necessary set of spatial mapping information. Collect and document the different formats for spatial descriptions as well as interoperability requirements for such descriptions. Identify where spatial computing functions run and which media, metadata, and description formats are used for exchange between these elements based on the architecture defined in the TS 26.506, notably in split processing scenarios. And document relevant procedures, flows, configurations, QoE metrics, and transport protocols. Identify gaps in 3GPP TSs. Identify and recommend potential areas for normative work as the next phase and communicate/align with other potential 3GPP WGs and external organizations on relevant aspects related to the study.
Progress in the last quarter
TR 26.819 Study on Spatial Computing for Augmented Reality (AR) Services, progressed to version 0.1.0 based on a proposed skeleton and inputs on a description of spatial computing functions.
Next steps
Progress:
  Study spatial computing functions identify the necessary set of spatial mapping information.
  Collect and document spatial description formats.
  Document interoperability requirements for such descriptions.
  Mapping of spatial computing functions to the architecture defined in TS 26.506.

## Slide 30: New Work and Study Item(s)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1040021 | Study on immersive Real-Time Communication for WebRTC, Phase 2 | FS_iRTCW_Ph2 | 6/6/2025 | - | SP-241315 |  | SID
1050113 | Terminal Audio quality performance and Test methods for Immersive Audio Services, Phase 2 | ATIAS_Ph2 | 9/9/2025 | - | SP-241314 |  | WID

## Slide 31: Study on immersive Real-Time Communication for WebRTC, Phase 2 (FS_iRTCW_Ph2)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1040021 | Study on immersive Real-Time Communication for WebRTC, Phase 2 | FS_iRTCW_Ph2 | 6/6/2025 | - | SP-241315 |  | SID
Purpose
Document the following key issues in detail, and in particular how they relate to the existing RTC architecture and protocols specified in TS 26.506 and TS 26.113:
  Media capabilities, profiles and codecs for RTC
  Signalling and metadata to support immersive media capabilities
  Support of tethered cases in RTC system
Identify solutions for each of the key issues
Identify suitable one for key issues requiring solutions and recommend potential normative work to relevant specifications.

## Slide 32: Terminal Audio quality performance and Test methods for Immersive Audio Services, Phase 2 (ATIAS_Ph2)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1050113 | Terminal Audio quality performance and Test methods for Immersive Audio Services, Phase 2 | ATIAS_Ph2 | 9/9/2025 | - | SP-241314 |  | WID
Purpose
The following objectives are intended to be achieved in this work item:
  Consider additional requirements corresponding to the test methods in TS 26.260 and/or update requirements marked as TBD for sending and receiving characteristics of terminals in TS 26.261.
  Define new test methods and performance requirements/objectives, for the assessment of capture and playback of complex sound scenes, i.e., sound scenes with more than one source and from more than one defined direction.
  Define new test methods and performance requirements/objectives for the assessment of acoustic echo control. Test methods may be either completely new or be based on existing ones for mono telephony (from e.g., TS 26.132). In the latter case, it has to be investigated if and how such methods can be adapted for UEs providing immersive audio playback and/or capture capabilities.
  Define test methods and performance requirements/objectives for the assessment of binaural rendering in receive direction, including headtracking and motion-to-sound latency. Electrical as well as acoustical interfaces should be considered.
  Consideration of aspects, that are based on other ongoing work items, such as complexity level definitions in IVAS_Codec_Ph2.

## Slide 33: SA4 planning

## Slide 34: Dependencies on IETF drafts in SA4
No new dependency introduced
one dependency removed
IETF dependencies in SA4: new ones with red colour, those removed with green colour, and other updates by blue colour:
IETF draft name | 3GPP spec. number | CR# which introduced the dependency | Responsible person (in SA4) | Feature (Release) | Comments
Draft draft-ietf-mimi-content-01 | 26.143 | pCR in S4aI230183 | Frédéric Gabin | PROMISE (Rel-18) | To be further studied in Rel-19 as part of FS_Meme
draft-ietf-mmusic-rfc2326bis-18 | 26.234 | CR0126 | Frédéric Gabin | PSS_MBMS_OMTV (Rel-8) | Replaced by IETF RFC 7826 in CR 0233 (SP-241116)

## Slide 35: Summary of action items
Action Points from SA#104 to SA4:
Action: SA3, SA4, and SA5 WG should assess whether their current SWG should continue in its current form, or whether the work should be performed in the WG using relevant breakout session(s).
  The WG agreed proposal should be submitted to TSG#105 for approval.
  SA4#129-e Working Agreement: “SA4 have assessed that their current SWG should continue in their current form. Compliance with Working procedures requires that ToRs submitted at SA#104 be re-submitted to SA#105 for approval. Also, the Audio SWG structure will be such that current “co-chairs”. See https://www.3gpp.org/delegates-corner/3gpp-working-procedures/tsg-working-agreements
Action items from SA4 to SA#105:
  Approve SA4 SWG ToRs (SP-241126)
  Approve revised FS_FGS Study Item (SP-241120) to create a new internal TR 26.8xx Film Grain Synthesis and approve the TR (SP-241299) with a newly allocated TR number.
  Approve New Study on immersive Real-Time Communication for WebRTC, Phase 2 (FS_iRTCW_Ph2) (SP-241315)
  Approve New Work Item on Terminal Audio quality performance and Test methods for Immersive Audio Services, Phase 2 (ATIAS_Ph2) (SP-241314)
  Note FS_5G_RTP_Ph2 TR 26.822 presented to SA for information (SP-241298)
  Approve all Rel-17 and Rel-18 SA4 agreed CRs
  Invitation to enjoy the SA4 IVAS codec real-time communication demo at TSG SA#105 (Room M14 – Tuesday/Wednesday)