3GPP TSG-SA WG4 Meeting #135	S4aP260002

Goa, India, 9 – 13 February 2026	revision of S4aP260002

Agenda item: 	11.1

Source: 	Qualcomm Incorporated (Rapporteur)

Title: 	[FS_6G_MED] Time and Work Plan for Study on Media Aspects for 6G System

Version:	0.0.0

Document for	Agreement

# Introduction

During SA4#134 the Feasibility Study on “Media Aspects for 6G System” was agreed in S4-252142 and approved in by SA plenary #110 in SP-251652.

The objective of this study is in the context of the above background, referred to as work topics. Specifically, the following objectives are identified:

1.	Document the work topics introduced above in more detail, in particular how they relate to media delivery and taking into account the progress in other working groups:

- 	WT#1: Media Delivery Architecture

-	WT#2: 6G Media

- 	WT#3: Media Aspects related to SA2 topics

-	WT#4: Media for ubiquitous access

-	WT#5: Trusted and private media communication

2.	Identify the dependencies of the issue to other working groups and collect information on relevant developments within 3GPP and externally.

NOTE: 	Topics potentially requiring input into other WG studies or those creating dependencies on other work topics will be prioritized.

3.	Based on existing media delivery architectures and functionalities, as well as the development in SA2 architectures, and design concepts with respect to 6G, map the work topics to basic functions and develop high-level call flows, if appropriate.

4.	Identify potential gaps and opportunities that may need solutions and either

a)	recommend potential further study or normative work for stage-2 and stage-3, including which existing specifications would be impacted and/or if any new specifications would preferably be developed.

b)	provide candidate solutions that may address the issues

5.	Coordinate work with other 3GPP groups e.g. SA1, SA2, SA3, SA5, SA6 and others as needed.

6.	Coordinate work with external organizations such as SVTA, CTA WAVE, ISO/IEC JTC1 SC 29, 5G-MAG, Metaverse Standards Forum, Khronos or IETF, as needed.

During the study, the progress and results of 3GPP TR 22.870 (SA1 study), TR 38.960 (RAN study), TR 23.801-01 (SA2 study) and possibly other working groups shall be taken into account.

Specific work topics may be concluded earlier than the envisaged timeline below and may then be progressed in a dedicated study in a newly defined timeframe. In such a case this study will refer to the dedicated study where relevant.

The overall timeline is as follows

| New specifications |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Type | TS/TR number | Title | For info at TSG# | For approval at TSG# | Rapporteur |
| Internal TR | 26.870 | Study on Media Aspects for 6G System | TSG SA#114 (Dec-26) | TSG SA#115 (Mar-27) | Elmira Ramazanirend, Vodafone, (elmira.ramazanirend1@vodafone.com) |

This document provides

-	Context for the work and the relation to other working groups in clause 2.

-	Processes and Status in clause 3.

-	initial work plan to consider the completion of the work in the envisaged timelines in clause 4.

# Context

## 2.1	Justification from Work Item Description

The 5G network architecture marked a significant leap forward compared with previous generations, with its adoption of a Service-Based Architecture (SBA) enabling a cloud-native deployment, and 5G promoted business opportunities to providing services to verticals. These innovations enhanced flexibility and scalability, enabling more dynamic and adaptable network orchestration.

5G media services are built on top of this new architecture, primarily referring to the Media Delivery Architecture as defined in TS 26.501 and TS 26.506 for streaming and real-time communication.

While 5G is continuously introducing remarkable advancements, there is the need from operators for further CAPEX/OPEX reduction and monetization opportunities by further improvement of overall 3GPP system performance, as well as to introduce new services and experiences in the era of 6G. 6G brings a good opportunity to provide solutions to meet those needs, e.g. by means of simplifying the overall system, integrating of new technologies, etc.

March 2025 Workshop on 6G indicated of the motivation to be: Enabling new services and use cases beyond traditional communication, such as integrated sensing and communication (ISAC), XR/immersive communication, and AI-based services – Compute. And one of the 6G Goals to be “Improved end-user/customer experience through seamless, ubiquitous connectivity, ensuring reliable, high-quality services delivery. Optimized Quality of Experience (QoE) across diverse devices and network conditions.”

3GPP SA1 has started the FS_6G_REQ study item to identify use cases and service/operational requirements for 6G system. TSG RAN has also initiated the FS_6G_RAN_Scen_Req study item to develop requirements for 6G Radio. 3GPP SA2 has started the FS_6G_ARC study item to address critical challenges identified in 5G deployments and study the architecture aspects to support both connectivity service and beyond connectivity services in 6G era in a more efficient, sustainable, and innovative way.

This study is aimed to identify media-related opportunities and gaps in the context of 6G, building on SA1-defined service requirements and SA2-defined architectural enhancements. One of the objectives is to support the 6G studies in other working groups with media-related aspects. Another objective is to identify media-related industry trends from operators, third-party providers and verticals that may impact 6G media architectures.

## 2.2	Details on Work Topics

Potential work topics related to media aspects include the following:

1) Media Delivery Architecture: Study Media Delivery architecture aspects for 6G based on TS 26.501, TS 26.506 and the new developments in 6G architecture to support flexible deployment scenarios of new services e.g. XR/Immersive communication and use cases while maintaining relevant baseline services in alignment with SA2. The media delivery architecture is defined as collection, of capabilities and high-level functionalities. Aspects to be taken into account include, but are not limited to and not in priority order:

-	whether the current 5G media delivery architecture functionalities accommodate the new 6G use cases and identify which relevant components from 5G and possibly earlier Gs may be re-used and improved,

-	simplification of the architecture, for example for improved deployability and implementability,

-	possibly further harmonization of the media delivery architecture for streaming and conversational services,

-	collect relevant existing and emerging content delivery protocols and enable their use in 6G,

-	aligning the media delivery architecture with 6G design concepts to be defined by SA2,

-	aligning the architecture to accommodate commercially relevant media services and evolving standardization activities.

2)	6G Media: Identify trends and expected services related to media, in particular including immersive and AI related media, that may impact mobile networks in the 6G era and collect potentially relevant QoE requirements, traffic characteristics and other design vectors, also taking into account SA1 service requirements and use cases to support other working groups in 6G design. Study aspects include:

a)	End-to-end service quality for media services: Study aspects and identify opportunities to define end-to-end service quality for media-related services, in particular but not limited to when UEs are included in capturing and rendering. This includes capturing, rendering as well as definition of media related QoE metrics. The study will summarize existing documented metrics and consider if any new metrics may be needed.

b)	Traffic characteristics: Study and identify traffic characteristics of media services and use cases, including those mentioned in TR 22.870. The goal is to support the design of 6G radio and service architectures, based on initial SA1 service requirements and new developments in the media industry. Traffic characteristics from current and past studies are taken into account.

c) Immersive media formats and communication: collect, categorize and characterize (3C) media formats (including different media types) are emerging in the industry and/or currently specified and/or studied in 3GPP or elsewhere that could fit with 6G XR/immersive media service requirements and the related impacts to services such as ongoing in TR 22.870. Information from current and past studies (such as TR 26.956) are taken into account.

d) Media communication for emerging AI services: collect and study AI representation formats and traffic characteristics used in AI-related media services based on use cases (e.g. agents, multi-modal large language models, diffusion models) and the related impacts to services such as developed in TR 22.870 and identify gaps to potentially be addressed in 3GPP specifications, e.g. QoS requirements, dynamic traffic characteristics, or definition of relevant identified AI-representation formats.

3)	Media Aspects related to SA2 topics: Study if there are any media related aspects and impacts resulting from different SA2 study topics and identify if any work is needed to be addressed in SA4 including:

a) AI for 6G: Study if there are any media-related impacts related to "AI for 6G (e.g. AI agent, framework)" based on decisions and in alignment with WT#3 in the SA2 study, and other involved working groups.

b)	Integration of Sensing and Communication: Study if there are any media-related impacts related to "Integration of Sensing and Communication" based on decisions and in alignment with WT#4 in the SA2 study, and other involved working groups.

c)	Data handling: Study if there are any media-related impacts related to data handling including, for example, data collection, distribution, processing, storage, data access and data exposure, with consideration of access control/user consent and privacy where relevant based on decisions and in alignment with WT#5 in the SA2 study, and other involved working groups.

d)	Computing: Study if there are any media-related impacts related to support of computing for UE and application servers in 6G based on decisions and in alignment with WT#6 in the SA2 study, and other involved working groups.

NOTE: 	The analysis of the each of the above topics may just confirm that there is no impact on SA4-related specifications.

NOTE: 	The topics above may be updated based on decisions in upcoming SA2 meetings.

4)	Media for ubiquitous access: Study aspects and opportunities for support of media services on ubiquitous networks including Non-Terrestrial Networks and other low bit-rate/low power scenarios beyond speech. The primary focus is to identify supported bitrates, functionalities, delays, power consumption and other design vectors, in particular also taking into account the information collected in the FS_ULBC study.

5)	Trusted and private communication for media: Study and identify aspects and opportunities to support trusted and private media communication in applications including, but not restricted, to generative AI or agent to agent communication, including end-to-end workflows, authentication, trust and other aspects, and explore what role 6G can play in this.

NOTE: 	Coordination with SA3 is expected on authentication and trust-related topics.

The progress of the topics above may depend on progress in other working groups, and it is not expected that the first phase necessarily completes all work topics. Certain topics may require more time and be addressed later.

Certain topics may complement other ongoing studies and are not expected to be covered in this study, but only referred to unless additional aspects (in particular 6G aspects) need to be addressed.

## 2.3	Supporting Companies

| Supporting IM name |  |
| --- | --- |
| ABS | MediaTek Inc. |
| Apple Inc. | Mesaqin.com sro (Ltd.) |
| AT&T | NERC-DTV |
| ATEME | Nokia |
| Beijing Xiaomi Mobile Software Co., Ltd | Novamint |
| Bytedance | NTT |
| CATT | ONE Media 3.0 |
| China Mobile Com. Corporation | Orange |
| Deutsche Telekom AG | ORS |
| Dolby Laboratories Inc. | Qualcomm Incorporated |
| EBU | PengCheng Laboratory |
| Ericsson LM | Philips International B.V. |
| Fraunhofer HHI | Samsung Electronics Co. Ltd. |
| Fraunhofer IIS | Shanghai Jiao Tong University |
| Free Stream Technologies | Sony Europe Limited |
| Google | Tencent |
| Hisilicon | Thales |
| Huawei Technologies Co Ltd. | vivo Mobile Communication |
| Interdigital Communications | Viasat |
| Lenovo | Vodafone Group Plc. |
| LG Electronics Inc. | VoiceAge Corporation |
| MATRIXX Software | ZTE |

## 2.4	Status in Other Working Groups

### 2.4.1	SA1

SP-241152, New SID on 6G Use Cases and Service Requirements

TR 22.870 v1.0.1, Study on 6G Use Cases and Service Requirements

### 2.4.2	SA2

The following documents are relevant as output from SA4#172 (November 2025, Dallas) and SA#110 (December 2025, Baltimore)

TR 23.801-01 v0.3.0, Study on Architecture for 6G System; Stage 2

|  | SP-251633 | SID revised | Revised SID: Study on Architecture for 6G System | SA WG2 | approved |
| --- | --- | --- | --- | --- | --- |
|  | S2-2511308 | other | Detailed FS_6G_ARC Work Task scopes. | SA WG2 | approved |

Note that the SA2 6G study completion (SP-251633) has been decided during the last SA meeting and this is planned for March 2027, like this study. We may need to postpone completion for SA#116 instead if SA#115 in order to address this.

### 2.4.3	Other WGs

To be added.

# Agreed Processes and Status

## 3.1	Leads and Contributors for Each Work Topic

A work plan for each topic is available online here: https://docs.google.com/spreadsheets/d/1AHXc41lTVAJ84ENKfi2GgmpGx26hqHSoNQ7JKxnBNBo/edit?usp=sharing

A snapshot will be provided here when the document is published.

## 3.2	Agreed Working Methods

The following working methods were agreed: tbd

# Proposed Time and Work Plan

| Meeting | Feasibility Study on “Study on Media Aspects for 6G System” - #1100010 | Completion Status |
| --- | --- | --- |
| SA4#134 (17 – 21 November 2025, Dallas, US) | - Agree Study Item - Initial discussion of time plan - Initial discussion of draft TR | Target 0% Real |
| SA#110 (09 – 12 December 2025, Baltimore, US) | - Approve Study Item - Assign rapporteurs |  |
| 3GPP SA4 AHG Telco (Jan 15, 2026, 16:00-17:30 CET, Host Qualcomm) | - Agree initial work and time plan - Agree skeleton TR 26.870 to prepare submissions for SA4#135 - Agree some initial working procedures - Prepare initial thoughts for work topics - Identify initial contributors to work topics - Submission Deadline: Jan 13, 16 CET | Target 3% Real |
| SA4#135 (09 – 13 February 2026, Goa, IN) | - Agree work and time plan - Agree skeleton TR 26.870 - Agree initial working procedures - Identify leads and contributors for work topics - Address baseline assumptions, including SA1-based use cases and requirements, new media trends and principal ideas. - Document the scope and objectives of the work topics in more detail, in particular how they relate to media delivery and taking into account the progress in other working groups - Progress TR 26.870 - Communicate with other 3GPP working groups and external organizations on need basis | Target 10% Real |
| 3GPP SA4 AHG Telco (Feb 25, 2026, 16:00-17:30 CET, Host Qualcomm) | - Preparation of extended AHG meeting on FS_6G_MED - Identify common themes for workshop inputs. - Submission Deadline: tbd |  |
| SA#111 (10 – 13 March 2026, Fukuoka, JP) | - No actions |  |
| 3GPP SA4 AHG Telco (March 23 and 24, 2026, online, details tbd) | - AHG Meeting on FS_6G_MED - Address baseline assumptions, including SA1-based use cases and requirements, new media trends and principal ideas, clustered in common themes - Identify moderators/leads to summarize common topics. - Proposed times: - March 23: 15:00 – 17:00 CET (PT start at 7am due to daylight savings) - March 24: 15:00 – 17:00 CET (PT start at 7am due to daylight savings) - Note: There is a workshop scheduled here https://www.5g-mag.com/post/19-03-2026-workshop-on-media-energy-consumption-measurement-and-exposure |  |
| SA4#135e-bis (13 – 17 April 2026, online) | - Summary of the workshop on 6G Media Topics - Progress the work topics in more detail, in particular how they relate to media delivery and taking into account the progress in other working groups - Start identifying dependencies of the WT to other working groups and collect information on relevant developments within 3GPP and externally - Progress TR 26.870 - Communicate with other 3GPP working groups and external organizations on need basis | Target 20% Real |
| SA4#136 (11 – 15 May 2026, Montreal, CA) | - Progress the work topics in more detail, in particular how they relate to media delivery and taking into account the progress in other working groups - Progress identifying dependencies of the issue to other working groups and collecting information on relevant developments within 3GPP and externally - Progress TR 26.870 - Communicate with other 3GPP working groups and external organizations on need basis | Target 35% Real |
| SA#112 (09 – 12 June 2026, Singapore, SG) | - No actions |  |
| SA4#137-e (24 – 28 August 2026, online) | - Progress the work topics in more detail, in particular how they relate to media delivery and taking into account the progress in other working groups - Progress identifying dependencies of each WT to other working groups and collecting information on relevant developments within 3GPP and externally - Start mapping the work topics to basic functions and develop high-level call flows, based on existing media delivery architectures and functionalities, as well as the development in SA2 architectures, and design concepts with respect to 6G, if appropriate. - Start identifying potential gaps and opportunities that may need solutions - Progress TR 26.870 - Communicate with other 3GPP working groups and external organizations on need basis | Target 50% Real |
| SA#113 (15 – 18 September 2026, Madrid, ES) | - No actions |  |
| SA4#138 (16 – 20 November 2026, Calgary, CA, tbc) | - Complete the work topics in more detail, in particular how they relate to media delivery and taking into account the progress in other working groups - Progress identifying dependencies of the issue to other working groups and collecting information on relevant developments within 3GPP and externally - Progress mapping the work topics to basic functions and developing high-level call flows, based on existing media delivery architectures and functionalities, as well as the development in SA2 architectures, and design concepts with respect to 6G, if appropriate. - Start identifying potential gaps and opportunities that may need solutions - Start drafting Conclusions - Agree TR 26.870 v1.0.0 - Communicate with other 3GPP working groups and external organizations on need basis | Target 65% Real |
| SA#114 (08 – 11 December 2026, Boston, US) | - Present TR 26.870 v1.0.0 for information |  |
| SA4#139 (22 – 26 Feb 2027, tbd, Korea) | - Complete the work topics in more detail, in particular how they relate to media delivery and taking into account the progress in other working groups - Complete identifying dependencies of each WT to other working groups and collect information on relevant developments within 3GPP and externally - Complete mapping the work topics to basic functions and develop high-level call flows, based on existing media delivery architectures and functionalities, as well as the development in SA2 architectures, and design concepts with respect to 6G, if appropriate. - Start identifying potential gaps and opportunities that may need solutions - Agree on Conclusions - Agree TR 26.870 v2.0.0 - Communicate with other 3GPP working groups and external organizations on need basis | Target 90% Real |
| SA#115 (16 – 19 March 2027, TBD Europe) | - Present TR 26.870 v2.0.0 for approval NOTE: As the SA2 study on FS_6G_ARC completes at this time, it may require an extension until SA#116. |  |