3GPP TSG-SA WG4 Meeting #135	S4-260130r2

# 9-13 February 2026, Goa, India

Source:	Xiaomi

Title:	Work Plan for Advanced Video Formats and Operation Points (FS_AVFOPS_MED)

Agenda item:	9.5

Document for:	AGREEMENT

# 1 Introduction

This document contains the Work Plan for Advanced Video Formats and Operation Points (FS_AVFOPS).

# 2 Objectives

The study item will address the following objectives:

1.	Identify relevant new representation formats not yet documented in TS 26.265 and provide their benefits in terms of user experience. The analysis includes potential format specificities for capture at interoperability point 2 and for rendering at interoperability point 4. Candidate representations include support for alpha, depth together with stereo, and additional colour subsampling 4:2:2 or 4:4:4.

2.	Study the feasibility of generating the video signals corresponding to the hypothetical optical system (interoperability point 2) by:

a.	Documenting the requirements of real-time capturing systems in order to meet the video signal characteristics, e.g. temporal alignment of captured pictures, frame rate, bit depth, etc. (interface points 1a and 1b)

b.	Identifying the different types of video processing functions applied to video source signals from typical UE capturing systems, including the possibility of AI-based image generation (interoperability point 2).

3.	Identify compression options for the representation formats based on video codecs supported in 3GPP specifications, with HEVC as priority (interoperability point 3 and 3bis).

4.	Identify the opportunities and needs to integrate the representation formats into different transport systems, including messaging, real-time communication, split rendering and streaming formats (interoperability point 3 and 3bis).

5.	Define the expected traffic characteristics for new representation formats to meet certain quality thresholds.

6.	Further develop the bitstream conformance environment, including hosting, tooling and process, as well as collecting sample bitstreams illustrating of the new representation formats identified in objective 1.

7.	Identify gaps in the following specifications:

- In 3GPP specifications, especially on operation points, and provide guidance for potential normative work.

- In specifications defined by other SDOs (e.g. MPEG) and coordinate possible actions with the relevant SDOs.

8.	Perform the above work in coordination with related SDOs and industrial fora such as MPEG, SVTA, CTA-WAVE, and IETF, and by referencing the related specifications, e.g. the Common Media Application Format (CMAF) and the ISO base media file format (ISOBMFF), among others.

# 3 Study working methods

## 3.1	Contributions to the study

The following working methods are recommended for developing the study:

- An individual CRs are created for specific aspects of the work, e.g., a CR per new scenario.

- A merged CR will be created at the end of the study to compile all the changes to TR 26.966.

- Company proposal to progress CRs are submitted as “discussion” TDoc. If agreed, the responsible person of the CR will implement the agreement.

## 3.2	CR statuses

| CR | Title | Latest endorsed version | Clause in spec | Responsible person |
| --- | --- | --- | --- | --- |
| 0001r3 | New scenario: Video with changeable background | S4-260131 | 5.6 (new clause) | Emmanuel Thomas |
| 0002r3 | New scenario: Refocusable video | S4-260143 | 5.7 (new clause) | Emmanuel Thomas |
| 0003r1 | New scenario: Video with semantic segmentation map | S4-260174 | 5.8 (new clause) | Emmanuel Thomas |
| 0004 | Updates to possible solutions and mapping to scenarios | S4-260224 | 6, 6.0, 6.10 (new), 6.11 (new) | Emmanuel Thomas |

## 3.3	Conformance PD

The AVFOPS_MED study covers conformance aspects of TS 26.265 and preparation work for possible normative work following AVFOPS_MED. To this end, a Permanent Document is maintained for tracking the progress of this work.

The latest agreed version is: S4-260352

# 4 Work plan

The following work plan is proposed. After each 3GPP SA4 meeting, Video SWG AhG call will be scheduled based on the current progress status and needs for progressing the work.

| Meeting | Action plan |
| --- | --- |
| SA4#134 (17th-21tst November 2025, Dallas, US) | - Start work on objectives 1, 2 and 3. - If needed, communicate with external organisations (objective 8). |
| 3GPP SA4 Video SWG AHG Telco (Dec 16, 2025, 15:00-17:00 CET, Host Qualcomm) | - Continue work on objectives 1, 2 and 3. - Submission deadline: Dec. 15th 3pm CET |
| SA4#135 (9th-13th Feb 2026, Goa, IN) | - Continue work on objectives 1, 2 and 3. - If needed, communicate with external organisations (objective 8). |
| 3GPP SA4 Video SWG AHG Telco (March 17th, 2026, 15:00-17:00 CET, Host Qualcomm) | - Continue work on objectives 1, 2 and 3. |
| 3GPP SA4 Video SWG AHG Telco (March 31st, 2026, 15:00-17:00 CEST, Host Qualcomm) | - Continue work on objectives 1, 2 and 3. - Start work on objectives 4, 5, 6 and 7. |
| SA#111 (10th – 13th March 2026, Fukuoka, JP) | No action |
| SA4#135-bis-e (13th – 17th April 2026) | - Continue work on objectives 4, 5, 6 and 7. - If needed, communicate with external organisations (objective 8). |
| SA4#136 (11th – 15th May 2026, Montreal, CA) | - Complete work on all objectives 1 to 7. - If needed, communicate with external organisations (objective 8). - Endorsement of Work Item Summary. |
| SA#112 (9th–12th June 2026, Singapore, SG) | - Approval of CR to TR 26.966. |

# 5 Proposal

It is proposed to agree on the work plan provided in clause 4.