## Slide 1: Exec Report SA5#133e Charging Management (CH)
Maryse Gardella SA5 Vice Chair, Nokia

## Slide 2: Incoming LSs
Tdoc | Title | Source | Decision | ReplyIn
S5-205012 | LS ccSA5 on support of stateless NFs | C3-204386 | Noted | 
S5-205014 | Resubmitted LS Out to SA2 and SA5 on making PSCELL ID available at the SGW of EPC | ETSI TC LI | Noted | 

## Slide 3: Outgoing LSs
Tdoc | Title | To | Cc | ReplyTo
S5-205436 | LS on Network Slice PA Charging per maximum utilized bandwidth | SA2 |  | 

## Slide 4: Charging (CH) WIs/SIs

## Slide 5: Summary of ongoing CH WIs/SIs
WI code | WI Title | Completion rate | Target date
5GSIMSCH | IMS Charging in 5G System Architecture | 30%->35% | SA#91 (03/2021)
5G_URLLC | Charging enhancement for URLLC | 0%-> 10% | SA#92 (06/2021)
TEI17_NIESGU | N40 Interface Enhancements to Support GERAN and UTRAN | 0%-> 0% | SA#93 (09/2021)
FS_EDGE_CH | Study on charging aspects of Edge Computing | 0%-> 15% | SA#91 (03/2021)
FS_5G_CIoT_CH | Study on charging aspects of 5GS CIoT | 0%-> 5% | SA#93 (09/2021)
FS_5G_Prose_CH | Study on charging aspects of Proximity-based Services in 5GC | 0%-> 0% | SA#91 (03/2021)

## Slide 6
New or Revised Charging SIDs/WIDs
Number | Title | Source
S5-205468 | Revised SID on charging aspects of Proximity-based Services in 5GC | CATT

## Slide 7
Charging Exception requests
Number | Title

## Slide 8
WI code | WI Title | Completion rate | TS/TR | Tdoc reference | Target date | Rapporteur | Related groups | Related topic
5GSIMSCH | IMS Charging in 5G System Architecture | 30%-> 35% | TS 32.240, TS 32.260, TS 32.275, TS 32.281, TS 32.290, TS 32.291, TS 32.298, TS 32.297 | SP-190367 | SA#91 (03/2021) | Ericsson | - | -
5GSIMSCH
CRs were agreed to TS 32.260 :
  Introduction of IMS converged charging architecture applicable to MRFC, IMS-GWF and SIP AS
  Introduction of CHF CDRs generation for IMS charging
Working Progress

## Slide 9
WI code | WI Title | Completion rate | TS/TR | Tdoc reference | Target date | Rapporteur | Related groups | Related topic
5G_URLLC | Charging enhancement for URLLC | 0%-> 10% | TS 32.255, TS 32.291, TS 32.298 | SP-200769 | SA#92 (06/2021) | Huawei | - | -
5G_URLLC
CRs were agreed to TS 32.255 :
  Introduction of URLLC Charging Requirement
  Introduction of few principles for URLLC charging for the 3 scenarios:
    - Dual Connectivity based end to end Redundant User Plane Paths;
    - Redundant transmission on N3/N9 interfaces;
    - Redundant transmission at transport layer.
Working Progress

## Slide 10
WI code | WI Title | Completion rate | TS/TR | Tdoc reference | Target date | Rapporteur | Related groups | Related topic
TEI17_NIESGU | N40 Interface Enhancements to Support GERAN and UTRAN | 0%-> 0% | TS 32.240,, TS 32.251, TS 32.255, TS 32.290, TS 32.291, TS 32.298 | SP-200854 | SA#93 (09/2021) | China Mobile | - | -
TEI17_NIESGU
(Not input)
Working Progress

## Slide 11
WI code | WI Title | Completion rate | TS/TR | Tdoc reference | Target date | Rapporteur | Related groups | Related topic
FS_EDGE_CH | Study on charging aspects of Edge Computing | 0%-> 15% | TR 28.815 | SP-200467 | SA#91 (03/2021) | Intel Corporation (UK) Ltd | - | -
FS_EDGE_CH
pCRs agreed to TS 28.815 for
  Business roles description (ASP, ECSP, MNO)
  SA6 and SA2 architectures references
  introduction of initial scenarios and potential charging requirements: subscribers charging for using the 5G capabilities supporting edge computing, ASP and/or ECSP charging for 5GS capabilities provided for edge computing
Proposals to cover the area of « Billing domain » did not reach consensus (not part of our ToR)
Draft TS 28.815 (email approval S5-205464)
Working Progress

## Slide 12
WI code | WI Title | Completion rate | TS/TR | Tdoc reference | Target date | Rapporteur | Related groups | Related topic
FS_5G_CIoT_CH | Study on charging aspects of 5GS CIoT | 0%-> 5% | TR 28.816 | SP-200771 | SA#93 (09/2021) | Huawei | - | -
FS_5G_CIoT_CH
pCRs agreed to TS 28.816 for Scope and general background
Draft TS 28.816 (email approval S5-205467)
Working Progress

## Slide 13
WI code | WI Title | Completion rate | TS/TR | Tdoc reference | Target date | Rapporteur | Related groups | Related topic
FS_5G_Prose_CH | Study on charging aspects of Proximity-based Services in 5GC | 0%-> 0% | TR 32.846 | SP-200767 | SA#91 (03/2021) | CATT | - | -
FS_5G_Prose_CH
Working Progress
pCRs agreed to TS 28.846 for skeleton and Scope
Draft TS 28.846 (email approval S5-205471)

## Slide 14
Charging TSs & TRs to be sent to SA#90
Number | Title | For

## Slide 15: Charging CRs
Maintenance and Rel-16 small Enhancements

## Slide 16: Thank you!