## Slide 1: AI/ML Management – Phase 2: Work plan & guidelines
NEC, Intel
3GPP TSG-SA5 Meeting #159 S5-250308
Sophia-Antipolis, France, 17 – 21 February 2025

## Slide 2: Content
Rel-19 WID objectives
Completion target & allocated TUs
Work plan & key milestones
General guidelines

## Slide 3: AI/ML management – phase 2 (1/3)
Rel-19 WID approved at SA#106 in SP-241944
Objectives:
The objectives of AI/ML management phase 2 work item are to specify the management capabilities to support AI/ML functions defined by 3GPP, including:
  - NG-RAN AIML-based Coverage and Capacity Optimization, and NG-RAN AIML-based Network Slicing defined by RAN3,
  - Model delivery/transfer as defined by RAN1/2,
  - ML model training and AI/ML inference functions for 5GC as defined by SA2, and
  - MDA (Management Data Analytics) as defined by SA5.
To achieve these objectives, the following work tasks are defined:

## Slide 4: AI/ML management – phase 2 (2/3)
To achieve these objectives, the following work tasks are defined:
WT-1: Specify the AI/ML management capabilities including use cases, requirements and solutions for the relevant AI/ML lifecycle operational steps based on TR 28.858, including:
WT-1.1: Management capabilities for ML model training:
- ML-Knowledge-based Transfer Learning, - ML pre-training and fine-tuning, - ML model training for multiple contexts, - ML training data statistics, - ML model confidence, - Management of Reinforcement Learning, - Sustainable AI/ML for ML training, - ML model Distributed training, - Management of Federated Learning, - ML authentication, - AI/ML prediction latency, - ML explainability.

## Slide 5: AI/ML management – phase 2 (3/3)
WT-1.2: Management capabilities for AI/ML inference emulation:
  - ML inference emulation, - ML inference emulation environment selection.
WT-1.3: Management capabilities for ML model deployment:
  - Enhancements to ML model loading,
  - ML model transfer/delivery.
WT-1.4: Management capabilities for AI/ML inference:
  - Coordination between the ML capabilities, - Sustainable AI/ML for AIML inference, - ML remedial action management, - Managing ML models in use in a live network, - AI/ML prediction latency, - ML explainability.
NOTE: Solutions for the defined use cases shall leverage the already existing specified capabilities in TS 28.105 where applicable.

## Slide 6: Completion target & allocated TUs
Completion target: SA#109, September 2025
Total of 4 SA5 meetings to completion target,
Estimated total time allocation: 5 Tus, an average of ~ 1.25 TU per meeting
Work Task ID | TU Estimate
1.1 | 1.7
1.2 | 0.4
1.3 | 0.6
1.4 | 1.2

## Slide 7: Work plan & key milestones
Address a subset of WI work tasks per meeting, adding other WTs progressively in following sessions to maintain focus and ensure manageable discussions, avoiding overload and making each meeting more productive, while ensuring focused and efficient discussions to drive progress, allowing quick resolution of issues and clear next steps.
Stabilize stage 1 & stage 2 content by May (SA5#161), providing a solid foundation for Stage 3 development, minimizing last-minute rework and avoiding stressful times prior to SA#109 (September 2025).
Complete Stage 3 development and finalization by end of SA5#162 (August 2025), allowing enough time for thorough review and adjustments to ensure a refined, well-reviewed Stage 3 well in time for September target completion.
CRs or Draft CR, Rapporteurs suggest adopting Draft CRs for content under progressive development, converting them into CRs once the content becomes mature and stable. For standalone and non-controversial content, it can be submitted directly as CRs to the TS…further guidelines on this approach from SA5 leads/MCC are welcome.
Outcome - the above measures allow us to achieve smooth progression towards the September 2025 completion target, ensuring that all specification stages are completed in time.

## Slide 8: Plan of work - SA5#159 (February 2025)
Focus is on WT-1.1 and WT-1.2, addressing both stage 1 and stage 2 specifications:
  WT-1: Specify the AI/ML management capabilities including use cases, requirements and solutions for the relevant AI/ML lifecycle operational steps based on TR 28.858, including:
  WT-1.1: Management capabilities for ML model training:
  - ML-Knowledge-based Transfer Learning, - ML pre-training and fine-tuning, - ML model training for multiple contexts, - ML training data statistics, - ML model confidence, - Management of Reinforcement Learning, - Sustainable AI/ML for ML training, - ML model Distributed training, - Management of Federated Learning, - ML authentication, - AI/ML prediction latency, - ML explainability.
  WT-1.2: Management capabilities for AI/ML inference emulation:
  - ML inference emulation, - ML inference emulation environment selection.

## Slide 9: Plan of work - SA5#160 (April 2025)
In addition to WT-1.1 & WT-1.2, the following WTs are also in the scope of SA5#160:
WT-1.3: Management capabilities for ML model deployment:
  - Enhancements to ML model loading,
  - ML model transfer/delivery.
WT-1.4: Management capabilities for AI/ML inference:
  - Coordination between the ML capabilities, - Sustainable AI/ML for AIML inference, - ML remedial action management, - Managing ML models in use in a live network, - AI/ML prediction latency, - ML explainability.

## Slide 10: Plan of work - SA5#161 (May 2025)
All WTs are in the scope of SA5#161,
while aiming to finalising/stabilising stage 1, specific goal would also be on finalising stage 2 specifications.

## Slide 11: Plan of work - SA5#162 (August 2025)
All WTs are in the scope of SA5#162,
specific focus would be on addressing any gaps in stage 2, aiming specifically to finalise Stage 2 and stage 3 specifications.

## Slide 12: Guidance & Recommendations for Contributions
Contributions are encouraged to include a “clear and detailed justification” for their proposed inclusion in the specification. It is worth noting that content in the TR may not always guarantee allocation in the normative specification.
It is recommended that contributions align with the overall goals and the corresponding Work Item tasks for consistency and relevance.
Contributors are advised to adhere to the planned scope for each meeting to ensure effective progress, as submissions outside the planned agenda may be deprioritized to maintain focus and efficiency.
Companies are encouraged to address controversial issues through offline discussions before F2F meetings. The rapporteur can assist by facilitating discussions via pre-arranged calls or ad hoc meetings to help resolve such issues.
For use cases with multiple, potentially contradictory or competing solutions, it is recommended to resolve discrepancies in advance to build consensus and avoid delays during decision making stage.