## Slide 1: Rel-19 SA5 work planning SA5#160, Goteborg, Sweden, 07 - 11 April 2025
Zou Lan, 3GPP SA5 Chair, HUAWEI
Thomas Tovinger, 3GPP SA5 Vice-Chair, ERICSSON
Anatoly Andrianov, 3GPP SA5 Vice-Chair, NOKIA
Gerald Görmer, SA5 Charging SWG Chair, MATRIXX Software

## Slide 2: Content
Release 19
  Release 19 timeline– figure with SA5
  WIs/SIs in other 3GPP WGs potentially related to SA5

## Slide 3
Group members are welcome to contact SA5 Chair offline for any opinions on the time plan
Release 19 timeline– figure with SA5 (Based on SA timeline)
Release 19 timeline
#101
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA including SA5)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop
Management requirements (SA5)
Stage 2 (SA5) Normative supporting SA&RAN
OAM:
Dec 2024: conclude Rel-19 studies which plan to have corresponding normative work in Rel-19.
Sep 2025: conclude all Rel-19 work items, majority work items are preferable to be finalized in Jun 2025.
CH:
Mar 2025: conclude Rel-19 studies which plan to have corresponding normative work in Rel-19.
Sep 2025: conclude all Rel-19 work items
Note: Studies can continue until Sep.2025 if no corresponding normative work is planned for Rel-19.
3GPP SA5
Time plan

## Slide 4: Reminder for Rel-19 work
All Rel-19 work shall be 100% completed no later than SA5#162 (Aug.2025), preferably majority normative work to be completed in SA5#161 (May.2025).
  The work tasks which need more time for discussion should be postponed, submitted to Rel-20 plan for approval if needed.

## Slide 5: Content
Release 19
  Release 19 timeline– figure with SA5
  WIs/SIs in other 3GPP WGs potentially related to SA5

## Slide 6: Overview of Rel-19 SA5 OAM topics (full list)
 |  | Abbr. | Acronym | Title | UID | rapp | Tdoc | TS/TR | Type
Intelligence and Automation | 1 | AIML | FS_AIML_MGT_Ph2 | Study on AI and ML management phase 2 | 1020007 | Intel, NEC | SP-231780 | TR 28.908 | SID
 |  |  | -> AIML_MGT_Ph2 | AI/ML management phase 2 | 1060011 | NEC, Intel | SP-241944 | TS 28.105/552/554/541 | WID
 | 2 | MDA | FS_eMDAS_Ph3 | Study on Management Data Analytics (MDA) – Phase 3 | 1020019 | Huawei | SP-231726 | TR 28.866 | SID
 |  |  | -> eMDAS_Ph3 | Management Data Analytics phase 3 | 1060014 | Huawei | SP-241947 | TS 28.104 | WID
 | 3 | IDM | FS_IDMS_MN_Ph3 | Study on intent driven management services for mobile networks phase 3 | 1020008 | Huawei, Ericsson | SP-231737 | TR 28.914 | SID
 |  |  | -> IDMS_MN_Ph3 | Intent driven management services for mobile network phase 3 | 1060013 | Huawei, Ericsson | SP-241946 | TS 28.312 | WID
 | 4 | CCL | FS_CCLM | Study on Closed Control loop management | 1020009 | Samsung, Nokia | SP-231735 | TR 28.867 | SID
 |  |  | -> CCLM | Closed Control Loop Management | 1060010 | Samsung, Nokia | SP-241943 | TS 28.567/535/536/622/32.161 | WID
 | 5 | NDT | FS_NDT | Study on Management aspect of Network Digital Twin | 1020018 | CMCC | SP-231727 | TR 28.915 | SID
 |  |  | -> NDT | Management aspects of Network Digital Twins | 1060005 | CMCC | SP-241938 | TS 28.561 | WID
Management Architecture and Mechanisms | 6 | CMO | FS_Cloud_OAM | Study on cloud aspects of management and orchestration | 1020010 | CMCC | SP-241566 | TR 28.869 | SID
 | 7 | MSEC | FS_SECM | Study on Enablers for Security Monitoring | 1020016 | Nokia | SP-231736 | TR 28.870 | SID
 | 8 | SBMA | FS_SBMA_Ph3 | Study on SBMA enhancement phase 3 | 1020011 | Huawei, Ericsson | SP-231725 | TR 28.871 | SID
 |  |  | ->SBMA_Ph3 | Service Based Management Architecture enhancement phase 3 | 1060006 | Huawei, Ericsson | SP-241939 | TS 28.533/… | WID
 | 9 | PTM | FS_PlanM | Study on Plan management | 1020033 | Nokia, Ericsson | SP-231721 | TR 28.872 | SID
 |  |  | -> PlanM | Management of planned configurations | 1050032 | Nokia | SP-241379 | TS 28.572 | WID
 | 10 | MADCOL | MADCOL_Ph2 | Data Management phase 2 | 1020025 | Nokia | SP-250116 | TS 28.622 | WID
 | 11 | SEPM | FS_Data_SREP | Study on data management, regarding subscriptions and reporting | 1020012 | Ericsson | SP-231732 | TR 28.873 | SID
 |  |  | -> Data_SREP | Data management, regarding subscriptions and reporting | 1050033 | Ericsson | SP-241380 | 28.537/28.550/28.532/32.421/32.422/32.423/28.404/28.405/28.622/28.623 | WID
 | 12 | PM | PM_KPI_5G_Ph4 | 5G performance measurements and KPIs phase 4 | 1020026 | China Telecom, ZTE | SP-231747 | TS 28.552/554 | WID
 | 13 | AdNRM | AdNRM_Ph3 | 5G Advanced NRM features phase 3 | 1020027 | Nokia, Huawei | SP-250123 | TS 28.541/622 | WID
 | 14 | TMQ | TraceQoE_OAM | Subscriber and Equipment Trace and QoE collection management | 1020028 | Ericsson | SP-250115 | TS 32.422/405 | WID
 | 15 | NTNM | FS_ NTN_OAM_Ph2 | Study on Management Aspects of NTN Phase 2 | 1020013 | China Unicom, CATT | SP-231733 | TR 28.874 | SID
 |  |  | ->NTN_OAM_Ph2 | Management Aspects of NTN Phase 2 | 1060016 | China Unicom, CATT | SP-241949 | TS 28.541/552/554/658/662/540/530 | WID
 | 16 | IABM | FS_NR_mobile_IAB_OAM | Study on Management of IAB Nodes | 1020014 | Ericsson | SP-231729 | TR 28.875 | SID
 |  |  | -> NR_mobile_IAB_OAM | Management of IAB nodes | 1060015 | Ericsson | SP-241948 | TS 28.541/540/531/314/315 | WID
 | 17 | RedcapM | FS_NR_RedCap_OAM | Study on management aspects of RedCap feature | 1020017 | China Unicom, Asiainfo | SP-231734 | TR 28.876 | SID
 |  |  | ->NR_RedCap_OAM | Management Aspects of RedCap features | 1060008 | China Unicom, Asiainfo | SP-241941 | TS 28.540/541/552/554 | WID
 | 18 | NWDAFM | FS_NWDAF_OAM_Ph2 | Study on Enhancement of Management Aspects related to NWDAF Phase 2 | 1020020 | China Telecom | SP-231724 | TR 28.877 | SID
 |  |  | -> NWDAF_OAM_Ph2 | Enhancement of Management Aspects related to NWDAF Phase 2 | 1050031 | China Telecom | SP-241378 | 28.552/28.541 | WID
 | 19 | NSM | FS_NetShare_OAM_Ph3 | Study on Management of Network Sharing Phase 3 | 1020015 | China Unicom | SP-231731 | TR 28.878 | SID
 |  |  | ->NetShare_OAM_Ph3 | Management of Network Sharing Phase 3 | 1060017 | China Unicom, China Telecom | SP-241950 | TS 28.552/32.130/28.541 | WID
Support of New Services | 20 | EE | FS_Energy_OAM_Ph3 | Study on energy efficiency and energy saving aspects of 5G networks and services | 1020021 | Huawei, Samsung | SP-231723 | TR 28.880 | SID
 |  |  | ->Energy_OAM_Ph3 | Energy efficiency and energy saving aspects of 5G networks and services | 1060007 | Huawei, Samsung | SP-241940 | TS 28.310/622/623/541/554/104 | WID
 | 21 | Mexpo | FS_MExpo | Study on Enhanced OAM for management exposure to external consumers | 1020022 | Nokia | SP-231728 | TR 28.879 | SID
 |  |  | ->MExpo | Enhanced OAM for management service exposure to external consumers through CAPIF | 1060009 | Nokia | SP-241942 | TS 28.579 | WID
 | 22 | MonStra | Monstra-OAM | Management for MonStra | 1060012 | Vodafone, Ericsson | SP-241945 | TS 28.560 | WID
22 topics including: 14 OAM prime features and 8 OAM support to network features (in red background). 16 topics completed the study, 1 normative WI completed, 18 ongoing normative WIs.

## Slide 7: Overview of Rel-19 SA5 OAM topics (ongoing SI+ All WIs)
 |  | Abbr. | Acronym | Title | UID | rapp | Tdoc | TS/TR | Type
Intelligence and Automation | 1 | AIML | AIML_MGT_Ph2 | AI/ML management phase 2 | 1060011 | NEC, Intel | SP-241944 | TS 28.105/552/554/541 | WI
 | 2 | MDA | eMDAS_Ph3 | Management Data Analytics phase 3 | 1060014 | Huawei | SP-241947 | TS 28.104 | WI
 | 3 | IDM | IDMS_MN_Ph3 | Intent driven management services for mobile network phase 3 | 1060013 | Huawei, Ericsson | SP-241946 | TS 28.312 | WI
 | 4 | CCL | CCLM | Closed Control Loop Management | 1060010 | Samsung, Nokia | SP-241943 | TS 28.567/535/536/622/32.161 | WI
 | 5 | NDT | NDT | Management aspects of Network Digital Twins | 1060005 | CMCC | SP-241938 | TS 28.561 | WI
Management Architecture and Mechanisms | 6 | CMO | FS_Cloud_OAM | Study on cloud aspects of management and orchestration | 1020010 | CMCC | SP-241566 | TR 28.869 | SI
 | 8 | SBMA | SBMA_Ph3 | Service Based Management Architecture enhancement phase 3 | 1060006 | Huawei, Ericsson | SP-241939 | TS 28.533/… | WI
 | 9 | PTM | PlanM | Management of planned configurations | 1050032 | Nokia | SP-241379 | TS 28.572 | WI
 | 10 | MADCOL | MADCOL_Ph2 | Data Management phase 2 | 1020025 | Nokia | SP-250116 | TS 28.622 | WI
 | 11 | SREP | Data_SREP | Data management, regarding subscriptions and reporting | 1050033 | Ericsson | SP-241380 | 28.537/28.550/28.532/32.421/32.422/32.423/28.404/28.405/28.622/28.623 | WI
 | 12 | PM | PM_KPI_5G_Ph4 | 5G performance measurements and KPIs phase 4 | 1020026 | China Telecom, ZTE | SP-231747 | TS 28.552/554 | WI
 | 13 | AdNRM | AdNRM_Ph3 | 5G Advanced NRM features phase 3 | 1020027 | Nokia, Huawei | SP-250123 | TS 28.541/622 | WI
 | 14 | TMQ | TraceQoE_OAM | Subscriber and Equipment Trace and QoE collection management | 1020028 | Ericsson | SP-250115 | TS 32.422/405 | WI
 | 15 | NTNM | NTN_OAM_Ph2 | Management Aspects of NTN Phase 2 | 1060016 | China Unicom, CATT | SP-241949 | TS 28.541/552/554/658/662/540/530 | WI
 | 16 | IABM | NR_mobile_IAB_OAM | Management of IAB nodes | 1060015 | Ericsson | SP-241948 | TS 28.541/540/531/314/315 | WI
 | 17 | RedcapM | NR_RedCap_OAM | Management Aspects of RedCap features | 1060008 | China Unicom, Asiainfo | SP-241941 | TS 28.540/541/552/554 | WI
 | 18 | NWDAFM | NWDAF_OAM_Ph2 | Enhancement of Management Aspects related to NWDAF Phase 2 | 1050031 | China Telecom | SP-241378 | 28.552/28.541 | WI
 | 19 | NSM | NetShare_OAM_Ph3 | Management of Network Sharing Phase 3 | 1060017 | China Unicom, China Telecom | SP-241950 | TS 28.552/32.130/28.541 | WI
Support of New Services | 20 | EE | Energy_OAM_Ph3 | Energy efficiency and energy saving aspects of 5G networks and services | 1060007 | Huawei, Samsung | SP-241940 | TS 28.310/622/623/541/554/104 | WI
 | 21 | MExpo | Mexpo | Enhanced OAM for management service exposure to external consumers through CAPIF | 1060009 | Nokia | SP-241942 | TS 28.579 | WI
 | 22 | MonStra | Monstra-OAM | Management for MonStra | 1060012 | Vodafone, Ericsson | SP-241945 | TS 28.560 | WI
22 topics including: 14 OAM prime features and 8 OAM support to network features (in red background).
16 topics completed the study, 1 normative WI completed, 18 ongoing normative Wis, 1 ongoing study.

## Slide 8
Overview of Rel-19 CH topics (full list)
 | Abbr. | Acronym | Title | UID | Rapp | Tdoc | TS/TR | Type
1 | CHSEG | CHFSeg | WID on CHF Segmentation | 1040012 | Verizon | SP-250122 | TS 32.290/291 | WI
2 | SATCH | FS_5GSAT_Ph3_CH | SID on Charging aspects of satellite access Phase 3 | 1040014 | CATT | SP-240980 | TR 28.846 | SI
3 | CAPCH | FS_CAPIF_Ph2_CH | SID on Charging Aspects of CAPIF | 1040015 | Nokia | SP-240981 | TR 28.849 | SI
4 | RTCCH | FS_NG_RTC_Ph2_CH | SID on Charging aspects of next generation real time communication services phase 2 | 1040016 | CMCC | SP-240982 | TR 28.851 | SI
5 | UASCH | FS_UAS_Ph2_CH | SID on Charging aspects of Uncrewed Aerial Vehicle | 1040017 | CMCC | SP-240983 | TR 28.853 | SI
6 | RAGCH | Ranging_SL_CH | WID on Charging Aspects of Ranging and Sidelink Positioning | 1040013 | China Telecom | SP-241002 | TS 32.240/290/ 271/291/298 | WI
7 | EESCH | EnergySys_CH | WID on Charging Aspects for Energy Efficiency of network slice | 1040018 | Huawei | SP-250124 | TS 28.201/202 TS 32.240/291/298 | WI
8 | NSCH | NetShare_CH | WID on Charging enhancement for indirect network sharing | 1040019 | Ericsson | SP-241004 | TS 32.240/255/256 | WI
9 | PROCH | 5G_ProSe_Ph3_CH | WID on Charging Aspects for 5G ProSe Phase 3 | 1050030 | China Telecom | SP-241377 | TS 32.277/291/298 | WI
10 | SATCH | 5GSAT_Ph3_CH | WID on Charging aspects of satellite access Phase 3 | 1070014 | CATT | SP-250365 | TS32.240/251/255/257/260/291/298 | WI
11 | CAPCH | CAPIF_Ph2_CH | WID on Charging aspects of CAPIF | 1070015 | Nokia | SP-250366 | TS32.240/254/291/298 | WI
12 | RTCCH | NG_RTC_Ph2_CH | WID on Charging aspects of next generation real time communication services phase 2 | 1070016 | CMCC | SP-250367 | TS32.254/255/260/291/298 | WI
13 | UASCH | UAS_Ph2_CH | WID on Charging for Uncrewed Aerial Systems Phase 2 | 1070017 | CMCC | SP-250396 | TS32.240/255/256/291/298 | WI
14 | LCSCH | 5G_eLCS_Ph3_CH | WID on Charging Aspects of 5GC LoCation Services | 1070019 | China Telecom | SP-250370 | TS32.271/290/291/298 | WI
15 | AIOCH | AmbientIoT_CH | WID on Charging for Ambient power-enabled Internet of Things | 1070018 | Huawei | SP-250369 | TS32.240/254/291/298 | WI
16 | CHNSH | CHNetShare | WID on charging enhancement for MOCN network sharing | 1070020 | Ericsson | SP-250371 | TS32.130/240/254/291/298 | WI
16 CH topics including: 2 CH prime feature (in white background) and 14 CH support to network features (in red background)

## Slide 9: Inputs from SA#107
Selecting the Release for the Charging aspects (SP-250327): 3 potential aspects were discussed, document is noted and will be revisited at the next TSG SA meeting. Action1: request SA5 companies to check the discussion and provide feedback to SA5 leaders. (details in SA report section 6.2.5)
Trial on a tool developed by MCC to identify OpenAPIs which are changed due to a change of a definition which is imported from a different TS/OpenAPI (ref: SP-241892 Status report of TSG CT#106 Slide 22)
  The tool has been informed to SA5 in SA5#159, detail procedure on how to use the tool in SA5 working procedure is proposed in update of working procedure (S5-251205).
SA#107 report in: https://www.3gpp.org/ftp/tsg_sa/TSG_SA/TSGS_107_Incheon_2025-03/Report

## Slide 10
Rel-19 Progress overview in SA#107
Reference：SP-250420
OCI = Overall Completion Index

## Slide 11: SA5 Rel-19 OAM TU planning (Jan.2024~Sep.2025)
 | Maintenance+R18 | R19 | R20 preparation | Buffer (revision session)
Jan.2024~Mar.2024 SA5#153 (1 meeting) (Last meeting for Rel-18) | 1.5 TU (CR)+13 TU (Rel-18)=14.5 TU | 2 TU | NA | 2 TU
Apr. 2024~Dec.2024: SA5#154~#158 (5 meetings) | 2.5 TU*5 meetings = 12.5 TU (CRs) | 14 TU*5 meetings= 70 TU | NA | 2 TU*5=10 TU
Jan.2025~Sep.2025: SA5#159~#162 (4 meetings) | 1.5 TU*4 meetings= 6 TU (CRs) | 13 TU*4 meetings= 52 TU | 2 TU*4 meetings = 8 TU | 2 TU*4=8 TU
Total=185 TU | 33 TU | 124 TU | 8 TU | 20 TU
Assumptions:
Every meeting day = 5 quarters (= 5 TUs)
Total TUs per meeting = 18.5 TUs
  Buffer = 2 TUs
  OAM = 16.5 TUs
    Maintenance CRs + remaining Rel-18 work (TU allocation will decrease over time )
    Rel-20 preparation work (TU allocation will be zero at the beginning and will increase over time )
    All remaining time is available for Rel-19 SIDs / WIDs
Total TUs allocated to Rel-19 SIDs / WIDs = 124 TUs

## Slide 12: SA5 meeting statistics (Rel-19 OAM topics)
Observation: AIML/CMO/NDT/EE/IDM/CCL/MDA are top 7 contribution topics in Rel-19
Chart: Rel-19 OAM submited tdocs
| AIML | MADCOL | SEPM | PM | AdNRM | TMQ | NTNM | IABM | RedcapM | NWDAFM | NSM | MDA | EE | Mexpo | MonstraM | IDM | CCL | NDT | CMO | MSEC | SBMA | PTM
#153 | 7 | 3 | 12 | 6 | 13 | 5
#154 | 29 | 9 | 5 | 18 | 8 | 6 | 13 | 7 | 6 | 8 | 5 | 14 | 16 | 13 | 19 | 19 | 14 | 25 | 6 | 5
#155 | 28 | 5 | 6 | 13 | 12 | 3 | 10 | 2 | 9 | 7 | 3 | 23 | 17 | 15 | 19 | 15 | 19 | 26 | 13 | 8
#156 | 50 | 2 | 4 | 27 | 15 | 6 | 16 | 5 | 14 | 9 | 8 | 21 | 22 | 15 | 25 | 24 | 29 | 25 | 4 | 23 | 11
#157 | 54 | 8 | 1 | 11 | 11 | 6 | 10 | 4 | 9 | 2 | 8 | 9 | 23 | 12 | 13 | 25 | 21 | 35 | 12 | 13
#158 | 43 | 4 | 0 | 9 | 9 | 7 | 13 | 0 | 4 | 4 | 6 | 13 | 24 | 14 | 15 | 14 | 7 | 14 | 28 | 3 | 7 | 8
#159 | 63 | 6 | 2 | 10 | 11 | 5 | 7 | 1 | 10 | 2 | 5 | 22 | 19 | 9 | 25 | 23 | 29 | 16 | 23 | 9
total | 267 | 34 | 18 | 88 | 66 | 33 | 69 | 19 | 52 | 32 | 35 | 102 | 128 | 81 | 15 | 127 | 119 | 139 | 160 | 7 | 84 | 54
Topics | Submitted tdocs
AIML | 267
MADCOL | 34
SEPM | 18
PM | 88
AdNRM | 66
TMQ | 33
NTNM | 69
IABM | 19
RedcapM | 52
NWDAFM | 32
NSM | 35
MDA | 102
EE | 128
Mexpo | 81
MonstraM | 15
IDM | 127
CCL | 119
NDT | 139
CMO | 160
MSEC | 7
SBMA | 84
PTM | 54

## Slide 13: SA5 Rel-19 CH TU planning (May.2024~Sep.2025)
 | Maintenance+R18 | R19 | R20 preparation | Buffer (revision session)
May. 2024: SA5#155 (1 meeting) | 2.5 TU*1eetings = 2.5 TU (CRs) | 6 TU*1 meetings= 6 TU 5 TU: Rel-19 topic discussion | NA | 2 TU*4=8 TU
July. 2024~Dec.2024: SA5#156~#158 (3 meetings) | 2.5 TU*3 meetings = 7.5 TU (CRs) | 11 TU*3 meetings= 33 TU | NA | 2 TU*4=8 TU
Jan.2025~Sep.2025: SA5#159~#162 (4 meetings) | 1.5 TU*4 meetings= 6 TU (CRs) | 11 TU*4 meetings= 44 TU | 1 TU*4 meetings = 4 TU | 2 TU*4=8 TU
Total= 124 TU | 16 TU | 83 TU | 4 TU | 16 TU
Assumptions:
Every meeting day = 5 quarters (= 5 TUs)
Total TUs per meeting = 15.5 TUs
  Buffer = 2 TUs
  CH = 13.5 TUs
    Maintenance CRs + remaining Rel-18 work (TU allocation will decrease over time )
    Rel-20 preparation work (TU allocation will be zero at the beginning and will increase over time )
    All remaining time is available for Rel-19 SIDs / WIDs
Total TUs allocated to Rel-19 SIDs / WIDs = 83 TUs

## Slide 14
Acronym | OAM | Not covered by SA5 OAM yet | CH | Not covered by SA5 CH yet
5GSAT_Ph3_ARCH | NTN_OAM_Ph2 |  | 5GSAT_Ph3_CH | 
NG_RTC_Ph2 | NA | NA | NG_RTC_Ph2_CH | 
XRMPh2 | PM_KPI_5G_Ph4(CMCC) | OAM (NRM)?? |  | CH?? (CH indicated in SA2 WID)
MPS4msg | NA | NA |  | CH?? (CH indicated in SA2 WID)
VMR_Ph2 | AdNRM_Ph3(Samsung) | (PM??) |  | CH?? (CH indicated in SA2 WID)
5G_ProSe_Ph3 | AdNRM_Ph3 (CATT) | (PM??) | 5G_ProSe_Ph3_CH | 
UIA_ARC | NA | NA |  | CH?? (CH indicated in SA2 WID)
eEDGE_5GC_Ph3 |  | OAM (NRM+PM)?? |  | CH?? (CH indicated in SA2 WID)
UAS_Ph3 | NA | NA | UAS_Ph3_CH | 
UPEAS_Ph2 |  | OAM (NRM+PM)?? |  | CH?? (CH indicated in SA2 WID)
5G_Femto | NA | NA | NA | NA
MASSS |  | OAM (NRM)?? PM (not related) | NA | NA
AIML_CN | AIML_MGT_Ph2 NWDAF_OAM_Ph2 |  |  | Potential Rel-20 topic
EnergySys | Energy_OAM_Ph3 MExpo |  | EnergySys_CH | 
TEI19_NetShare | NetShare_OAM_Ph3 |  | NetShare_CH | 
AmbientIoT | AdNRM_Ph3(Huawei) |  | AmbientIoT_CH | 
Summary of SA5 Rel-19 management support to SA2 features
OAM Summary
The following features, there are no extra management standardization support identified so far:
  NG_RTC_Ph2
  MPS4msg
  UIA_ARC
  UAS_Ph3
  5G_Femto
The following features, need to check whether OAM support are needed in Rel-19.
  XRMPh2
  VMR_Ph2
  5G_ProSe_Ph3
  eEDGE_5GC_Ph3
  UPEAS_Ph2
  MASSS
CH Summary
The following features, there are no extra CH management standardization support identified so far:
  5G_Femto
  MASSS
The following features, need to check whether Charging support are needed in Rel-19.
  XRMPh2
  MPS4msg
  VMR_Ph2
  UIA_ARC
  eEDGE_5GC_Ph3
  UPEAS_Ph2
  AIML_CN
  FS_AmbientIoT
  FS_EnergySys
The content of this slides is to be updated based on working progress

## Slide 15
Acronym | OAM | Not covered by SA5 yet
NR_MIMO_Ph5-Core | NA | NA
FS_NR_7_24GHz_CHmod | NA | NA
NR_MIMO_Ph5-Core | NA | NA
Netw_Energy_NR_enh-Core | NA | NA
FS_Sensing_NR |  | OAM (TBD)
NR_AIML_air-Core | AIML_MGT_Ph2 | other OAM (TBD)
NR_duplex_evo-Core | NA | NA
NR_LPWUS-Core |  | OAM (NRM+PM)？？
IoT_NTN_TDD-Core |  | OAM (NRM+PM)？？
NR_MC_enh2-Core |  | OAM (NRM+PM)？？
LTE_terr_bcast_Ph2-Core |  | OAM (NRM+PM)？？
Ambient_IoT_Solutions-Core | AdNRM_Ph3(Huawei) | 
FS_NR_AIML_Mob | AIML_MGT_Ph2 | other OAM (TBD)
NR_Mob_Ph4-Core | PM_KPI_5G_Ph4 AdNRM_Ph3 | 
NR_NTN_Ph3-Core | NTN_OAM_Ph2 | 
IoT_NTN_Ph3-Core | NTN_OAM_Ph2 | 
NR_XR_Ph3-Core | NA | NA
LTE_TN_NR_NTN_mob-Core | NTN_OAM_Ph2 | 
NR_SL_relay_multihop-Core |  | OAM (NRM+PM)？？
LCS_BDS_B2b_LTE_NR-Core |  | OAM (NRM+PM)？？
LCS_NAVIC_L1_SPS_NR_LTE-Core |  | OAM (NRM+PM)？？
NR_ENDC_SON_MDT_Ph4-Core | PM_KPI_5G_Ph4 AdNRM_Ph3 TraceQoE_OAM | 
NR_WAB_5GFemto | AdNRM_Ph3 | 
NR_AIML_NGRAN_enh-Core | AIML_MGT_Ph2 Energy_OAM_Ph3 | 
Summary of SA5 Rel-19 management support to RAN1/2/3 features
RAN1
RAN2
RAN3
OAM Summary:
RAN1:
1. The following features, there are no extra management standardization support identified so far:
NR_MIMO_ph5-Core
FS_NR_7_24GHz_CHmod
NR_MIMO_Ph5
Netw_Energy_NR_enh-Core
NR_duplex_evo
2. The following features, need to check whether OAM support are needed in Rel-19.
FS_Sensing_NR
NR_LPWUS-Core
IoT_NTN_TDD-Core
NR_MC_enh2-Core
LTE_terr_bcast_Ph2-Core
RAN2:
1. The following features, there are no extra management standardization support identified so far:
NR_XR_Ph3-Core
CH Summary: There are no extra CH features related to RAN features.
The content of this slides is to be updated based on working progress

## Slide 16
SA5 Rel-19 topics relation to other WGs (OAM)
Abbreviation | Acronym | SA1 | SA2 | SA3 | SA4 | SA6 | RAN1 | RAN2 | RAN3 | CT3 | CT4 | Other related groups
AIML | AIML_MGT_Ph2 | TS 22.261 (AIML) | AIML_CN(R19) | X |  | X | NR_AIML_air-Core (R19) | FS_NR_AIML_Mob(R19) | NR_AIML_NGRAN_enh-Core(R19) |  |  | 3GPP SA (TR 22.850)
MDA | eMDAS_Ph3 |  |  |  |  |  |  |  | X (EE cost index) |  |  | 
IDM | IDMS_MN_Ph3 | TS 22.125 (UAV pre-flight) |  |  |  |  |  |  |  |  |  | GSMA/CAMARA/ETSI ZSM/TMF
CCL | CCLM |  |  |  |  |  |  |  |  |  |  | ETSI ZSM
NDT | NDT |  | X |  |  |  |  |  |  |  |  | ETSI ZSM
CMO | FS_Cloud_OAM |  |  |  |  |  |  |  |  |  |  | ETSI NFV
MSEC | FS_SECM |  |  | X |  |  |  |  |  |  |  | 
SBMA | SBMA_Ph3 |  |  |  |  |  |  |  |  |  |  | 
PTM | PlanM |  |  |  |  |  |  |  |  |  |  | 
MADCOL | MADCOL_Ph2 |  |  |  |  |  |  |  |  |  |  | 
SREP | Data_SREP |  |  |  |  |  |  |  |  |  |  | 
PM | PM_KPI_5G_Ph4 | TS 22.137 (Sensing KPI) (TBD) | XRMPh2 (R19) |  |  |  | FS_Sensing_NR (TBD) | NR_Mob_Ph4-Core (R19) | NR_ENDC_SON_MDT_Ph4-Core (R19) |  |  | 
AdNRM | AdNRM_Ph3 |  | VMR_Ph2 (R19) 5G_ProSe_Ph3 (R19) AmbientIoT (R19) |  |  | eEDGE_5GC_Ph3 (R19) | FS_Sensing_NR?? Ambient_IoT_Solutions-Core(R19) | NR_Mob_Ph4-Core(R19) | NR_ENDC_SON_MDT_Ph4-Core (R19) NR_WAB_5GFemto(R19) |  | SBIProtoc19 (R19) | GSMA (GST)
TMQ | TraceQoE_OAM |  | X |  | X |  |  | X | X |  | X | 
NTNM | NTN_OAM_Ph2 |  | 5GSAT_Ph3_ARCH (R19) |  |  |  |  | NR_NTN_Ph3-Core(R19) IoT_NTN_Ph3-Core(R19) | LTE_TN_NR_NTN_mob(R19) |  |  | 
IABM | NR_mobile_IAB_OAM |  |  |  |  |  |  |  | X |  |  | 
RedcapM | NR_RedCap_OAM |  | NR_REDCAP_Ph2 (R18) |  |  |  | NR_redcap_enh-Core (R18) |  |  |  |  | 
NWDAFM | NWDAF_OAM_Ph2 |  | TS 23.288, eNA_Ph 2 (R17) |  |  |  |  |  |  |  |  | 
NSM | NetShare_OAM_Ph3 | TS 22.261 | TEI19_NetShare(R19) |  |  |  |  |  |  |  | X | 
EE | Energy_OAM_Ph3 | TS 22.261 (EE as a service) | EnergySys (R19) |  |  |  |  |  | NR_AIML_NGRAN_enh-Core (R19) |  |  | NGMN/ETSI NFV/ETSI EE/ITU-T SG5
Mexpo | Mexpo | TS 22.261 (EE as a service) |  | TS 33.222 (CAPIF) |  | TS 23.222(CAPIF) |  |  |  | TS 29.222 (CAPIF) |  | GSMA OPG/CAMARA/TMF
MonStra | Monstra-OAM | TS 22.261-6.51 (MonStra) |  |  |  |  |  |  |  |  |  | 
The content of this slides is to be updated based on working progress

## Slide 17
SA5 Rel-19 topics relation to other WGs (CH)
Abbreviation | Acronym | SA1 | SA2 | SA6 | CT1 | CT3 | CT4 | Other related groups
SATCH | 5GSAT_Ph3_CH | 5GSAT_Ph3 (R19) (TS 22.261) | 5GSAT_Ph3_ARCH (TS 23.501; TS 23.502; TS 23.503; TS 23.682; TS 23.228; TS 23.401 ) | 5GSAT_Ph3_App (TS 23.558; TS 23.434; TS 23.289 ) |  |  |  | 
CAPCH | CAPIF_Ph2_CH |  |  | CAPIF(R15)?? eCAPIF(R16)?? FS_CAPIF_Ph3 |  |  |  | 
RTCCH | NG_RTC_Ph2_CH |  | NG_RTC_Ph2?? (TS 23.228; TS 23.502 ) FS_NG_RTC_Ph2 (TR 23.700-77) |  |  |  |  | 
UASCH | UAS_Ph3_CH | ID_UAS (R17) (TS 22.125) UAS_Ph3(R19)?? | ID_UAS (R17) (23.501; 23.502; 23.503; 23.401) UAS_Ph2 (R18) (23.256) UAS_Ph3 (R19) ?? (TS 23.256; TS 23.288; TS 23.503; TS 23.502; TS 23.401 ) | UASAPP_Ph3?? |  | UASAPP_Ph3?? ID_UAS（R17） UAS_Ph2（R18) (TS 29.502；TS 29.503；TS 29.504；TS 29.505；TS 29.510；TS 29.518；TS 29.571；TS 29.274；TS 29.256；TS 23.008） | ID_UAS（R17） UAS_Ph2（R18) (TS 29.502；TS 29.503；TS 29.504；TS 29.505；TS 29.510；TS 29.518；TS 29.571；TS 29.274；TS 29.256；TS 23.008） | 
CHSEG | CHFSeg |  |  |  |  |  |  | 
RAGCH | Ranging_SL_CH | Ranging (R18) (TS 22.261) | Ranging_SL(R18) (23.304; 23.287; 23.273; 23.502; 23.503 ; 23.586) |  | Ranging_SL (R18) (24.501; 24.554; 24.555; 24.571; 24.587; 24.588; 24.514) | Ranging_SL (R18) (29.513; 29.122; 29.522; 29.591; 29.525; 29.519) | Ranging_SL (R18) (24.080; 29.503; 29.504; 29.505; 29.510; 29.515; 29.518; 29.571; 29.572; 29.586) | 
EESCH | EnergySys_CH | EnergyServ (R19) (TS 22.261) | FS_EnergySys (R19) (TR 23.700-66) |  |  |  |  | 
NSCH | NetShare_CH | NetShare (R19) (TS 22.261) | TEI19_NetShare (R19) (TS 23.501; TS 23.502 ) |  | TEI19_NetShare (24.501) |  | TEI19_NetShare (29.502; 29.503; 29.509; 29.510; 29.531) | 
PROCH | 5G_ProSe_Ph3_CH |  | 5G_ProSe_Ph3 (R19) |  |  |  |  | 
The content of this slides is to be updated based on working progress

## Slide 18: Rel-19 work progress in other SA groups
SA1 (42 topics with 9 topics potentially related to SA5)
Ref: List of Approved Rel-19 topics （https://www.3gpp.org/ftp/Information/WORK_PLAN）
Rapporteurs are requested to identify concrete related aspects in corresponding SA5 topics
Color code: Blue (OAM related)/ Yellow(CH related)/Green( OAM&CH)
960019 | Study on Energy Efficiency as service criteria | FS_EnergyServ | SP-230235 | Xiaonan Shi, CMCC
1000033 | Stage 1 of Energy Efficiency as Service Criteria | EnergyServ | SP-230520 | Xiaonan Shi, CMCC
950008 | Study on AI/ML Model Transfer Phase2 | FS_AIML_MT_Ph2 | SP-220439 | Yang Xu, OPPO
1000030 | AI/ML Model Transfer Phase 2 | AIML_MT_Ph2 | SP-230514 | Yang Xu, OPPO
950004 | Study on Ambient power-enabled Internet of Things | FS_AmbientIoT | SP-220085 | Rapporteur:Xu, weijie, OPPO
1020030 | Stage 1 of Ambient power-enabled Internet of Things | AmbientIoT | SP-231403 | Xu, Weijie, OPPO
960016 | Study on satellite access - Phase 3 | FS_5GSAT_Ph3 | SP-220679 | Rapporteur: Thierry Bérisot, Novamint
1000024 | Stage 1 of Satellite access Phase 3 | 5GSAT_Ph3 | SP-230516 | Rapporteur: Thierry Bérisot, Novamint
950005 | Study on Localized Mobile Metaverse Services | FS_Metaverse | SP-220353 | Guttman, Erik, Samsung
1000028 | Stage 1 of Localized Mobile Metaverse Services | Metaverse | SP-230509 | Guttman, Erik, Samsung
990052 | Supporting UE Mobility for XR Services | XRMobility | SP-230233 | Xiaonan Shi, ChinaMobile
950006 | Study on Network Sharing Aspects | FS_NetShare | SP-220087 | Wei, Qun, China Unicom
1000029 | (Stage 1 of) Indirect Network Sharing | NetShare | SP-230511 | Wei, Qun, China Unicom
960015 | Study on roaming value added services | FS_RVAS | SP-220442 | Peter Bleckert, Ericsson
990051 | Roaming Value-Added Services | RVAS | SP-230231 | Peter Bleckert, Ericsson
1000027 | Non-Public Network (NPN) security considerations | SecNPN | SP-230523 | Yinglin Chen, China Telecom
1050114 | Monitoring of signalling traffic in 5G | MonSTra | SP-240793 | Cristina Romaguera
1040082 | Stage 1 for MonSta | MonSTra | SP-240793 | Cristina Romaguera
950003 | Study on Integrated Sensing and Communication | FS_Sensing | SP-220717 | Aleksiev, Vasil, Deutsche Telekom
1000026 | Stage 1 of Integrated Sensing and Communication | Sensing | SP-230750 | Aleksiev, Vasil, Deutsche Telekom AG
960017 | Study on (Stage 1 of) UAV Phase 3 | FS_UAV_Ph3 | SP-220954 | Pengtai Qin , China Mobile
1000032 | Stage 1 of Uncrewed Aerial System Phase 3 | UAS_Ph3 | SP-230518 | Pengtai Qin , China Mobile
960018 | Study on Upper layer traffic steering, switching and split over dual 3GPP access | FS_DualSteer | SP-220445 | Francesco Pica; Qualcomm
1020031 | Upper layer traffic steering and switching over dual 3GPP access | DualSteer | SP-231412 | Pica Francesco, Qualcomm
1010022 | Edge Computing Considering the Operational Needs of Service Hosting Environment | EdgeOpNeeds | SP-231037 | Yuying Zhang, China Telecom
1050115 | Proximity-based Services in 5GS Phase 3 | 5G_ProSe_Ph3 | SP-231037 | Hugh Shieh (AT&T)
950007 | Study on FRMCS Phase 5 | FS_FRMCS_Ph5 | SP-220437 | Patrick WIMART, UIC
1000031 | FRMCS Phase 5 | FRMCS_Ph5 | SP-230512 | Nikolopoulou, Vassiliki, UIC
850044 | Study on Supporting of Railway Smart Station Services | FS_RAILSS | SP-190838 | Han, Andrew Min-gyu, Hansung University
960020 | Study on Network of Service Robots with Ambient Intelligence | FS_SOBOT | SP-220447 | LEE, Ki-Dong, LG Electronics
990053 | Study on Interconnect of SNPN | FS_ISN | SP-230236 | Thierry Bérisot, Novamint
1030041 | Interconnect of SNPN | ISN | SP-240194 | Thierry Bérisot, Novamint,
990050 | Edge Computing for Industrial Scenarios | EDGINDUS | SP-230229 | Bruno Tossou, Orange
990049 | PS Data Off for IMS Data Channel Service | IMSDCDataOff | SP-230227 | Yue Hu, China Mobile
970044 | Multi-path relay | MultiRelay | SP-220943 | Yuying Zhang, China Telecom
1000025 | UE-to-UE multi-hop relay | UEMHopRelay | SP-230521 | Lipford, Mark, FirstNet Authority,
970043 | Interworking of Non-3GPP Digital Terrestrial Broadcast Networks with 5GS Multicast Broadcast Services | DTT4MBS | SP-220941 | Saha, Anindya, Saankhya Labs
970042 | (stage 1 of) MPS for Messaging services | MPS4msg | SP-220939 | Singh, Ray, Peraton Labs
1050104 | Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2 | SP-220992 | Yinglin Chen, China Telecom
970041 | Stage 2 of Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2 | SP-220992 | Yinglin Chen, China Telecom
980108 | Measurement Data Collection | MeasureData | SP-221263 | Yingjun Zhou, ZTE Corporation
1010025 | Local traffic routing for multi-access UE | LTR_MA | SP-231035 | Yinglin Chen, China Telecom

## Slide 19: Rel-19 work progress in other SA groups
1030038 | Study on security aspects of energy saving in 5G | FS_Energy_Sec | SP-240512 | Bo Bjerrum
1030035 | Study on security aspects of Core Network Enhanced Support for AIML | FS_AIML_CN_SEC | SP-240509 | Chang Liu,
1030031 | Study on Security Aspect of Ambient IoT Services in 5G | FS_Ambient_IoT_Sec | SP-240506 | Marcus Wong,
1020044 | Study on Security Aspects of 5G Satellite Access Phase 3 | FS_5GSAT_Ph3_SEC | SP-240232 | Zhou Wei
1030039 | Study on security aspects of 5G Mobile Metaverse services | FS_Metaverse_Sec | SP-240508 | Rohini Rajendran,
1040025 | Study on security aspects of CAPIF Phase 3 | FS_CAPIF_Ph3-sec | SP-240654 | Henry Leung ( Xiaomi)
1020039 | Study on security for PLMN hosting a NPN | PLMNNPN_SEC | SP-231786 | Jun Shen
1040023 | Security aspects of NR mobility enhancement Phase 4 | NR_Mob_Ph4_Sec | SP-240652 | Rajavelsamy R
1050028 | Security for MonStra | MonStra-Sec | SP-241376 | Vodafone, Susana Sabater
1030036 | Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC phase 3 | FS_EDGE_Ph3 | SP-240510 | Ge Yao,
1030037 | Study on security aspects for Multi-Access (DualSteer + ATSSS Ph-4) | FS_MASSS_Sec | SP-240511 | Kolekar, Abhijeet (Intel)
1030033 | UAS security enhancements | FS_UAS_Ph3_Sec | SP-240504 | Markus Hanhisalo,
1030028 | Study on security aspects of 5G NR Femto Document for: Approval | FS_5G_Femto_Sec | SP-240505 | Peilin LIU (ZTE)
1030034 | Study on Security Aspects of Enhancement for Proximity Based Services in 5GS Phase 3 | FS_5G_ProSe_Ph3_SEC | SP-240513 | Lei, Ao (Huawei)
1030032 | Study on security aspects of User Identities and Authentication | FS_UIA_Sec | SP-240507 | Samir Ferdi,
1030030 | Security aspects for MSGin5G Service Phase 3 | 5GMARCH_SEC_Ph3 | SP-240516 | Xiaoting Huang,
1030029 | Security Assurance Specification for maintenance of 5G features | SCAS_5G_Maint | SP-240515 | Rong Wu (Huawei)
1010010 | 5G Security Assurance Specification (SCAS) for the Unified Data Repository (UDR) | SCAS_5G_UDR | SP-230864 | Andreas, Joerg, BSI Germany
1010011 | 5G Security Assurance Specification (SCAS) for the Short Message Service Function (SMSF) | SCAS_5G_SMSF | SP-231158 | Manjesh K. Hanawal, IIT Bombay
1010012 | Addition of 256-bit security Algorithms | 256_Algo | SP-240476 | Orkopoulos, Stawros
1020036 | Addition of Milenage-256 algorithm | Milenage_256 | SP-241087 | Mireille Pauliac
1020041 | Study on enabling a cryptographic algorithm transition to 256-bits | FS_CAT256 | SP-231788 | Yuto Nakano
1020034 | Study on enablers for Zero Trust Security | FS_eZTS | SP-231784 | Sheeba Backia Mary Baskaran
1020035 | Mission critical security enhancements for release 19 | MCXSec4 | SP-231783 | Woodward, Tim, Motorola Solutions, Inc.
1020038 | Study on the security support for the Next Generation Real Time Communication services phase 2 | FS_NG_RTC_SEC_Ph2 | SP-240233 | Vlasios Tsiatsis
1020040 | Study of ACME for Automated Certificate Management in SBA | FS_ACME_SBA | SP-231787 | Charles Eckel
1020042 | 3GPP profiles for cryptographic algorithms and security protocols | CryptoSP | SP-231793 | Mohsin Khan A
1020043 | Study on mitigations against bidding down attacks | FS_MiBiDA | SP-231789 | Noamen Ben Henda
1020045 | Study on Security for mobility over non-3GPP access to avoid full primary authentication | FS_Non3GPPMob_Sec | SP-231791 | Saurabh Khare, Nokia
1040024 | Security for mobility over non-3GPP access to avoid full primary authentication | Non3GPPMob_Sec | SP-241088 | Khare, Saurabh
SA3 (30 topics with 2 topics potentially related to SA5 OAM)
Rapporteurs are requested to identify concrete related aspects in corresponding SA5 topics
Ref: List of Approved Rel-19 topics （https://www.3gpp.org/ftp/Information/WORK_PLAN）

## Slide 20: Rel-19 work progress in other SA groups
1050044 | Application enablement for AI/ML services | AIML_App | SP-241008 | Pateromichelakis, Emmanouil (Manos),
1040075 | Stage 2 of Application enablement for AI/ML services | AIML_App | SP-241008 | Pateromichelakis, Emmanouil (Manos),
1010005 | Study on application layer support for AI/ML services | FS_AIMLAPP | SP-231182 | Pateromichelakis, Emmanouil (Manos)
1020053 | Study on application enablement for Satellite access enabled 5G Services | FS_5GSAT_Ph3_App | SP-240296 | Basavaraj (Basu) Pattan, Samsung
1040077 | Application enablement for satellite access Phase 3 | 5GSAT_Ph3_App | SP-241010 | Basavaraj (Basu) Pattan, Samsung
1040076 | Application enablement for mobile metaverse services | Metaverse_App | SP-241390 | Shah, Sapan, Samsung
1020052 | Study on application enablement for Localized Mobile Metaverse Services | FS_Metaverse_App | SP-231806 | Shah, Sapan, Samsung
1020051 | Study on Application enabler for XR Services | FS_XRApp | SP-2315739 | Zheng, Shaowen, CMCC
1040074 | Application enablement for XRM Services Phase 2 | XRM_Ph2_App | SP-241207 | Zheng, Shaowen, CMCC
1050034 | Study on Service Enabler Architecture Layer (SEAL) Phase 4 | FS_SEAL_Ph4 | SP-241375 | Yang, Yanmei, Huawei Technologies Co.,Ltd.
1010009 | Guidelines for CAPIF Usage | CAPIF_EXT | SP-231161 | Junpei Uoshima, NTT DOCOMO
1020062 | Study on CAPIF Phase 3 | FS_CAPIF_Ph3 | SP-231741 | Preciado Rojas, Diego, Nokia
1050035 | Common API Framework (CAPIF) Phase 3 | CAPIF_Ph3 | SP-241381 | Niranth Amogh, Nokia
1040071 | Study on MC services support on IOPS mode of operation for 5G | FS_Generic_IOPS | SP-241017 | FirstNet, Mark Lipford
1050036 | MC services for generic support on IOPS mode of operation | Generic_IOPS | SP-241382 | FirstNet, Mark Lipford
1010008 | Application Architecture for UAS applications Phase 3 | UASAPP_Ph3 | SP-240741 | Roy, Michel, InterDigital
1000038 | Stage 2 of Railways specific Enhancements to Mission Critical Services | FRMCS_Ph5 | SP-230780 | Oettl, Martin, Nokia,
1000034 | Study on Service aspects for supporting the eMMTel service | FS_eMMTelAPP | SP-230779 | Liu, Yue, China Mobile
1040073 | Application enablement aspects for MMTel | MMTel_App | SP-241019 | Liu, Yue, China Mobile
1050053 | Enhanced application layer support for location services | eLSAPP | SP-241005 | Liping Wu, CATT
1000035 | Study on enhanced application layer support for location services | FS_eLSAPP | SP-230778 | Liping Wu, CATT
1040072 | Stage 2 of Enhanced application layer support for location services | eLSAPP | SP-241005 | Liping Wu, CATT
1000036 | Sharing of administrative configuration between interconnected MC service systems | MCShAC | SP-230692 | andreas.flander@bdbos.bund.de
1000037 | 5GMSG Service phase 3 | 5GMARCH_Ph3 | SP-230781 | Liu, Yue, China Mobile,
1000039 | Enhanced Mission Critical Architecture | enhMC | SP-230988 | Negalaguli, Harish, Motorola Solutions,
1050071 | SEAL DD (Data Delivery) Phase 2 | SEALDD_Ph2 | SP-230989 | Cuili Ge, Huawei
1010006 | Stage 2 of SEAL DD (Data Delivery) Phase 2 | SEALDD_Ph2 | SP-230989 | Cuili Ge, Huawei
1010007 | Stage 2 of enabling Edge Applications Phase 3 | EDGEAPP_Ph3 | SP-231160 | Hyesung Kim, Samsung
SA6 (28 topics with 2 topics potentially related to SA5 OAM)
Rapporteurs are requested to identify concrete related aspects in corresponding SA5 topics
Ref: List of Approved Rel-19 topics （https://www.3gpp.org/ftp/Information/WORK_PLAN）

## Slide 21: Rel-19 SA5 Management and Orchestration cooperation with other groups (for SA5 internal use)
SA1
Requirements
SA2
Architecture
SA3
Security
SA4
Media
SA5 OAM
Stage 3
SA6
Apps/MC
RAN
Radio Access
CT – Protocols & Coding
Stage 1
Stage 2
Stage 3
time
SA5 OAM
Stage 1
SA5 OAM
Stage 2
3GPP Internal Cooperation:
  1. SA1: Management related requirements
  2. SA2: EE, AIML, NWDAF, CN NF management
  3. SA3: OAM Security
  4. SA4: QoE data collection
  5. SA6: MEC, Exposure
  6. CT: Trace, OpenAPI stage3 coordination
  7. RAN1: AIML,EE
  8. RAN2: Measurements, MDT, QoE
  8. RAN3: SON, EE, data collection, AIML, RAN NF management, Trace,MDT, QoE
3GPP External Cooperation:
  1. GSMA: OPG requirements, slicing
  2. CAMARA: support of service API
  3. ETSI ZSM: management architecture, intent, closed loop control
  4. ETSI EE/ITU-T SG5: EE
  5. ITU-T SG2/SG13: intent, AIML, slicing
  6. ETSI NFV: virtualization, cloud native
  7. TMF: Autonomous networks level and evaluation, intent
  8. ONAP/O-RAN: reuse SA5 specifications where appropriate
GSMA/
CAMARA/ETSI ZSM/
ETSI EE/
ETSI NFV/
ITU-T SG2/SG5/SG13/
TMF/
ONAP/
O-RAN
Note: the topics for cooperation are not exhaustive.

## Slide 22: Leaders’ recommendation for SA5 work improvement
Provide opportunities for more involvement from 3GPP companies (esp. from operators) to SA5 work in general
  Potential enhancement solutions:
    SA5 to consider always collocating SA5 with other SA WGs as much as possible in 2026 onwards. This could allow the maximum possibilities for companies who like to share the standard delegation resources across multiple SA WGs.
    Dedicated timeslot in SA5 plenary could be planned for operators’ presentation to share their opinions/expectations upon request.
Improve the SA5 technical visibility and work planning on TSG level, involving SA5 in early discussion of every release. Plan the management work considering close relationship with the new network features developed by other WGs more efficiently.
  Potential enhancement opportunities:
    Early involvement and planning of SA5 work in each release, closely monitor the progress of SA2 and RAN groups to provide the necessary management features as early as possible.
    SA5 to regularly report the progress of management support to network features in SA meetings, with the goal of getting wider inputs about important management features.
    As SA5 also provides management support to RAN features, the management support to RAN network features should also be shared to RAN WGs and get inputs from RAN in regular basis.

## Slide 23: Thank you!

## Slide 24: Annex
Release 19
  Expectation of SA5 rapporteur role
  SA5 TU planning & statistics

## Slide 25: Chair’s recommendation on Rel-19 study
Encourage companies and delegates to keep positive and collaborative attitude, be creative, open-minded to capture multiple potential solutions in the study.
Focus the efforts on the comparison and evaluation between multiple solutions and provide concrete conclusion at the end of the study.
3GPP standardization focuses on the interoperability in multi-vendor environment.
SA5’s work is an important component in a large eco-system. Rapporteurs and interested companies are encouraged to keep close track of the technical progress of related discussion within 3GPP and SDOs outside of 3GPP. Progress presentations on dedicated technical topics are welcome to keep SA5 updated.
Chair would be happy to help on:
  Coordinate joint meetings if needed based on the working progress
  Coordinate SA5 highlights inputs and tech articles in ETSI website
  Represent SA5 and promote SA5 achievement in external fora

## Slide 26: Expectation of SA5 rapporteur role
Expectation of SA5 rapporteur role:
  Actively contribute and facilitate the progress of the WI/SI, coordinate the discussion within SA5 and with external groups if necessary
  Prepare tdoc sequence list and tdoc grouping suggestion before the meeting
  Provide inputs to Rel-19 TU planning/TU consumption for each meeting.
  Provide timely progress report in NWM before closing plenary with clear highlights for external readers with references to the WID/SID objectives.
  Implement any necessary draftCR/draft TR/draft TS and facilitate the email approval of draftCR/draft TR/draft TS
  Moderate the breakout sessions/offline calls and provide summary report
  Refer to TR 21.900 clause 6.3.2 for Role of the work item rapporteur and 4.1.2 Role of the specification rapporteur
  Be familiar with 3GPP drafting rules as specified in TR 21.801.
If you agree with the expectation above, please provide the nomination for the new WIDs/SIDs (one company one reply email please):
  Please consider the guidance (bullet 2/3/4/5) provided in Rel-19 Rapporteurship document SP-230746 from SA.
  Indicate if the nomination is for the role of Primary Rapporteur.
  Indicate if the nomination is for the role of Secondary Rapporteur.
  The work responsibility of Primary/Secondary Rapporteurs shall be clearly described if there are proposals for co-rapporteurs.

## Slide 27
Reference: SP-230746
Note: The first bullet does not applicable to SA5.

## Slide 28: Reference From TR 21.900 on rapporteur roles
4.1.2 Role of the specification rapporteur
The role of the rapporteur is to:
- Serve as Editor (following the guidance of the WG) until the specification is placed under change control.
- Deliver a clean specification to the MCC for editorial clean-up before submission for TSG approval to come under change control.
and, in co-operation with MCC, to:
- Review all CRs to the specification prior to agreement in the Working Group. This includes identifying and resolving clashes.
- Oversee the technical quality of the specification.
- Explain the specification to any other group (WG, TSG, inside or outside 3GPP), where appropriate.
- Serve as focal point for technical questions.
6.3.2 Role of the work item rapporteur
Every Work Item shall have a rapporteur. The rapporteur should be selected from regular attendees of the primary responsible Group and shall be selected from supporting companies. The role of the rapporteur is to:
- Monitor the progress of the work in all WGs for the WI.
- Report to the responsible WG and produce a report to the WG plenary on progress.
- Provide feedback to allow the work plan to be updated.
- Keep the WI sheet up-to-date.
- Identify the completion of the WI.
NOTE: Updates of WI sheets require approval by the responsible WG/TSG.

## Slide 29: Annex
Release 19
  Expectation of SA5 rapporteur role
  SA5 TU planning & statistics

## Slide 30: SA5 TU planning & statistics
OAM uses TU to facilitate the Rel-19 discussion.
Based on the collection of opinions in CH SWG from SA5#153, so far there is no need to use TU for CH time management in Rel-19 because of no expected need for prioritization process. This will be re-evaluated once Rel-19 Charging topics are identified.

## Slide 31: Template for TU estimation
Work Task ID | TU Estimate (Study) | TU Estimate (Normative) | RAN Dependency (Yes/No/Maybe) | SA Dependency (Yes/No/Maybe) | Non-3GPP Dependency
WT-1 | 1 | 1 | No | Maybe | No
WT-2 |  |  |  |  | 
WT-3 |  |  |  |  | 
TU estimates and dependencies
Total TU estimates for the study phase: ?
Total TU estimates for the normative phase: ?
Total TU estimates: 6
Moderators are requested to provide the following TU estimation based on the proposed objectives

## Slide 32: SA5 Rel-19 OAM TU statistics (Study phase)
Chart: Planned & Used TU statistics
1. The following topics used TU is very close to planned TU:
AIML/IDM/NDT/adNRM/PM/TMQ/EE/Monstra
2. The following topics taking advantage of BONUS TU, they are mainly OAM prime topics:
AIML/IDM/CMO/NDT/EE/Mexpo/CCL/MDA
3. Using the topics which used BONUS TU as example, average TU for decent study for a topic should be around 8~10 TU, adding TU in normative phase, 10~15 TU per topic would be desired.
 | Planned TU (study phase) | Bonus TU | Total TU
AIML | 6.2 | 5.7 | 11.9
MDA | 4.7 | 0.33 | 5.03
IDM | 4 | 3.76 | 7.76
CCL | 6.4 | 1 | 7.4
NDT | 3.3 | 2.5 | 5.8
CMO | 6.6 | 6.26 | 12.9
EE | 5 | 3.7 | 8.7
MExpo | 4.55 | 2.7 | 7.25
Chart: BONUS TU statistics
| AIML | MDA | IDM | CCL | NDT | CMO | MSEC | SBMA | PTM | MADCOL | SREP | PM | AdNRM | TMQ | NTNM | IABM | RedcapM | NWDAFM | NSM | EE | Mexpo | Monstra
 | 5.7 | 0.33 | 3.76 | 1 | 2.5 | 6.26 | 0 | 0 | 0 | 0 | 0 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7 | 2.7 | 0

## Slide 33: SA5 calendar with OAM TU (one track)
Time | Monday | Tuesday | Wednesday | Thursday | Friday (Closing plenary)
Q0 (8:00~8:55) (If needed) | NA | Breakout (opt.) | Breakout (opt.) | Breakout (opt.) | Closing plenary Start at 8:30am (may change depends on the host restriction)
Q1 (9:00 - 10:30) | Plenary Session#1 (1TU) [Single Stream] | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
10:30 - 11:00 | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break
Q2 (11:00 - 12:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
12:30 - 14:00 | Lunch | Lunch | Lunch | Lunch | Lunch
Q3 (14:00 - 15:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
15:30 - 16:00 | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break
Q4 (16:00 - 17:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
17:30 - 17:40 | Break | Break | Break | Break | Break
Q5 (17:40 – 19:10) | Stream#1 (1TU) | Stream#1 (0.5 TU) Stop around 18:45 Social evening | Stream#1 (1TU) | Revision session | 
Assumption: Every day = 5 sessions (TUs), total TU in 1 ordinary meeting (exclude closing plenary TUs) = 18.5 TUs

## Slide 34: TU Budget for SA5 OAM
Assumptions for SA5 OAM :
  6 ordinary meeting per year.
  Rel-19 spans 21 months for SA5 (with early start of studies) = 10 meetings
  1 Session = 1.5 hour time window
  Max 5 sessions per meeting day
  1 Stream = 1 TU (Time Unit)
  1 TU is time (i.e., 1.5 hours) spent to discuss/handle technical contributions.
  Revisions/Drafting/offline conference call are not counted for the TU estimates.
  OAM revision sessions normally planned to be in Thursday Q4 and Q5 (initial assump.)
  1 parallel (OAM) stream per session => 18.5 TUs per meeting (incl. 2 TUs as buffer) = 185
  Assume Maintenance + Buffer = 33% as in SA2 => ~ 61 TU
  Resulting total TUs avail. f. SI/WI: 10 meetings x 18.5 sessions = 185 TU minus 61 => 124 TU
  With 21 SI/WI => Average 6 TU per SI/WI (0.6/meeting).

## Slide 35: Sample of OAM TU planning and statistics
TU planning: to be proposed by rapporteurs and agreed by the group
TU statistics: to be filled by chair based on the time consumed after each meeting
This is an example to illustrate TU planning and statistics

## Slide 36: SA5 calendar with CH TU (one track)
Time | Monday | Tuesday | Wednesday | Thursday | Friday (Closing plenary)
Q0 (8:00~8:55) (If needed) |  | Breakout (opt.) | Breakout (opt.) |  | Closing plenary Start at 8:30am (may change depends on the host restriction)
Q1 (9:00 - 10:30) | Plenary Session#1 (1TU) [Single Stream] | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
10:30 - 11:00 | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break
Q2 (11:00 - 12:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
12:30 - 14:00 | Lunch | Lunch | Lunch | Lunch | Lunch
Q3 (14:00 - 15:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | CH Closing | Closing plenary
15:30 - 16:00 | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break
Q4 (16:00 - 17:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | CH Closing | Closing plenary
17:30 - 17:40 | Break | Break | Break | Break | Break
Q5 (17:40 – 19:10) | Stream#1 (1TU) | Stream#1 (0.5 TU) Stop around 18:45 Social evening | Stream#1 (1TU) | CH Closing(Opt.) | 
Assumption: Every day = 5 sessions (TUs), total TU in 1 ordinary meeting (exclude closing plenary TUs) = 15.5 TUs

## Slide 37: TU Budget for SA5 CH
Assumptions for SA5 CH :
  6 ordinary meeting per year.
  Rel-19 spans 18 months for SA5 (with early start of studies) = 8 meetings
  1 Session = 1.5 hour time window
  Max 5 sessions per meeting day
  1 Stream = 1 TU (Time Unit)
  1 TU is time (i.e., 1.5 hours) spent to discuss/handle technical contributions.
  Revisions/Drafting/offline conference call are not counted for the TU estimates.
  CH revision sessions normally planned to be in Thursday Q1 and Q2 (initial assump.),CH closing plenary planned to be in Thursday Q3 and Q4.
  1 (CH) stream per session => 15.5 TUs per meeting (incl. 2 TUs as buffer) = 124
  Assume Maintenance + Buffer = 33% as in SA2 => ~ 41 TU
  Resulting total TUs avail. f. SI/WI: 9 meetings x 15.5 sessions = 124 TU minus 41 => 83 TU
  => Recommended MAX no. of SI/WI = 14
  With 14 SI/WI => Average 6 TU per SI/WI (0.75/meeting).