## Slide 1: Rel-18 (Individual) Work plans
Prepared by the Rapporteurs

## Slide 2: Work Plan – MCOver5MBS (WID)
Meeting | 2021 |  | Proposed work plan for MCOver5MBS | Estimated TUs
SA6#46-e | 15 – 23 November 2021 | Online | WID:5G MBS MC service functional model impact applicable for 5GS only mode and 5GS/EPS dual mode | 2
 | 2022 |  |  | 
SA6#47-e | 14 – 22 February 2022 | Online | WID: Procedures and flows to support 5G MBS (5GS only mode) | 2
SA6#48 | 04 – 08 April 2022 | North America, Location, TBC | WID: Procedures and flows to support 5G MBS (5GS only mode) | 1
SA6#49 | 16 – 20 May 2022 | Asia, Location, TBC | WID: Procedures and flows to support 5G MBS (5GS only mode and 5GS/EPS dual mode, left overs and error corrections) | 1
SA6#49-BIS | 27 June – 01 July 2022 | [Only, if needed] Location, TBC | WID: Procedures and flows to support 5G MBS ( left overs and error corrections) | 1
SA6#50 | 22 – 26 August 2022 | Europe, Location, TBC | None | None
SA6#51 | 10 – 14 October 2022 | Asia, Location, TBC | None | None
SA6#52 | 14 – 18 November 2022 | North America, Location, TBC | None | None
 | 2023 |  |  | 
SA6#52-BIS | 16 – 20 January 2023 | [Only, if needed] Location, TBC | None | None
SA6#53 | 27 Feb – 03 Mar 2023 | Europe, Location, TBC | None | None
Total TUs |  |  |  | 7

## Slide 3: Work Plan – MCOver5GProSe (WID)
Meeting | 2021 |  | Proposed work plan for MCOver5MBS | Estimated TUs
SA6#46-e | 15 – 23 November 2021 | Online | WID: Architecture alignment | 1
 | 2022 |  |  | 
SA6#47-e | 14 – 22 February 2022 | Online | WID: 5G ProSe identifiers | 1
SA6#48 | 04 – 08 April 2022 | North America, Location, TBC | WID: Procedures | 1
SA6#49 | 16 – 20 May 2022 | Asia, Location, TBC | WID: Procedures | 0.5
SA6#49-BIS | 27 June – 01 July 2022 | [Only, if needed] Location, TBC |  | 
SA6#50 | 22 – 26 August 2022 | Europe, Location, TBC |  | 
SA6#51 | 10 – 14 October 2022 | Asia, Location, TBC | Alignment with SA2, if any | 0.5
SA6#52 | 14 – 18 November 2022 | North America, Location, TBC | Alignment with SA2, if any | 0.5
 | 2023 |  |  | 
SA6#52-BIS | 16 – 20 January 2023 | [Only, if needed] Location, TBC |  | 
SA6#53 | 27 Feb – 03 Mar 2023 | Europe, Location, TBC |  | 
Total TUs |  |  |  | 4.5

## Slide 4: Work Plan - eEDGEAPP (SID + WID)
Meeting | 2021 |  | Proposed work plan for eEDGEAPP | Estimated TUs
SA6#46-e | 15 – 23 November 2021 | Online | SID: Key issues + Solutions | 4
 | 2022 |  |  | 
SA6#47-e | 14 – 22 February 2022 | Online | SID: Key issues + Solutions | 4
SA6#48 | 04 – 08 April 2022 | North America, Location, TBC | SID: Key issues + Solutions + Evaluations | 6
SA6#49 | 16 – 20 May 2022 | Asia, Location, TBC | SID: Solutions + Evaluations + Conclusion + WI approval | 6
SA6#49-BIS | 27 June – 01 July 2022 | [Only, if needed] Location, TBC | WID: Requirements/Architecture | 4
SA6#50 | 22 – 26 August 2022 | Europe, Location, TBC | WID: Requirements/Architecture + Procedures | 4
SA6#51 | 10 – 14 October 2022 | Asia, Location, TBC | WID: Procedures | 5
SA6#52 | 14 – 18 November 2022 | North America, Location, TBC | WID: Procedures | 5
 | 2023 |  |  | 
SA6#52-BIS | 16 – 20 January 2023 | [Only, if needed] Location, TBC | WID: Procedures | 5
SA6#53 | 27 Feb – 03 Mar 2023 | Europe, Location, TBC | WID: Procedures | 5
Total TUs |  |  |  | 48

## Slide 5: Work Plan – eV2XAPP2 (SID + WID)
Meeting | 2021 |  | Proposed work plan for MCOver5MBS | Estimated TUs
SA6#46-e | 15 – 23 November 2021 | Online | SID: Key Issues + Solutions | 0.5
 | 2022 |  |  | 
SA6#47-e | 14 – 22 February 2022 | Online | SID: Key issues + Solutions | 1
SA6#48 | 04 – 08 April 2022 | North America, Location, TBC | SID: Key issues + Solutions + Evaluations | 1
SA6#49 | 16 – 20 May 2022 | Asia, Location, TBC | SID: Solutions + Evaluations + Conclusion + WI approval | 1.5
SA6#49-BIS | 27 June – 01 July 2022 | [Only, if needed] Location, TBC | WID: TS template + Scope + Few procedures | 1
SA6#50 | 22 – 26 August 2022 | Europe, Location, TBC | WID: Requirements + Procedures | 1
SA6#51 | 10 – 14 October 2022 | Asia, Location, TBC | WID: Procedures | 1
SA6#52 | 14 – 18 November 2022 | North America, Location, TBC | WID: Procedures | 1
 | 2023 |  |  | 
SA6#52-BIS | 16 – 20 January 2023 | [Only, if needed] Location, TBC | None | None
SA6#53 | 27 Feb – 03 Mar 2023 | Europe, Location, TBC | None | None
Total TUs |  |  |  | 8

## Slide 6: Work Plan – SEALDD (SID + WID)
Meeting | 2021 |  | Proposed work plan for MCOver5MBS | Estimated TUs
SA6#46-e | 15 – 23 November 2021 | Online | SID: Key Issues + Solutions | 2
 | 2022 |  |  | 
SA6#47-e | 14 – 22 February 2022 | Online | SID: Key issues + Solutions | 2
SA6#48 | 04 – 08 April 2022 | North America, Location, TBC | SID: Key issues + Solutions + Evaluations | 2
SA6#49 | 16 – 20 May 2022 | Asia, Location, TBC | SID: Solutions + Evaluations + Conclusion + WI approval | 2
SA6#49-BIS | 27 June – 01 July 2022 | [Only, if needed] Location, TBC | WID: TS template + Scope + Few procedures | 1
SA6#50 | 22 – 26 August 2022 | Europe, Location, TBC | WID: Requirements + Procedures | 1
SA6#51 | 10 – 14 October 2022 | Asia, Location, TBC | WID: Procedures | 1
SA6#52 | 14 – 18 November 2022 | North America, Location, TBC | WID: Procedures | 1
 | 2023 |  |  | 
SA6#52-BIS | 16 – 20 January 2023 | [Only, if needed] Location, TBC | WID: Procedures | 1
SA6#53 | 27 Feb – 03 Mar 2023 | Europe, Location, TBC | WID: Procedures | 1
Total TUs |  |  |  | 14

## Slide 7: Work Plan – FFAPP (WID)
Meeting | 2021 |  | Proposed work plan for FFAPP | Estimated TUs
SA6#46-e | 15 – 23 November 2021 | Online | WID: Requirements/Architecture + Deployment models + Involved entities and relationships | 0.5
 | 2022 |  |  | 
SA6#47-e | 14 – 22 February 2022 | Online | WID: Requirements/Architecture + Deployment models + Involved entities and relationships | 0.5
SA6#48 | 04 – 08 April 2022 | North America, Location, TBC | WID: Procedures and information flows + Identities + APIs | 1
SA6#49 | 16 – 20 May 2022 | Asia, Location, TBC | WID: Procedures and information flows + Identities + APIs | 1
SA6#49-BIS | 27 June – 01 July 2022 | [Only, if needed] Location, TBC | WID: Procedures and information flows + Identities + APIs | 1
SA6#50 | 22 – 26 August 2022 | Europe, Location, TBC | WID: Procedures and information flows + Identities + APIs | 1
SA6#51 | 10 – 14 October 2022 | Asia, Location, TBC | WID: Procedures and information flows + Identities + APIs | 1
SA6#52 | 14 – 18 November 2022 | North America, Location, TBC | WID: Procedures and information flows + Identities + APIs | 1
 | 2023 |  |  | 
SA6#52-BIS | 16 – 20 January 2023 | [Only, if needed] Location, TBC | WID: solve issues and corrections | 0.5
SA6#53 | 27 Feb – 03 Mar 2023 | Europe, Location, TBC | WID: solve issues and corrections | 0.5
Total TUs |  |  |  | 8

## Slide 8: Work Plan - eSEAL2 (WID)
Meeting | 2021 |  | Proposed work plan for eSEAL2 | Estimated TUs
SA6#46-e | 15 – 23 November 2021 | Online | Potential WID revision | 0
 | 2022 |  |  | 
SA6#47-e | 14 – 22 February 2022 | Online | WID: Requirements/Architecture | 1
SA6#48 | 04 – 08 April 2022 | North America, Location, TBC | WID: Requirements/Architecture + Procedures | 1
SA6#49 | 16 – 20 May 2022 | Asia, Location, TBC | WID: Procedures | 1
SA6#49-BIS | 27 June – 01 July 2022 | [Only, if needed] Location, TBC | WID: Procedures | 0.5
SA6#50 | 22 – 26 August 2022 | Europe, Location, TBC | WID: Requirements/Architecture + Procedures | 1.5
SA6#51 | 10 – 14 October 2022 | Asia, Location, TBC | WID: Requirements/Architecture + Procedures | 1
SA6#52 | 14 – 18 November 2022 | North America, Location, TBC | WID: Procedures | 0.5
 | 2023 |  |  | 
SA6#52-BIS | 16 – 20 January 2023 | [Only, if needed] Location, TBC | WID: Procedures | 0.5
SA6#53 | 27 Feb – 03 Mar 2023 | Europe, Location, TBC | WID: Procedures | 0.5
Total TUs |  |  |  | 7.5

## Slide 9: Work Plan - NSCALE (SID + WID)
Meeting | 2021 |  | Proposed work plan for NSCALE | Estimated TUs
SA6#46-e | 15 – 23 November 2021 | Online | SID: Key issues + Solutions+ Evaluations | 1.5
 | 2022 |  |  | 
SA6#47-e | 14 – 18 February 2022 | To be converted to e-meeting | SID: Solutions+ Evaluations | 1
SA6#48 | 04 – 08 April 2022 | North America, Location, TBC | SID: Solutions + Evaluations | 1
SA6#49 | 16 – 20 May 2022 | Asia, Location, TBC | SID: Solutions + Evaluations + Conclusion + WI approval | 1.5
SA6#49-BIS | 27 June – 01 July 2022 | [Only, if needed] Location, TBC | WID: TS template + Scope + Requirements/Architecture | 1
SA6#50 | 22 – 26 August 2022 | Europe, Location, TBC | WID: Requirements/Architecture + Procedures | 1
SA6#51 | 10 – 14 October 2022 | Asia, Location, TBC | WID: Procedures | 1
SA6#52 | 14 – 18 November 2022 | North America, Location, TBC | WID: Procedures | 1
 | 2023 |  |  | 
SA6#52-BIS | 16 – 20 January 2023 | [Only, if needed] Location, TBC | WID: Procedures | 0.5
SA6#53 | 27 Feb – 03 Mar 2023 | Europe, Location, TBC | WID: Procedures | 0.5
Total TUs |  |  |  | 10

## Slide 10: Work Plan - SNAAPP (SID + WID)
Meeting | 2021 |  | Proposed work plan for SNAAPP | Estimated TUs
SA6#46-e | 15 – 23 November 2021 | Online | SID: Solutions + Evaluations | 0.5
 | 2022 |  |  | 
SA6#47-e | 14 – 22 February 2022 | Online | SID: Solutions + Evaluations + Conclusion + WI approval | 1
SA6#48 | 04 – 08 April 2022 | North America, Location, TBC | WID: CRs to TS 23.222 | 1
SA6#49 | 16 – 20 May 2022 | Asia, Location, TBC | WID: CRs to TS 23.222 | 0.5
SA6#49-BIS | 27 June – 01 July 2022 | [Only, if needed] Location, TBC |  | 
SA6#50 | 22 – 26 August 2022 | Europe, Location, TBC |  | 
SA6#51 | 10 – 14 October 2022 | Asia, Location, TBC |  | 
SA6#52 | 14 – 18 November 2022 | North America, Location, TBC |  | 
 | 2023 |  |  | 
SA6#52-BIS | 16 – 20 January 2023 | [Only, if needed] Location, TBC |  | 
SA6#53 | 27 Feb – 03 Mar 2023 | Europe, Location, TBC |  | 
Total TUs |  |  |  | 3

## Slide 11: Work Plan – ACE_IoT (SID + WID)
Meeting | 2021 |  | Proposed work plan for ACE_IoT | Estimated TUs
SA6#46-e | 15 – 23 November 2021 | Online | SID: Key issues/Solutions | 0.5
 | 2022 |  |  | 
SA6#47-e | 14 – 18 February 2022 | Online | SID: Solutions/Evaluations | 0.5
SA6#48 | 04 – 08 April 2022 | North America, Location, TBC | SID: Solutions/Evaluations/Conclusion | 0.5
SA6#49 | 16 – 20 May 2022 | Asia, Location, TBC | SID: Evaluations/Conclusion; WID | 0.5
SA6#49-BIS | 27 June – 01 July 2022 | [Only, if needed] Location, TBC | SID: Solutions / Evaluations | 0.5
SA6#50 | 22 – 26 August 2022 | Europe, Location, TBC | WID: SEAL functional and procedural updates | 0.5
SA6#51 | 10 – 14 October 2022 | Asia, Location, TBC | WID: SEAL functional and procedural updates | 0.5
SA6#52 | 14 – 18 November 2022 | North America, Location, TBC | WID: SEAL functional and procedural updates | 0.5
 | 2023 |  |  | 
SA6#52-BIS | 16 – 20 January 2023 | [Only, if needed] Location, TBC | WID: SEAL functional and procedural updates | 0.5
SA6#53 | 27 Feb – 03 Mar 2023 | Europe, Location, TBC |  | 0
Total TUs |  |  |  | 4.5

## Slide 12: Work Plan – 5GFLS (SID + WID)
Meeting | 2021 |  | Proposed work plan for 5GFLS | Estimated TUs
SA6#46-e | 15 – 23 November 2021 | Online | SID: Key issues + Solutions | 1
 | 2022 |  |  | 
SA6#47-e | 14 – 22 February 2022 | Online | SID: Key issues + Solutions + Evaluations | 2
SA6#48 | 04 – 08 April 2022 | North America, Location, TBC | SID: Key issues + Solutions + Evaluations | 1
SA6#49 | 16 – 20 May 2022 | Asia, Location, TBC | SID: Solutions + Evaluations + Conclusion + WI approval | 2
SA6#49-BIS | 27 June – 01 July 2022 | [Only, if needed] Location, TBC | WID: TS template + Scope + Requirements/Architecture | 1
SA6#50 | 22 – 26 August 2022 | Europe, Location, TBC | WID: Requirements/Architecture + Procedures | 1
SA6#51 | 10 – 14 October 2022 | Asia, Location, TBC | WID: Procedures | 1
SA6#52 | 14 – 18 November 2022 | North America, Location, TBC | WID: Procedures | 1
 | 2023 |  |  | 
SA6#52-BIS | 16 – 20 January 2023 | [Only, if needed] Location, TBC | WID: Procedures | 1
SA6#53 | 27 Feb – 03 Mar 2023 | Europe, Location, TBC | WID: Procedures | 1
Total TUs |  |  |  | 12

## Slide 13: Work Plan – ADAES (SID + WID)
Meeting | 2021 |  | Proposed work plan for ADAES | Estimated TUs
SA6#46-e | 15 – 23 November 2021 | Online |  | -
 | 2022 |  |  | 
SA6#47-e | 14 – 22 February 2022 | Online | SID: Editorial / Architecture model / Requirements / Key issues | 2
SA6#48 | 04 – 08 April 2022 | North America, Location, TBC | SID: Architecture model / Key issues / Solutions | 2
SA6#49 | 16 – 20 May 2022 | Asia, Location, TBC | SID: Key issues / Solutions | 1.5
SA6#49-BIS | 27 June – 01 July 2022 | [Only, if needed] Location, TBC | SID: Solutions / Evaluations | 2.5
SA6#50 | 22 – 26 August 2022 | Europe, Location, TBC | SID: Solutions / Evaluations / Conclusions | 2
SA6#51 | 10 – 14 October 2022 | Asia, Location, TBC | WID: Editorial / Functional Model / High level features | 1
SA6#52 | 14 – 18 November 2022 | North America, Location, TBC | WID: Functional description, procedures and information flows | 1
 | 2023 |  |  | 
SA6#52-BIS | 16 – 20 January 2023 | [Only, if needed] Location, TBC | WID: Functional description, procedures and information flows | 1
SA6#53 | 27 Feb – 03 Mar 2023 | Europe, Location, TBC | WID: Identities / APIs | 1
Total TUs |  |  |  | 14

## Slide 14: Work Plan - SFCEDN (SID + WID)
Meeting | 2021 |  | Proposed work plan for SFCEDN | Estimated TUs
SA6#46-e | 15 – 23 November 2021 | Online | SID Approval | -
 | 2022 |  |  | 
SA6#47-e | 14 – 22 February 2022 | Online | SID: Key issues | 0.5
SA6#48 | 04 – 08 April 2022 | North America, Location, TBC | SID: Key issues + Solutions | 1
SA6#49 | 16 – 20 May 2022 | Asia, Location, TBC | SID: Key Issues + Solutions + Evaluations | 1
SA6#49-BIS | 27 June – 01 July 2022 | [Only, if needed] Location, TBC | SID: Solution + Evaluations + Conclusions | 1
SA6#50 | 22 – 26 August 2022 | Europe, Location, TBC | SID: Evaluations + Conclusions + WI Approval | 0.5
SA6#51 | 10 – 14 October 2022 | Asia, Location, TBC | WID: TS Template + Scope + Requirements/Architecture | 0.5
SA6#52 | 14 – 18 November 2022 | North America, Location, TBC | WID: Procedures | 0.5
 | 2023 |  |  | 
SA6#52-BIS | 16 – 20 January 2023 | [Only, if needed] Location, TBC | WID: Procedures | 1
SA6#53 | 27 Feb – 03 Mar 2023 | Europe, Location, TBC | WID: Procedures | 1
Total TUs |  |  |  | 7