## Slide 1: SA6 Release 18 Planning
[Time Unit Estimation]
SA6 Leadership

## Slide 2: Rel-18 Work Planning (S6-212437)
Step 1: SA6 leadership to prepare the available TUs in Rel-18 based on the agreed meeting schedule and the template for Rapporteur inputs. The TUs will be based on regular F2F meetings (Deadline: Oct 22nd, Friday)
Step 2: Rapporteurs to provide estimates of TUs for the proposed WID/SID objectives based on the provided template (Deadline: Oct 27th, Wed)
Step 3: SA6 leadership to provide the aggregated summary of inputs (Deadline: Oct 29th, Friday)
Step 4: SA6 to review the aggregated summary provided by the leadership over an informal conference call (Deadline: Nov 8th, Monday)
Step 5: SA6 to endorse the workload assessment summary during SA6#46-e meeting.

## Slide 3: Definition of a Time Unit (TU)
A “quarter” is a meeting block at a F2F meeting
  There are 4 quarters in a normal meeting day
  Each quarter has a duration of 1.5 hours
  On average SA6 handles 8-9 Tdocs per quarter
We have had additional quarters in a day by meeting before or after the normal day, but very rarely did we exceed 5 quarters in a day
During a normal meeting, we have had parallel sessions for up to 9 quarters, this can be extend to 12 quarters i.e. Monday Q3 – Wednesday Q4 (see next slide)
A TU is a quarter dedicated to study or work items
  Those quarters not dedicated to study or work items (e.g. LSs) are not counted as TUs
  Quarters dedicated to revisions are not counted as TUs e.g. plenary sessions, handling revisions

## Slide 4: Expected SA6 meeting schedule (after F2F resumption)
 | Monday |  | Tuesday |  | Wednesday |  | Thursday | Friday
 | Meeting will start at 9:00 local time |  | Placeholder for early start or drafting sessions |  |  |  |  | 
Quarter 1 09:00 to 10:30 | Main plenary session (Agenda, Reports, LSs, early discussion papers, Future work, FASMOs, etc.) |  | Parallel Track I | Parallel Track II | Parallel Track I | Parallel Track II | Main plenary session (Revisions) | Main plenary session (Revisions)
Quarter 2 11:00 to 12:30 | Main plenary session (Agenda, Reports, LSs, early discussion papers, Future work, FASMOs, etc.) |  | Parallel Track I | Parallel Track II | Parallel Track I | Parallel Track II | Main plenary session (Revisions) | Main plenary session (Revisions)
Lunch break (12:30 – 14:00) |  |  |  |  |  |  |  | 
Quarter 3 14:00 to 15:30 | Parallel Track I | Parallel Track II | Parallel Track I | Parallel Track II | Parallel Track I | Parallel Track II | Main plenary session (Revisions) | Main plenary session (Work plan review, Future meetings, AOB)
Quarter 4 16:00 to 17:30 | Parallel Track I | Parallel Track II | Parallel Track I | Parallel Track II | Parallel Track I | Parallel Track II | Main plenary session (Revisions) | Meeting will close at the latest by 16:00
Quarter 5 18:00 to 19:30 | Parallel Track I | Parallel Track II | Parallel Track I | Parallel Track II | Main plenary session (Future work, Outgoing LSs) |  | Main plenary session (Revisions) | 
 | Placeholder for drafting session(s) |  |  |  |  |  |  | 

## Slide 5: Total TUs in Rel-18
There are 12 quarters that count as TUs in the Parallel Track I and 12 quarters that count as TUs in the Parallel Track 2 for a total of 24 TUs per F2F meeting
Assuming that all BIS meetings are held, there are 10 meetings left in Rel-18
That gives a total of 240 TUs for all study and work items in Rel-18
Meeting | Date | Location
2021 |  | 
SA6#46-e | 15 – 23 November 2021 | Online
2022 |  | 
SA6#47-e | 14 – 22 February 2022 | Online
SA6#48 | 04 – 08 April 2022 | North America, Location, TBC
SA6#49 | 16 – 20 May 2022 | Asia, Location, TBC
SA6#49-BIS | 27 June – 01 July 2022 | [Only, if needed] Location, TBC
SA6#50 | 22 – 26 August 2022 | Europe, Location, TBC
SA6#51 | 10 – 14 October 2022 | Asia, Location, TBC
SA6#52 | 14 – 18 November 2022 | North America, Location, TBC
2023 |  | 
SA6#52-BIS | 16 – 20 January 2023 | [Only, if needed] Location, TBC
SA6#53 | 27 Feb – 03 Mar 2023 | Europe, Location, TBC

## Slide 6: TU Estimate per Study / Work Item
SID/WID | Schedule dependencies (on other WG)* | SA6#46-e TUs | SA6#47-e TUs | SA6#48 TUs | SA6#49 TUs | SA6#49-BIS TUs | SA6#50 TUs | SA6#51 TUs | SA6#52 TUs | SA6#52-BIS TUs | SA6#53 TUs | Total
FS_eEDGEAPP | None | 4 (SID) | 4 (SID) | 4 (SID) | 4 (SID) | 4 (WID) | 4 (WID) | 4 (WID) | 4 (WID) | 4 (WID) | 4 (WID) | 40 TUs
FS_eUASAPP |  |  |  |  |  |  |  |  |  |  |  | 
FS_eV2XAPP2 |  | 0.5 |  |  |  |  |  |  |  |  |  | 
FS_SEALDD |  | 1? |  |  |  |  |  |  |  |  |  | 
FFAPP |  |  |  |  |  |  |  |  |  |  |  | 
eSEAL2 |  | 0 | 0.5 | 0.5 | 0.5 | 1? | 1? |  |  |  |  | 
FS_ADAES |  |  |  |  |  |  |  |  |  |  |  | 
FS_GRIDAPP |  |  |  |  |  |  |  |  |  |  |  | 
FS_SFCEDN |  |  |  |  |  |  |  |  |  |  |  | 
Rapporteurs to fill estimated TUs for each meeting for each study / work item
  If a follow-up WID (to a Rel-18 SID) is expected in Rel-18, that should be included
* List any strong dependencies on other WGs, if it has impacts our schedule e.g. if SA6 work needs to be planned based on output from the other WGs
Example

## Slide 7: TU Estimate per Study / Work Item
SID/WID | Schedule dependencies (on other WG)* | SA6#46 TUs | SA6#47 TUs | SA6#48 TUs | SA6#49 TUs | SA6#49-BIS TUs | SA6#50 TUs | SA6#51 TUs | SA6#52 TUs | SA6#52-BIS TUs | SA6#53 TUs | Total
FS_MCOver5GS |  | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 7 TUs
MCOver5MBS |  |  |  |  |  |  |  |  |  |  |  | 
MCOver5GProSe |  |  |  |  |  |  |  |  |  |  |  | 
MCGWUE |  |  |  |  |  |  |  |  |  |  |  | 
enh4MCPTT |  |  |  |  |  |  |  |  |  |  |  | 
FS_IRail |  |  |  |  |  |  |  |  |  |  |  | 
FS_NSCALE |  |  |  |  |  |  |  |  |  |  |  | 
FS_SNAAPP |  |  |  |  |  |  |  |  |  |  |  | 
FS_ACE_IOT |  |  |  |  |  |  |  |  |  |  |  | 
FS_5GFLS |  |  |  |  |  |  |  |  |  |  |  | 
Rapporteurs to fill estimated TUs for each meeting for each study / work item
  If a follow-up WID (to a Rel-18 SID) is expected in Rel-18, that should be included
* List any strong dependencies on other WGs, if it has impacts our schedule e.g. if SA6 work needs to be planned based on output from the other WGs
Example

## Slide 8: Action(s)
Rapporteurs to fill the TU estimates as per the slides 6/7 for your respective WID/SIDs (and follow-up WIDs)
  Rapporteur inputs to be mailed directly to the leadership (Suresh, Alan, Jukka), NOT to the SA6 mailing list, by Oct 27th (Wed) – Step 2
Informal conference call to be held on Oct 26th (Tue) with Rapporteurs for any clarifications on the template, at 13:00 UTC (30mins)
SA6 leadership to provide the aggregated summary of the Rapporteur inputs, by Oct 29th – Step 3

## Slide 9: Annex

## Slide 10: Example work plan template (SID + WID)
Meeting | 2021 |  | Proposed work plan for <WID/SID> | Estimated TUs
SA6#46-e | 15 – 23 November 2021 | Online | SID: Key issues + Solutions | To be filled
 | 2022 |  |  | 
SA6#47-e | 14 – 22 February 2022 | Online | SID: Key issues + Solutions | To be filled
SA6#48 | 04 – 08 April 2022 | North America, Location, TBC | SID: Key issues + Solutions + Evaluations | To be filled
SA6#49 | 16 – 20 May 2022 | Asia, Location, TBC | SID: Solutions + Evaluations + Conclusion + WI approval | To be filled
SA6#49-BIS | 27 June – 01 July 2022 | [Only, if needed] Location, TBC | WID: TS template + Scope + Requirements/Architecture | To be filled
SA6#50 | 22 – 26 August 2022 | Europe, Location, TBC | WID: Requirements/Architecture + Procedures | To be filled
SA6#51 | 10 – 14 October 2022 | Asia, Location, TBC | WID: Procedures | To be filled
SA6#52 | 14 – 18 November 2022 | North America, Location, TBC | WID: Procedures | To be filled
 | 2023 |  |  | 
SA6#52-BIS | 16 – 20 January 2023 | [Only, if needed] Location, TBC | WID: Procedures | To be filled
SA6#53 | 27 Feb – 03 Mar 2023 | Europe, Location, TBC | WID: Procedures | To be filled
Total TUs |  |  |  | To be filled
Red text to be completed

## Slide 11: Example: Schedule for SA6#35 (Our last F2F Meeting)
 | Monday |  | Tuesday |  | Wednesday |  | Thursday | Friday
 | Meeting will start at 9:00 local time |  | Placeholder for early start or drafting sessions |  |  |  |  | 
Quarter 1 09:00 to 10:30 | Opening of the meeting (AI 1) Agenda and Chairman's notes (AI 2) Report from previous meetings (AI 3) Incoming LSs (AI 4.1) Rel-16 Corrections (AI 9) - eCAPIF/V2XAPP/SEAL |  | Parallel Track I Rel-17 eMCData3 (AI 10.3) | Parallel Track II Rel-17 EDGEAPP (AI 10.4) | Parallel Track I Revisions | Parallel Track II 8-9: Drafting session 9:00-10:30: Rel-17 EDGEAPP (AI 10.4) | Outgoing LSs (AI 4.2) Revisions Rel-16 Work Items | Revisions all AIs Creation of UPDATE04 folder (LAST UPDATE FOLDER)
Quarter 2 11:00 to 12:30 | Rel-16 Corrections (AI 9) - eCAPIF/V2XAPP/SEAL Studies - FS_eV2XAPP (AI 11.6) |  | Parallel Track I TEI17 (AI 10.5) | Parallel Track II Rel-17 EDGEAPP (AI 10.4) | Studies - FS_eV2XAPP (AI 11.6) Studies - FS_5GMARCH (AI 11.7) |  | Revisions Studies | Revisions all AIs
Lunch break |  |  |  |  |  |  |  | 
Quarter 3 14:00 to 15:30 | Parallel Track I Rel-17 eMONASTERY2 (AI 10.1) | Parallel Track II Studies - FS_EDGEAPP (AI 11.5) | Parallel Track I Studies - FS_MCOver5GS (AI 11.1) | Parallel Track II Rel-17 EDGEAPP (AI 10.4) | Studies – FS_FFAPP (AI 11.3) |  | Creation of UPDATE02 folder Revisions Studies | Work Plan review (AI 13) Future meetings (AI 14) AOB (AI 15)
Quarter 4 16:00 to 17:30 | Parallel Track I Rel-17 eMONASTERY2 (AI 10.1) | Parallel Track II Rel-17 EDGEAPP (AI 10.4) | Parallel Track I Studies - FS_MCOver5GS (AI 11.1) | Parallel Track II Rel-17 EDGEAPP (AI 10.4) | Studies - FS_UASAPP (AI 11.4) |  | Revisions Rel-17 Work Items | Meeting will close at the latest by 16:00
Quarter 5 18:00 to 19:30 | Parallel Track I Rel-17 MCIOPS (AI 10.2) | Parallel Track II Rel-17 EDGEAPP (AI 10.4) | Parallel Track I Studies - FS_ enhMCLoc (AI 11.2) Studies -FS_MC5MBS (AI 11.8) | Parallel Track II Rel-17 EDGEAPP (AI 10.4) | Future work / New WIDs (AI 12) Creation of UPDATE01 folder |  | Revisions Rel-17 Work Items Creation of UPDATE03 folder | 
 | Placeholder for drafting session(s) |  |  |  |  |  |  |