## Slide 1: SA6#41-e Work Plan discussion
Suresh Chitturi
SA6 Chairman
SAMSUNG

## Slide 2: Overview: Rel-17 Work Items – 1/2
Work Item | WI Code | WID Approved | SA#90 | SA6#41 | Target Completion | Remarks
Enhancements to Application Architecture for the Mobile Communication System for Railways Phase 2 | eMONASTERY2 | SA#84 (06/2019) | 100% | 100% | SA#89 (09/2020) | Declared 100%
MC services support on IOPS mode of operation | MCIOPS | SA#84 (06/2019) | 100% | 100% | SA#89 (09/2020) | Declared 100%
Enhanced Mission Critical Push-to-talk architecture phase 3 | enh3MCPTT | SA#87 (03/2020) | 45% | 50% | SA#89 (09/2020) | To align with Stage2 freeze
Enhancements for functional architecture and information flows for Mission Critical Data | eMCData3 | SA#86 (12/2019) | 85% | 90% | SA#89 (09/2020) | To align with Stage2 freeze
Architecture for enabling Edge Applications | EDGEAPP | SA#86 (12/2019) | 85% | 90% | SA#90 (12/2020) | TS for approval at SA#91

## Slide 3: Overview: Rel-17 Work Items – 2/2
Work Item | WI Code | WID Approved | SA#90 | SA6#41 | Target Completion | Remarks
Enhanced application layer support for V2X services | eV2XAPP | SA#89 (09/2020) | 35% | 45% | SA#91 (03/2021) | To align with Stage2 freeze
Application Architecture for MSGin5G Service | 5GMARCH | SA#89 (09/2020) | 5% | 10% | SA#91 (03/2021) | To align with Stage2 freeze
Mission Critical Services over 5GS | MCOver5GS | SA#89 (09/2020) | 30% | 50% | SA#91 (03/2021) | To align with Stage2 freeze Send TS for information at SA#91
Enhanced Service Enabler Architecture Layer for Verticals | eSEAL | SA#90 (12/2020) | 10% | 15% | SA#92 (06/2021) | To align with Stage2 freeze
Application layer support for Unmanned Aerial System (UAS) | UASAPP | SA#90 (12/2020) | 0% | 10% | SA#92 (06/2021) | To align with Stage2 freeze

## Slide 4: Overview: Studies
Study Item | WI Code | SID Approved | SA#90 | SA6#41 | Target Completion | Remarks
Study on Mission Critical Services support over 5G System | FS_MCOver5GS | SA#80 (06/2018) | 65% | 65% | SA#93 (09/2021) | Rel-18 study
Study on application layer support for Factories of the Future in 5G NW | FS_FFAPP | SA#82 (12/2018) | 80% | 90% | SA#91 (03/2021) | TR for approval planned at SA#91/92?
Study on application layer support for Unmanned Aerial System (UAS) | FS_UASAPP | SA#82 (12/2018) | 75% | 85% | SA#91 (03/2021) | TR for approval planned at SA#91?
Study on support of the 5GMSG Service | FS_5GMARCH | SA#84 (06/2019) | 80% | 85% | SA#90 (12/2020) | TR for approval planned at SA#91?
Study of Gateway UE function for Mission Critical Communication | FS_MCGWUE | SA#88 (06/2020) | 30% | 30% | SA#93 (09/2021) | Rel-18 study. Will be on the agenda for SA6#42-e
Study of Interconnection and Migration Aspects for Railways | FS_IRail | SA#88 (06/2020) | 10% | 15% | SA#93 (09/2021) | Rel-18 study. Will not be on the agenda for SA6#42-e

## Slide 5: Conference calls and other items
Pre-SA6#42-e conference calls
  5GMARCH – 1 (TBD)
  EDGEAPP – 1 (TBD)
  MCX – 1 (TBD)
  New SID (FS_NSCALE) – 1 (TBD)?
Inclusive language
  Rapporteurs and MCC to check Rel-17 specifications and prepare CRs
SA6 Chair to submit endorsed ToR update to SA#91-e
Rapporteurs to make the draft TRs/TSs available within one week!
All revisions MUST be in the inbox folder!

## Slide 6: Thank You!