## Slide 1: 2024 Calendar
Alan Soloway (Qualcomm)
SA6 Chair

## Slide 2: Outline
The SA Chair required that 2024 WG calendars be provided by April 10 at the latest
SA6 needs to endorse a 2024 SA6 calendar in SA6#48-e in order to provide that to the SA Chair by April 10

## Slide 3: Guidelines
The following have been taken into consideration in preparation of the calendar
  No more than 6 ordinary meetings per year
  Two weeks spacing before and after plenary meetings
  At least 4 weeks between successive SA6 meetings
  Avoidance of summer vacation periods and major regional holiday periods
The proposed 2024 RAN and CT calendar was provided which includes the SA plenary meetings
  This was used as a baseline in which to schedule SA6 meetings

## Slide 4: Proposal
SA6 agrees to the following quarterly pattern for 2024 WG meetings
  1 – 2 – 1 – 2
  Ordinary meetings will be scheduled as F2F meetings
  F2F meetings will be scheduled for 5 sequential days (Monday – Friday)
SA6 agrees to reserve an ad-hoc meeting in Q1 2024
  This may have a reduced agenda
  This shall be cancelled if not needed
  Ad-hoc meetings are potentially possible as either F2F or e-meetings
  Meeting duration will be 5 sequential days (Monday – Friday) if F2F or 8 sequential business days if e-meeting

## Slide 5: Proposal (cont’d)
Meeting dates
  SA6#58-Adhoc-e: January 22 – 31
  SA6#59: February 26 – March 1
  SA6#60: April 15 – 19
  SA6#61: May 20 – 24
  SA6#62: August 19 – 23
  SA6#63: October 14 – 18
  SA6#64: November 18 – 22

## Slide 6: Summary
Guidance on F2F and e-meetings may be discussed by the PCG and at the SA plenary
Any outcomes from PCG or SA plenary may impact this proposed schedule
It is not yet known how these proposed dates will correspond to the release schedule (i.e. Rel-19)
All dates currently align with the CT WGs and may align with other SA WG schedules
  Opportunities to co-locate will be evaluated based upon need and logistics