## Slide 1: SA6#70 Work Plan Review
Atle Monrad (InterDigital)
SA6 Chair
3GPP TSG-SA WG6 Meeting #70 S6-255005
Dallas, USA, 17th – 21st November 2025

## Slide 2: Overview: Rel-20 5GA Studies
Study Item | WI Code | SID Approved | SA6#69 | SA6#70 | Target Completion | Remarks
Study on Discreet listening and monitoring of mission critical services, Phase 2 | FS_MCDISC_Ph2 | SA#107 (03/2025) | 35% | % | SA#111 (03/2026) | 
Study on Logging and recording of mission critical services, Phase 2 | FS_MCLOG_Ph2 | SA#107 (03/2025) | 35% | % | SA#111 (03/2026) | 
Study on Service Enabler Architecture Layer (SEAL) Phase 4 | FS_SEAL_Ph4 | SA#105 (09/2024) | 100% | Complete | SA#110 (12/2025) | 
Study on Stage 2 for AI/ML service Phase 2 | FS_AIML_App_Ph2 | SA#107 (03/2025) | 75% | % | SA#110 (12/2025) | 
Study on Application enabler for XR Services Phase 3 | FS_XRM_Ph3_APP | SA#107 (03/2025) | 90% | % | SA#110 (12/2025) | 
Study on Stage 2 for MMTel Phase 2 | FS_MMTel_Ph2_APP | SA#107 (03/2025) | 60% | % | SA#111 (03/2026) | 
Study on SEAL data delivery Phase 3 | FS_SEALDD_Ph3 | SA#107 (03/2025) | 65% | % | SA#111 (03/2026) | 

## Slide 3: Overview: Rel-20 5GA Studies
Study Item | WI Code | SID Approved | SA6#69 | SA6#70 | Target Completion | Remarks
Study on application enablement for satellite access enabled 5G services Phase 4 | FS_5GSAT_Ph4_APP | SA#108 (06/2025) | 20% | % | SA#111 (03/2026) | 
Study on application enablement for Ambient IoT services Phase 2 | FS_AmbientIoT_Ph2_APP | SA#108 (06/2025) | 40% | % | SA#111 (03/2026) | 
Study on Application user consent | FS_APCOT | SA#108 (06/2025) | 30% | % | SA#111 (03/2026) | 
Study of CAPIF Phase 4 | FS_CAPIF_Ph4 | SA#108 (06/2025) | 40% | % | SA#111 (03/2026) | 
Study on Application Enablement to support Energy Saving Phase 2 | FS_EnergySys_Ph2_APP | SA#108 (06/2025) | 25% | % | SA#111 (03/2026) | 
Study on use of Sensing results for Vertical Applications | FS_Sensing_APP | SA#108 (06/2025) | 30% | % | SA#111 (03/2026) | 

## Slide 4: Overview: Rel-20 5GA Work-Items
Work Item | WI Code | WID Approved | SA6#67 | SA6#68 | Target Completion | Remarks
Stage 2 for Enhanced Mission Critical Services Architecture Phase 2 | enhMC_Ph2-MC | SA#107 (03/2025) | 30% | % | SA#112 (06/2026) | 
Stage 2 for FRMCS Phase 6 | FRMCS_Ph6 | SA#107 (03/2025) | 55% | % | SA#112 (06/2026) | 
Stage 2 for Mission Critical Services for UE-to-UE and UE-to-Network over multi-hop relay | MultiHop-MC | SA#107 (03/2025) | 85% | % | SA#111 (03/2026) | 
Stage 2 for mobile metaverse services Phase 2 | Metaverse_Ph2-APP | SA#107 (03/2025) | 85% | % | SA#110 (12/2025) | 
Guidelines for 3GPP Application Enablement usage | AppEnable_EXT | SA#108 (06/2025) | 35% | % | SA#111 (03/2026) | 
Service Enabler Architecture Layer (SEAL) Phase 4 | SEAL_Ph4-APP | SA#109 (09/2025) | 5% | % | SA#112 (06/2026) | 

## Slide 5: Conference calls and other items
Rapporteurs to make the draft TRs/TSs available Wednesday November 26th 23:00 UTC
All documents must be uploaded before End-of-Meeting
Pre-SA6#71 conference calls (Dates are TBD) – Maximum 2 hours/call and 1 hour/topic
  Potential Topics
    FS_MCDISC_Ph2
    FS_MCLOG_Ph2
    FS_5GSAT_Ph4_APP
    FS_AmbientIoT_Ph2_APP
    FS_APCOT
    FS_CAPIF_Ph4
    FS_EnergySys_Ph2_APP
    FS_Sensing_APP
    6G-study on application enablement
    FS_MMTel_Ph2_APP
    FS_SEALDD_Ph3
Colour coding: Mission Critical – conference calls seems needed
Application Enablement – conference calls seems needed
6G-study – conference call may be useful
Progressing well – conference calls seems not needed

## Slide 6: SA6 Rel-20 6G-study planning Application Enablement
 | SA6#68 (Aug 25 - 29) | Moderated Discussion#1 (Sep 1 - 14) | SA6#69 (Oct 13 - 17) | Moderated Discussion#2 (Oct 20 - 29) | SA6#70 (Nov 17 - 21) | Post SA6#70 untill end of Study
Input | 1. Company proposed work tasks and initial analysis SA1 TR 22.870. 2. Discussion on Working methods (NWM, email, conf calls) for Moderated discussions. 3. Discuss the questions for Moderated Discussions | Candidate Work Tasks from SA6#68 Dates: Sep 1 to 14 (2 weeks) | 1. Moderator collated Work Tasks 2. Company proposed Work Tasks to SA6#69 | Candidate Work Tasks from SA6#69 Dates: Oct 20 to Oct 29 | 1. Moderator collates Work Tasks 2. Company proposed Work Tasks to SA6#70 | Company proposed key issues, solutions etc. to the agreed Work-Tasks
Output | 1. Populate candidate Work Tasks 2. Finalize tool and plan for Moderated Discussions. 3. Agree to questions for Moderated Discussions | Moderator collates Work Tasks and prepares discussion summary | Intermediate SID based on the agreed Work Tasks (Round 1) | Moderator collates Work Tasks and prepares discussion summary | Finalize Work Tasks (Round 2). Finalize SID considering agreed Work Tasks and submit for SA plenary approval | Finalize TR with relevant Key Issues, Solutions and Conclusions for all Work Tasks by end of release. The conclusions of this study will form the basis for normative 6G application enablement work.

## Slide 7: SA6 Rel-20 6G-study planning Mission Critical
If needed, a dedicated study on Mission Critical aspects can be performed
Any interest ????

## Slide 8: SA6 meeting schedule
Meeting | Date | Location
2026 |  | 
SA6#71 | 9 – 13 Feb 2026 | Goa, India
SA6#72 | 13 – 17 April 2026 | Saint Paul’s Bay, Malta
SA6#73 | 18 – 22 May 2026 | China, Location TBD
SA6#74 | 24 – 28 August 2026 | Prague, Czech Republic
SA6#75 | 12 – 16 October 2026 | Prague, Czech Republic
SA6#76 | 16 – 20 November 2026 | Calgary, Canada
2027 |  | 
SA6#77 | 22 – 26 Feb 2027 | South Korea, Location TBD
SA6#78 | 19 – 23 April 2027 | Location TBD
SA6#79 | 24 – 28 May 2027 | China, Location TBD
SA6#80 | 30 Aug. – 3 Sept. 2027 | Location TBD
SA6#81 | 11 – 15 October 2027 | Location TBD
SA6#82 | 15 – 19 November 2027 | Location TBD

## Slide 9: Thank You!