## Slide 1: FS_5MBS Status Report
Li, Meng
Huawei

## Slide 2
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 50% > 65 % | Sep, 2020 -> Dec, 2020 | SP-200092
Progress since SA#88-e:
  12 new solutions added, and 29 contributions agreed to update current solutions.
  Conclude KI#5 and KI#8, and have an interim requirement for conclusion on KI#1.
  1 LS sent to SA, RAN, RAN2 and RAN3 informing the interim agreement and list identified RAN dependencies.
  TR 23.757 is sent to SA plenary for information.
RAN impacts and dependencies:
  Most of the key issues may lead to RAN impact.
  Timely RAN feedback is needed for SA2 proceeding to normative stages.
Risks:
  Due to RAN dependencies, completion of the study may not be possible in Q4 for all key issues,
Next steps:
  Organize a conference call to discuss Way Forward proposals to finalize the conclusions.
  Draw final evaluations and conclusions in Q4.
  Submit a WID to SA plenary for normative work.
  Target Completion: The target completion date for the study is proposed to be moved to Dec 2020.
FS_5MBS status at SA#89

## Slide 3: FS_5MBS status after SA2#140e (1/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 50% > 65 % | Sep, 2020 -> Dec, 2020 | SP-200092
General
  TR 23.757v0.5.0 is available. The TR is sent to SA plenary for information.
  In 2020Q3 FS_5MBS was discussed in SA2#140E.
Architectural options
  Companies tried to have a consolidated architecture in SA2#140E.
  Architecture shall be determined as early as possible to not impede the progress.
  Next step: Conclude the architecture.
Key Issue 1 (MBS session management)
  16 solutions available: 14 already existing (of which 12 updated in SA2#140E) plus 2 new.
  Interim requirements for conclusions agreed.
  Next step: Evaluate and Conclude the solutions.
Key Issue 7 (MC-UC switch)
  13 solutions available: 11 already existing (of which 9 updated in SA2#140E) plus 2 new.
  Next step: Evaluate and Conclude the solutions.

## Slide 4: FS_5MBS status after SA2#140e (2/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 50% > 65 % | Sep, 2020 -> Dec, 2020 | SP-200092
Key Issue 4 (QoS)
  8 solutions available (3 new, and 1 updated).
  Next step: Evaluate and conclude the solutions.
Key Issue 6 (Local MBS)
  5 solutions available: 3 updated in SA2#140E plus 1 new.
  Next step: Evaluate and conclude the solutions.
Key Issue 9 (Interworking with EPC/eMBMS for Public Safety)
  3 solutions agreed in SA2#140E.
  Next step: Finalize descriptions of solutions and new solutions can be proposed.
Key Issue 2 (Levels of services)
  1 solution available which was introduced in SA2#136AH and updated in SA2#139E.
  Next step: Address other KIs firstly and come back after concluding those KIs.
Key Issue 3 (Levels of authorization)
  Agreed not to have a separate solutions in the TR.
  Next step: If authorization is need, address this KI in the individual solutions and conclude as part of KI#1.

## Slide 5: FS_5MBS status after SA2#140e (3/3)
  RAN impacts and dependencies:
  Most of the key issues and related solutions may lead to RAN impact.
  Solutions specific questions were included in the LS sent to RAN, RAN2 and RAN3.
Contentious Issue:
  None identified so far.
Focus for the Next Meeting (SA2#141E):
  Proposals for new solution will NOT be discussed unless they are for KI#9. New/updated key issue will NOT be discussed.
  Evaluate and conclude the architecture and KIs.
Overall Plan:
  SA2#141e: Evaluate and conclude the architecture and KIs.
  SA2#142e: Evaluate and conclude the remaining KIs.
  TR 23.757 and WID expected to be sent to SA#90E for approval.
Risks:
  Due to RAN dependencies, completion of the study may not be possible in Q4 for all key issues,

## Slide 6: backup

## Slide 7: FS_5MBS status at SA#87
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 15% > 35% | Jun, 20 | 830030/ SP-200xxx
Progress since SA#86:
  Only one SA2 WG meeting in Q1 (SA2#136AH)
  Total TUs requested for Study Phase in 2020 is 8, 2 TUs used in SA2#136AH and 6 TUs remaining.
  Objective B/Key Issue #5 (enTV services) and E-UTRA access removed as a result of downscoping in SA#86 and of NR_MBS WI approved in RAN#86.
  Added new Key Issue 9 (NR/5GC and E-UTRAN/EPC interworking for public safety)
  RAN impacts and dependencies:
  Most of the key issues may lead to RAN impact.
Next steps:
  Address open key issues with focus on the most important ones.
  Finalize description for already captured solutions with strong support.
  Capture new solutions with strong support.
  Select solutions for at least most important key issues.
  List identified RAN dependencies and send liaisons to relevant RAN WGs.

## Slide 8: FS_5MBS status after SA2#136AH (1/2)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 15% > 35% | Jun, 20 | 830030/ SP-200xxx
General
  TR 23.757v0.3.0 is available.
  Total TUs requested for Study Phase in 2020 is 8, 2 TUs used in SA2#136AH and 6 TUs remaining.
  Objective B/Key Issue #5 (enTV services) and E-UTRA access removed as a result of downscoping in SA#86 and of NR_MBS WI approved in RAN#86.
  Added new Key Issue 9 (NR/5GC and E-UTRAN/EPC iwk for public safety)
Architectural options
  Two architectural options captured in Annex A. Option 1 has no new network entities for transport only mode while additional CP and UP entities are needed for full service mode. Option 2 uses new, MBS specific functional components both for transport only mode and full service mode.
Key Issue 1 (MBS session management)
  Five new solutions were included in the TR.
  Next step: in SA2#138 finalize description for solutions with strong support. Proceed with solution evaluation and interim conclusion.
Key Issue 2 (Levels of services)
  One solution captured.
  Next step: in SA2#138 finalize solution description and discuss other solutions if time allows. Proceed with solution evaluation and interim conclusion.
Key Issues 7/8 (MC-UC switch/BC-UC switch)
  No solution captured.
  Next step: in SA2#138 discuss and capture solutions, evaluate and proceed with interim conclusions.
Key Issue 6 (Local MBS)
  One solution captured.
  Next step: if time allows, discuss other solutions if available, evaluate and reach interim conclusions.
Key Issues 3/4/9 (levels of authorization/QoS/IWK with EPC/eMBMS for Public Safety)
  No solution captured.
  Next step: if time allows, discuss solutions if available and time allows, evaluate and reach interim conclusion.

## Slide 9: FS_5MBS status after SA2#136AH (2/2)
  RAN impacts and dependencies:
  Most of the key issues may lead to RAN impact.
Contentious Issue:
  Selection of architectural option.
  Selection of solution(s) for MBS session establishment/management.
Focus for the Next Meeting (SA2#138):
  No new key issues.
  Prioritize solutions for Key Issue 2 (Levels of services), KI1 (MBS session management) and KI7 (MC-UC switch).
  Complete solution descriptions and list RAN impacts for which feedback is needed. Liaise RAN WGs as needed.
  Start solution evaluations and draw interim conclusions.
  If time allows, address other Key Issues and related solutions.
  Evaluate solutions and capture conclusions.
Overall Plan:
  2020Q2:
  Complete description of existing solutions and new solutions with strong support for most important KIs (KI2/1/7).
  Start solutions and architecture options evaluations and draw interim conclusions for most important KIs.
  If time allows, address solutions for other KIs.
  TR 23.757 and WID expected to be sent to SA#88 for approval.

## Slide 10: FS_5MBS status after SA2#139E (1/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 35% -> 50% |  | SP-200092
General
  TR 23.757v0.4.0 is available.
  In 2020Q2 FS_5MBS was only discussed in SA2#139E.
  No new key issue. 24 new solutions added, mostly vs. KI1 and KI7. Previously existing solutions updated.
  Terminology issues fixed: PTP vs. PTM and Individual vs. Shared MBS traffic delivery methods.
Architectural options
  The two architectural options captured in Annex A have been updated and are now more mature.
  Next step: Start evaluation and attempt interim conclusion.
Key Issue 1 (MBS session management)
  14 solutions available: 5 already existing (of which 4 updated in SA2#139E) plus 9 new
  Next step: Conclude descripton of solutions. Start evaluation and, if possible, capture interim conclusions.
Key Issue 7 (MC-UC switch)
  11 solutions available (all new)
  Next step: Conclude descripton of solutions. Start evaluation and, if possible, capture interim conclusions.

## Slide 11: FS_5MBS status after SA2#139E (2/3)
WI Code | Work Item Title | WP | Target Date | WID#
FS_5MBS | Study on architectural enhancements for 5G multicast-broadcast services | 35% -> 50% |  | SP-200092
Key Issue 4 (QoS)
  3 solutions available (all new, of which two apply also to KI1).
  Next step: Capture new solutions, if available. Finalize descriptions of solutions.
Key Issue 6 (Local MBS)
  4 solutions available: 1 already existing (and updated in SA2#139E) plus 3 new.
  Next step: Capture new solutions, if available. Finalize descriptions of solutions.
Key Issue 9 (Interworking with EPC/eMBMS for Public Safety)
  2 solutions proposed in SA2#139E but not captured to wait for KI#1/2/7 to progress.
  Next step: Capture new solutions. Finalize descriptions of solutions.
Key Issue 2 (Levels of services)
  1 solution available which was introduced in SA2#136AH and updated in SA2#139E.
  Next step: If companies still have interest, try to conclude solution description.
Key Issue 8 (BC-UC switch)
  Agreed not to address this KI in Rel-17 timeframe.
Key Issue 3 (Levels of authorization)
  No solutions submitted for this KI.
  Next step: agree not to address this in KI in Rel-17 timeframe

## Slide 12: FS_5MBS status after SA2#139E (3/3)
  RAN impacts and dependencies:
  Most of the key issues and related solutions may lead to RAN impact.
  Solutions specific questions may need to be asked to reach conclusion.
Contentious Issue:
  Evaluation and selection of architectural option.
  Evaluation and selection of solution(s) for MBS session establishment/management and UC-MC switch
Focus for the Next Meeting (SA2#140E):
  No new key issues. Last meeting for new solutions. New solutions allowed only if complete.
  Merging of solutions is encouraged.
  Prioritize solutions for KI1 (MBS session management) and KI7 (MC-UC switch)
    Complete solution descriptions and list RAN impacts for which feedback is needed.
    Start solution evaluations and draw interim conclusions wherever possible.
  Address other Key Issues and related solutions.
    If possible, evaluate solutions and capture conclusions.
  Rappoteur will collect RAN impacts. TR 23.757 for information. Specific questions for feedback may be included.
Overall Plan:
  Conclusion of all KIs (and therefore of SI) by Sep. 2020 unlikely, due to RAN dependencies.
  2020H2:
    Complete description of solutions for all open KIs.
    Complete evaluation of solutions and architecture options evaluations, including RAN feedback where needed, and complete conclusions for all open KIs.
  TR 23.757 and WID expected to be sent to SA#90E for approval.