## Slide 1: FS_SFC Status Report
Ellen Liao Intel (Rapporteur)

## Slide 2: FS_SFC status after SA2#149E (1/2)
General
  Specification is linked to Work item: #940052 - FS_SFC - Study on System Enabler for Service Function Chaining
  The latest TR 23.700-18 is available here.
  Total TUs requested for Study Phase is 2.5 TUs, 2.0 TU remaining.
  Total 6 documents agreed.
  Scope in S2-2201086, TR Skeleton in S2-2201079 agreed.
Architecture Assumption: S2-2201848
Related to Key Issues (SA2#95 is the last e-meeting for any new Key Issue)
  Related to Key Issue 1: S2-2201849
  Traffic Steering Policy and SFC Enhancements
  Next Steps: Solutions proposals in the next three meetings
  Related to Key Issue 2: S2-2201747
  Exposure to enable AF to request predefined SFC for traffic flow(s) related with target UE(s)
  Next Steps: Solutions proposals in the next three meetings
Annex for Pre-R18 Traffic Steering Control: S2-2201748
WI Code | Work Item Title | WP | Target Date | WID#
FS_SFC | Study on System Enabler for Service Function Chaining | 0% > 25% | Aug., 22 | SP-211594

## Slide 3: FS_SFC status after SA2#149E (2/2)
Progress since SA#94-e:
  TR Skeleton, TR Scope, Architectural Assumption, 2 Key Issue, Annex.
No RAN impacts
Next steps:
  Continue the study
WI Code | Work Item Title | WP | Target Date | WID#
FS_SFC | Study on System Enabler for Service Function Chaining | 0% > 25% | Aug., 2022 | SP-211594

## Slide 4: FS_SFC Work Plan
SA5 dependencies
  SA5 dependencies related to Service Function Management
Contentious Issue:
  N/A
Focus for the Next Meeting (SA2#150E):
  Last e-meeting for any new Key Issue, solutions for all Key Issues
Overall Plan:
  SA2#149-E: TR Skeleton, TR Scope, Architectural Assumption, Key Issues, solutions for KIs related to WT#2 and WT#3 (low priority if exceeding 30 papers limits)
  SA2#150-E: any new Key Issue (last meeting), new/revised solutions for all Key Issues/WTs
  SA2#151-E: any new/revised solution (last e-meeting), initial evaluation and potential conclusion, TR for information at SA#96.
  SA2#152-E: solution evaluation and conclusion completion, normative WID, TR for approval at SA#97.
  SA2#153-154AH: update of normative WID if needed, and normative works.
Risks:
  -
TR submission to June 2022 TSG SA#96
for Information
TR and WID submission to Sept. 2022 TSG SA#97 for Approval