## Rel-18 TU stats
| Planned | [22 empty] | Stage 2 freeze | Actual until freeze | [22 empty] | Actual since freeze
| Study TU | Normative TU | Total TU | Feb, 22 |  | Apr, 22 |  | May, 22 |  | Aug, 22 |  | Oct, 22 |  | Nov, 22 |  | Jan, 23 |  | Feb, 23 |  | Apr, 23 |  | May, 23 |  |  | Study TU | Normative TU | Total TU | Aug, 23 |  | Oct, 23 |  | Nov, 23 |  | Jan, 24 |  | Feb, 24 |  | Apr, 24 |  | May, 24 |  | Aug, 24 |  | Oct, 24 |  | Nov, 24 |  | Study TU | Normative TU | Total TU
|  |  |  | #149E |  | #150E |  | #151E |  | #152E |  | #153E |  | #154 |  | #154AHE |  | #155 |  | #156 |  | #157 | [5 empty] | #158 |  | #159 |  | #160 |  | #160AHE |  | #161 |  | #162 |  | #163 |  | #164 |  | #165 |  | #166
[23 empty] | From agenda | [5 empty] | From agenda |  | From agenda |  | From agenda |  | Quota
FS_SATB / SATB | 3.5 | 1.5 | 5 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 |  | 3.5 | 2 | 5.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.16 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0.66 | 0.66
FS_5GSAT_Ph2 / 5GSAT_Ph2 | 4 | 1 | 5 | 0.5 | 0 | 0.5 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0.5 | 0 | 2 | 0 | 0.5 | 0 | 1 |  | 4 | 4 | 8 | 0 | 1 | 0 | 0 | 0 | 0.75 | 0 | 0.16 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1.91 | 1.91
FS_PIN / PIN | 3.5 | 2 | 5.5 | 0.5 | 0 | 0.5 | 0 | 1 | 0 | 1 | 0 | 0.5 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 1 | 0 | 2 |  | 3.5 | 6 | 9.5 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0.16 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2.16 | 2.16
FS_UAS_Ph2 / UAS_Ph2 | 3.25 | 2.25 | 5.5 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 1 | 0 | 0.75 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 |  | 3.25 | 4 | 7.25 | 0 | 0 | 0 | 0.5 | 0 | 0.25 | 0 | 0.03 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0.78 | 0.78
FS_Ranging_SL / Ranging_SL | 3.5 | 2 | 5.5 | 0.5 | 0 | 0.5 | 0 | 1 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 1.5 | 0 | 2 | 0 | 2 | 0 | 2 |  | 3 | 7.5 | 10.5 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 7 | 7
FS_eLCS_Ph3 /eLCS_Ph3 | 6.25 | 4 | 10.25 | 1 | 0 | 1 | 0 | 1 | 0 | 1.5 | 0 | 1.75 | 0 | 0 | 2 | 0 | 1.5 | 0 | 2 | 0 | 1 | 0 | 2 |  | 6.25 | 8.5 | 14.75 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2.5 | 2.5
FS_5G_ProSe_Ph2 / 5G_Prose_Ph2 | 6 | 3.25 | 9.25 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 2 | 0 | 0 | 2 | 0 | 1 | 0 | 2 | 0 | 1 | 0 | 2 |  | 6 | 8 | 14 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | 4
FS_GMEC / GMEC | 4 | 1.75 | 5.75 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.75 | 0 | 0 | 0 | 1 | 0 | 0 |  | 4 | 2.25 | 6.25 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1.4 | 1.4
FS_AIMLsys / AIMLsys | 7 | 5 | 12 | 1 | 0 | 1 | 0 | 1.5 | 0 | 2 | 0 | 1.5 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 |  | 7 | 10 | 17 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0.4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3.4 | 3.4
FS_5MBS_Ph2 / 5MBS_Ph2 | 7.5 | 4.5 | 12 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 1 | 0 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 1 | 0 | 0 |  | 7 | 7 | 14 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2.5 | 2.5
FS_eNS_Ph3 / eNS_Ph3 | 6 | 3.25 | 9.25 | 1 | 0 | 1 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 0 | 2 | 0 | 1.25 | 0 | 2 |  | 6 | 8.25 | 14.25 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 1.7 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 6.7 | 6.7
FS_XRM / XRM | 9 | 5 | 14 | 1 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 3 | 0 | 2 | 0 | 2 |  | 9 | 11 | 20 | 0 | 2 | 0 | 3 | 0 | 3 | 0 | 2 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 10 | 10
FS_REDCAP_Ph2 / REDCAP_Ph2 | 2 | 1 | 3 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.25 | 0 | 1 |  | 2 | 2.25 | 4.25 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.4 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0.9 | 0.9
FS_NG_RTC / NG_RTC | 4 | 2 | 6 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 2 |  | 4 | 5.5 | 9.5 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0.6 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2.6 | 2.6
FS_ATSSS_Ph3 / ATSSS_Ph3 | 6 | 2.5 | 8.5 | 0.5 | 0 | 1.5 | 0 | 1 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 1.25 | 0 | 0 | 0 | 1.25 | 0 | 0 |  | 6 | 2.5 | 8.5 | 0 | 1 | 0 | 0 | 0 | 0.25 | 0 | 0.25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1.5 | 1.5
FS_UPEAS / UPEAS | 3.25 | 2.25 | 5.5 | 0.5 | 0 | 0.5 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0 | 0 |  | 3 | 2.5 | 5.5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.14 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1.14 | 1.14
FS_EDGE_Ph2 / EDGE_Ph2 | 7.25 | 4.25 | 11.5 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 1 | 0 | 0 | 2 | 0 | 1.5 | 0 | 2 | 0 | 1.5 | 0 | 2 |  | 7 | 9 | 16 | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 4 | 4
FS_5TRS_URLLC / TRS_URLLC | 5 | 4 | 9 | 1 | 0 | 1 | 0 | 1 | 0 | 1.5 | 0 | 0 | 1.5 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 0.5 | 0 | 1 |  | 4.5 | 7 | 11.5 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3 | 3
FS_VMR / VMR | 2.75 | 2.25 | 5 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 2 | 0 | 0.5 | 0 | 0 | 0 | 1 | 0 | 1 |  | 2.5 | 4.5 | 7 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 2.5 | 2.5
FS_5WWC_Ph2 / 5WWC_Ph2 | 1.5 | 1 | 2.5 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0.75 | 0 | 2 |  | 1.5 | 3.5 | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.25 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 1.25 | 1.25
MPS_WLAN | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 |  | 0 | 2 | 2 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0.16 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0.41 | 0.41
FS_AMP / AMP | 1.5 | 0.5 | 2 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.5 | 0.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0.1 | 0.1
FS_eNA_Ph3 / eNA_Ph3 | 8 | 6 | 14 | 1 | 0 | 1 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 3 | 0 | 2 | 0 | 3 |  | 8 | 12 | 20 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 1.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 7.5 | 7.5
FS_eNPN_Ph2 / eNPN_Ph2 | 5.5 | 4.25 | 9.75 | 1 | 0 | 1 | 0 | 1.5 | 0 | 1 | 0 | 1.5 | 0 | 0 | 2 | 0 | 1 | 0 | 2 | 0 | 1 | 0 | 0 |  | 6 | 6 | 12 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3.5 | 3.5
FS_eUEPO / eUEPO | 4.25 | 1.5 | 5.75 | 0.5 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0.75 | 0 | 0 | 0 | 0 | 0.75 | 0 | 1 | 0 | 1 | 0 | 2 |  | 4.25 | 4.75 | 9 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1.3 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 3.3 | 3.3
FS_SFC / SFC | 2.5 | 1.5 | 4 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 1 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0.5 | 0 | 0 |  | 2.5 | 1.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0
FS_DetNet / DetNet | 1 | 1 | 2 | 0.25 | 0 | 0 | 0 | 0.5 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0.5 | 0 | 1 | 0 | 0.5 | 0 | 0 |  | 1 | 2 | 3 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0.03 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0.28 | 0.28
FS_SUECR / SUECR | 1.5 | 0.25 | 1.75 | 0.5 | 0 | 0.5 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.5 | 0.25 | 1.75 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0.5 | 0.5
Total for Rel-18 SID/WID | 119.5 | 71.75 | 191.25 | 19.25 | 0 | 21.5 | 0 | 27.5 | 0 | 29.75 | 0 | 19.75 | 6.5 | 0 | 23 | 0 | 27.25 | 0 | 31 | 0 | 26.5 | 0 | 30 |  | 117.75 | 144.25 | 262 | 0 | 19 | 0 | 20.5 | 0 | 19.25 | 0 | 16.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 75.49 | 75.49
Note on R9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 (Normative) + 0.5 (Study)
Note on P14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 0.5 + 0.5
Note on N20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .25 + .75
Note on P21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .25 + .75
Note on N22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 0.5 + 1
Note on P23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: .25 + .75
Note on M28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 (Study) + 0.5 (normative)

## SA2#160AHE Jan
|  |  | Month | Aug, 23 | Oct, 23 | Nov, 23 | Jan, 24 | Feb, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24
|  |  | Meeting | #158 | #159 | #160 | E Ad hoc | #161 | #162 | #163 | #164 | #165 | #166
|  |  | TU total (for planning purposes) | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Pre-Rel-17 maintenance
Planned |  |  |  | 1 | 1 | 1 | 0 | bar: #161 to #166
Actual |  |  |  | 2 | 1 | 1.7
Rel-17 maintenance
Planned |  |  |  | 3 | 2 | 2 | 0 | bar: #161 to #166
Actual |  |  |  | 3 | 2 | 1.2
Rel-18 maintenance
Planned |  |  |  | 20 | 18 | 18 | 14 | 14 | 10 | 8 | 8 | 6 | 6
Actual |  |  |  | 22 | 22 | 20.6
Buffer (TEI19, overflow, other)
Planned |  |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Actual |  |  |  | 0 | 1 | 6
Total of Maintenance + Buffer
Planned |  |  |  | 30 | 27 | 27 | 20 | 22 | 18 | 16 | 16 | 14 | 14
Actual |  |  |  | 27 | 26 | 29.5
Rel-19
Planned |  |  |  | 6 | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Actual |  |  |  | 9 | 10 | 5.25
Overall total
Planned |  |  |  | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Actual |  |  |  | 36 | 36 | 34.75
Rel-19 SID/WID detailed plan |  | TU estimates (from SID)
FS_5GSAT_Ph3_ARCH | Study TU's planned | 7 | 7 |  | 1 | 1 | 1.5 | #161: 1; #162: 1.5; #163: 1
Jean Yves Fine | Study TU's used |  | 2 |  | 1 | 1
Hucheng Wang | Normative TU's planned | 5.5 | 0
Normative TU's used
FS_NG_RTC_Ph2 | Study TU's planned | 6 | 6 |  | 1 | 1.5 | 1 | #161: 1; #162: 1; #163: 0.5
Yi Jiang | Study TU's used |  | 2.5 |  | 1 | 1.5
| Normative TU's planned | 5.5 | 0
Normative TU's used
FS_XRM Ph2 | Study TU's planned | 7 | 7 |  | 1 | 1 | 1 | #161: 1; #162: 1; #163: 2
Devaki Chandramouli | Study TU's used |  | 2 |  | 1 | 1
Curt Wong | Normative TU's planned | 6 | 0
Normative TU's used
FS_EnergySys | Study TU's planned | 6.5 | 6.5 |  | 1 | 1 | 1 | #161: 1.5; #162: 1; #163: 1
Junshin Park | Study TU's used |  | 2 |  | 1 | 1
Konstantinos Samdanis | Normative TU's planned | 6.5 | 0
Normative TU's used
FS_MPS4msg | Study TU's planned | 3 | 3 |  |  | 0.75 | 0.5 | #161: 1; #162: 0; #163: 0.75
Robert Streijl | Study TU's used |  | 0.75 |  |  | 0.75
| Normative TU's planned | 3 | 0
Normative TU's used
FS_VMR_Ph2 | Study TU's planned | 3 | 3 |  |  |  | 0.5 | #161: 0.5; #162: 1; #163: 1
Hong Cheng | Study TU's used |  | 0
Lars Nord | Normative TU's planned | 2.5 | 0
Normative TU's used
FS_5G_ProSe_Ph3 | Study TU's planned | 2 | 2 |  |  |  | 0.5 | #161: 0.5; #162: 0.5; #163: 0.5
Hugh Shieh | Study TU's used |  | 0
Nassima Toumi | Normative TU's planned | 1.5 | 0
Normative TU's used
FS_UIA_ARC | Study TU's planned | 5.25 | 5.25 |  |  |  | 0.5 | #161: 1.5; #162: 1.75; #163: 1.5
Mike Starsinic | Study TU's used |  | 0
| Normative TU's planned | 4.25 | 0
Normative TU's used
FS_eEDGE_5GC_ph3 | Study TU's planned | 4.5 | 4.5 |  |  |  | 0.5 | #161: 1.5; #162: 1.5; #163: 1
Changhong Shan | Study TU's used |  | 0
| Normative TU's planned | 3 | 0
Normative TU's used
FS_UAS_Ph3 | Study TU's planned | 3.5 | 3.5 |  |  |  | 0.5 | bar: #161 to #163
LaeYoung Kim | Study TU's used |  | 0
Shabnam Sultana | Normative TU's planned | 3 | 0
Normative TU's used
FS_ISAC_ARC | Study TU's planned | 0 | 0
| Study TU's used |  | 0
| Normative TU's planned | 0 | 0
Normative TU's used
FS_UPEAS_Ph2 | Study TU's planned | 2.25 | 2.25 |  |  |  | 0.25 | #161: 0.5; #162: 1; #163: 0.5
Jinguo Zhu | Study TU's used |  | 0
| Normative TU's planned | 2.25 | 0
Normative TU's used
FS_5G_Femto | Study TU's planned | 2 | 2.25 |  |  |  | 0.5 | #161: 0.5; #162: 0.5; #163: 0.75
Malla Reddy Sama | Study TU's used |  | 0
| Normative TU's planned | 3 | 0
Normative TU's used
FS_MASSS | Study TU's planned | 7.5 | 7.5 |  |  |  | 1.5 | #161: 2; #162: 2; #163: 2
Krizstian Kiss | Study TU's used |  | 0
Zhuoyi Chen | Normative TU's planned | 6 | 0
Normative TU's used
FS_AmbientIoT | Study TU's planned | 11.5 | 11.5 |  |  |  | 0.5 | 2 | 2 | 2 | 2 | 1.5 | 1.5
Runze Zhou | Study TU's used |  | 0
Fei Lu | Normative TU's planned | 0 | 0
Normative TU's used
FS_AIML_CN | Study TU's planned | 4 | 4 |  |  |  | 0.5 | #161: 1.5; #162: 1; #163: 1
Xiaobo Wu | Study TU's used |  | 0
Mehrdad Shariat | Normative TU's planned | 4 | 0
Normative TU's used
Total planned (overall plan) |  |  |  |  | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Total planned (sum of item plans) |  |  |  |  | 4 | 5.25 | 10.75 | 17 | 16.75 | 16.5 | 2 | 1.5 | 1.5
|  | Planned | Used
Total for Rel-19 Studies |  | 75 | 9.25 |  | 4 | 5.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total for Rel-19 Normative |  | 56 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total for Rel-19 SID/WID |  | 131 | 9.25 |  | 4 | 5.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## SA2#161 Feb
|  |  | Month | Aug, 23 | Oct, 23 | Nov, 23 | Jan, 24 | Feb, 24 | Apr, 24 | May, 24 | Aug, 24 | Oct, 24 | Nov, 24
|  |  | Meeting | #158 | #159 | #160 | E Ad hoc | #161 | #162 | #163 | #164 | #165 | #166
|  |  | TU total (for planning purposes) | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Pre-Rel-17 maintenance
Planned |  |  |  | 1 | 1 | 1 | 0 | bar: #161 to #166
Actual |  |  |  | 2 | 1 | 1.7 | N/A
Rel-17 maintenance
Planned |  |  |  | 3 | 2 | 2 | 0 | bar: #161 to #166
Actual |  |  |  | 3 | 2 | 1.2 | N/A
Rel-18 maintenance
Planned |  |  |  | 20 | 18 | 18 | 14 | 14 | 10 | 8 | 8 | 6 | 6
Actual |  |  |  | 22 | 22 | 20.6 | N/A
Buffer (TEI19, overflow, other)
Planned |  |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Actual |  |  |  | 0 | 1 | 6 | N/A
Total of Maintenance + Buffer
Planned |  |  |  | 30 | 27 | 27 | 20 | 22 | 18 | 16 | 16 | 14 | 14
Actual |  |  |  | 27 | 26 | 29.5 | N/A
Rel-19
Planned |  |  |  | 6 | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Actual |  |  |  | 9 | 10 | 5.25 | 10.75
Overall total
Planned |  |  |  | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36 | 36
Actual |  |  |  | 36 | 36 | 34.75 | N/A
Rel-19 SID/WID detailed plan |  | TU estimates (from SID)
FS_5GSAT_Ph3_ARCH | Study TU's planned | 7 | 7 |  | 1 | 1 | 1.5 | #161: 1; #162: 1.5; #163: 1
Jean Yves Fine | Study TU's used |  | 3.5 |  | 1 | 1 | 1.5
Hucheng Wang | Normative TU's planned | 5.5 | 0
Normative TU's used
FS_NG_RTC_Ph2 | Study TU's planned | 6 | 6 |  | 1 | 1.5 | 1 | #161: 1; #162: 1; #163: 0.5
Yi Jiang | Study TU's used |  | 3.5 |  | 1 | 1.5 | 1
| Normative TU's planned | 5.5 | 0
Normative TU's used
FS_XRM Ph2 | Study TU's planned | 7 | 7 |  | 1 | 1 | 1 | #161: 1; #162: 1; #163: 2
Devaki Chandramouli | Study TU's used |  | 3 |  | 1 | 1 | 1
Curt Wong | Normative TU's planned | 6 | 0
Normative TU's used
FS_EnergySys | Study TU's planned | 6.5 | 6.5 |  | 1 | 1 | 1 | #161: 1.5; #162: 1; #163: 1
Junshin Park | Study TU's used |  | 3 |  | 1 | 1 | 1
Konstantinos Samdanis | Normative TU's planned | 6.5 | 0
Normative TU's used
FS_MPS4msg | Study TU's planned | 3 | 3 |  |  | 0.75 | 0.5 | #161: 1; #162: 0; #163: 0.75
Robert Streijl | Study TU's used |  | 1.25 |  |  | 0.75 | 0.5
| Normative TU's planned | 3 | 0
Normative TU's used
FS_VMR_Ph2 | Study TU's planned | 3 | 3 |  |  |  | 0.5 | #161: 0.5; #162: 1; #163: 1
Hong Cheng | Study TU's used |  | 0.5 |  |  |  | 0.5
Lars Nord | Normative TU's planned | 2.5 | 0
Normative TU's used
FS_5G_ProSe_Ph3 | Study TU's planned | 2 | 2 |  |  |  | 0.5 | #161: 0.5; #162: 0.5; #163: 0.5
Hugh Shieh | Study TU's used |  | 0.5 |  |  |  | 0.5
Nassima Toumi | Normative TU's planned | 1.5 | 0
Normative TU's used
FS_UIA_ARC | Study TU's planned | 5.25 | 5.25 |  |  |  | 0.5 | #161: 1.5; #162: 1.75; #163: 1.5
Mike Starsinic | Study TU's used |  | 0.5 |  |  |  | 0.5
| Normative TU's planned | 4.25 | 0
Normative TU's used
FS_eEDGE_5GC_ph3 | Study TU's planned | 4.5 | 4.5 |  |  |  | 0.5 | #161: 1.5; #162: 1.5; #163: 1
Changhong Shan | Study TU's used |  | 0.5 |  |  |  | 0.5
| Normative TU's planned | 3 | 0
Normative TU's used
FS_UAS_Ph3 | Study TU's planned | 3.5 | 3.5 |  |  |  | 0.5 | bar: #161 to #163
LaeYoung Kim | Study TU's used |  | 0.5 |  |  |  | 0.5
Shabnam Sultana | Normative TU's planned | 3 | 0
Normative TU's used
FS_ISAC_ARC | Study TU's planned | 0 | 0
| Study TU's used |  | 0
| Normative TU's planned | 0 | 0
Normative TU's used
FS_UPEAS_Ph2 | Study TU's planned | 2.25 | 2.25 |  |  |  | 0.25 | #161: 0.5; #162: 1; #163: 0.5
Jinguo Zhu | Study TU's used |  | 0.25 |  |  |  | 0.25
| Normative TU's planned | 2.25 | 0
Normative TU's used
FS_5G_Femto | Study TU's planned | 2 | 2.25 |  |  |  | 0.5 | #161: 0.5; #162: 0.5; #163: 0.75
Malla Reddy Sama | Study TU's used |  | 0.5 |  |  |  | 0.5
| Normative TU's planned | 3 | 0
Normative TU's used
FS_MASSS | Study TU's planned | 7.5 | 7.5 |  |  |  | 1.5 | #161: 2; #162: 2; #163: 2
Krizstian Kiss | Study TU's used |  | 1.5 |  |  |  | 1.5
Zhuoyi Chen | Normative TU's planned | 6 | 0
Normative TU's used
FS_AmbientIoT | Study TU's planned | 11.5 | 11.5 |  |  |  | 0.5 | 2 | 2 | 2 | 2 | 1.5 | 1.5
Runze Zhou | Study TU's used |  | 0.5 |  |  |  | 0.5
Fei Lu | Normative TU's planned | 0 | 0
Normative TU's used
FS_AIML_CN | Study TU's planned | 4 | 4 |  |  |  | 0.5 | #161: 1.5; #162: 1; #163: 1
Xiaobo Wu | Study TU's used |  | 0.5 |  |  |  | 0.5
Mehrdad Shariat | Normative TU's planned | 4 | 0
Normative TU's used
Total planned (overall plan) |  |  |  |  | 9 | 9 | 16 | 14 | 18 | 20 | 20 | 22 | 22
Total planned (sum of individual plans) |  |  |  |  | 4 | 5.25 | 10.75 | 17 | 16.75 | 16.5 | 2 | 1.5 | 1.5
|  | Planned | Used
Total for Rel-19 Studies |  | 75 | 20 |  | 4 | 5.25 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0
Total for Rel-19 Normative |  | 56 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total for Rel-19 SID/WID |  | 131 | 20 |  | 4 | 5.25 | 10.75 | 0 | 0 | 0 | 0 | 0 | 0