## Slide 1: Release 19 MPS4msg Status Report
Robert Streijl
Peraton Labs (Rapporteur)

## Slide 2: MPS4msg Status at SA#105
Progress since SA#104
  Started normative phase.
  15 Normative Change Requests submitted: 9 agreed (including content of 4 merged), and 2 noted (alternative solutions identified).
RAN impacts and dependencies
  None
Contentious issues
  None
WI Code | Work Item Title | WP | Target Date | WID#
1040029 | MPS for IMS Messaging and SMS services | 80% | Dec 2024 | SP-240987

## Slide 3: MPS4msg Status after SA2#164
  General
  Study (FS_MPS4msg) and WID (MPS4msg) were approved at SA#104 (Jun 24).
  Started normative phase in SA2#164 (Aug 24).
  15 normative CRs submitted. 9 agreed, 4 merged, 2 noted.
  Agreed CRs will be sent to SA#105 for approval
  RAN or Other WG impacts and dependencies
  None
  Contentious issues
  None
Next steps
  Outstanding topics will be identified before next meeting.
  1 TU used, 2 TUs left:
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010031 | Study on MPS for IMS Messaging and SMS services | FS_MPS4msg | 18/06/2024 | - | SP-231672 | 100% | 
1040029 | MPS for IMS Messaging and SMS services | MPS4msg | 10/12/2024 | 0% | SP-240987 | 80% | 

## Slide 4: Annex FS_MPS4msg

## Slide 5: FS_MPS4msg Status at SA#104
Progress since SA#104
  Presented nine CRs
  Agreed nine CRs
  Study goals completed
RAN impacts and dependencies
  None
Contentious issues
  None
Next steps
  Start normative phase:
WI Code | Work Item Title | WP | Target Date | WID#
FS_MPS4msg | MPS for IMS Messaging and SMS services | 100% | Sep 2024 | SP-231672
 | Aug, 24 | Oct, 24 | Nov, 24 | 
WID | #164 | #165 | #166 | Total TUs
MPS4msg | 1 | 1 | 1 | 3

## Slide 6: FS_MPS4msg Work Plan
Total 6 TUs
  3 TUs for Study Phase – used 2.25
  3 TUs for Normative Work
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#159 | Oct 2023 | 0 | 0 | 
SA2#160 | Nov 2023 | 0.75 | 0.75 | TR skeleton, scope, architectural assumptions, key issue discussion
SA2#160-AH-e | Jan 2024 | 0.5 | 0.5 | Start solution discussion, last meeting for Key Issue proposals
SA2#161 | Feb 2024 | 0.5 | 0.5 | Complete solutions
SA2#162 | Apr 2024 | 0 | 0 | 
SA2#163 | May 2024 | 1.25 | 0.5 | Resolve open issues and ENs. Evaluations and conclusions.
 | Total | 3 | 2.25 |