## Slide 1: Discussion of TU budget for Rel-20
Guidance provided by SA Chair
So SA2 needs to come to a consensus on our capacity in Rel-20 by the end of the November meeting
22 | 5G-Adv in Rel-20 Workshop
22.1 | General
22.1.1 | 5G-Adv in Rel-20 planning
22.1.2 | Incoming LSs
22.1.3 | Cross TSG Coordination
22.2 | Input Documents to the Workshop
22.2.1 | SA WG1 inputs on Rel-20 status
22.2.2 | SA WGs inputs on WG capacity for Rel-20 (e.g., TU Budget, Max# of SIDs/WIDs, Max size per SID/WID)
22.2.3 | 3GPP Member/MRP/other contributions on Rel-20 views/priority
22.3 | Output of the Workshop
22.3.1 | High-level summary report from the WS
22.3.2 | Identify the Core and Miscellaneous Rel-20 items/direction

## Slide 2: Discussion of TU budget for Rel-20
The Rel-20 work can broadly be separated into two parts: 5G-Advanced and 6G
6G will be entirely study work in the Rel-20 timeframe
5G-Advanced will be a mixture of study and normative work

## Slide 3: Discussion of TU budget for Rel-20
The main milestones for Rel-20 have mostly been decided
  Rel-20 content defined: June 2025
  5G-Advanced Stage 2 80%: June 2026
  5G-Advanced Stage 2 100%: September 2026
  6G Study 100%: December 2026 or March 2027 (TBD)
For planning purposes SA2 will also need to decide on an internal target for 5G-Advanced study item completion
A possible timeline for 5G-Advanced topics is shown on the next slide

## Slide 4: Potential 5G Advanced timeline in Rel-20
This shows the meetings available for items needing study and normative work
Items that only require normative work (because the study phase was completed in the Rel-20 timeframe) could potentially start in April 2025 (subject to WI approval)
It is important to note that any 5G Advanced study items only approved by SA in June would have just 4 meetings until the suggested SA2 study completion target of February 2026
  It is important then that larger study + normative items will need to be approved by SA in March
The study completion target is required to ensure sufficient number of meetings to complete the normative work (and even so, only gives 3 meetings for this)
Stage 2 100% completion is intended to mean that there are no exceptions
  This is likely to be a challenge for anything more than a small/medium sized study + work item
 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
Meetings | SA#106 | SA2 ad hoc | SA2#167 | SA#107 | SA2#168 | SA2#169 | SA#108 |  | SA2#170 | SA#109 | SA2#171 | SA2#172 | SA#110 | TBD | SA2#173 | SA#111 | SA2#174 | SA2#175 | SA#112 |  | SA2#176 | SA#113 | SA2#177 | SA2#178 | SA#114
Rel-19 Milestones | Stage 2 100% |  |  |  |  |  |  |  |  | Stage 3 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Rel-20 milestones and events | 5GA WS |  |  | 6G WS Some SA2 5GA content |  |  | 5GA Stage 1 100% Rel-20 Content defined |  |  |  |  |  |  |  | Rel-20 5GA study 100% | 6G FS Stage 1 100% |  |  | 5GA Stage 2 80% |  |  | 5GA Stage 2 100% |  |  | 6G Study 100% (TBC)
5GA timeline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Preparation Phase |  |  | #1 |  | #2 | #3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Study Phase |  |  |  |  | #1 | #2 |  |  | #3 |  | #4 | #5 |  |  | #6 |  |  |  |  |  |  |  |  |  | 
Normative phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | #1 | #2 |  |  | #3 |  |  |  | 
Maintenance phase |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | #1 | #2 | 

## Slide 5: Potential 6G timeline in Rel-20
This shows the meetings available for the 6G study work
The timeline extends beyond when the 5G-Advanced work needs to be completed
The additional duration of the work, and no normative work in Rel-20, should mean approval of 6G Study Item(s) in June 2025 is soon enough
 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
Meetings | SA#106 | SA2 ad hoc | SA2#167 | SA#107 | SA2#168 | SA2#169 | SA#108 |  | SA2#170 | SA#109 | SA2#171 | SA2#172 | SA#110 | TBD | SA2#173 | SA#111 | SA2#174 | SA2#175 | SA#112 |  | SA2#176 | SA#113 | SA2#177 | SA2#178 | SA#114
Rel-19 Milestones | Stage 2 100% |  |  |  |  |  |  |  |  | Stage 3 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Rel-20 milestones and events | 5GA WS |  |  | 6G WS Some SA2 5GA content |  |  | 5GA Stage 1 100% Rel-20 Content defined |  |  |  |  |  |  |  | Rel-20 5GA study 100% | 6G FS Stage 1 100% |  |  | 5GA Stage 2 80% |  |  | 5GA Stage 2 100% |  |  | 6G Study 100% (TBC)
6G study timeline |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Preparation Phase |  |  |  |  | #1 | #2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Study Phase |  |  |  |  |  |  |  |  | #1 |  | #2 | #3 |  |  | #4 |  | #5 | #6 |  |  | #7 |  | #8 | #9 | 

## Slide 6: SA2 Rel-20 planning in more detail
The Rel-19 planning was based on a total number of TU’s per meeting of 36, or which 6 were buffer TU’s
The 6 buffer TU’s were for TEI19, Rel-18 alignment, overflow, 5G deployment issues, etc
We’ve seen that typically there are many drafting sessions in addition to the regular sessions, and these occupy Q0, lunch breaks and some Q5 time
It has proved very helpful to have work planning/single stream discussions on Wednesday and Thursday
It is proposed that the default session plan shown here is used as the basis for determining SA2 capacity during the Rel-20 timeframe
Therefore 30 TU’s per meeting should be counted for release planning purposes
It is proposed that the TEI20 budget also comes from the 30 TU’s per meeting budget
 | Default session plan |  |  |  | 
 | Mon | Tue | Wed | Thur | Fri
Q0 |  |  |  |  | 
Q1 | Opening plenary | 10 | 22 | rev | rev
 |  | 11 | 23 | rev | rev
 |  | 12 | 24 | rev | rev
Q2 | 1 | 13 | 25 | rev | rev
 | 2 | 14 | 26 | rev | rev
 | 3 | 15 | 27 | rev | rev
Q3 | 4 | 16 | 28 | rev | Closing plenary
 | 5 | 17 | 29 | rev | 
 | 6 | 18 | 30 | rev | 
Q4 | 7 | 19 | rev | rev | 
 | 8 | 20 | rev | rev | 
 | 9 | 21 | rev | rev | 
Q5 |  |  | Work plan, etc | Work plan, etc | 

## Slide 7: SA2 Rel-20 planning in more detail
Making estimates for maintenance work based on previous releases, and making some assumptions for the amount of Rel-19 exception work:
These provide the following totals for the meetings after March 2025 and before September 2026
  Pre-Rel 18 maintenance: 11
  Rel-18 maintenance: 18
  Rel-19 maintenance: 57
  Rel-19 exceptions: 0
  A total of 86 TU’s for pre-Rel-20 items
 | Dec-24 | Jan-25 | Feb-25 | Mar-25 | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26
Meetings | SA#106 | SA2 ad hoc | SA2#167 | SA#107 | SA2#168 | SA2#169 | SA#108 |  | SA2#170 | SA#109 | SA2#171 | SA2#172 | SA#110 | TBD | SA2#173 | SA#111 | SA2#174 | SA2#175 | SA#112 |  | SA2#176 | SA#113 | SA2#177 | SA2#178 | SA#114
Rel-19 Milestones | Stage 2 100% |  |  |  |  |  |  |  |  | Stage 3 100% |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Rel-20 milestones and events | 5GA WS | e-meeting |  | 6G WS Some SA2 5GA content |  |  | 5GA Stage 1 100% Rel-20 Content defined |  |  |  |  |  |  |  | Rel-20 5GA study 100% | 6G FS Stage 1 100% |  |  | 5GA Stage 2 80% |  |  | 5GA Stage 2 100% |  |  | 6G Study 100% (TBC)
Pre-Rel-18 maintenance |  | 1 | 2 |  | 2 | 2 |  |  | 1 |  | 1 | 1 |  |  | 1 |  | 1 | 1 |  |  | 1 |  | 1 | 1 | 
Rel-18 maintenance |  | 2 | 3 |  | 2 | 2 |  |  | 2 |  | 2 | 2 |  |  | 2 |  | 2 | 2 |  |  | 2 |  | 2 | 2 | 
Rel-19 maintenance |  | 15 | 15 |  | 11 | 11 |  |  | 9 |  | 6 | 6 |  |  | 4 |  | 4 | 4 |  |  | 2 |  | 2 | 2 | 

## Slide 8: SA2 Rel-20 planning in more detail
For the period from March 2025 to the Stage 2 100% date (September 2026) there are 2 fewer meetings, giving 30 * 9 = 270 TU’s
86 TU’s are planned for maintenance in this period
So the total to consider when planning Rel-20 TU capacity during the period of 5G-Advanced Rel-20 work is 270 – 86 = 184 TU’s
These 184 TU’s are for 5G-Advanced SIDs and WIDs, TEI20 and 6G study work
Note, there will be additional TU’s for 6G after the 5G-Advanced work is complete

## Slide 9: Things to be learnt from Rel-19
Drafting sessions for the study items comprised an additional ~30% of TU’s on top of the normal sessions budgeted
Due to clashes between topics it wasn’t possible to allocate all sessions
In particular, it is difficult to schedule topics in parallel with large items that wide interest
  Should limit the TU’s per meeting per item allocation to 2, and limit the number of large items
All study items stayed close to their planned TU budget, but not all study items completed their scope by the planned study completion target
The plan to complete normative work in 3 meetings was ambitious for some items
  It is likely that ~6 of 14 work items will not complete by the Stage 2 freeze
  It hasn’t been possible to allocate more TU’s due to topic clash limitations
  But allocation of additional TU’s would not necessarily have ensured completion as time between meetings is required for discussion to resolve issues

## Slide 10: Rel-20 budget
From an earlier slide, 184 TU’s are available for 5G-Advanced SIDs and WIDs and 6G study work (between March 2025 and September 2026)
  This is based on a 30 TU budget per meeting for all agenda items less the budget for maintenance items
In Rel-19 a buffer of 6 TU’s was set aside from the budget of 36 TU’s per meeting
  For TEI-19, Rel-18 alignment, 5G deployment issues, …
But a significant amount (15 TU’s in total, or ~30%) of this buffer was consumed by drafting sessions during the “buffer” quarters (Monday and Tuesday Q5)
And, the Stage 2 100% milestone is understood to mean no exceptions, so there is less scope for delays in finishing 5G Advanced studies
Therefore some additional buffer time should be set aside during Rel-20
Recommendation: 3 additional buffer TU’s per meeting
This means reserving 3 * 9 = 27 TU’s from the 184 TU’s above
So for planning purposes the TU budget for 5G-Advanced SIDs and WIDs, TEI20 and 6G study work between March 2025 and September 2026 is 184 – 27 = 157 TU’s

## Slide 11: SA2 Rel-20 planning in more detail
How do we decide the split between 5G Advanced and 6G work?
At this point SA2 doesn’t have a 6G study item with objectives/work tasks and TU estimates
SA2 also doesn’t have a set of candidate 5G Advanced study/work items with objectives/work tasks and TU estimates
So there isn’t a clear and unambiguous basis for deciding how much to allocate to these two areas of work
Without that there seem to be four basic options:
  Decide now on a maximum number of averagely sized 5G Advanced items
  Decide now on a split between 5G Advanced and 6G eg 30/70
  Decide now to approve 3 or 4 5G Advanced items in March and then decide how many more are possible in June when the 6G study is approved
  Don’t decide on the split now, wait until the 5G Advanced and 6G SIDs are all defined (June)
Recommendation: Plan to approve 3 – 5 5G Advanced items in March and then decide how many more are possible in June when the 6G study is approved

## Slide 12: SA2 Rel-19 capacity summary (Taken from SWS-230086)
SA2 capacity (see SWS-230052 / SWS-230053):
  Max TUs: 134
    Additional buffer TUs: 48 (for TEI-19, Rel-18 alignment, 5G deployment issues, …)
  Max number of SIs/WIs: 10 – 14
    Note: one feature made up of SI+WI is counted as one item
  Max TUs per Feature: 14
Assumptions
  Start: Sept 2023, End: Dec 2024 (15 months)
  Number of meetings: 8
  Expected total TUs per meeting (for all releases): 36
  Total TUs (for all releases): 288
  TUs for maintenance of past releases: 106
The SA Chair has asked the SA WGs to provide their input to December in the form shown on this slide (from Rel-19)

## Slide 13: Summary of TU plan
SA2 | #167 | #168 | #169 | #170 | #171 | #172 | #173 | #174 | #175 | #176 | #177 | #178
Date | Feb-25 | Apr-25 | May-25 | Aug-25 | Oct-25 | Nov-25 | Feb-26 | Apr-26 | May-26 | Aug-26 | Oct-26 | Nov-26
Milestones and deadlines |  | Start some 5GA |  | Start all 5GA and 6G |  | Complete some 5GA studies | Complete all 5GA studies |  | 5GA Stage 2 80% | 5GA Stage 2 100% |  | 
Pre-Rel-19 maint | 5 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Rel-19 maint | 15 | 11 | 11 | 9 | 6 | 6 | 4 | 4 | 4 | 2 | 2 | 2
Rel-19 exceptions | 8 |  |  |  |  |  |  |  |  |  |  | 
Rel-20 | 3 | 12 | 12 | 15 | 18 | 18 | 20 | 20 | 20 | 22 | 15 | 15
Rel-20 maint |  |  |  |  |  |  |  |  |  |  | 7 | 7
Total | 31 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27 | 27
 |  | Duration of 5GA work in Rel-20 |  |  |  |  |  |  |  |  |  | 
 |  |  |  | Duration of 6G study work in Rel-20 (tbc) |  |  |  |  |  |  |  | 
 |  | Total TU's for Rel-20 March 25 - September 26 |  |  |  |  | 157 |  |  |  |  | 
 |  | Additional TU's for 6G after September 26 |  |  |  |  | 30 |  |  |  |  | 

## Slide 14: SA2 Rel-20 capacity summary
SA2 capacity (March 2025 – September 2026):
  Max TU’s for release planning purposes: 157
    For 5G Advanced SIDs and WIDs, TEI20 and 6G SID
  Max number of SIs/WIs: 10 - 12
    Note: one feature made up of SI+WI is counted as one item
  Max TUs per Feature: 2 TU’s per meeting (excluding the 6G study)
Additional TU’s for 6G study after September: 30
Assumptions
  Number of meetings: 9
  Expected total TUs per meeting (for all releases): 30
  Total TUs (for all releases): 270
  TUs for maintenance of past releases: 86
  TUs for additional buffer: 27

## Slide 15: Backup slides

## Slide 16: Rel-19 outcomes compared with the original plans (at the end of SA2#165)
Study items
  Planned TU’s for the studies: 75
  Normal session TU’s consumed: 79.75
  2 Studies consumed fewer TU’s than planned
  8 Studies consumed more TU’s than planned
  Drafting sessions
    In addition 28 drafting sessions were also allocated
    So, drafting sessions added ~30% of additional TU’s on top of the regular sessions
Normative items
  After two meetings 8 out of 14 Work Items are on target
  28.5 TU’s out of 56 have been consumed (51%)
  In addition, 6.5 TU’s planned for normative work were consumed by study work after June