## Slide 1: Rel-20 5GA and 6G TU budget split
Andy Bennett
SA2 Chair
SA WG2 Meeting #169 Fukuoka
May 19 – May 23, 2025

## Slide 2: Rel-20 5GA and 6G TU budget split
The previously discussed planning for Rel-20 TU’s:
 |  |  | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026
 |  |  | Apr #168 | May #169 | Aug #170 | Oct #171 | Nov #172 | Feb #173 | Apr #174 | May #175 | Aug #176 | Oct #177 | Nov #178
 |  | Totals between March and September |  |  |  |  | Study deadline A | Study deadline B |  | Stage 2 80% | Stage 2 100% |  | 
Rel-20 |  |  |  |  |  |  |  |  |  |  |  |  | 
20.x | Planned TU's (not TEI20, Maint) | 148 | 4 | 8 | 15 | 18 | 19 | 21 | 21 | 21 | 21 | 12 | 12
20.x | TEI20 | 12 |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 |  | 
20.x | Rel-20 maintenance | 0 |  |  |  |  |  |  |  |  |  | 9 | 9

## Slide 3: Rel-20 5GA and 6G TU budget split
We consumed 4 TU’s in April have scheduled 8 TU’s in May for technical work on 5GA Rel-20 SIDs approved in March
We used 6 TU’s for 6G SID preparation in April (2 single stream sessions)
We used 3 TU’s for 5GA SID preparation in April (1 single stream session)
  (Some time in the Work Planning sessions was also used)
We have planned 6 TU’s for 6G SID preparation in May (2 single stream sessions)
We have planned 6 TU’s for 5GA SID preparation in May (2 single stream sessions)
  (Some time in the Work Planning sessions will also be used)

## Slide 4: Rel-20 5GA and 6G TU budget split
The TU budget for Rel-20 was previously stated to be 156 TU’s
This included time for SID preparation
The overall budget for technical work is therefore 148, to be shared between 5GA and 6G topics
It is anticipated that until the end of 2025 all 6G study work will be as a single stream. In November 2025 we will assess the what 6G study topics can be run in parallel
The 6G study will be considerably more complex than a typical large study item spanning a broader range of issues
We allocate 2 TU’s (2 sessions) per meeting for those “typical large studies” and so it is reasonable to expect to need considerably more sessions per meeting

## Slide 5: Rel-20 5GA and 6G TU budget split
Scenario 1: 6G sessions not scheduled in parallel with 5GA or maintenance
  The 6G study is not run in parallel with any other topic (5GA, maintenance)
  Allocating 12 TU’s in a meeting to 6G would provide 4 sessions
 | Mon | Tue | Wed | Thur | Fri | 
 | Opening plenary |  |  | rev | rev | 
 |  |  |  | rev | rev | 
 |  |  |  | rev | rev | 
 |  |  |  | rev | rev | 
 |  |  |  | rev | rev | 
 |  |  |  | rev | rev | 
 |  |  |  | rev | Closing plenary | 
 |  |  |  | rev |  | 
 |  |  |  | rev |  | 
 |  |  | rev | rev |  | 
 |  |  | rev | rev |  | 
 |  |  | rev | rev |  | 
 |  |  | Work plan, etc | Work plan, etc |  | 
Maint (pre Rel19) | 2 | 1 | 0 | 2 | 1 | 3
Maint (Rel-19) | 4 | 2 | 0 | 7 | 4 | 6
Rel-20 5GA | 3 | 6 | 0 | 1 | 1 | 9
Rel-20 6G | 0 | 3 | 9 | 3 | 1 | 12
Example session plan in 2026

## Slide 6: Rel-20 5GA and 6G TU budget split
Scenario 2a: 6G sessions scheduled in parallel with 5GA or maintenance
  The 6G study is run in parallel with one other topic (5GA, maintenance)
  Allocating 12 TU’s in a meeting to 6G would provide 6 sessions
 | Mon | Tue | Wed | Thur | Fri | 
 | Opening plenary |  |  | rev | rev | 
 |  |  |  | rev | rev | 
 |  |  |  | rev | rev | 
 |  |  |  | rev | rev | 
 |  |  |  | rev | rev | 
 |  |  |  | rev | rev | 
 |  |  |  | rev | Closing plenary | 
 |  |  |  | rev |  | 
 |  |  |  | rev |  | 
 |  |  | rev | rev |  | 
 |  |  | rev | rev |  | 
 |  |  | rev | rev |  | 
 |  |  | Work plan, etc | Work plan, etc |  | 
Maint (pre Rel19) | 2 | 1 | 0 | 2 | 1 | 3
Maint (Rel-19) | 5 | 1 | 0 | 7 | 4 | 6
Rel-20 5GA | 2 | 4 | 3 | 1 | 1 | 9
Rel-20 6G | 0 | 6 | 6 | 3 | 1 | 12
 |  |  |  |  |  | 30
Example session plan in 2026

## Slide 7: Rel-20 5GA and 6G TU budget split
Assuming that typically 6 sessions per meeting are required for the 6G study, and the 6G study is scheduled in parallel with 5GA
The per-meeting schedule and totals could look something like this
This per-meeting schedule is for illustration purposes only and for determining the overall TU budget for release planning purposes. The per-meeting allocation may change over time
 |  |  | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026
 |  |  | Apr #168 | May #169 | Aug #170 | Oct #171 | Nov #172 | Feb #173 | Apr #174 | May #175 | Aug #176 | Oct #177 | Nov #178
 |  | Totals between March and September |  |  |  |  | Study deadline A | Study deadline B |  | Stage 2 80% | Stage 2 100% |  | 
Rel-20 |  |  |  |  |  |  |  |  |  |  |  |  | 
20.x | Planned TU's (not TEI20, Maint) | 148 | 4 | 8 | 15 | 18 | 19 | 21 | 21 | 21 | 21 |  | 
5GA |  | 72 | 4 | 8 | 7 | 8 | 9 | 9 | 9 | 9 | 9 |  | 
6G |  | 76 | 0 | 0 | 8 | 10 | 10 | 12 | 12 | 12 | 12 |  |