## Slide 1: Status report for EnergySys Phase 2
Konstantinos Samdanis (Lenovo)
Zhuoyi Chen (China Telecom)

## Slide 2: FS_EnergySys_Ph2 Status at SA#169
  Progress – 17 pCRs Agreed
  Approved updated TR skeleton
  Approved 5 solution related to KI1
  Approved 6 solutions related to KI2
  Approved 5 solutions related to KI3
  Impacts and dependencies on other WGs
  Dependency on SA5 related to new performance measurements regarding renewable energy.
  Dependency on RAN WGs regarding new performance measurements.
  Contentious issues
  Improvements of “accuracy“ in terms of energy related measurements for Rel-20 is still open.
  There are at least 2 contradicting solution types on discovery and selection of NFs considering energy metrics.
  Next steps:
  Try to agree on the notion of accuracy related to energy related measurements for Rel-20.
  Continue to handle new solutons for KI1, KI 2 and KI 3
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070058 | New SID on Energy Efficiency and Energy Saving Phase 2 | FS_EnergySys_Ph2 | 12/12/2025 | 0% | SP-250417 | 50% | 

## Slide 3: FS_EnergySys_Ph2 Status at SA#168
  Progress – 13 pCRs Agreed
  Approved updated TR skeleton
  Approved 5 solution related to KI1
  Approved 6 solutions related to KI2
  Approved 5 solutions related to KI3
  Impacts and dependencies on other WGs
  Dependency on SA5 related to new performance measurements regarding renewable energy.
  Dependency on RAN WGs regarding new performance measurements.
  Contentious issues
  Improvements of “accuracy“ in terms of energy related measurements for Rel-20 is still open.
  There are at least 2 contradicting solution type on discovery and selection of NFs considering energy metrics.
  Next steps:
  Try to agree on the notion of accuracy related to energy related measurements for Rel-20.
  Continue to handle new solutons for KI1, KI 2 and KI 3
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1070058 | New SID on Energy Efficiency and Energy Saving Phase 2 | FS_EnergySys_Ph2 | 12/12/2025 | 0% | SP-250417 | 20% | 

## Slide 4: FS_EnergySys_Ph2 Work Plan
Meeting | Date | Planned TUs | Actual Used TUs | Action plan
SA2#168 | Apr. 2025 | 1 | 1 | TR skeleton, scope, Terms, Architectural assumptions & Requirements Key Issues for all WTs.
SA2#169 | May 2025 | 2 |  | Key Issue updates (if necessary), New solutions for approved Key Issues.
SA2#170 | Aug. 2025 | 1 |  | New solutions and solution updates. Last meeting for new solutions.
SA#109 | Sep. 2025 | - | - | For information
SA2#171 | Oct. 2025 | 1 |  | Solution updates. Interim Agreements and conclusion.
SA2#172 | Nov.2025 | 1 |  | Conclusion.
SA#110 | Dec 2025 | - | - | For Approval
 | Total | 6 | 1 |