## Slide 1: XRM_Ph2 Status Report
Georgios Gkellas (Nokia)
Curt Wong (Meta USA)
SA WG2 Meeting #170 Gothenburg
Aug 25 – Aug 29, 2025

## Slide 2: FS_XRM_Ph2/XRM_Ph2
  Progress since SA#108:
  Maintenance work at SA2#170
  SA2#170: LS OUT on Uplink Rate Control postponed with 1 related CR approved (23.502) and 2 related CRs endorsed (23.501, 23.503). LS out on N6-Unmarked PDUs approved
  All KIs completed
  Impacts and dependencies on other WGs:
  None
  Controversial issues:
  None
  Next steps:
  Work on postponed LSs (Uplink Rate Control), unhandled LSs, continue maintenance work
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010032 | Study on Extended Reality and Media Service (XRM) Phase 2 | FS_XRM_Ph2 | 09/09/2024 | 100% | SP-231671 | 100% | 
1040032 | Extended Reality and Media Service (XRM) Phase 2 | XRM_Ph2 | 12/03/2025 | 100% | SP-241385 | 100% | 

## Slide 3: FS_XRM_Ph2/XRM_Ph2
  Progress since SA2#169:
  Maintenance work at SA2#170
  SA2#170: LS OUT on Uplink Rate Control postponed with 1 related CR approved (23.502) and 2 related CRs endorsed (23.501, 23.503). LS out on N6-Unmarked PDUs approved
  All KIs completed
  Impacts and dependencies on other WGs:
  None
Controversial issues:
  None
Next steps (SA2#171):
  Work on postponed LSs (Uplink Rate Control), unhandled LSs, continue maintenance work
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1010032 | Study on Extended Reality and Media Service (XRM) Phase 2 | FS_XRM_Ph2 | 09/09/2024 | 100% | SP-231671 | 100% | 
1040032 | Extended Reality and Media Service (XRM) Phase 2 | XRM_Ph2 | 12/03/2025 | 100% | SP-241385 | 100% | 

## Slide 4
(FS)_XRM_Ph2 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#159 | Oct 2023 | 1 | 1 | TR Skeleton, TR Scope, Key Issues discussion, Arch Assumptions
SA2#160 | Nov 2023 | 1 | 1 | Focus on Key Issues
SA2#160E-AH | Jan 2024 | 1 | 1 | Solutions discussions, Complete Key Issues
SA2#161 | Feb 2024 | 1 | 1 | New Solutions
SA2#162 | Apr 2024 | 1 | 1 | Only postponed/unhandled papers for new solutions. Focus on solution updates mainly. Start with evaluation and conclusion
SA2#163 | May 2024 | 1.5 | 1.5 | No new solutions. Critical solution updates essential for conclusion. Complete conclusions
SA2#164 | Aug 2024 | 0.5 | 1 | Resolution of open items in the conclusion to complete the study. Discuss normative CRs
SA2#165 | Oct 2024 | 2 | 2 | Normative work
SA2#166 | Nov 2024 | 2 | 2 | Normative work

## Slide 5
XRM_Ph2 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#166-AH-e | Jan 2025 | 0.75 | 2 | Normative work on: AQP with PDU Set QoS PDU Set QoS information for DSCP marking Exposure of rate limitation Expedited Data Transfer Differentiated QoS handling (in DL only) of ciphered multiplexed XRM traffic TS 23.502, TS 23.503 CRs
SA2#167 | Feb 2025 | 1.8 | 2 | Normative work on: PDU Set Information marking in case of no DL PDU Set QoS AL-FEC awareness at NG-RAN Exposure of available data rate Differentiated QoS handling (in DL only) of ciphered multiplexed XRM traffic Expedited Data Transfer TS 23.502, TS 23.503 CRs AQP with PDU Set QoS Exposure of rate limitation
SA2#168 | Apr 2025 | 1 | 1 | Maintenance work
SA2#169 | May 2025 | 1 | 1 | Maintenance work
SA2#170 | Aug 2025 | 0.5 | 0.5 | Maintenance work
 | Total | 16.05 | 18 | 
Total Actual 18 TUs
  7.0 TUs for Study Phase
  11 TUs for Normative Work