## Slide 1: SA2 6G Study Item Planning Overview
Rapporteurs:
Malla Reddy Sama (NTT DOCOMO)
Stefan Rommer (Ericsson)

## Slide 2: 6G SID Overview
SID WTs (high-level - for information only):
  WT1: Define the overall architecture (incl. control signalling, SBA framework, network slicing, network sharing, user plane architecture, QoS framework, policy framework, network exposure framework, architecture for specific scenarios e.g. fixed wireless access, localized service access.)
  WT2: Migration and Interworking
  WT3: AI in 6G, incl. AI agent, AI framework
  WT4: ISAC
  WT5: Data Framework
  WT6: Support of computing for UE, core network and application servers
  WT7: Support of 6G RAT for NTN
  WT8: Support of cellular IoT enablers in 6G
Approved SID: SP-250806
Start Date: SA2#170 (Aug 2025)
Target Completion: SA#114 (Dec 2026) or SA#115 (Mar 2027)
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1080047 | Study on Architecture for 6G System | FS_6G_ARC | TBD |  |  |  | 

## Slide 3: Key Milestones
SA2#172 (Nov 2025):
  Finalize WTs and (as far as possible) KI descriptions, TU estimates, and dependencies (including between WTs/KIs).
  Make substantial progress on identifying and documenting architecture principles, assumptions, and requirements, aiming for convergence where possible.
  Update the SID with revised Work Task descriptions from the TR annex (based on S2-2505648).
  NOTE: The final SI timeline decision will be taken at SA#110 (Dec 2025), i.e., SI completion will be either SA#114 (Dec 2026) or SA#115 (Mar 2027).
SA2#xxx (TBD): preparation for Key architecture coordination with RAN, such as
  RAN-CN functional split and interface (P2P vs SBI), AS/NAS split, etc.
  Migration and interworking aspects.
  NOTE: Potential target will be SA2#175 (May 2026). We need to evaluate our progress and update this milestone.

## Slide 4: (Tentative) 6G SI work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan | Comment
SA2#170 | Aug 2025 | - |  | TR skeleton, invite companies for WT scope and justification discussion including potential WTs/KI, potential TU, dependencies, architectural principles, assumptions and requirements. | As endorsed in S2-2505648, the completion of Key Issues, architectural assumptions, and principles is generally targeted for the end of SA2#172 meeting, unless there are dependencies on other WGs. Identify other 5G features that will be supported and/or adapted in 6G. The Study Item Description (SID) should be updated with: Revised Work Task descriptions from the TR annex TU estimates Target completion date for the SID Agree on 2nd Phase planning (including parallel streams). Checkpoint#1 (SA2#172): Stability check on WTs (and, based on those, potential KIs).
SA2#171 | Oct 2025 |  |  | Continue WT/KI and assumptions discussions including dependencies | 
SA2#172 | Nov 2025 |  |  | Complete KIs, SID update with WT scope dependencies and TU. Aim to complete the architecture requirements & assumptions. | 
SA2#173 | Feb 2026 |  |  | Start documentation of solutions. Last meeting for Key Issue proposals (FIRM DEADLINE). | Checkpoint#2: Stability check on KIs. Evaluate whether any exceptions (e.g., for KI updates) are needed for another one meeting (for SA2#174) due to dependencies on other WGs. Re-evaluate the deadline for accepting new solution proposals, i.e., to determine whether SA2#176 remains appropriate or whether to shift to SA2#177, for instance, based on the status of KIs.
SA2#174 | Apr 2026 |  |  | Continue solution discussion, coordination with other WGs. | 
SA2#175 | May 2026 |  |  | Continue solution discussion, coordination with other WGs. | Checkpoint#3: Stability check (per WT) and coordination on dependencies. Cross-TSGs/WGs coordination.
SA2#176 | Aug 2026 |  |  | Last meeting for new solution proposals, start discussion on solution principles and interim conclusion. | Checkpoint#4: some aspects of Architecture conclusion and notification to other WGs. Cross-TSGs/WGs coordination. Decide whether to allow new solution(s) for SA2#177 meeting.
SA2#177 | Oct 2026 |  |  | Complete conclusions on KIs and overall architecture. | 
SA2#178 | Nov 2026 |  |  | Complete conclusions on KIs and overall architecture. | Checkpoint#5: Architecture conclusion and WID approval
SA2#179 | Feb 2027 |  |  | Complete conclusions on KIs and overall architecture. | If the SI completion is Mar’27, checkpoint#5 can be moved to Q1’27.
NOTE: This is an ongoing timeline. We need to evaluate our progress and make changes if we're falling behind.

## Slide 5: Rel-20 6G study planning for Q3/Q4 2025
SA2#170 August 2025
  Input papers to provide justification and clarification of Work Task scope
  During the meeting assess for each WT whether Key Issue submission can start in the next meeting
    (Drafting of Key Issues during the meeting is not precluded)
  Document agreed Work Task scope updates in an annex of the TR
  Input papers on architectural assumptions and principles, with a focus on WT’s in August
SA2#171 October 2025
  Start Key Issue discussions for Work Tasks identified in previous meeting
  For the Work Tasks not identified in previous meeting as ready for Key Issues, continue 1. 2. and 3. above
  Input papers on architectural assumptions and principles
SA2#172 November 2025
  Continue as in SA2#171 for Work Tasks and Key Issues
  Completion of Key Issues, Arch assumptions and principles is in general targeted for the end of this meeting unless there are dependencies on other WG’s
  Update Study Item Description with updated Work Task descriptions from the TR annex
  Add TU estimates and completion date to the SID
  Input papers on architectural assumptions and principles
Endorsed

## Slide 6: SA2#170 (Aug) Meeting planning
Companies are invited to submit contributions addressing, Scope and justification of the Work Task (WT) e.g.:
  WT justifications, WT scope updates, possibility to divide the WT into sub-WTs, potential Key Issues (KIs) relevant to the WT, Identified dependencies and architecture principles, assumption and requirements.
To ensure efficiency:
  Separate contribution(s) per WT.
  It may not be feasible to open each individual contribution in the meeting.
  Companies are encouraged to focus contributions on their areas (WTs) of interest.
  The detailed approach for handling contributions (e.g., rapporteur summary/grouping or identify the baseline tdoc(s) or potential need to assign pen-holders, etc) will be decided after the submission deadline, e.g., based on factors such as the number of contributions.
    Goal: Ensure efficient discussion and good coverage of topics during the meeting.
    NOTE: In case we assign any pen-holders, these assignments will be temporary and based on workload, not implying a long-term role.
Meeting Objective:
  Agree on TR skeleton and scope
  Document agreed architectural requirements & assumptions and principles in the TR, and Work Task scope updates in an annex of the TR.
    If there is consensus that a given WT/sub-WT is stable, the drafting of Key Issues during the meeting is not precluded.
  For WT that are not agreed/endorsed, use baseline tdoc(s) for a WT (sub-WT, topic) scope, which will be further developed (considered for baseline) for the October meeting.

## Slide 7: SA2#170 (Aug) meeting guidance
Given the expected volume of contributions, we foresee that a large number of tdocs may be submitted for SA2#170. Therefore, we encourage companies to limit the number of contributions per WT/sub-WT. The interpretation of “limited” is left to each company’s delegation to assess, with the intent to avoid overwhelming the number of tdocs per company per WT/sub-WT.
In this context, we as rapporteurs strongly recommend including clear tags in the contribution titles, for example:
"[WT#x, Topic Name] Contribution Title..."
E.g.:
[WT#1.1, Control signalling for 6G] Contribution Title
[WT#1.2, SBA framework] Contribution Title
[WT#2, Migration and Interworking] Contribution Title
Following this tagging convention will significantly help in filtering and organizing tdocs efficiently, and will support a more structured and productive discussion.