## Task_Table1
ID | Unique_ID | Name | Acronym | Outline_Level | Release | Resource_Names | Start | Finish | Completion | Hyperlink | Status_Report | WI_rapporteur_name | WI_rapporteur_e_mail | Notes | Impacted_TSs_and_TRs | TSG_approved | PCG_approved | TSG_stopped | PCG_stopped | Created | last_modif
1 | 0 | Work Plan 3GPP version October 1st 2025 |  | 1 | Rel-20 |  | 2019-03-07 08:00 | 2019-03-07 17:00 | 0% | [10 empty] | Thu 15/01/15 | Thu 05/03/15
2 | 0 | Pre TSG#109 version, UIDs "109xxxx" pending TSG#109 approval |  | 1 | Rel-20 |  | 2019-03-07 08:00 | 2019-03-07 17:00 | 0% | [10 empty] | Thu 15/03/18 | NA
3 | 0 | Next main milestones: Rel-19 St.3: Sept.25 |  | 1 | Rel-20 |  | 2019-03-07 08:00 | 2019-03-07 17:00 | 0% | [10 empty] | Wed 12/08/15 | NA
4 | 0 |  |  | 1 | Rel-20 |  | 2019-03-07 08:00 | 2019-03-07 17:00 | 0% | [10 empty] | Fri 03/03/17 | NA
5 | 0 | --- RELEASE 20 --- | - | 1 | Rel-20 |  | 2019-03-07 07:00 | 2019-03-07 07:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
6 | 0 | Rel-20 6G Studies | - | 1 | Rel-20 |  | 2024-04-02 08:00 | 2026-06-11 15:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
7 | 1050110 | Study on 6G Use Cases and Service Requirements | FS_6G_REQ | 1 | Rel-20 | S1 | 2024-09-04 08:00 | 2026-03-03 17:00 | 77% | SP-241391 |  | Xiaonan Shi, China Mobile | shixiaonan@chinamobile.com | 6/3/25: 0%->25; 5/6/25: 25%->66; 12/9/25: 66%->77 |  | 105 | 53 |  |  | Wed 04/09/24 | Fri 12/09/25
8 | 1080057 | Study on Architecture for 6G System | FS_6G_ARC | 1 | Rel-20 | S2 | 2025-06-05 08:00 | 2026-06-06 17:00 | 5% | SP-250806 |  | Malla Reddy Sama, NTT DOCOMO | sama@docomolab-euro.com | 12/9/25: 0%->5 |  | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
9 | 1060079 | Study on 6G Scenarios and Requirements | FS_6G_RAN_Scen_Req | 1 | Rel-20 | RP | 2024-12-08 08:00 | 2026-06-06 17:00 | 40% | RP-251395 | RP-251396 | CMCC |  | 6/3/25: FCD:01/03/2026->05/06/2026; Compl:0%->5%; Stat Rep: ->RP-250266; ; 26/3/25: 38.914 added;; 3/4/25: WID:RP-243327->RP-250810; 6/6/25: Compl:5%->10%; Stat Rep: RP-250266->RP-251396; List of Impacted TS & TR updated; ; 18/7/25: WID:RP-250810->RP-2513 | 38,914 | 106 | 54 |  |  | Fri 24/01/25 | Tue 30/09/25
10 | 1080064 | Study on Modernization of Specification Format and Procedures for 6G | FS_6GSpecs | 1 | Rel-20 | SP | 2025-06-27 08:00 | 2026-03-03 17:00 | 0% | SP-250802 |  | Baker, Matthew, Nokia | matthew.baker@nokia.com |  |  | 108 | 55 |  |  | Fri 27/06/25 | NA
11 | 1080072 | Study on 6G Radio | FS_6G_Radio | 1 | Rel-20 | R1 | 2025-06-06 08:00 | 2027-06-06 17:00 | 2% | RP-252912 | RP-252475 | NTT DOCOMO |  | TR 38.9xx (RAN; work done in WGs!), TR 38.8xx (RAN1), TR 38.8xx (RAN2), TR 38.8xx (RAN3), TR 38.8xx (RAN4) ; note: SID shows June 27 as target which would be REL-21 so corrected to March 27 ; 11/9/25: FCD:Wed 03/03/27->Fri 04/06/27; Compl:0%->2%; Stat Re |  | 108 | 55 |  |  | Fri 18/07/25 | Mon 29/09/25
12 | 1090013 | Study on Charging Aspects of 6G System | FS_6G_CH | 1 | Rel-20 | S5 | 2025-09-09 08:00 | 2027-03-03 17:00 | 0% | SP-251218 |  | Zhiwei Mo (China Telecom) | mozw@chinatelecom.cn | [6 empty] | Wed 10/09/25 | NA
13 | 1090044 | Study on Security for the 6G System | FS_6G_SEC | 1 | Rel-20 | S3 | 2025-09-29 08:00 | 2027-06-06 17:00 | 0% | SP-251233 |  | Todor Gamishev, Orange | todor.gamishev@orange.com | [6 empty] | Wed 24/09/25 | NA
14 | 0 | Rel-20 Satellite, Non-Terrestrial Networks (NTN) | - | 1 | Rel-20 |  | 2019-03-07 08:00 | 2021-06-09 15:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
15 | 1080054 | Satellite access - Phase 4 | 5GSAT_Ph4 | 1 | Rel-20 |  | 2024-04-02 08:00 | 2025-06-06 17:00 | 100% | [6 empty] | 108 | 55 |  |  | Thu 05/06/25 | NA
16 | 1030042 | Study on satellite access - Phase 4 | FS_5GSAT_Ph4 | 2 | Rel-20 | S1 | 2024-04-02 08:00 | 2024-12-12 17:00 | 100% | SP-241824 |  | Thierry Bérisot, Novamint | tberisot@novamint.com | 13/6/24: 0%->30; 4/9/24: 30%->60; 8/1/25: WID:SP-240495->SP-241824; 6/3/25: 60%->85; 5/6/25: 85%->100 | 22.887 | 103 | 52 |  |  | Wed 13/03/24 | Thu 05/06/25
17 | 1060071 | Stage 1 for Satellite access - Phase 4 | 5GSAT_Ph4-REQ | 2 | Rel-20 | S1 | 2024-12-05 08:00 | 2025-06-06 17:00 | 100% | SP-250386 |  | Thierry Bérisot, Novamint, | tberisot@novamint.com | ; 6/3/25: 0%->60; 26/3/25: WID:SP-241822->SP-250386; 26/3/25: FCD:03/02/2025->/25; 5/6/25: 60%->100 | 22.261 | 106 | 54 |  |  | Thu 05/12/24 | Thu 05/06/25
18 | 1070011 | Study on Integration of satellite components in the 5G architecture Phase 4 | FS_5GSAT_Ph4_ARC | 1 | Rel-20 | S2 | 2025-03-26 08:00 | 2025-12-12 17:00 | 60% | SP-250787 |  | Hucheng Wang (CATT) | wanghucheng@catt.cn | 27/6/25: WID:SP-250400->SP-250787; 12/9/25: 0%->60 |  | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
19 | 1050105 | Indirect Network Sharing on Satellite Access Network | INS_SAT | 1 | Rel-20 | S1 | 2024-09-04 08:00 | 2024-09-09 17:00 | 100% | SP-241393 |  | Qun Wei, China Unicom | weiqun5@chinaunicom.cn |  | 22.261 | 105 | 53 |  |  | Wed 04/09/24 | NA
20 | 1060072 | MPS support in 3GPP system with satellite | MPS_Sat | 1 | Rel-20 | S1 | 2024-12-05 08:00 | 2024-12-12 17:00 | 100% | SP-241823 |  | Singh, Ray, Peraton Labs, | rsingh@peratonlabs.com | ; 5/12/24: 0%->100 | 22.153 | 106 | 54 |  |  | Thu 05/12/24 | Thu 05/12/24
21 | 1080027 | Study on application enablement for satellite access enabled 5G services Phase 4 | FS_5GSAT_Ph4_APP | 1 | Rel-20 | S6 | 2025-06-05 08:00 | 2026-03-03 17:00 | 10% | SP-250874 |  | Zhou Zhe, China Telecom, | zhouz11@chinatelecom.cn | 18/7/25: 23.700-02 added;; 12/9/25: 0%->10 | 23.700-02 | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
22 | 1080071 | Study on GNSS resilient NR-NTN operation | FS_NR_NTN_GNSS_resilient | 1 | Rel-20 | R1 | 2025-06-06 08:00 | 2026-06-06 17:00 | 10% | RP-251933 | RP-251934 | Thales |  | compare REL-16 SI FS_NR_NTN_solutions, REL-17 WI NR_NTN_solutions, REL-18 WI NR_NTN_enh, REL-19 WI NR_NTN_Ph3 ; 11/9/25: FCD:Sat 06/06/26->Fri 05/06/26; Compl:0%->10%; Stat Rep: ->RP-251934; ; 29/9/25: WID:RP-251863->RP-251933; 30/9/25: 38.742 added; | 38.742 | 108 | 55 |  |  | Fri 18/07/25 | Tue 30/09/25
23 | 1070055 | Study on Ultra Low Bitrate Speech Codec | FS_ULBC | 1 | Rel-20 | S4 | 2025-03-26 08:00 | 2026-06-06 17:00 | 15% | SP-250635 |  | Xu Jiayi, China Mobile | xujiayi@chinamobile.com | 3/4/25: 26.940 added;; 5/6/25: 0%->10; 27/6/25: WID:SP-250378->SP-250635; 12/9/25: 10%->15 | 26.940 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
24 | 1080091 | E-UTRA TN (Terrestrial Network) to NR NTN handover enhancements | LTE_TN_NR_NTN_HO | 1 | Rel-20 |  | 2025-06-06 08:00 | 2027-09-09 17:00 | 0% | RP-252890 |  | CATT |  | to support RRC connected mode mobility; compare: REL-19 WI LTE_TN_NR_NTN_mob-Core which introduced idle mode mobility ; 29/9/25: WID:RP-251878->RP-252890 |  | 108 | 55 |  |  | Fri 18/07/25 | Mon 29/09/25
25 | 1081091 | Core part: E-UTRA TN to NR NTN handover enhancements | LTE_TN_NR_NTN_HO-Core | 2 | Rel-20 | R2 | 2025-06-06 08:00 | 2027-03-03 17:00 | 0% | RP-252890 |  | CATT |  | to support RRC connected mode mobility; compare: REL-19 WI LTE_TN_NR_NTN_mob-Core which introduced idle mode mobility |  | 108 | 55 |  |  | Fri 18/07/25 | NA
26 | 1082091 | Perf. Part: E-UTRA TN to NR NTN handover enhancements | LTE_TN_NR_NTN_HO-Perf | 2 | Rel-20 | R4 | 2025-06-06 08:00 | 2027-09-09 17:00 | 0% | RP-252890 |  | CATT |  |  |  | 108 | 55 |  |  | Fri 18/07/25 | NA
27 | 1080090 | NTN for IoT Phase 4 | IoT_NTN_Ph4 | 1 | Rel-20 |  | 2019-03-07 08:00 | 2027-03-03 17:00 | 0% | RP-252473 |  | vivo |  | no Perf. part; compare: REL-19 WI IoT_NTN_Ph3, REL-18 WI IoT_NTN_enh, REL-17 WI LTE_NBIOT_eMTC_NTN; enhancement of NB-IoT-NTN to support IMS voice call over GSO ; 29/9/25: WID:RP-251867->RP-252473 |  | 108 | 55 |  |  | Fri 18/07/25 | Mon 29/09/25
28 | 1081090 | Core part: NTN for IoT Phase 4 | IoT_NTN_Ph4-Core | 2 | Rel-20 | R2 | 2019-03-07 08:00 | 2027-03-03 17:00 | 0% | RP-252473 | RP-252012 | vivo |  | no Perf. part; compare: REL-19 WI IoT_NTN_Ph3, REL-18 WI IoT_NTN_enh, REL-17 WI LTE_NBIOT_eMTC_NTN; enhancement of NB-IoT-NTN to support IMS voice call over GSO ; 11/9/25: FCD:Wed 09/06/21->Wed 03/03/27; Stat Rep: ->RP-252012; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
29 | 1090070 | Enhanced requirements for NR NTN and IoT NTN Phase 2 | NR_IoT_NTN_req_Ph2 | 1 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-09-09 17:00 | 0% | RP-252962 |  | Mediatek |  | compare REL-19 WI NR_IoT_NTN_req_test_enh |  | 109 | 55 |  |  | Mon 29/09/25 | NA
30 | 1091070 | Core part: Enhanced requirements for NR NTN and IoT NTN Phase 2 | NR_IoT_NTN_req_Ph2-Core | 2 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-03-03 17:00 | 0% | RP-252962 |  | Mediatek |  | compare REL-19 WI NR_IoT_NTN_req_test_enh |  | 109 | 55 |  |  | Mon 29/09/25 | NA
31 | 1092070 | Perf. part: Enhanced requirements for NR NTN and IoT NTN Phase 2 | NR_IoT_NTN_req_Ph2-Perf | 2 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-09-09 17:00 | 0% | RP-252962 |  | Mediatek |  |  |  | 109 | 55 |  |  | Mon 29/09/25 | NA
32 | 0 | Rel-20 Internet of Things (IoT), Ambient power-enabled IoT (AmbientIoT), RedCap, MTC | - | 1 | Rel-20 |  | 2024-05-05 08:00 | 2125-12-12 17:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
33 | 1080061 | MPS Enhancements for IoT | MPS_IOT-ARC | 1 | Rel-20 | S2 | 2025-06-27 08:00 | 2025-12-12 17:00 | 0% | SP-250842 |  | Hala Mowafy, (Peraton Labs) | hala.mowafy@peratonlabs.com |  | 23.401; 23.682 | 108 | 55 |  |  | Thu 05/06/25 | NA
34 | 1080063 | Study on Architecture support of AmbientIoT - Phase 2 | FS_AmbientIoT_Ph2_ARC | 1 | Rel-20 | S2 | 2025-06-05 08:00 | 2026-03-03 17:00 | 15% | SP-250834 |  | Runze ZHOU, huawei | zhourunze@huawei.com | 12/9/25: 0%->15 |  | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
35 | 1080023 | Study on application enablement for Ambient IoT services Phase 2 | FS_AmbientIoT_Ph2_APP | 1 | Rel-20 | S6 | 2025-06-05 08:00 | 2026-03-03 17:00 | 20% | SP-250870 |  | Liping Wu, CATT | wuliping@cictmobile.com | 18/7/25: 23.700-26 added;; 12/9/25: 0%->10; 12/9/25: 10%->20 | 23.700-26 | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
36 | 1080073 | Study on enhancements for solutions for Ambient IoT in NR outdoor for active devices | FS_Ambient_IoT_Outdoor_Active | 1 | Rel-20 | R1 | 2019-03-07 08:00 | 2026-03-03 17:00 | 25% | RP-252964 | RP-252344 | LG Electronics |  | affecting TR 38.769 of REL-19 SI FS_Ambient_IoT_solutions ; 11/9/25: FCD:Wed 09/06/21->Tue 03/03/26; Compl:0%->25%; Stat Rep: ->RP-252344; ; 29/9/25: WID:RP-251884->RP-252964 |  | 108 | 55 |  |  | Fri 18/07/25 | Mon 29/09/25
37 | 1080086 | Solutions for Ambient IoT in NR Phase 2 | Ambient_IoT_Solutions_Ph2 | 1 | Rel-20 |  | 2025-06-06 08:00 | 2026-03-03 17:00 | 0% | RP-252894 |  | Huawei |  | compare REL-19 WI Ambient_IoT_Solutions; note: There is a parallel REL-20 SI FS_Ambient_IoT_Outdoor_Active (no overlap allowed); SI TR 38.769 must be removed from this WID ; 29/9/25: WID:RP-251885->RP-252894 |  | 108 | 55 |  |  | Fri 18/07/25 | Mon 29/09/25
38 | 1081086 | Core part: Solutions for Ambient IoT in NR Phase 2 | Ambient_IoT_Solutions_Ph2-Core | 2 | Rel-20 | R1 | 2025-06-06 08:00 | 2026-03-03 17:00 | 0% | RP-252894 | RP-252361 | Huawei |  | compare REL-19 WI Ambient_IoT_Solutions; note: There is a parallel REL-20 SI FS_Ambient_IoT_Outdoor_Active (no overlap allowed); SI TR 38.769 must be removed from this WID ; 11/9/25: Stat Rep: ->RP-252361; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
39 | 1082086 | Perf. Part: Solutions for Ambient IoT in NR Phase 2 | Ambient_IoT_Solutions_Ph2-Perf | 2 | Rel-20 | R4 | 2025-06-06 08:00 | 2026-03-03 17:00 | 0% | RP-252894 | RP-252361 | Huawei |  | ; 11/9/25: Stat Rep: ->RP-252361; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
40 | 0 | See also "NTN for IoT Phase 4" (UID 1080090) |  | 1 | Rel-20 |  | 2019-03-07 08:00 | 2019-03-07 17:00 | 0% | [10 empty] | Fri 18/07/25 | NA
41 | 0 | Rel-20 AIML (Artificial Intelligence/Machine Learning) | - | 1 | Rel-20 |  | 2024-04-02 08:00 | 2026-06-11 15:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
42 | 1070013 | Study on Core Network Enhanced Support for AIML Phase 2 | FS_AIML_CN_Ph2 | 1 | Rel-20 | S2 | 2025-03-26 08:00 | 2025-12-12 17:00 | 70% | SP-250810 |  | Xiaobo Wu, vivo | xiaobo.wu@vivo.com | 27/6/25: WID:SP-250413->SP-250810; 12/9/25: 0%->70 |  | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
43 | 1080074 | Study on AIML for NG-RAN Phase 3 | FS_NR_AIML_NGRAN_Ph3 | 1 | Rel-20 | R3 | 2025-06-06 08:00 | 2026-03-03 17:00 | 0% | RP-252867 | RP-252455 | ZTE |  | compare REL-17 SI FS_NR_ENDC_data_collect and REL-19 SI FS_NR_AIML_NGRAN_enh; TR 38.7XX ; 11/9/25: Stat Rep: ->RP-252455; ; 29/9/25: WID:RP-251868->RP-252867; 30/9/25: 38.745 added; | 38.745 | 108 | 55 |  |  | Fri 18/07/25 | Tue 30/09/25
44 | 1070029 | Study on Stage 2 for AI/ML service Phase 2 | FS_AIML_App_Ph2 | 1 | Rel-20 | S6 | 2025-03-26 08:00 | 2025-12-12 17:00 | 60% | SP-250384 |  | Pateromichelakis, Emmanouil (Manos), Lenovo | epateromiche@lenovo.com | 3/4/25: 23.700-83 added;; 6/6/25: 0%->40; 12/9/25: 40%->60 | 23.700-83 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
45 | 1080012 | Study on AIML management phase 3 | FS_AIML_MGT_Ph3 | 1 | Rel-20 | S5 | 2025-06-05 08:00 | 2026-03-03 17:00 | 0% | SP-250867 |  | Hassan Al-Kanani (NEC), | Hassan.Alkanani@EMEA.NEC.COM | 18/7/25: 28.882 added; | 28.882 | 108 | 55 |  |  | Thu 05/06/25 | Fri 18/07/25
46 | 1080049 | Media aspects for AI/ML in IMS services | AIML_IMS-MED | 1 | Rel-20 | S4 | 2025-07-07 08:00 | 2026-03-03 17:00 | 0% | SP-250878 |  | Yip, Eric, Samsung Electronics Co., Ltd, | eric dot yip AT samsung dot com |  | 26.114; 26.264 | 108 | 55 |  |  | Fri 12/09/25 | NA
47 | 1080085 | AIML for NR air interface Phase 2 | NR_AIML_air_Ph2 | 1 | Rel-20 |  | 2025-06-06 08:00 | 2027-09-09 17:00 | 2% | RP-252445 |  | Qualcomm |  | follow-up WI of REL-19 SI FS_NR_AIML_air_Ph2; compare REL-19 WI NR_AIML_air ; 29/9/25: WID:RP-251870->RP-252445 |  | 108 | 55 |  |  | Fri 18/07/25 | Mon 29/09/25
48 | 1081085 | Core part: AIML or NR air interface Phase 2 | NR_AIML_air_Ph2-Core | 2 | Rel-20 | R1 | 2025-06-06 08:00 | 2027-03-03 17:00 | 4% | RP-252445 | RP-252444 | Qualcomm |  | follow-up WI of REL-19 SI FS_NR_AIML_air_Ph2; compare REL-19 WI NR_AIML_air ; 11/9/25: Compl:0%->4%; Stat Rep: ->RP-252444; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
49 | 1082085 | Perf. Part: AIML for NR air interface Phase 2 | NR_AIML_air_Ph2-Perf | 2 | Rel-20 | R4 | 2025-06-06 08:00 | 2027-09-09 17:00 | 0% | RP-252445 | RP-252444 | Qualcomm |  | ; 11/9/25: Stat Rep: ->RP-252444; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
50 | 1080087 | AIML for mobility in NR | NR_AIML_Mob | 1 | Rel-20 |  | 2025-06-06 08:00 | 2027-09-09 17:00 | 0% | RP-252899 |  | OPPO |  | follow-up WI of REL-19 SI FS_NR_AIML_Mob ; 29/9/25: WID:RP-251864->RP-252899 |  | 108 | 55 |  |  | Fri 18/07/25 | Mon 29/09/25
51 | 1081087 | Core part: AIML for mobility in NR | NR_AIML_Mob-Core | 2 | Rel-20 | R2 | 2025-06-06 08:00 | 2027-03-03 17:00 | 0% | RP-252899 | RP-251967 | OPPO |  | follow-up WI of REL-19 SI FS_NR_AIML_Mob ; 11/9/25: Stat Rep: ->RP-251967; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
52 | 1082087 | Perf. Part: AIML for mobility in NR | NR_AIML_Mob-Perf | 2 | Rel-20 | R4 | 2025-06-06 08:00 | 2027-09-09 17:00 | 0% | RP-252899 | RP-251967 | OPPO |  | ; 11/9/25: FCD:Sun 06/06/27->Thu 09/09/27; Stat Rep: ->RP-251967; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
53 | 0 | Rel-20 Energy Efficiency, Energy Saving | - | 1 | Rel-20 |  | 2024-05-05 08:00 | 2125-12-12 17:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
54 | 1080053 | Energy Efficiency as Service Criteria Phase 2 |  | 1 | Rel-20 |  | 2024-04-02 08:00 | 2025-06-06 17:00 | 100% | [6 empty] | 108 | 55 |  |  | Thu 05/06/25 | NA
55 | 1030044 | Study on Energy Efficiency as Service Criteria Phase 2 | FS_EnergyServ_Ph2 | 2 | Rel-20 | S1 | 2024-04-02 08:00 | 2025-03-03 17:00 | 100% | SP-240494 |  | Laurent-WalterGoix, Nokia | laurent-walter.goix@NOKIA.COM | 13/6/24: 0%->25; 4/9/24: 25%->55; 6/3/25: 55%->100 | 22.883 | 103 | 52 |  |  | Wed 13/03/24 | Thu 06/03/25
56 | 1070051 | Stage 1 for Energy Efficiency as Service Criteria Phase 2 | EnergyServ_Ph2-REQ | 2 | Rel-20 | S1 | 2025-03-06 08:00 | 2025-06-06 17:00 | 100% | SP-250385 |  | Laurent-Walter Goix, Nokia | laurent-walter.goix@nokia.com | ; 26/3/25: WID:SP-250271->SP-250385 | 22.261 | 107 | 54 |  |  | Wed 05/03/25 | Wed 26/03/25
57 | 1070058 | Study on Energy Efficiency and Energy Saving Phase2 | FS_EnergySys_Ph2 | 1 | Rel-20 | S2 | 2025-03-26 08:00 | 2025-12-12 17:00 | 85% | SP-250791 |  | Konstantinos Samdanis (Lenovo) | ksamdanis@lenovo.com | 27/6/25: WID:SP-250417->SP-250791; 12/9/25: 0%->85 |  | 107 | 54 |  |  | Wed 26/03/25 | Fri 12/09/25
58 | 1080024 | Study on Application Enablement to support Energy Saving Phase 2 | FS_EnergySys_Ph2_APP | 1 | Rel-20 | S6 | 2025-06-05 08:00 | 2026-03-03 17:00 | 15% | SP-250871 |  | Yue, Jing, Ericsson | jing.yue@ericsson.com | 18/7/25: 23.700-44 added;; 12/9/25: 0%->15 | 23.700-44 | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
59 | 1080005 | Study on energy efficiency and energy saving aspects of 5G Advanced | FS_Energy_Ph4_OAM | 1 | Rel-20 | S5 | 2025-06-05 08:00 | 2026-03-03 17:00 | 0% | SP-251025 |  | Srilakshmi S (Nokia), | srilakshmi.s@nokia.com | 18/7/25: 28.885 added;; 29/9/25: WID:SP-250860->SP- 251025 | 28.885 | 108 | 55 |  |  | Thu 05/06/25 | Mon 29/09/25
60 | 1080050 | Study on Media energy consumption exposure and evaluation framework Phase 2 | FS_Energy_Ph2_MED | 1 | Rel-20 | S4 | 2025-06-05 08:00 | 2026-03-03 17:00 | 0% | SP-250636 |  | Julien Lemotheux, Orange | <julien.lemotheux@orange.com> |  | 26.942 | 108 | 55 |  |  | Thu 05/06/25 | NA
61 | 0 | Rel-20 Radio-centric: NR-only, not band-related | - | 1 | Rel-20 |  | 2019-03-07 08:00 | 2021-06-09 15:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
62 | 1080092 | Data Collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR Phase 5 | NR_SON_MDT_Ph5 | 1 | Rel-20 |  | 2025-06-06 08:00 | 2027-03-03 17:00 | 0% | RP-252560 |  | China Unicom |  | no Perf. part; compare: REL-19 WI NR_ENDC_SON_MDT_Ph4, REL-18 WI NR_ENDC_SON_MDT_enh2, REL-17 WI NR_ENDC_SON_MDT_enh, REL-16 WI NR_SON_MDT ; 29/9/25: WID:RP-251869->RP-252560 |  | 108 | 55 |  |  | Fri 18/07/25 | Mon 29/09/25
63 | 1081092 | Core part: Data collection for SON/MDT in NR Phase 5 | NR_SON_MDT_Ph5-Core | 2 | Rel-20 | R3 | 2025-06-06 08:00 | 2027-03-03 17:00 | 0% | RP-252560 | RP-252561 | China Unicom |  | no Perf. part; compare: REL-19 WI NR_ENDC_SON_MDT_Ph4, REL-18 WI NR_ENDC_SON_MDT_enh2, REL-17 WI NR_ENDC_SON_MDT_enh, REL-16 WI NR_SON_MDT ; 11/9/25: Stat Rep: ->RP-252561; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
64 | 1080088 | NR mobility enhancements Phase 5 | NR_Mob_Ph5 | 1 | Rel-20 | R2 | 2025-06-06 08:00 | 2027-06-06 17:00 | 0% | RP-252113 |  | Apple |  | compare: REL-16 WI NR_Mob_enh, REL-18 WI NR_Mob_enh2, REL-19 WI NR_Mob_Ph4 ; 29/9/25: WID:RP-251865->RP-252113 |  | 108 | 55 |  |  | Fri 18/07/25 | Mon 29/09/25
65 | 1081088 | Core part: NR mobility enhancements Phase 5 | NR_Mob_Ph5-Core | 2 | Rel-20 | R2 | 2025-06-06 08:00 | 2027-03-03 17:00 | 0% | RP-252113 | RP-252112 | Apple |  | compare: REL-16 WI NR_Mob_enh, REL-18 WI NR_Mob_enh2, REL-19 WI NR_Mob_Ph4 ; 11/9/25: Stat Rep: ->RP-252112; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
66 | 1082088 | Perf. part: NR mobility enhancements Phase 5 | NR_Mob_Ph5-Perf | 2 | Rel-20 | R4 | 2025-06-06 08:00 | 2027-06-06 17:00 | 0% | RP-252113 | RP-252112 | Apple |  | ; 11/9/25: Stat Rep: ->RP-252112; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
67 | 1080083 | NR MIMO Phase 6 | NR_MIMO_Ph6 | 1 | Rel-20 |  | 2025-06-06 08:00 | 2027-09-09 17:00 | 4% | RP-252936 |  | MediaTek |  | compare REL-19 WI NR_MIMO_Ph5, REL-18 WIs NR_MIMO_evo_DL_UL, NR_MIMO_OTA_enh, REL-17 WIs NR_feMIMO, NR_MIMO_OTA, REL-16 WI NR_eMIMO ; 29/9/25: WID:RP-251856->RP-252936 |  | 108 | 55 |  |  | Fri 18/07/25 | Mon 29/09/25
68 | 1081083 | Core part: NR MIMO Phase 6 | NR_MIMO_Ph6-Core | 2 | Rel-20 | R1 | 2025-06-06 08:00 | 2027-03-03 17:00 | 10% | RP-252936 | RP-252509 | MediaTek |  | compare REL-19 WI NR_MIMO_Ph5, REL-18 WIs NR_MIMO_evo_DL_UL, NR_MIMO_OTA_enh, REL-17 WIs NR_feMIMO, NR_MIMO_OTA, REL-16 WI NR_eMIMO ; 11/9/25: FCD:Wed 03/03/27->Fri 04/06/27; Compl:0%->10%; Stat Rep: ->RP-252509; ; 30/9/25: FCD:Sun 06/06/->/27 |  | 108 | 55 |  |  | Fri 18/07/25 | Tue 30/09/25
69 | 1082083 | Perf. part: NR MIMO Phase 6 | NR_MIMO_Ph6-Perf | 2 | Rel-20 | R4 | 2025-06-06 08:00 | 2027-09-09 17:00 | 0% | RP-252936 | RP-252509 | MediaTek |  | ; 11/9/25: Stat Rep: ->RP-252509; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
70 | 1080084 | NR coverage enhancements Phase 3 | NR_cov_Ph3 | 1 | Rel-20 |  | 2025-06-06 08:00 | 2027-03-03 17:00 | 0% | RP-252824 |  | China Telecom |  | compare REL-18 WI NR_cov_enh2, REL-17 WI NR_cov_enh ; 29/9/25: WID:RP-251862->RP-252824 |  | 108 | 55 |  |  | Fri 18/07/25 | Mon 29/09/25
71 | 1081084 | Core part: NR coverage enhancements Phase 3 | NR_cov_Ph3-Core | 2 | Rel-20 | R1 | 2025-06-06 08:00 | 2026-12-12 17:00 | 0% | RP-252824 | RP-252571 | China Telecom |  | compare REL-18 WI NR_cov_enh2, REL-17 WI NR_cov_enh ; 11/9/25: Stat Rep: ->RP-252571; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
72 | 1082084 | Perf. part: Coverage enhancements for NR Phase 3 | NR_cov_Ph3-Perf | 2 | Rel-20 | R4 | 2025-06-06 08:00 | 2027-03-03 17:00 | 0% | RP-252824 | RP-252571 | China Telecom |  | ; 11/9/25: Stat Rep: ->RP-252571; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
73 | 1090064 | Study on spatial channel model for demodulation performance requirements for NR: MultiUser-MIMO | FS_NR_demod_SCM_MUMIMO | 1 | Rel-20 | R4 | 2019-03-07 08:00 | 2021-03-06 14:00 | 0% | RP-252956 |  | Nokia |  | compare REL-19 SI FS_NR_demod_SCM | [5 empty] | Mon 29/09/25 | NA
74 | 1090065 | UE RF enhancements for NR FR1, Phase 5 | NR_UE_RF_Ph5 | 1 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-09-09 17:00 | 0% | RP-252952 |  | Huawei |  | compare REL-19 WI NR_ENDC_RF_Ph4, REL-18 WI NR_RF_FR2_req_Ph3, REL-17 WI NR_RF_FR1_enh, REL-16 WI NR_RF_FR1 | [5 empty] | Mon 29/09/25 | NA
75 | 1091065 | Core part: UE RF enhancements for NR FR1, Phase 5 | NR_UE_RF_Ph5-Core | 2 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-03-03 17:00 | 0% | RP-252952 |  | Huawei |  | compare REL-19 WI NR_ENDC_RF_Ph4, REL-18 WI NR_RF_FR2_req_Ph3, REL-17 WI NR_RF_FR1_enh, REL-16 WI NR_RF_FR1 | [5 empty] | Mon 29/09/25 | NA
76 | 1092065 | Perf. part: UE RF enhancements for NR FR1, Phase 5 | NR_UE_RF_Ph5-Perf | 2 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-09-09 17:00 | 0% | RP-252952 |  | Huawei | [7 empty] | Mon 29/09/25 | NA
77 | 1090066 | NR base station (BS) RF requirement evolution for FR1/FR2 and testing, Phase 2 | NR_BS_RF_req_evo_Ph2 | 1 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-09-09 17:00 | 0% | RP-252905 |  | ZTE |  | compare REL-19 WI NR_BS_RF_req_evo; TR 38.8xx | [5 empty] | Mon 29/09/25 | NA
78 | 1091066 | Core part: NR base station (BS) RF requirement evolution for FR1/FR2 and testing, Phase 2 | NR_BS_RF_req_evo_Ph2-Core | 2 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-03-03 17:00 | 0% | RP-252905 |  | ZTE |  | compare REL-19 WI NR_BS_RF_req_evo; TR 38.8xx | [5 empty] | Mon 29/09/25 | NA
79 | 1092066 | Perf. part: NR base station (BS) RF requirement evolution for FR1/FR2 and testing, Phase 2 | NR_BS_RF_req_evo_Ph2-Perf | 2 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-09-09 17:00 | 0% | RP-252905 |  | ZTE | [7 empty] | Mon 29/09/25 | NA
80 | 1090067 | Enhancement of UE OTA test method and requirements for NR | NR_UE_OTA_enh | 1 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-09-09 17:00 | 0% | RP-252903 |  | vivo |  | compare REL-19 WI TRP_TRS_MIMO_OTA_Ph3; introduces test method enhancements for NTN VSAT; new TR or TS? | [5 empty] | Mon 29/09/25 | NA
81 | 1091067 | Core part: Enhancement of UE OTA test method and requirements for NR | NR_UE_OTA_enh-Core | 2 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-03-03 17:00 | 0% | RP-252903 |  | vivo |  | compare REL-19 WI TRP_TRS_MIMO_OTA_Ph3; introduces test method enhancements for NTN VSAT; new TR or TS? | [5 empty] | Mon 29/09/25 | NA
82 | 1092067 | Perf. part: Enhancement of UE OTA test method and requirements for NR | NR_UE_OTA_enh-Perf | 2 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-09-09 17:00 | 0% | RP-252903 |  | vivo | [7 empty] | Mon 29/09/25 | NA
83 | 1090068 | NR Radio Resource Management (RRM), Phase 6 | NR_RRM_Ph6 | 1 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-09-09 17:00 | 0% | RP-252955 |  | Ericsson |  | compare: REL-19 WI NR_RRM_Ph5, REL-18 WI NR_RRM_enh3, REL-17 WI NR_RRM_enh2, REL-16 WI NR_RRM_enh | [5 empty] | Mon 29/09/25 | NA
84 | 1091068 | Core part: NR Radio Resource Management (RRM), Phase 6 | NR_RRM_Ph6-Core | 2 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-03-03 17:00 | 0% | RP-252955 |  | Ericsson |  | compare: REL-19 WI NR_RRM_Ph5, REL-18 WI NR_RRM_enh3, REL-17 WI NR_RRM_enh2, REL-16 WI NR_RRM_enh | [5 empty] | Mon 29/09/25 | NA
85 | 1092068 | Perf. part: NR Radio Resource Management (RRM), Phase 6 | NR_RRM_Ph6-Perf | 2 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-09-09 17:00 | 0% | RP-252955 |  | Ericsson | [7 empty] | Mon 29/09/25 | NA
86 | 1090069 | NR demodulation performance Phase 6 | NR_demod_Ph6 | 1 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-03-03 17:00 | 0% | RP-252957 |  | China Telecom |  | compare: REL-19 WI NR_demod_Ph5, REL-18 WI NR_demod_enh3, REL-17 WI NR_demod_enh2, REL-16 WI NR_perf_enh | [5 empty] | Mon 29/09/25 | NA
87 | 1092069 | Perf. part: NR demodulation performance Phase 6 | NR_demod_Ph6-Perf | 2 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-03-03 17:00 | 0% | RP-252957 |  | China Telecom |  | compare: REL-19 WI NR_demod_Ph5, REL-18 WI NR_demod_enh3, REL-17 WI NR_demod_enh2, REL-16 WI NR_perf_enh | [5 empty] | Mon 29/09/25 | NA
88 | 1090071 | Enhancement of low NR band carrier aggregation via switching | NR_LBCA_Sw_enh | 1 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-09-09 17:00 | 0% | RP-252953 |  | Telus |  | compare: REL-19 WI NR_LBCA_Sw | [5 empty] | Mon 29/09/25 | NA
89 | 1091071 | Core part: Enhancement of low NR band carrier aggregation via switching | NR_LBCA_Sw_enh-Core | 2 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-03-03 17:00 | 0% | RP-252953 |  | Telus |  | compare: REL-19 WI NR_LBCA_Sw | [5 empty] | Mon 29/09/25 | NA
90 | 1092071 | Perf. part: Enhancement of low NR band carrier aggregation via switching | NR_LBCA_Sw_enh-Perf | 2 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-09-09 17:00 | 0% | RP-252953 |  | Telus | [7 empty] | Mon 29/09/25 | NA
91 | 1090072 | Enhancement of NR RF and RRM requirements for uncrewed aerial vehicle (UAV) | NR_UAV_req | 1 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-09-09 17:00 | 0% | RP-252954 |  | CMCC |  | compare: REL-18 WI NR_UAV | [5 empty] | Mon 29/09/25 | NA
92 | 1091072 | Core part: Enhancement of NR RF and RRM requirements for uncrewed aerial vehicle (UAV) | NR_UAV_req-Core | 2 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-03-03 17:00 | 0% | RP-252954 |  | CMCC |  | compare: REL-18 WI NR_UAV | [5 empty] | Mon 29/09/25 | NA
93 | 1092072 | Perf. part: Enhancement of NR RF and RRM requirements for uncrewed aerial vehicle (UAV) | NR_UAV_req-Perf | 2 | Rel-20 | R4 | 2025-09-09 08:00 | 2027-09-09 17:00 | 0% | RP-252954 |  | CMCC | [7 empty] | Mon 29/09/25 | NA
94 | 0 | Rel-20 Radio-centric: NR-only, band-related | - | 1 | Rel-20 |  | 2019-03-07 08:00 | 2021-05-15 12:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
95 | 1080093 | Introduction of NR TDD 4.9GHz band for US operation | NR_TDD_band_4900MHz_US | 1 | Rel-20 | R4 | 2025-06-06 08:00 | 2026-06-06 17:00 | 5% | RP-252929 |  | Fujitsu |  | 4940-4990 MHz NR TDD band for public safety in US, REL-independent from REL-15; Core part target colliding with REL-19 ASN.1 freeze ; 29/9/25: WID:RP-251887->RP-252929 |  | 108 | 55 |  |  | Fri 18/07/25 | Mon 29/09/25
96 | 1081093 | Core part: Introduction of NR TDD 4.9GHz band for US operation | NR_TDD_band_4900MHz_US-Core | 2 | Rel-20 | R4 | 2025-06-06 08:00 | 2025-12-12 17:00 | 15% | RP-252929 | RP-252349 | Fujitsu |  | 4940-4990 MHz NR TDD band for public safety in US, REL-independent from REL-15; Core part target colliding with REL-19 ASN.1 freeze ; 11/9/25: Compl:0%->15%; Stat Rep: ->RP-252349; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
97 | 1082093 | Perf. part: Introduction of NR TDD 4.9GHz band for US operation | NR_TDD_band_4900MHz_US-Perf | 2 | Rel-20 | R4 | 2025-06-06 08:00 | 2026-06-06 17:00 | 0% | RP-252929 | RP-252349 | Fujitsu |  | ; 11/9/25: Stat Rep: ->RP-252349; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
98 | 0 | Rel-20 Extended reality, Metaverse, Media | - | 1 | Rel-20 |  | 2024-04-02 08:00 | 2026-06-06 17:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
99 | 1070033 | Stage 2 for mobile metaverse services Phase 2 | Metaverse_Ph2-APP | 1 | Rel-20 | S6 | 2025-03-26 08:00 | 2025-12-12 17:00 | 65% | SP-250392 |  | Ramamoorthy, Arunprasath (Arun), Samsung, | arun.prasath@samsung.com | ; 6/6/25: 0%->45; 12/9/25: 45%->65 | 23.437; 23.438 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
100 | 1080089 | XR (eXtended Reality) for NR Phase 4 | NR_XR_Ph | 1 | Rel-20 | R2 | 2025-06-06 08:00 | 2027-03-03 17:00 | 0% | RP-252755 |  | Meta |  | no Perf. part; no affected RAN2 spec??? ; 29/9/25: WID:RP-251866->RP-252755 |  | 108 | 55 |  |  | Fri 18/07/25 | Mon 29/09/25
101 | 1081089 | Core part: XR (eXtended Reality) for NR Phase 4 | NR_XR_Ph4-Core | 2 | Rel-20 | R2 | 2025-06-06 08:00 | 2027-03-03 17:00 | 0% | RP-252755 | RP-252754 | Meta |  | no Perf. part; no affected RAN2 spec??? ; 11/9/25: Stat Rep: ->RP-252754; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
102 | 1090041 | Study on Usage of Dynamically Changing Traffic Characteristics and Enhanced QoS support in Media Applications and Services | FS_DCTC_eQOS_MED | 1 | Rel-20 | S4 | 2025-09-10 08:00 | 2026-09-09 17:00 | 0% | SP-251201 |  | Rufael Mekuria, Huawei | Rufael.mekuria@huawei.com |  | 26.926; 26.925; 26.822; 26.812 | 109 | 55 |  |  | Wed 10/09/25 | NA
103 | 1090042 | Study of Advanced Video Formats and Operation Points | FS_AVFOPS_MED | 1 | Rel-20 | S4 | 2025-09-10 08:00 | 2026-09-09 17:00 | 0% | SP-251202 |  | Emmanuel Thomas, Xiaomi | thomase@xiaomi.com | ; 29/9/25: WID:SP-250938->SP-251202 | 26.966 | 109 | 55 |  |  | Wed 10/09/25 | Mon 29/09/25
104 | 1090043 | Study on 3D Gaussian splats | FS_3DGS_MED | 1 | Rel-20 | S4 | 2025-09-10 08:00 | 2026-03-03 17:00 | 0% | SP-251190 |  | Ricard Julien, Tencent | jricard@global.tencent.com |  |  | 109 | 55 |  |  | Wed 10/09/25 | NA
105 | 1090046 | Study on Advanced Media Delivery Phase 2 | FS_AMD_Ph2 | 1 | Rel-20 | S4 | 2025-09-10 08:00 | 2026-06-06 17:00 | 0% | SP-251265 |  | Thomas Stockhammer, Qualcomm Incorporated, | tsto@qti.qualcomm.com. |  | 26.802; 26.804; 26.941; 26.802; 26.804; 26.941 | 109 | 55 |  |  | Mon 29/09/25 | NA
106 | 1060022 | Diverse audio Capturing System for UEs | DaCAS | 1 | Rel-20 | S4 | 2024-12-05 08:00 | 2026-06-06 17:00 | 55% | SP-241962 |  | Wang Bin, Xiaomi Technology | wangbin23@xiaomi.com | 6/3/25: 0%->5; 5/6/25: 5%->50; 5/6/25: FCD:Fri 06/06/->/25; 12/9/25: 50%->55; 12/9/25: FCD:Tue 09/09/->/2026; Rel-19->Rel-20 | 26.533 | 106 | 54 |  |  | Thu 05/12/24 | Fri 12/09/25
107 | 1030009 | Study on Audio Codec APIs | FS_ACAPI | 1 | Rel-20 | S4 | 2024-04-02 08:00 | 2025-12-12 17:00 | 49% |  |  | Stefan Döhla | (stefan DOT doehla AT iis DOT fraunhofer DOT de) | 14/5/24: 26.858 added;; 13/6/24: 0%->10; 5/12/24: 10%->20; 5/12/24: FCD:03/03/2025->/25; 6/3/25: 20%->40; 5/6/25: 40%->47; 5/6/25: FCD:Sat 25/01/->12/25; 12/9/25: 47%->49; Rel-19->Rel-20 | 26.858 | 103 | 52 |  |  | Wed 13/03/24 | Fri 12/09/25
108 | 0 | Rel-20 Integrated Sensing and Communication (Sensing, ISAC) | - | 1 | Rel-20 |  | 2024-04-02 08:00 | 2026-06-06 17:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
109 | 1070012 | Study on Stage 2 for Integrated Sensing and Communication | FS_Sensing_ARC | 1 | Rel-20 | S2 | 2025-03-26 08:00 | 2025-12-12 17:00 | 65% | SP-250809 |  | Jianning LIU, Xiaomi | liujianning@xiaomi.com | ; 27/6/25: WID:SP-250401->SP-250809; 12/9/25: 0%->65 |  | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
110 | 1090020 | Study on Security and Privacy Aspects of Integrated Sensing and Communication | FS_Sensing_SEC | 1 | Rel-20 | S3 | 2025-09-10 08:00 | 2026-06-06 17:00 | 0% | SP-251242 |  | Henry Leung (Xiaomi | lianghaoran@xiaomi.com |  |  | 109 | 55 |  |  | Wed 10/09/25 | NA
111 | 1080028 | Study on use of Sensing results for Vertical Applications | FS_Sensing_APP | 1 | Rel-20 | S6 | 2025-06-05 08:00 | 2026-03-03 17:00 | 15% | SP-251044 |  | Liu, Yue, China Mobile | liuyueyjy@chinamobile.com | 18/7/25: 23.700-15 added;; 12/9/25: 0%->15; 29/9/25: WID:SP-250875->SP-251044 | 23.700-15 | 108 | 55 |  |  | Thu 05/06/25 | Mon 29/09/25
112 | 1080070 | Study on Integrated Sensing And Communication (ISAC) for NR | FS_Sensing_NR_bis | 1 | Rel-20 | R1 | 2025-06-06 08:00 | 2026-06-06 17:00 | 15% | RP-252819 | RP-252200 | Xiaomi |  | compare REL-19 RAN1 SI FS_Sensing_NR and REL-20 SA2 SI FS_Sensing_ARC; 38.xxx ? ; 11/9/25: FCD:Sat 06/06/26->Fri 05/06/26; Compl:0%->15%; Stat Rep: ->RP-252200; ; 29/9/25: WID:RP-251861->RP-252819; 30/9/25: 38.765 added; | 38.765 | 108 | 55 |  |  | Fri 18/07/25 | Tue 30/09/25
113 | 0 | Rel-20 Other topics | - | 1 | Rel-20 |  | 2024-04-02 08:00 | 2026-06-06 17:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
114 | 1080052 | Indirect Network Sharing Phase 2 | NetShare_Ph2 | 1 | Rel-20 |  | 2024-02-08 08:00 | 2026-09-09 17:00 | 32% | SP-241147 |  | Qun Wei, China Unicom | weiqun5@chinaunicom.cn |  | 22.261 | 105 | 53 |  |  | Wed 04/09/24 | NA
115 | 1050106 | Stage 1 for Indirect Network Sharing Phase 2 | NetShare_Ph2-REQ | 2 | Rel-20 | S1 | 2024-02-08 08:00 | 2024-09-09 17:00 | 100% | SP-241147 |  | Qun Wei, China Unicom | weiqun5@chinaunicom.cn |  |  | 105 | 53 |  |  | Thu 05/06/25 | NA
116 | 1080059 | Stage 2 for Indirect Network Sharing Phase2 | TEI20_NetShare_Ph2-ARC | 2 | Rel-20 | S2 | 2025-06-05 08:00 | 2026-09-09 17:00 | 0% | SP-250838 |  | Tianqi Xing, China Unicom | xingtq@chinaunicom.cn |  | 23.501; 23.502; 23.503 | 108 | 55 |  |  | Thu 05/06/25 | NA
117 | 1080055 | FRMCS Phase 6 | FRMCS_Ph6 | 1 | Rel-20 |  | 2024-03-13 08:00 | 2026-06-06 17:00 | 72% | [6 empty] | 108 | 55 |  |  | Thu 05/06/25 | NA
118 | 1030043 | Study on FRMCS Phase 6 | FS_FRMCS_Ph6 | 2 | Rel-20 | S1 | 2024-03-13 08:00 | 2025-03-03 17:00 | 100% | SP-241392 |  | Nikolopoulou, Vassiliki, UIC, | nikolopoulou@uic.org | ; 13/6/24: 0%->20; 4/9/24: 20%->40; 26/9/24: WID:SP-240199->SP-241392; 26/9/24: FCD:09/09/2024->/25; 6/3/25: 40%->100 | 22.989 | 103 | 52 |  |  | Wed 13/03/24 | Thu 06/03/25
119 | 1070054 | Stage 1 for FRMCS Phase 6 | FRMCS_Ph6-REQ | 2 | Rel-20 | S1 | 2025-03-06 08:00 | 2025-09-09 17:00 | 100% | SP-250277 |  | Nikolopoulou, Vassiliki, UIC | nikolopoulou@uic.org | ; 6/6/25: 0%->10; 6/6/25: FCD:Fri 06/06/->/25; 12/9/25: 10%->100 | 22.280; 22.179; 22.281 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
120 | 1070031 | Stage 2 for FRMCS Phase 6 | FRMCS_Ph6-MC | 2 | Rel-20 | S6 | 2025-03-26 08:00 | 2026-06-06 17:00 | 45% | SP-250390 |  | Oettl, Martin, Nokia | martin.oettl@nokia.com | ; 6/6/25: 0%->35; 12/9/25: 35%->45 | 23.280; 23.281; 23.282; 23.379; 23.283; 23.289 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
121 | 1080056 | Short Message Service to Emergency Response Centre | SMS2EC | 1 | Rel-20 |  | 2025-02-02 08:00 | 2026-03-03 17:00 | 26% | [6 empty] | 108 | 55 |  |  | Thu 05/06/25 | NA
122 | 1070052 | Stage 1 of SMS to Emergency Centre | SMS2EC-REQ | 2 | Rel-20 | S1 | 2025-02-02 08:00 | 2025-03-03 17:00 | 100% | SP-250387 |  | Francesco Pica, Qualcomm | fpica@qti.qualcomm.com |  | 22.201 | 107 | 54 |  |  | Wed 05/03/25 | NA
123 | 1080062 | Study on Short Message Service to Emergency Response Centre | FS_SMS2EC_ARC | 2 | Rel-20 | S2 | 2025-06-05 08:00 | 2026-03-03 17:00 | 25% | SP-251216 |  | Krisztian Kiss, Apple | krisztian@apple.com | 12/9/25: 0%->25; 29/9/25: WID:SP-250837->SP-251216 | 23.700-65 | 108 | 55 |  |  | Thu 05/06/25 | Mon 29/09/25
124 | 1090038 | Service Enabler Architecture Layer (SEAL) Phase 4 | SEAL_Ph4-APP | 1 | Rel-20 | S6 | 2025-09-10 08:00 | 2026-03-03 17:00 | 0% | SP-251215 |  | Yang, Yanmei, Huawei Technologies Co. Ltd. | <yangyanmei@huawei.com> |  | 23.433; 23.434; 23.435; 23.436; 23.437; 23.438; 23.222 | 109 | 55 |  |  | Wed 10/09/25 | NA
125 | 1070025 | Study on Logging and recording of mission critical services, Phase 2 | FS_MCLOG_Ph2 | 1 | Rel-20 | S6 | 2025-03-26 08:00 | 2026-03-03 17:00 | 20% | SP-250581 |  | Vialen, Jukka, Airbus | jukka.vialen@airbus.com | 3/4/25: 23.700-39 added;; 6/6/25: 0%->10; 27/6/25: WID:SP-250380->SP-250581; 12/9/25: 10%->20 | 23.700-39 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
126 | 1070024 | Study on Discreet listening and monitoring of mission critical services, Phase 2 | FS_MCDISC_Ph2 | 1 | Rel-20 | S6 | 2025-03-26 08:00 | 2026-03-03 17:00 | 20% | SP-250580 |  | Verweij, Kees, Netherlands Police, | kees.verweij@politie.nl | 3/4/25: 23.700-37 added;; 6/6/25: 0%->10; 12/9/25: 10%->20. Rapporteur corrected to Kees (was Juha) | 23.700-37 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
127 | 1090015 | Study on Security Aspects for IMS resiliency | FS_IMSRE_SEC | 1 | Rel-20 | S3 | 2025-09-10 08:00 | 2026-03-03 17:00 | 0% | SP-251237 |  | Rohini Rajendran (Samsung | r.rohini@samsung.com |  | 33.768 | 109 | 55 |  |  | Wed 10/09/25 | NA
128 | 1090016 | Study on AIMLE Service Security | FS_AIMLE_SEC | 1 | Rel-20 | S3 | 2025-09-10 08:00 | 2026-03-03 17:00 | 0% | SP-251238 |  | Sheeba Backia Mary Baskaran, Lenovo | smary@lenovo.com |  | 33.786 | 109 | 55 |  |  | Wed 10/09/25 | NA
129 | 1090025 | Study on security aspect of support of Ambient power-enabled Internet of Things-Phase 2 | FS_AIoT_SEC_Ph2 | 1 | Rel-20 | S3 | 2025-09-10 08:00 | 2026-06-06 17:00 | 0% | SP-251246 |  | Lihui Xiong (OPPO | xionglihui@oppo.com |  | 33.714 | 109 | 55 |  |  | Wed 10/09/25 | NA
130 | 1090017 | Study on security for PLMN hosting a NPN phase 2 | FS_PLMNNPN_Ph2 | 1 | Rel-20 | S3 | 2025-09-10 08:00 | 2026-06-06 17:00 | 0% | SP-251239 |  | Jun Shen (China Telecom | shenjun6@chinatelecom.cn |  | 33.758 | 109 | 55 |  |  | Wed 10/09/25 | NA
131 | 1090018 | Study on providing PSK for MPQUIC/TLS | FS_PSK_MQC_TLS | 1 | Rel-20 | S3 | 2025-09-10 08:00 | 2026-03-03 17:00 | 0% | SP-251240 |  | Li He, (Huawei | lihe2@huawei.com |  | 33.778 | 109 | 55 |  |  | Wed 10/09/25 | NA
132 | 1090019 | Study on Security for Core Network Enhanced Support for Artificial Intelligence (AI) / Machine Learning (ML) Phase 2 | FS_AIML_CN_Ph2_SEC | 1 | Rel-20 | S3 | 2025-09-10 08:00 | 2026-03-03 17:00 | 0% | SP-251241 |  | samir.ferdi(InterDigital, | samir.ferdi@interdigital.com) |  | 33.785 | 109 | 55 |  |  | Wed 10/09/25 | NA
133 | 1090022 | Study on Security Aspects of Satellite Access in 5G Phase 4 | FS_5GSAT_Ph4_SEC | 1 | Rel-20 | S3 | 2025-09-10 08:00 | 2026-06-06 17:00 | 0% | SP-251244 |  | Hongil Kim (Qualcomm | hongilk@qti.qualcomm.com |  | 33.700-30 | 109 | 55 |  |  | Wed 10/09/25 | NA
134 | 1090023 | Study on Security aspects of CAPIF Phase 4 | FS_CAPIF_Ph4_SEC | 1 | Rel-20 | S3 | 2025-09-10 08:00 | 2026-12-12 17:00 | 0% | SP-251245 |  | Weiyin Zhang(China Telecom, | zhangwy12@chinatelecom.cn |  | 33.700-23 | 109 | 55 |  |  | Wed 10/09/25 | NA
135 | 1090021 | Study on Security Assurance Specification (SCAS) for Container-based Product | FS_SCAS_CP | 1 | Rel-20 | S3 | 2025-09-10 08:00 | 2026-09-09 17:00 | 0% | SP-251243 |  | Markus Hanhisalo (Ericsson | markus.hanhisalo@ericsson.com |  | 33.730 | 109 | 55 |  |  | Wed 10/09/25 | NA
136 | 1090024 | PRINS Refinement | RefinePRINS | 1 | Rel-20 | S3 | 2025-09-10 08:00 | 2026-03-03 17:00 | 0% | SP-251251 |  | Tao Wan (CableLabs | t.wan@cablelabs.com |  | 33.501 | 109 | 55 |  |  | Wed 10/09/25 | NA
137 | 1090026 | Security Assurance Specification (SCAS) for NR Femto | SCAS_NR_Femto | 1 | Rel-20 | S3 | 2025-09-10 08:00 | 2026-06-06 17:00 | 0% | SP-251252 |  | Zhonghuai Xie (China Unicom | xiezh55@chinaunicom.cn |  | 33.546, 33.926 | 109 | 55 |  |  | Wed 10/09/25 | NA
138 | 1090027 | 5G Security Assurance Specification (SCAS) for NR Femto Security Gateway (SeGW) | SCAS_Femto_SeGW | 1 | Rel-20 | S3 | 2025-09-10 08:00 | 2026-06-06 17:00 | 0% | SP-251253 |  | Shihan Bao (CATT | baoshihan@cictmobile.com |  | 33.547, 33.926 | 109 | 55 |  |  | Wed 10/09/25 | NA
139 | 1090045 | Study on security aspects of WAB nodes for NR | FS_5G_WAB_SEC | 1 | Rel-20 | S3 | 2025-09-29 08:00 | 2026-06-06 17:00 | 0% | SP-251250 |  | Weihan Gao (China Telecom) | gaowh@chinatelecom..cn |  | 33.724 | 109 | 55 |  |  | Mon 29/09/25 | NA
140 | 1090030 | Study on Security Aspect for NR Femto Phase 2 | FS_NR_Femto_SEC_Ph2 | 1 | Rel-20 | S3 | 2025-09-10 08:00 | 2026-06-06 17:00 | 0% | SP-251249 |  | Peilin Liu (ZTE | liu.peilin@zte.com.cn |  | 33.746 | 109 | 55 |  |  | Wed 10/09/25 | NA
141 | 1090029 | Study on best security practices for SBA | FS_BSP4SBA | 1 | Rel-20 | S3 | 2025-09-10 08:00 | 2026-03-03 17:00 | 0% | SP-251248 |  | Imran Saleem (Huawei | imran.saleem1@huawei.com |  | 33.755 | 109 | 55 |  |  | Wed 10/09/25 | NA
142 | 1090028 | Study on supporting AEAD algorithms | FS_AEAD | 1 | Rel-20 | S3 | 2025-09-10 08:00 | 2026-09-09 17:00 | 0% | SP-251247 |  | Yuto Nakano (KDDI, | yt-nakano@kddi.com |  | 33.771 | 109 | 55 |  |  | Wed 10/09/25 | NA
143 | 1090039 | Stage 1 for Phase 2 of Mission Critical Discreet listening | MCDISC_Ph2-REQ | 1 | Rel-20 | S1 | 2025-08-08 08:00 | 2025-09-09 17:00 | 100% | SP-251267 |  | Kees Verweij, Netherlands Police: | keesdotverweijatpolitiedotnl | ; 12/9/25: 0%->100 | 22.280 | 109 | 55 |  |  | Wed 10/09/25 | Fri 12/09/25
144 | 1090002 | Model Evaluation Metrics Enhancement | TEI20_Metrics | 1 | Rel-20 | S2 | 2025-09-10 08:00 | 2026-03-03 17:00 | 0% | SP-251207 |  | Yuang Feng(ZTE) | feng.yuang@zte.com.cn |  | 23.288 | 109 | 55 |  |  | Wed 10/09/25 | NA
145 | 1090003 | NR to LTE mobility restriction | TEI20_NRLTEREST | 1 | Rel-20 | S2 | 2025-09-29 08:00 | 2026-03-03 17:00 | 0% | SP-251208 |  | Sushmit Bhattacharjee (NTT DOCOMO) | bhattacharjee@docomolab-euro.com |  | 23.501 | 109 | 55 |  |  | Wed 10/09/25 | NA
146 | 1090004 | Support for Ethernet PDU session for backhauling of MWAB | TEI20_Eth4MWAB | 1 | Rel-20 | S2 | 2025-09-10 08:00 | 2026-03-03 17:00 | 0% | SP-251209 |  | Cheng, Hong, Qualcomm Incorporated | hongc@qti.qualcomm.com |  | 23.501 | 109 | 55 |  |  | Wed 10/09/25 | NA
147 | 1090005 | Support of NSSAA in EPS | TEI20_NEPS | 1 | Rel-20 | S2 | 2025-09-29 08:00 | 2026-03-03 17:00 | 0% | SP-251210 |  | Alessio Casati, Nokia | alessio.casati@nokia.com |  | 23.501; 23.502 | 109 | 55 |  |  | Wed 10/09/25 | NA
148 | 1090006 | Deferred AM Policies in the 5GC | TEI20_DAMP | 1 | Rel-20 | S2 | 2025-09-10 08:00 | 2026-03-03 17:00 | 0% | SP-251211 |  | Baniel, Uri, Oracleuri dot baniel at oracle dot com, O | uri dot baniel at oracle dot com |  | 23.503; 23.502 | 109 | 55 |  |  | Wed 10/09/25 | NA
149 | 1090007 | Dynamic NITZ Update | TEI20_DNU | 1 | Rel-20 | S2 | 2025-08-08 08:00 | 2026-03-03 17:00 | 0% | SP-251212 |  | Aihua Li, China Mobile | <liaihua@chinamobile.com> |  | 23.501; 23.502; 23.503 | 109 | 55 |  |  | Wed 10/09/25 | NA
150 | 1090008 | Providing per-subscriber Allowed MAC addresses from UDM | TEI20_MACSUB | 1 | Rel-20 | S2 | 2025-09-10 08:00 | 2026-03-03 17:00 | 0% | SP-251213 |  | Ashok Kumar Nayak, Samsung | ashok.nayak @ samsung.com |  | 23.501; 23.502 | 109 | 55 |  |  | Wed 10/09/25 | NA
151 | 1080044 | Mission critical security for Rel-20 | MCX20-SEC | 1 | Rel-20 | S3 | 2019-03-07 08:00 | 2020-12-01 16:00 | 10% | SP-250653 |  | Woodward, Tim, Motorola Solutions, Inc., | tim.woodward@motorolasolutions.com | ; 12/9/25: 0%->10 | 33.180 | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
152 | 1060070 | Vehicle-Mounted Relays Phase3 | VMR_Ph3 | 1 | Rel-20 | S1 | 2024-12-05 08:00 | 2024-12-12 17:00 | 100% | SP-241821 |  | Qing Wan, CATT, | wanqing1@cictmobile.com | ; 5/12/24: 0%->100 | 22.261 | 106 | 54 |  |  | Thu 05/12/24 | Thu 05/12/24
153 | 1050107 | Resident Phase 2 | Resident_Ph2 | 1 | Rel-20 | S1 | 2024-09-04 08:00 | 2024-09-09 17:00 | 100% | SP-241149 |  | Qun Wei, China Unicom | weiqun5@chinaunicom.cn |  | 22.261 | 105 | 53 |  |  | Wed 04/09/24 | NA
154 | 1080058 | 5G ProSe Phase 4 | ProSe_Ph4-ARC | 1 | Rel-20 | S2 | 2025-06-05 08:00 | 2026-09-09 17:00 | 0% | SP-250839 |  | Toumi, Nassima, KPN N.V. | nassima (dot) toumi (dot) tno (dot) nl |  | 23.304 | 108 | 55 |  |  | Thu 05/06/25 | NA
155 | 1080045 | Study on Transitioning to Post Quantum Cryptography in 3GPP | FS_CryptoPQC | 1 | Rel-20 | S3 | 2025-06-05 08:00 | 2026-06-06 17:00 | 15% | SP-250858 |  | Primary: Zander, Huawei | lei.zhongding@huawei.com | 12/9/25: 0%->15; 12/9/25: 33.703 added; | 33.703 | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
156 | 1080047 | CPAS specific requirement | CPAS-REQ | 1 | Rel-20 | S1 | 2025-06-05 08:00 | 2025-06-06 17:00 | 100% | SP-250627 |  | Pengtai Qin | qinpengtai@chinamobile.com | ; 5/6/25: 0%->100 | 23.304 | 108 | 55 |  |  | Thu 05/06/25 | Thu 05/06/25
157 | 1080042 | Security Assurance Specification for 5G-Advanced | SCAS_5GA | 1 | Rel-20 | S3 | 2025-06-05 08:00 | 2026-09-09 17:00 | 15% | SP-250877 |  | Wurong (raina), Huawei | raina.wu@huawei.com | 12/9/25: 0%->15 |  | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
158 | 1080041 | Security related Events Handling | SECHAND | 1 | Rel-20 | S3 | 2025-06-05 08:00 | 2025-12-12 17:00 | 20% | SP-250876 |  | Susana Sabater, Vodafone | susana.sabater@vodafone.com | 18/7/25: 33.502 added;; 12/9/25: 0%->20 | 33.502 | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
159 | 1080029 | Guidelines for 3GPP Application Enablement usage | AppEnable_EXT | 1 | Rel-20 | S6 | 2025-06-05 08:00 | 2026-03-03 17:00 | 5% | SP-250883 |  | David Artuñedo, Telefónica | david.artunedoguillen@telefonica.com | 12/9/25: 0%->5 |  | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
160 | 1080026 | Study of CAPIF Phase 4 | FS_CAPIF_Ph4 | 1 | Rel-20 | S6 | 2025-06-05 08:00 | 2026-03-03 17:00 | 0% | SP-251043 |  | Sapan Shah, Nokia | sapan.shah@nokia.com | 18/7/25: 23.700-43 added;; 29/9/25: WID:SP-250873->SP-251043 | 23.700-43 | 108 | 55 |  |  | Thu 05/06/25 | Mon 29/09/25
161 | 1080025 | Study on Application user consent | FS_APCOT | 1 | Rel-20 | S6 | 2025-06-05 08:00 | 2026-03-03 17:00 | 5% | SP-250872 |  | Cristina Badulescu | cristina.badulescu@ericsson.com | 18/7/25: 23.700-42 added;; 12/9/25: 0%->5 | 23.700-42 | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
162 | 1080060 | Study on system architecture for Phase 3 of NG RTC | FS_NG_RTC_Ph3_ARC | 1 | Rel-20 | S2 | 2025-06-05 08:00 | 2026-03-03 17:00 | 20% | SP-250855 |  | Christopher Joul, T-Mobile USA, | chris.joul@t-mobile.com | 12/9/25: 0%->20 |  | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
163 | 1050034 | Study on Service Enabler Architecture Layer (SEAL) Phase 4 | FS_SEAL_Ph4 | 1 | Rel-20 | S6 | 2024-09-04 08:00 | 2025-12-12 17:00 | 95% | SP-250374 |  | Yang, Yanmei, Huawei Technologies Co.,Ltd. | yangyanmei@huawei.com | 5/12/24: 0%->20; 6/3/25: 20%->40. Moved from Rel-19; 26/3/25: WID:SP-241375->SP-250374; 26/3/25: FCD:12/12/2024->12/25; 6/6/25: 40%->75; 12/9/25: 75%->95 |  | 105 | 53 |  |  | Wed 04/09/24 | Fri 12/09/25
164 | 1070053 | Stage 1 for Ambient listening enhancements including pause and resume in MCS | ALPR-REQ | 1 | Rel-20 | S1 | 2025-02-11 15:00 | 2025-03-03 17:00 | 100% | SP-250275 |  | S. (Ram) Ramanan | Sivasubramaniam.ramanan@homeoffice.gov.uk | ; 26/3/25: 0%->100 | 22.179; 22.280 | 107 | 54 |  |  | Wed 05/03/25 | Wed 26/03/25
165 | 1070026 | Study on Application enabler for XR Services Phase 3 | FS_XRM_Ph3_APP | 1 | Rel-20 | S6 | 2025-03-26 08:00 | 2025-12-12 17:00 | 70% | SP-251042 |  | Liu, Tangqing, China Mobile | liutangqing@chinamobile.com | 3/4/25: 23.700-51 added;; 6/6/25: 0%->35; 12/9/25: 35%->70; 29/9/25: WID:SP-250381->SP-251042 | 23.700-51 | 107 | 54 |  |  | Wed 05/03/25 | Mon 29/09/25
166 | 1070027 | Study on SEAL data delivery Phase 3 | FS_SEALDD_Ph3 | 1 | Rel-20 | S6 | 2025-03-26 08:00 | 2026-03-03 17:00 | 40% | SP-251217 |  | Ge, Cuili, Huawei | gecuili@huawei.com | 3/4/25: 23.700-52 added;; 6/6/25: 0%->30; 12/9/25: 30%->40; 29/9/25: FCD:Fri 12/12/->/26; 29/9/25: WID:SP-250382->SP-251217 | 23.700-52 | 107 | 54 |  |  | Wed 05/03/25 | Mon 29/09/25
167 | 1070028 | Study on Stage 2 for MMTel Phase 2 | FS_MMTel_Ph2_APP | 1 | Rel-20 | S6 | 2025-03-26 08:00 | 2026-03-03 17:00 | 40% | SP-250383 |  | Liu, Yue, China Mobile | liuyueyjy@chinamobile.com | 3/4/25: 23.700-57 added;; 6/6/25: 0%->30; 12/9/25: 30%->40 | 23.700-57 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
168 | 1070030 | Stage 2 for Mission Critical Services for UE-to-UE and UE-to-Network over multi-hop relay | MultiHop-MC | 1 | Rel-20 | S6 | 2025-03-26 08:00 | 2026-03-03 17:00 | 0% | SP-250389 |  | Lipford, Mark, FirstNet Authority | mark.lipford@firstnet.gov | ; 6/6/25: 0%->75; 12/9/25: 0%->75 | 23.289 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
169 | 1070032 | Stage 2 for Enhanced Mission Critical Services Architecture Phase 2 | enhMC_Ph2-MC | 1 | Rel-20 | S6 | 2025-03-26 08:00 | 2026-06-06 17:00 | 30% | SP-250391 |  | Negalaguli, Harish, Motorola Solutions | harish.negalaguli@motorolasolutions.com | ; 6/6/25: 0%->15; 12/9/25: 15%->30 | 23.280; 23.379; 23.281; 23.282; 23.283; 23.289 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
170 | 1050108 | Combined QoS configuration and monitoring | CombQoS | 1 | Rel-20 | S1 | 2024-09-04 08:00 | 2024-09-09 17:00 | 100% | SP-241150 |  | Yansheng Liu, ZTE | liu.yansheng@zte.com.cn |  | 22.261 | 105 | 53 |  |  | Wed 04/09/24 | NA
171 | 1050109 | Legacy Residential Gateway Supporting 5G LAN-type Service | LegacyRG_5GLAN | 1 | Rel-20 | S1 | 2024-09-04 08:00 | 2024-09-09 17:00 | 100% | SP-241151 |  | Yuying Zhang, China Telecom | zhangyy45@chinatelecom.cn |  | 22.261 | 105 | 53 |  |  | Wed 04/09/24 | NA
172 | 1050111 | Exposure for Virtual Network information and capability | VNExposure | 1 | Rel-20 | S1 | 2024-09-04 08:00 | 2024-09-09 17:00 | 100% | SP-241153 |  | Pengtai Qin, China Mobile | qinpengtai@chinamobile.com |  | 22.261 | 105 | 53 |  |  | Wed 04/09/24 | NA
173 | 0 | Rel-20 Miscellaneous OAM&Charging | - | 1 | Rel-20 |  | 2024-04-02 08:00 | 2026-06-06 17:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
174 | 1080006 | Study on intent driven management services for mobile network phase 4 | FS_IDMS_MN_Ph4 | 1 | Rel-20 | S5 | 2025-06-05 08:00 | 2026-03-03 17:00 | 15% | SP-250861 |  | Ruiyue Xu (Huawei), | xuruiyue@huawei.com | 18/7/25: 28.881 added;; 12/9/25: 0%->15 | 28.881 | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
175 | 1080007 | Study on Management Data Analytics (MDA) phase 4 | FS_eMDAS_Ph4 | 1 | Rel-20 | S5 | 2025-06-05 08:00 | 2026-03-03 17:00 | 15% | SP-250862 |  | Brendan T Hassett (Huawei), | brendan.t.hassett@huawei.com | 18/7/25: 28.886 added;; 12/9/25: 0%->15 | 28.886 | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
176 | 1080008 | Study on Service Based Management Architecture enhancement phase 4 | FS_SBMA_Ph4 | 1 | Rel-20 | S5 | 2025-06-05 08:00 | 2026-03-03 17:00 | 0% | SP-250863 |  | Kai Zhang (Huawei), | kai.zhangkai@huawei.com | 18/7/25: 28.884 added; | 28.884 | 108 | 55 |  |  | Thu 05/06/25 | Fri 18/07/25
177 | 1080009 | Study on Enhanced exposure of management services | FS_EnExpo | 1 | Rel-20 | S5 | 2025-06-05 08:00 | 2026-03-03 17:00 | 0% | SP-250864 |  | Winnie Nakimuli (Nokia) | winnie.nakimuli@nokia.com | 18/7/25: 28.888 added; | 28.888 | 108 | 55 |  |  | Thu 05/06/25 | Fri 18/07/25
178 | 1080010 | Study for Data management phase 3 | FS_MADCOL_Ph3 | 1 | Rel-20 | S5 | 2025-06-05 08:00 | 2026-03-03 17:00 | 2% | SP-250865 |  | Sreekumar PK (Nokia), | sreekumar.pk@nokia.com | 18/7/25: 28.887 added;; 12/9/25: 0%->2 | 28.887 | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
179 | 1080011 | Study on management aspects of Network Digital Twins phase 2 | FS_NDT_Ph2 | 1 | Rel-20 | S5 | 2025-06-05 08:00 | 2026-03-03 17:00 | 0% | SP-250866 |  | Xian Zhao (Huawei), | zhaoxian7@huawei.com | 18/7/25: 28.883 added; | 28.883 | 108 | 55 |  |  | Thu 05/06/25 | Fri 18/07/25
180 | 1080013 | Study on Closed Control Loop Management phase 2 | FS_CCLM_Ph2 | 1 | Rel-20 | S5 | 2025-06-05 08:00 | 2026-03-03 17:00 | 0% | SP-250868 |  | Deepanshu Gautam (Samsung), | deepanshu.g@samsung.com | 18/7/25: 28.889 added; | 28.889 | 108 | 55 |  |  | Thu 05/06/25 | Fri 18/07/25
181 | 1080015 | 5G performance measurements/KPIs and Trace/MDT/QoE | PM_KPI_Trace_MDT_QoE-OAM | 1 | Rel-20 | S5 | 2025-06-05 08:00 | 2026-09-09 17:00 | 5% | SP-250879 |  | XiuMin Chen (China Telecom), | chenxiumin@chinatelecom.cn | ; 12/9/25: 0%->5 | 28.552; 28.554; 28.532; 28.558; 32.404; 32.421; 32.422; 32.423; 28.404; 28.405; 28.406; 28.622; 28.623; 28.541 | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
182 | 1080017 | Management Aspects related to NWDAF phase 3 | NWDAF_Ph3-OAM | 1 | Rel-20 | S5 | 2025-06-05 08:00 | 2026-06-06 17:00 | 30% | SP-251026 |  | Song Zhao (China Telecom), | zhaosong1@chinatelecom.cn | ; 12/9/25: 0%->30; 29/9/25: WID:SP-250881->SP- 251026 | 28.541; 28.552; 28.554 | 108 | 55 |  |  | Thu 05/06/25 | Mon 29/09/25
183 | 1080018 | 5G Advanced NRM features phase 4 | AdNRM_Ph4-OAM | 1 | Rel-20 | S5 | 2025-06-05 08:00 | 2026-12-12 17:00 | 10% | SP-251024 |  | Sean Sun (Nokia) | sean.sun@nokia-sbell.com | ; 12/9/25: 0%->10; 29/9/25: WID:SP-250882->SP- 251024 | 28.540; 28.541; 28.622; 28.623; 32.160 | 108 | 55 |  |  | Thu 05/06/25 | Mon 29/09/25
184 | 1090010 | Study on 5GA roaming charging reliability enhancement | FS_RoamRE_CH | 1 | Rel-20 | S5 | 2025-09-10 08:00 | 2026-03-03 17:00 | 0% | SP-251203 |  | Wang Han (Huawei) | wanghan28@huawei.com |  |  | 109 | 55 |  |  | Wed 10/09/25 | NA
185 | 1090011 | Study on Unified Management interface for Multi-RAT support | FS_UMMR_OAM | 1 | Rel-20 | S5 | 2025-09-10 08:00 | 2026-09-09 17:00 | 0% | SP-251204 |  | Veronica Gonzalez, Vodafone | veronica.gonzalez2@vodafone.com |  |  | 109 | 55 |  |  | Wed 10/09/25 | NA
186 | 1020010 | Study on Cloud Aspects of Management and Orchestration | FS_Cloud_OAM | 1 | Rel-20 | S5 | 2024-01-03 08:00 | 2025-09-09 17:00 | 95% | SP-241566 |  | Guangjing Cao (CMCC) | caoguangjing@chinamobile.com | 14/3/24: 0%->2; 13/6/24: 2%->40; 4/9/24: 40%->80; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 80%->90; 8/1/25: WID:SP-231781->SP-241566 (rapp changed); 6/3/25: 90%->85; 6/3/25: FCD:30/08/2024->/25; 6/6/25: 85%->90; 12/9/25: 90%->95. Rel-19->Rel-20 |  | 102 | 52 |  |  | Thu 07/12/23 | Fri 12/09/25
187 | 1089999 | (Small) Technical Enhancements and Improvements for Rel-20 | TEI20 | 1 | Rel-20 |  | 2025-06-05 08:00 | 2026-12-12 17:00 | 0% | [6 empty] | 92 | 47 |  |  | Mon 15/06/15 | Mon 15/06/15
188 | 1040011 | Lawful Interception Rel-20 | LI20 | 1 | Rel-20 | S3LI | 2025-03-06 08:00 | 2027-03-03 17:00 | 0% | SP-250447 |  | Koen Jaspers, PIDS, | k.b.jaspers@minjenv.nl | ; 26/3/25: WID:SP-241012->SP-250388; 27/6/25: WID:SP-250388->SP-250447 | 33.107; 33.108; 33.126; 33.127; 33.128; 33.928 ; 33.129 | 104 | 53 |  |  | Wed 12/06/24 | Fri 27/06/25
189 | 0 | --- RELEASE 19 --- | - | 1 | Rel-19 |  | 2019-03-07 07:00 | 2019-03-07 07:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
190 | 0 | Rel-19 Energy Efficiency, Energy Saving | - | 1 | Rel-19 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
191 | 1020060 | Energy Efficiency as Service Criteria | EnergyServ | 1 | Rel-19 |  | 2022-06-02 08:00 | 2025-09-09 17:00 | 99% | SP-230520 |  | Xiaonan Shi, CMCC | shixiaonan@chinamobile.com | ; 6/9/23: 0%->75; 8/12/23: 75%->100 | 22.261 | 100 | 51 |  |  | Thu 08/06/23 | Fri 08/12/23
192 | 960019 | Study on Energy Efficiency as service criteria | FS_EnergyServ | 2 | Rel-19 | S1 | 2022-06-02 08:00 | 2023-09-09 17:00 | 100% | SP-230235 |  | Xiaonan Shi, CMCC | shixiaonan@chinamobile.com | 13/7/22: 22.882 added;; 9/9/22: 0%->10; 10/12/22: FCD:10/03/2023->06/23; 10/12/22: 10%->40; 16/3/23: WID:SP-220446->SP-230235; 17/3/23: 40%->70; 8/6/23: 70%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->95; 8/12/23: 95%->100 | 22.882 | 96 | 49 |  |  | Thu 02/06/22 | Fri 08/12/23
193 | 1000033 | Stage 1 of Energy Efficiency as Service Criteria | EnergyServ | 2 | Rel-19 | S1 | 2023-06-08 08:00 | 2023-12-12 17:00 | 100% | SP-230520 |  | Xiaonan Shi, CMCC | shixiaonan@chinamobile.com | ; 6/9/23: 0%->75; 8/12/23: 75%->100 | 22.261 | 100 | 51 |  |  | Thu 08/06/23 | Fri 08/12/23
194 | 1040018 | Charging Aspects for Energy Efficiency of Network Slice | EnergySys_CH | 2 | Rel-19 | S5 | 2024-06-12 08:00 | 2025-06-06 17:00 | 100% | SP-250124 |  | YiMeng, DENG, Huawei, | dengyimeng@huawei.com | ; 4/9/24: 0%->45; 6/3/25: 45%->100; 26/3/25: WID:SP-241003->SP-250124; 26/3/25: FCD:12/12/2024->6/6/25. Name changed from "Charging Aspects for Energy Efficiency of 5G" | 32.240; 28.201; 28.202; 32.291; 32.298 | 104 | 53 |  |  | Wed 12/06/24 | Wed 26/03/25
195 | 1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | 2 | Rel-19 | S2 | 2023-09-09 08:00 | 2024-06-06 17:00 | 100% | SP-231391 |  | Jungshin Park (Samsung) | shin02.park@samsung.com | 9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-66 added;; 8/12/23: 0%->15; 4/1/24: 28.880 added;; 14/3/24: 15%->55; 13/6/24: 55%->100; 4/9/24: 99%->100 | SP-231192; 23.700-66; 28.880 | 101 | 51 |  |  | Wed 20/09/23 | Wed 04/09/24
196 | 1050112 | Energy Efficiency and Energy Saving | EnergySys | 2 | Rel-19 | S2 | 2024-09-04 08:00 | 2024-12-12 17:00 | 100% | SP-250069 |  | Primary Rapporteur: Jungshin Park (Samsung) | shin02.park@samsung.com | ; 5/12/24: 0%->70; 6/3/25: 70%->100; 26/3/25: WID:SP-241388->SP-250069 | 23.501; 23.502; 23.503 | 105 | 53 |  |  | Wed 04/09/24 | Wed 26/03/25
197 | 1070002 | CT aspects of energy efficiency and energy saving | EnergySys | 2 | Rel-19 |  | 2025-03-03 08:00 | 2025-09-09 17:00 | 93% | CP-250247 |  | Suh, Kyungjoo(Grace), Samsung | joo.suh@samsung.com |  | 29.508,29.513,29.522,29.122,29.519,29.510,29.503,29.504,29.518 | 105 | 53 |  |  | Wed 04/09/24 | Thu 05/12/24
198 | 1070034 | CT3 aspects of energy efficiency and energy saving | EnergySys | 3 | Rel-19 | C3 | 2025-03-03 08:00 | 2025-09-09 17:00 | 90% | CP-250247 |  | Suh, Kyungjoo(Grace), Samsung | joo.suh@samsung.com |  | 29.508,29.513,29.522,29.122,29.519,29.510,29.503,29.504,29.518 | 105 | 53 |  |  | Wed 04/09/24 | Thu 05/12/24
199 | 1070035 | CT4 aspects of energy efficiency and energy saving | EnergySys | 3 | Rel-19 | C4 | 2025-03-03 08:00 | 2025-09-09 17:00 | 95% | CP-250247 |  | Suh, Kyungjoo(Grace), Samsung | joo.suh@samsung.com |  | 29.508,29.513,29.522,29.122,29.519,29.510,29.503,29.504,29.518 | 105 | 53 |  |  | Wed 04/09/24 | Thu 05/12/24
200 | 1020021 | Study on energy efficiency and energy saving aspects of 5G networks and services | FS_Energy_OAM_Ph3 | 2 | Rel-19 | S5 | 2023-12-08 08:00 | 2024-12-12 17:00 | 100% | SP-241568 |  | Jean-Michel Cornily (Huawei) | jean.michel.cornily@huawei.com | 4/1/24: 28.866 added;; 14/3/24: 0%->10; 13/6/24: 10%->25; 4/9/24: 25%->60; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 60%->100; 8/1/25: WID:SP-231723->SP-241568 | 28.866 | 102 | 52 |  |  | Thu 07/12/23 | Wed 08/01/25
201 | 1030038 | Study on security aspects of energy saving in 5G | FS_Energy_Sec | 2 | Rel-19 | S3 | 2024-04-02 08:00 | 2024-12-12 17:00 | 100% | SP-240512 |  | Bo Bjerrum | bo.bjerrum@nokia.com | 3/4/24: 33.766 added;; 13/6/24: 0%->30; 5/9/24: 30%->70; 5/12/24: 70%->90; 6/3/25: 90%->100; 5/6/25: 100%->100 | 33.766 | 103 | 52 |  |  | Thu 14/03/24 | Thu 05/06/25
202 | 1060007 | Energy efficiency and energy saving aspects of 5G networks and services | Energy_OAM_Ph3 | 2 | Rel-19 | S5 | 2025-03-01 16:00 | 2025-09-09 17:00 | 100% | SP-251274 |  | Jean-Michel Cornily (Huawei) | jean.michel.cornily@huawei.com | ; 6/3/25: 0%->20; 6/6/25: 20%->70; 12/9/25: 70%->100; 29/9/25: WID:SP-241940->SP- 251274 | 28.310; 28.622; 28.623; 28.541; 28.554; 28.104 | 106 | 54 |  |  | Thu 05/12/24 | Mon 29/09/25
203 | 1020095 | Enhancements of Network energy savings for NR | Netw_Energy_NR_enh | 1 | Rel-19 |  | 2023-12-13 08:00 | 2025-03-03 17:00 | 60% | RP-252332 |  | Ericsson |  | 2/4/24: WID:RP-234065->RP-240170; 23/7/24: WID:RP-240170->RP-241650; 26/9/24: WID:RP-241650->RP-242354; 3/4/25: WID:RP-242354->RP-250343; 18/7/25: WID:RP-250343->RP-251678; 29/9/25: WID:RP-251678->RP-252332 |  | 102 | 52 |  |  | Tue 02/01/24 | Mon 29/09/25
204 | 1021095 | Core part: Enhancements of Network energy savings for NR | Netw_Energy_NR_enh-Core | 2 | Rel-19 | R1 | 2023-12-13 08:00 | 2025-09-09 17:00 | 100% | RP-252332 | RP-252331 | Ajit Nimbalker, Ericsson | Ajit.Nimbalker@ericsson.com | 14/3/24: Compl:0%->5%; Stat Rep: ->RP-240169; Rapporteur: Ericsson->Ajit Nimbalker, Ericsson; Rap eMail: ->Ajit.Nimbalker@ericsson.com; ; 13/6/24: Compl:5%->25%; Stat Rep: RP-240169->RP-241182; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:25%->35%; Stat Re |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
205 | 1022095 | Perf. part: Enhancements of Network energy savings for NR | Netw_Energy_NR_enh-Perf | 2 | Rel-19 | R4 | 2024-08-18 16:00 | 2026-03-03 17:00 | 15% | RP-252332 | RP-252331 | Ajit Nimbalker, Ericsson | Ajit.Nimbalker@ericsson.com | 14/3/24: Stat Rep: ->RP-240169; Rapporteur: Ericsson->Ajit Nimbalker, Ericsson; Rap eMail: ->Ajit.Nimbalker@ericsson.com; ; 13/6/24: Stat Rep: RP-240169->RP-241182; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241182->RP-241866; ; 6/12/24: FCD:03/03 |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
206 | 1030004 | Study on Media enerGy consumption exposuRE and EvaluatioN framework | FS_MediaEnergyGREEN | 1 | Rel-19 | S4 | 2024-04-02 08:00 | 2025-03-03 17:00 | 100% | SP-240481 |  | Julien Lemotheux, Orange, | julien.lemotheux@orange.com | 14/5/24: 26.942 added;; 13/6/24: 0%->15; 4/9/24: 15%->30; 5/12/24: 30%->60; 6/3/25: 60%->100 | 26.942 | 103 | 52 |  |  | Wed 13/03/24 | Thu 06/03/25
207 | 1020094 | Low-power wake-up signal and receiver for NR (LP-WUS/WUR) | NR_LPWUS | 1 | Rel-19 |  | 2023-12-13 08:00 | 2025-03-03 17:00 | 65% | RP-251200 |  | vivo |  | 2/4/24: WID:RP-234056->RP-240801; 26/9/24: WID:RP-240801->RP-241824; 26/9/24: 38.774 added;; 18/7/25: WID:RP-241824->RP-251200 | 38.774 | 102 | 52 |  |  | Tue 02/01/24 | Fri 18/07/25
208 | 1021094 | Core part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) | NR_LPWUS-Core | 2 | Rel-19 | R1 | 2023-12-13 08:00 | 2025-09-09 17:00 | 100% | RP-251200 | RP-252008 | Xueming Pan, vivo | panxueming@vivo.com | 14/3/24: Compl:0%->8%; Stat Rep: ->RP-240134; Rapporteur: vivo->Xueming Pan, vivo; Rap eMail: ->panxueming@vivo.com; ; 13/6/24: Compl:8%->20%; Stat Rep: RP-240134->RP-241039; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:20%->30%; Stat Rep: RP-241039->RP-24 |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
209 | 1022094 | Perf. part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) | NR_LPWUS-Perf | 2 | Rel-19 | R4 | 2024-08-18 16:00 | 2026-03-03 17:00 | 25% | RP-251200 | RP-252008 | Xueming Pan, vivo | panxueming@vivo.com | 14/3/24: Stat Rep: ->RP-240134; Rapporteur: vivo->Xueming Pan, vivo; Rap eMail: ->panxueming@vivo.com; ; 13/6/24: Stat Rep: RP-240134->RP-241039; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241039->RP-241822; ; 6/12/24: FCD:03/03/2025->03/03/2026; |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
210 | 0 | Rel-19 Artificial Intelligence (AI)/Machine Learning (ML) | - | 1 | Rel-19 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
211 | 1060078 | Study on Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface Phase 2 | FS_NR_AIML_air_Ph2 | 1 | Rel-19 | R1 | 2024-10-14 14:00 | 2025-09-09 17:00 | 100% | RP-250308 | RP-252444 | Qualcomm |  | 6/3/25: FCD:07/09/2025->09/09/2025; Compl:0%->50%; Stat Rep: ->RP-250307; ; 3/4/25: WID:RP-243245->RP-250308; 6/6/25: Compl:50%->90%; Stat Rep: RP-250307->RP-251184; ; 11/9/25: Compl:90%->100%; Stat Rep: RP-251184->RP-252444; |  | 106 | 54 |  |  | Fri 24/01/25 | Thu 11/09/25
212 | 1040084 | Study on 3GPP AI/ML Consistency Alignment | FS_AIML_CAL | 1 | Rel-19 | SP | 2024-10-06 12:00 | 2025-12-12 17:00 | 0% | SP-250745 |  | Johannes Achter, Magenta |  | 26/9/24: WID:SP-240970->SP-241368; 27/6/25: WID:SP-241368->SP-250745; 27/6/25: FCD:Fri 06/06/->12/25 |  | 104 | 53 |  |  | Thu 20/06/24 | Fri 27/06/25
213 | 950008 | Study on AI/ML Model Transfer Phase2 | FS_AIML_MT_Ph2 | 1 | Rel-19 | S1 | 2022-03-10 08:00 | 2023-09-09 17:00 | 100% | SP-220439 |  | Yang Xu, OPPO | xuyang@oppo.com | 5/4/22: 22.875 added;; 4/6/22: 0%->15; 21/6/22: WID:SP-220083->SP-220439. FS_AIML_Ph2->FS_AIML_MT_Ph2; 13/7/22: 22.876 added;; 10/12/22: 15%->50; 10/12/22: FCD:12/12/2022->06/23; 17/3/23: 50%->75; 8/6/23: 75%->95; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 95 | 22.875; 22.876 | 95 | 48 |  |  | Thu 10/03/22 | Wed 06/09/23
214 | 950011 | Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media | FS_AI4Media | 1 | Rel-19 | S4 | 2022-03-12 08:00 | 2025-06-06 17:00 | 100% | SP-220328 |  | Eric Yip, Samsung | eric.yip@samsung.com | 5/4/22: 26.927 added;; 4/6/22: 0%->10; 12/9/22: 10%->15; 12/9/22: FCD:12/03/2022->12/23; 11/12/22: 15%->20; 17/3/23: 20%->25; 8/6/23: 25%->35; 8/6/23: FCD:12/12/2023->/24; 7/9/23: 35%->40; 21/9/23: 26.847 added;; 8/12/23: 40%->50; 14/3/24: 50%->60; 14/... | 26.927; 26.847 | 95 | 48 |  |  | Thu 10/03/22 | Thu 05/06/25
215 | 1000030 | AI/ML Model Transfer Phase 2 | AIML_MT_Ph2 | 1 | Rel-19 | S1 | 2023-06-08 08:00 | 2023-12-12 17:00 | 100% | SP-230514 |  | Yang Xu, OPPO | xuyang<at>oppo.com | ; 6/9/23: 0%->80; 8/12/23: 80%->100 | 22.261 | 100 | 51 |  |  | Thu 08/06/23 | Fri 08/12/23
216 | 1050047 | Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | 1 | Rel-19 |  | 2024-06-12 08:00 | 2025-09-09 17:00 | 93% | SP-240991 |  | Xiaobo Wu, vivo | (xiaobo.wu@vivo.com) |  | 23.288; 23.501; 23.502; 23.503; 23.273 | 105 | 53 |  |  | Wed 12/06/24 | NA
217 | 1040033 | Stage 2 of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | 2 | Rel-19 | S2 | 2024-06-12 08:00 | 2024-10-17 12:00 | 99% | SP-240991 |  | Xiaobo Wu, vivo | (xiaobo.wu@vivo.com) | ; 4/9/24: 0%->15; 5/12/24: 15%->85; 6/3/25: 85%->98; 5/6/25: 98%->99; 12/9/25: 99%->99 | 23.288; 23.501; 23.502; 23.503; 23.273 | 104 | 53 |  |  | Wed 12/06/24 | Fri 12/09/25
218 | 1050014 | CT aspects of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 90% | CP-251283 |  | Yizhong ZHANG, vivo | yizhong.zhang@vivo.com |  | 29.508,29.513,29.520,29.522,29.552,29.574,29.575,29.576,29.591,24.080,29.503,29.510,29.518,29.572 | 105 | 53 |  |  | Wed 12/06/24 | NA
219 | 1050048 | CT3 aspects of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2025-09-09 17:00 | 85% | CP-251283 |  | Yizhong ZHANG, vivo | yizhong.zhang@vivo.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
220 | 1050049 | CT4 aspects of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | AIML_CN | 3 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-09-09 17:00 | 95% | CP-251283 |  | Yizhong ZHANG, vivo | yizhong.zhang@vivo.com | ; 26/3/25: 29.570 added; | 29.570 | 105 | 53 |  |  | Wed 12/06/24 | Wed 26/03/25
221 | 1060059 | Security aspects of Core Network Enhanced Support for AIML | AIML_CN_SEC | 2 | Rel-19 | S3 | 2024-12-05 08:00 | 2025-06-06 17:00 | 100% | SP-241957 |  | Chang Liu, China Mobile | liuchangyjy@chinamobile.com | ; 6/3/25: 0%->80; 5/6/25: 80%->100 | 33.501 | 106 | 54 |  |  | Thu 05/12/24 | Thu 05/06/25
222 | 1050044 | Application enablement for AI/ML services | AIML_App | 1 | Rel-19 |  | 2024-07-16 08:00 | 2025-09-09 17:00 | 80% | SP-241008 |  | Pateromichelakis, Emmanouil (Manos), | epateromiche@lenovo.com |  | 23.436; 23.434; 23.558 | 105 | 53 |  |  | Wed 12/06/24 | NA
223 | 1040075 | Stage 2 of Application enablement for AI/ML services | AIML_App | 2 | Rel-19 | S6 | 2024-07-16 08:00 | 2024-12-12 17:00 | 100% | SP-241008 |  | Pateromichelakis, Emmanouil (Manos), | epateromiche@lenovo.com | ; 4/9/24: 0%->40; 26/9/24: 23.482 added;; 5/12/24: 40%->100 | 23.436; 23.434; 23.558 ; 23.482 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/12/24
224 | 1050024 | CT aspects of Application enablement for AI/ML services | AIML_App | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 78% | CP-243310 |  | Atarius, Roozbeh (Lenovo) | ratarius@motorola.com |  | 24.559, 29.549, 29.558, 24.559, 29.549, 29.558 | 105 | 53 |  |  | Wed 12/06/24 | NA
225 | 1050045 | CT1 aspects of Application enablement for AI/ML services | AIML_App | 3 | Rel-19 | C1 | 2024-09-09 08:00 | 2025-09-09 17:00 | 75% | CP-243310 |  | Atarius, Roozbeh (Lenovo) | ratarius@motorola.com | ; 26/9/24: 24.560 added; |  | 105 | 53 |  |  | Wed 12/06/24 | Thu 26/09/24
226 | 1050046 | CT3 aspects of Application enablement for AI/ML services | AIML_App | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2025-09-09 17:00 | 80% | CP-243310 |  | Atarius, Roozbeh (Lenovo) | ratarius@motorola.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
227 | 1060011 | AI/ML Management Phase 2 | AIML_MGT_Ph2 | 1 | Rel-19 | S5 | 2025-03-01 16:00 | 2025-09-09 17:00 | 100% | SP-251197 |  | Hassan Al-Kanani (NEC) | Hassan.Alkanani@EMEA.NEC.COM | ; 6/3/25: 0%->15; 6/6/25: 15%->52; 12/9/25: 52%->100; 12/9/25: 100%->; 29/9/25: WID:SP-241944->SP- 251197 | 28.105; 28.552; 28.554; 28.541 | 106 | 54 |  |  | Thu 05/12/24 | Mon 29/09/25
228 | 1020068 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | FS_AIML_CN | 1 | Rel-19 | S2 | 2024-01-04 08:00 | 2024-06-06 17:00 | 100% | SP-241936 |  | Xiaobo Wu, vivo | xiaobo.wu@vivo.com) | 14/3/24: 0%->25; 13/6/24: 25%->100; 26/9/24: WID:SP-231800->SP-241383; 8/1/25: WID:SP-241383->SP-241936; 6/3/25: 100%->100 |  | 102 | 52 |  |  | Wed 03/01/24 | Thu 06/03/25
229 | 1030035 | Study on security aspects of Core Network Enhanced Support for AIML | FS_AIML_CN_SEC | 1 | Rel-19 | S3 | 2024-04-02 08:00 | 2024-12-12 17:00 | 100% | SP-240509 |  | Chang Liu, | liuchangyjy@chinamobile.com | 3/4/24: 33.784 added;; 13/6/24: 0%->35; 5/9/24: 35%->60; 5/12/24: 60%->100; 6/3/25: 100%->100; 5/6/25: 100%->100 | 33.784 | 103 | 52 |  |  | Thu 14/03/24 | Thu 05/06/25
230 | 1020007 | Study on AI/ML management - phase 2 | FS_AIML_MGT_Ph2 | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-241567 |  | Yizhi Yao (Intel) | yizhi.yao@intel.com | 13/6/24: 0%->19; 16/7/24: WID:SP-231780->SP-240965; 4/9/24: 19%->55; 4/9/24: FCD:09/09/2024->12/24; 26/9/24: 28.858 added;; 5/12/24: 55%->100; 8/1/25: WID:SP-240965->SP-241567; 6/6/25: 100%->100 | 28.858 | 102 | 52 |  |  | Thu 07/12/23 | Fri 06/06/25
231 | 1010005 | Study on application layer support for AI/ML services | FS_AIMLAPP | 1 | Rel-19 | S6 | 2023-09-07 08:00 | 2024-09-09 17:00 | 100% | SP-231182 |  | Pateromichelakis, Emmanouil (Manos) | epateromiche@lenovo.com | 8/12/23: 0%->35; 4/1/24: 23.700-82 added;; 14/3/24: 35%->55; 13/6/24: 55%->95; 4/9/24: 95%->100 | 23.700-82 | 101 | 51 |  |  | Thu 07/09/23 | Wed 04/09/24
232 | 1020083 | Study on enhancements for Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN | FS_NR_AIML_NGRAN_enh | 1 | Rel-19 | R3 | 2023-12-13 08:00 | 2024-09-09 17:00 | 100% | RP-240323 | RP-241791 | ZTE |  | 14/3/24: FCD:06/06/2024->/24; 2/4/24: WID:RP-234054->RP-240323; 3/4/24: 38.743 added;; 13/6/24: Compl:0%->80%; Stat Rep: ->RP-241097; ; 4/9/24: FCD:09/09/2024->24/09/2024; Compl:80%->100%; Stat Rep: RP-241097->RP-241791; | 38.743 | 102 | 52 |  |  | Tue 02/01/24 | Wed 04/09/24
233 | 1020084 | Study on Artificial Intelligence (AI)/Machine Learning (ML) for mobility in NR | FS_NR_AIML_Mob | 1 | Rel-19 | R2 | 2019-03-07 08:00 | 2025-09-09 17:00 | 100% | RP-242393 | RP-251965 | Zhongda Du, OPPO | duzhongda@oppo.com | 14/3/24: FCD:28/05/2021->12/12/2024; Stat Rep: ->RP-240083; Rapporteur: Oppo->Zhongda Du, OPPO; Rap eMail: ->duzhongda@oppo.com; ; 2/4/24: WID:RP-234055->RP-240082; 3/4/24: 38.744 added;; 4/9/24: FCD:12/12/2024->25/09/2024; Compl:0%->38%; Stat Rep: RP-... | 38.744 | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
234 | 1020093 | Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface | NR_AIML_air | 1 | Rel-19 |  | 2023-12-13 08:00 | 2025-03-03 17:00 | 62% | RP-252930 |  | Qualcomm |  | 2/4/24: WID:RP-234039->RP-240774; 26/9/24: WID:RP-240774->RP-242399; 24/1/25: WID:RP-242399->RP-243244; 12/9/25: WID:RP-243244->RP-251186; 29/9/25: WID:RP-251186->RP-252930 |  | 102 | 52 |  |  | Tue 02/01/24 | Mon 29/09/25
235 | 1021093 | Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface | NR_AIML_air-Core | 2 | Rel-19 | R1 | 2023-12-13 08:00 | 2025-12-12 17:00 | 90% | RP-252930 | RP-252447 | Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson | juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsson.com | 14/3/24: Compl:0%->5%; Stat Rep: ->RP-240499; Rapporteur: Qualcomm->Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson; Rap eMail: ->juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsso... |  | 102 | 52 |  |  | Tue 02/01/24 | Tue 30/09/25
236 | 1022093 | Perf. part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface | NR_AIML_air-Perf | 2 | Rel-19 | R4 | 2024-08-18 16:00 | 2026-03-03 17:00 | 25% | RP-252930 | RP-252447 | Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson | juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsson.com | 14/3/24: Stat Rep: ->RP-240499; Rapporteur: Qualcomm->Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson; Rap eMail: ->juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsson.com; ; 13/6/... |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
237 | 1050124 | Enhancements for Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN | NR_AIML_NGRAN_enh | 1 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | RP-251245 |  | ZTE |  | 3/4/25: WID:RP-242385->RP-250326; 18/7/25: WID:RP-250326->RP-251245 |  | 105 | 53 |  |  | Thu 26/09/24 | Fri 18/07/25
238 | 1051124 | Core part: Enhancements for Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN | NR_AIML_NGRAN_enh-Core | 2 | Rel-19 | R3 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | RP-251245 | RP-252150 | ZTE |  | 6/12/24: Compl:0%->30%; Stat Rep: ->RP-242503; ; 6/3/25: FCD:20/05/2025->09/09/2025; Compl:30%->50%; Stat Rep: RP-242503->RP-250327; ; 6/6/25: Compl:50%->80%; Stat Rep: RP-250327->RP-251246; ; 11/9/25: Compl:80%->100%; Stat Rep: RP-251246->RP-252150; |  | 105 | 53 |  |  | Thu 26/09/24 | Thu 11/09/25
239 | 0 | Rel-19 Ambient power-enabled Internet of Things | - | 1 | Rel-19 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
240 | 1020055 | Ambient power-enabled Internet of Things | AmbientIoT | 1 | Rel-19 |  | 2022-03-10 08:00 | 2025-10-23 17:00 | 89% | SP-231403 |  | Xu, Weijie, OPPO | xuweijie@oppo.com | ; 8/12/23: 0%->95; 29/9/25: FCD:Tue 09/09/25->Thu 23/10/25; Compl:97%->89%; | 22.261 | 102 | 52 |  |  | Thu 07/12/23 | Mon 29/09/25
241 | 950004 | Study on Ambient power-enabled Internet of Things | FS_AmbientIoT | 2 | Rel-19 | S1 | 2022-03-10 08:00 | 2023-05-28 09:00 | 89% | SP-220085 |  | Rapporteur:Xu, weijie, OPPO | xuweijie@oppo.com | 5/4/22: 22.840 added;; 4/6/22: 0%->25; 9/9/22: 25%->50; 10/12/22: 50%->65; 17/3/23: 65%->80; 17/3/23: FCD:12/12/2022->/23; 8/6/23: 80%->90; 8/6/23: FCD:03/03/2023->12/20; 6/9/23: 90%->95; 8/12/23: 95%->100 | 22.840 | 95 | 48 |  |  | Thu 10/03/22 | Fri 08/12/23
242 | 1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | 2 | Rel-19 | S2 | 2024-01-04 08:00 | 2024-08-30 15:00 | 89% | SP-240969 |  | Runze Zhou (Huawei) | zhourunze@huawei.com | 14/3/24: 0%->25; 13/6/24: 25%->65; 16/7/24: WID:SP-231803->SP-240969; 4/9/24: 65%->80; 5/12/24: 80%->90; 6/3/25: 90%->100 |  | 102 | 52 |  |  | Wed 03/01/24 | Thu 06/03/25
243 | 1020030 | Stage 1 of Ambient power-enabled Internet of Things | AmbientIoT | 2 | Rel-19 | S1 | 2023-12-07 08:00 | 2023-12-12 17:00 | 89% | SP-231403 |  | Xu, Weijie, OPPO | xuweijie@oppo.com | ; 8/12/23: 0%->95; 6/3/25: 95%->100 | 22.261 | 102 | 52 |  |  | Thu 07/12/23 | Thu 06/03/25
244 | 1070010 | Architecture support of Ambient power-enabled Internet of Things | AmbientIoT-ARC | 2 | Rel-19 | S2 | 2025-03-26 08:00 | 2025-06-06 17:00 | 89% | SP-250377 |  | Runze Zhou (Huawei) | zhourunze@huawei.com | ; 5/6/25: 0%->90; 12/9/25: 90%->95 | 23.501; 23.502 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
245 | 1080021 | CT aspects of Ambient power-enabled Internet of Things | AmbientIoT-CT | 2 | Rel-19 |  | 2025-06-06 08:00 | 2025-10-23 17:00 | 89% | CP-252196 |  | Wass, Mikael, Huawei | mikael.wass@huawei.com | ; 18/7/25: 24.369 added;; 29/9/25: FCD:Tue 09/09/25->Thu 23/10/25; WID: CP-251281->CP-252196; List of Impacted TS & TR updated; | 24.007, 29.522, 23.003, 29.518, 29.504, 29.510, 29.571 | 107 | 54 |  |  | Wed 05/03/25 | Mon 29/09/25
246 | 1080030 | CT1 aspects of Ambient power-enabled Internet of Things | AmbientIoT-CT | 3 | Rel-19 | C1 | 2025-06-06 08:00 | 2025-10-23 17:00 | 75% | CP-252196 |  | Wass, Mikael, Huawei | mikael.wass@huawei.com | ; 29/9/25: FCD:Tue 09/09/25->Thu 23/10/25; WID: CP-251281->CP-252196; | 29.522, 23.003, 29.518, 29.504, 29.505, 29.510, 29.571 | 107 | 54 |  |  | Wed 05/03/25 | Mon 29/09/25
247 | 1080031 | CT3 aspects of Ambient power-enabled Internet of Things | AmbientIoT-CT | 3 | Rel-19 | C3 | 2025-06-06 08:00 | 2025-10-23 17:00 | 98% | CP-252196 |  | Wass, Mikael, Huawei | mikael.wass@huawei.com | ; 29/9/25: FCD:Tue 09/09/25->Thu 23/10/25; WID: CP-251281->CP-252196; | 29.522, 23.003, 29.518, 29.504, 29.505, 29.510, 29.571 | 107 | 54 |  |  | Wed 05/03/25 | Mon 29/09/25
248 | 1080032 | CT4 aspects of Ambient power-enabled Internet of Things | AmbientIoT-CT | 3 | Rel-19 | C4 | 2025-06-06 08:00 | 2025-10-23 17:00 | 95% | CP-252196 |  | Wass, Mikael, Huawei | mikael.wass@huawei.com | ; 18/7/25: 29.506, 29.369added;; 29/9/25: FCD:Tue 09/09/25->Thu 23/10/25; WID: CP-251281->CP-252196; | 29.522, 23.003, 29.518, 29.504, 29.505, 29.510, 29.571; 29.506; 29.369 | 107 | 54 |  |  | Wed 05/03/25 | Mon 29/09/25
249 | 1020085 | Study on solutions for Ambient IoT (Internet of Things) in NR | FS_Ambient_IoT_solutions | 1 | Rel-19 | R1 | 2023-12-13 08:00 | 2024-12-12 17:00 | 100% | RP-240826 | RP-242965 | Xiaodong Shen, CMCC | shenxiaodong@chinamobile.com | 14/3/24: Compl:0%->8%; Stat Rep: ->RP-240155; Rapporteur: CMCC->Xiaodong Shen, CMCC; Rap eMail: ->shenxiaodong@chinamobile.com; ; 2/4/24: WID:RP-234058->RP-240826; 3/4/24: 38.769 added;; 13/6/24: Compl:8%->40%; Stat Rep: RP-240155->RP-241206; ; 4/9/24: FC | 38.769 | 102 | 52 |  |  | Tue 02/01/24 | Fri 24/01/25
250 | 1030031 | Study on Security Aspect of Ambient IoT Services in 5G | FS_Ambient_IoT_Sec | 1 | Rel-19 | S3 | 2024-04-02 08:00 | 2024-12-12 17:00 | 100% | SP-240506 |  | Marcus Wong, | marcus.wong@oppo.com | 3/4/24: 33.713 added;; 13/6/24: 0%->30; 5/9/24: 30%->35; 5/12/24: 35%->55; 6/3/25: 55%->75; 6/3/25: FCD:12/12/2024->/25; 5/6/25: 75%->90; 12/9/25: 90%->100 | 33.713 | 103 | 52 |  |  | Thu 14/03/24 | Fri 12/09/25
251 | 1070018 | Charging for Ambient power-enabled Internet of Things | AmbientIoT-CH | 1 | Rel-19 | S5 | 2025-03-26 08:00 | 2025-06-06 17:00 | 100% | SP-250369 |  | YiMeng, DENG, Huawei | dengyimeng@huawei.com | ; 6/6/25: 0%->100; 12/9/25: FCD:Tue 09/09/->/25 | 32.240; 32.254; 32.291; 32.298 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
252 | 1070022 | Security Aspects of Ambient IoT Services in 5G for Isolated Private Networks | AmbientIoT-SEC | 1 | Rel-19 | S3 | 2025-03-26 08:00 | 2025-09-09 17:00 | 95% | SP-251196 |  | Marcus Wong | marcus.wong@oppo.co | 3/4/25: 33.369 added;; 5/6/25: 0%->45; 12/9/25: 45%->95; 29/9/25: WID:SP-250359->SP- 251196 | 33.369 | 107 | 54 |  |  | Wed 26/03/25 | Mon 29/09/25
253 | 1060084 | Solutions for Ambient IoT (Internet of Things) in NR | Ambient_IoT_Solutions | 1 | Rel-19 |  | 2024-05-19 08:00 | 2026-03-02 17:00 | 49% | RP-252105 |  | CMCC |  | 26/3/25: 38.391 added;; 26/3/25: 38.191 added;; 26/3/25: 38.194 added;; 26/3/25: 38.195 added;; 3/4/25: WID:RP-243326->RP-250796; 29/9/25: WID:RP-250796->RP-252105 | 38.391; 38.191; 38.194; 38.195 | 106 | 54 |  |  | Fri 24/01/25 | Mon 29/09/25
254 | 1061084 | Core part: Solutions for Ambient IoT (Internet of Things) in NR | Ambient_IoT_Solutions-Core | 2 | Rel-19 | R1 | 2024-10-14 14:00 | 2025-09-09 17:00 | 100% | RP-250796 | RP-252104 | CMCC |  | 6/3/25: FCD:07/09/2025->09/09/2025; Compl:0%->27%; Stat Rep: ->RP-250267; ; 6/6/25: Compl:27%->84%; WID: RP-250796->RP-240796; Stat Rep: RP-250267->RP-251399; ; 11/9/25: Compl:84%->100%; WID: RP-240796->RP-250796; Stat Rep: RP-251399->RP-252104; |  | 106 | 54 |  |  | Fri 24/01/25 | Thu 11/09/25
255 | 1062084 | Perf. part: Solutions for Ambient IoT (Internet of Things) in NR | Ambient_IoT_Solutions-Perf | 2 | Rel-19 | R4 | 2024-12-08 08:00 | 2026-03-03 17:00 | 11% | RP-250796 | RP-252104 | CMCC |  | 6/3/25: FCD:01/03/2026->03/03/2026; Stat Rep: ->RP-250267; ; 6/6/25: WID: RP-250796->RP-240796; Stat Rep: RP-250267->RP-251399; ; 11/9/25: Compl:0%->11%; WID: RP-240796->RP-250796; Stat Rep: RP-251399->RP-252104; |  | 106 | 54 |  |  | Fri 24/01/25 | Thu 11/09/25
256 | 0 | See also IoT_NTN_Ph3 under Satellite/NTN | - | 1 | Rel-19 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
257 | 0 | Rel-19 Internet of Things, RedCap, MTC | - | 1 | Rel-19 |  | 2019-03-07 07:00 | 2019-03-07 07:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
258 | 1040133 | NR power class 2 RedCap (Reduced Capability) UE in FR1 | NR_PC2_RedCap_UE | 1 | Rel-19 |  | 2024-06-06 08:00 | 2025-06-06 17:00 | 43% | RP-243267 |  | China Telecom |  | 26/9/24: WID:RP-241665->RP-241997; 24/1/25: WID:RP-241997->RP-243267 |  | 104 | 53 |  |  | Tue 23/07/24 | Fri 24/01/25
259 | 1041133 | Core part: NR power class 2 RedCap (Reduced Capability) UE in FR1 | NR_PC2_RedCap_UE-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-06-06 17:00 | 100% | RP-243267 | RP-251452 | China Telecom |  | 4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->20%; Stat Rep: ->RP-241998; ; 6/12/24: Compl:20%->50%; Stat Rep: RP-241998->RP-242859; ; 6/3/25: FCD:14/02/2025->06/06/2025; Compl:50%->70%; Stat Rep: RP-242859->RP-250372; ; 6/6/25: Compl:70%->100%; Stat Rep |  | 104 | 53 |  |  | Tue 23/07/24 | Fri 06/06/25
260 | 1080078 | UE Conformance - NR power class 2 RedCap (Reduced Capability) UE in FR1 | NR_PC2_RedCap_UE-UEConTest | 2 | Rel-19 | R5 | 2025-06-06 08:00 | 2026-12-12 17:00 | 5% | RP-251456 | RP-252553 | China Telecom |  | tested: REL-19 WI NR_PC2_RedCap_UE-Core ; 11/9/25: FCD:Sat 12/12/26->Thu 10/12/26; Compl:0%->5%; Stat Rep: ->RP-252553; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
261 | 1050123 | Introduction of IoT-NTN TDD mode | IoT_NTN_TDD | 1 | Rel-19 |  | 2024-09-09 08:00 | 2026-03-03 17:00 | 49% | RP-252935 |  | Iridium |  | 24/1/25: WID:RP-242415->RP-243293; 29/9/25: WID:RP-243293->RP-252935 |  | 105 | 53 |  |  | Thu 26/09/24 | Mon 29/09/25
262 | 1051123 | Core part: Introduction of IoT-NTN TDD mode | IoT_NTN_TDD-Core | 2 | Rel-19 | R1 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | RP-252935 | RP-252329 | Iridium |  | 6/12/24: Compl:0%->20%; Stat Rep: ->RP-242652; ; 6/3/25: FCD:20/05/2025->09/09/2025; Compl:20%->30%; Stat Rep: RP-242652->RP-250045; ; 6/6/25: Compl:30%->76%; Stat Rep: RP-250045->RP-251175; ; 11/9/25: Compl:76%->100%; Stat Rep: RP-251175->RP-252329; |  | 105 | 53 |  |  | Thu 26/09/24 | Thu 11/09/25
263 | 1052123 | Perf. part: Introduction of IoT-NTN TDD mode | IoT_NTN_TDD-Perf | 2 | Rel-19 | R4 | 2025-02-23 11:00 | 2026-03-03 17:00 | 0% | RP-252935 | RP-252329 | Iridium |  | 6/12/24: Stat Rep: ->RP-242652; ; 6/3/25: Stat Rep: RP-242652->RP-250045; ; 6/6/25: Stat Rep: RP-250045->RP-251175; ; 11/9/25: Stat Rep: RP-251175->RP-252329; |  | 105 | 53 |  |  | Thu 26/09/24 | Thu 11/09/25
264 | 1060008 | Management Aspects of RedCap features | NR_RedCap_OAM | 1 | Rel-19 | S5 | 2025-03-01 16:00 | 2025-09-09 17:00 | 100% | SP-241941 |  | Zhen Xing (China Unicom) | xingz12@chinaunicom.cn | ; 6/3/25: 0%->50; 6/6/25: 50%->90; 12/9/25: 90%->100 | 28.540; 28.541; 28.552; 28.554 | 106 | 54 |  |  | Thu 05/12/24 | Fri 12/09/25
265 | 0 | Rel-19 Satellite (5GSAT), NTN | - | 1 | Rel-19 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
266 | 1020058 | Satellite access Phase 3 | 5GSAT_Ph3 | 1 | Rel-19 |  | 2022-06-02 08:00 | 2025-09-09 17:00 | 99% | SP-230516 |  | Rapporteur: Thierry Bérisot, Novamint | tberisot@novamint.com | ; 6/9/23: 0%->95; 8/12/23: 95%->100 | 22.261 | 100 | 51 |  |  | Thu 08/06/23 | Fri 08/12/23
267 | 960016 | Study on satellite access - Phase 3 | FS_5GSAT_Ph3 | 2 | Rel-19 | S1 | 2022-06-02 08:00 | 2023-09-09 17:00 | 100% | SP-220679 |  | Rapporteur: Thierry Bérisot, Novamint | tberisot@novamint.com | 17/8/22: WID:SP-220443->SP-220679; 9/9/22: 0%->35; 10/12/22: 35%->55; 10/12/22: FCD:10/03/2023->06/23; 17/3/23: 55%->80; 8/6/23: 80%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->100 |  | 96 | 49 |  |  | Thu 02/06/22 | Wed 06/09/23
268 | 1000024 | Stage 1 of Satellite access Phase 3 | 5GSAT_Ph3 | 2 | Rel-19 | S1 | 2023-06-08 08:00 | 2023-12-12 17:00 | 100% | SP-230516 |  | Rapporteur: Thierry Bérisot, Novamint | tberisot@novamint.com | ; 6/9/23: 0%->95; 8/12/23: 95%->100 | 22.261 | 100 | 51 |  |  | Thu 08/06/23 | Fri 08/12/23
269 | 1010033 | Study on Integration of satellite components in the 5G architecture Phase 3 | FS_5GSAT_Ph3_ARCH | 2 | Rel-19 | S2 | 2023-09-20 08:00 | 2024-06-06 17:00 | 100% | SP-231199 |  | Jean-Yves Fine (Thales) | jean-yves.fine@thalesgroup.com | 9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-29 added;; 8/12/23: 0%->15; 4/1/24: 28.874 added;; 14/3/24: 15%->55; 13/6/24: 55%->100; 4/9/24: 99%->100 | 23.700-29; 28.874 | 101 | 51 |  |  | Wed 20/09/23 | Wed 04/09/24
270 | 1020053 | Study on application enablement for Satellite access enabled 5G Services | FS_5GSAT_Ph3_App | 2 | Rel-19 | S6 | 2024-01-03 08:00 | 2024-09-09 17:00 | 100% | SP-240296 |  | Basavaraj (Basu) Pattan, Samsung | basavarajjp@samsung.com | 8/12/23: 0%->5; 14/3/24: 0%->25; 2/4/24: WID:SP-231738->SP-240296; 3/4/24: 23.700-01 added;; 13/6/24: 25%->60; 4/9/24: 60%->100 | 23.700-01 | 102 | 52 |  |  | Thu 07/12/23 | Wed 04/09/24
271 | 1040027 | Integration of satellite components in the 5G architecture Phase 3 | 5GSAT_Ph3-ARC | 2 | Rel-19 | S2 | 2024-06-12 08:00 | 2024-12-12 17:00 | 100% | SP-241386 |  | Hucheng Wang (CATT) | wanghucheng@catt.cn | 4/9/24: 0%->15; 26/9/24: WID:SP-240986->SP-241386; 5/12/24: 15%->65; 6/3/25: 65%->100; 5/6/25: 100%->100 | 23.501; 23.502; 23.503; 23.682; 23.228; 23.401 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/06/25
272 | 1040077 | Application enablement for satellite access Phase 3 | 5GSAT_Ph3_App | 2 | Rel-19 | S6 | 2024-07-16 08:00 | 2024-10-28 10:00 | 100% | SP-241690 |  | Basavaraj (Basu) Pattan, Samsung | basavarajjp@samsung.com | ; 4/9/24: 0%->5; 5/12/24: 5%->75; 8/1/25: WID:SP-241010->SP-241690; 6/3/25: 75%->100 | 23.558; 23.434; 23.289 | 104 | 53 |  |  | Wed 12/06/24 | Thu 06/03/25
273 | 1060023 | CT aspects for application enablement for satellite access Phase 3 | 5GSAT_Ph3_App | 2 | Rel-19 |  | 2024-12-02 08:00 | 2025-09-09 17:00 | 96% | CP-243071 |  | Narendranath Durga Tangudu, Samsung | n.tangudu@samsung.com | ; 4/9/24: 0%->5 |  | 104 | 53 |  |  | Wed 12/06/24 | Wed 04/09/24
274 | 1060032 | CT1 aspects for application enablement for satellite access Phase 3 | 5GSAT_Ph3_App | 3 | Rel-19 | C1 | 2024-12-02 08:00 | 2025-09-09 17:00 | 95% | CP-243071 |  | Narendranath Durga Tangudu, Samsung | n.tangudu@samsung.com | ; 4/9/24: 0%->5 |  | 104 | 53 |  |  | Wed 12/06/24 | Wed 04/09/24
275 | 1060033 | CT3 aspects for application enablement for satellite access Phase 3 | 5GSAT_Ph3_App | 3 | Rel-19 | C3 | 2024-12-02 08:00 | 2025-09-09 17:00 | 97% | CP-243071 |  | Narendranath Durga Tangudu, Samsung | n.tangudu@samsung.com | ; 4/9/24: 0%->5 |  | 104 | 53 |  |  | Wed 12/06/24 | Wed 04/09/24
276 | 1050019 | CT aspects of integration of satellite components in the 5G architecture Phase 3 | 5GSAT_Ph3_ARCH | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 99% | CP-250134 |  | Zhao, Xiaoxue (CATT) | zhaoxiaoxue@cictmobile.com | 24.301,23.040,27.007,24.229,29.122,29.214,29.508,29.512,29.513,29.514,29.272,29.128,29.336,29.502,29.571,29.230 |  | 105 | 53 |  |  | Wed 12/06/24 | NA
277 | 1050041 | CT1 aspects of integration of satellite components in the 5G architecture Phase 3 | 5GSAT_Ph3_ARCH | 3 | Rel-19 | C1 | 2024-09-09 08:00 | 2025-09-09 17:00 | 96% | CP-250134 |  | Zhao, Xiaoxue (CATT) | zhaoxiaoxue@cictmobile.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
278 | 1050042 | CT3 aspects of integration of satellite components in the 5G architecture Phase 3 | 5GSAT_Ph3_ARCH | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-250134 |  | Zhao, Xiaoxue (CATT) | zhaoxiaoxue@cictmobile.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
279 | 1050043 | CT4 aspects of integration of satellite components in the 5G architecture Phase 3 | 5GSAT_Ph3_ARCH | 3 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-250134 |  | Zhao, Xiaoxue (CATT) | zhaoxiaoxue@cictmobile.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
280 | 1060016 | Management Aspects of NTN Phase 2 | NTN_OAM_Ph2 | 1 | Rel-19 | S5 | 2025-01-30 11:00 | 2025-06-06 17:00 | 100% | SP-250514 |  | MingRui Sun (China Unicom) | sunmr19@chinaunicom.cn | ; 6/3/25: 0%->25; 6/6/25: 25%->100; 27/6/25: WID:SP-241949->SP-250514 | 28.541; 28.552; 28.554; 28.658; 28.540; 28.530 ; TS 28.657;TS 28.659;TS 28.707;TS 28.708;TS 28.709 | 106 | 54 |  |  | Thu 05/12/24 | Fri 27/06/25
281 | 1020044 | Study on Security Aspects of 5G Satellite Access Phase 3 | FS_5GSAT_Ph3_SEC | 1 | Rel-19 | S3 | 2024-01-04 08:00 | 2024-12-12 17:00 | 100% | SP-240232 |  | Zhou Wei | zhouwei@catt.cn | No end date in initial WID SP-231317; 4/1/24: 33.700-29 added;; 14/3/24: 0%->10; 2/4/24: WID:SP-231790->SP-240232; 13/6/24: 10%->65; 5/9/24: 65%->75; 5/12/24: 75%->85; 6/3/25: 85%->100; 5/6/25: 100%->100 | 33.700-29 | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/06/25
282 | 1060065 | Security Aspects of 5G Satellite Access Phase 3 | 5GSAT_Ph3_SEC | 1 | Rel-19 | S3 | 2024-12-05 08:00 | 2025-06-06 17:00 | 100% | SP-241780 |  | Wei Zhou, CATT | zhouwei@catt.cn | ; 6/3/25: 0%->35; 5/6/25: 35%->100 | 33.401 | 106 | 54 |  |  | Thu 05/12/24 | Thu 05/06/25
283 | 1040014 | Study on charging aspects of satellite access Phase 3 | FS_5GSAT_Ph3_CH | 1 | Rel-19 | S5 | 2024-06-12 08:00 | 2024-12-11 12:00 | 100% | SP-240980 |  | Yingying Liu, CATT, | liuyingying@cictmobile.com | 13/6/24: 0%->10; 4/9/24: 10%->40; 26/9/24: 28.846 added;; 5/12/24: 40%->75; 5/12/24: FCD:12/12/2024->/25; 6/3/25: 75%->100 | 28.846 | 104 | 53 |  |  | Wed 12/06/24 | Thu 06/03/25
284 | 1070014 | Charging aspects of satellite access Phase 3 | 5GSAT_Ph3-CH | 1 | Rel-19 | S5 | 2025-03-26 08:00 | 2025-09-09 17:00 | 100% | SP-250365 |  | Yingying Liu, CATT | liuyingying@cictmobile.com | ; 6/6/25: 0%->90; 12/9/25: 90%->100; 12/9/25: FCD:Fri 06/06/->/25 | 32.240; 32.251; 32.255; 32.257; 32.260; 32.291; 32.298 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
285 | 1020097 | Non-Terrestrial Networks (NTN) for NR Phase 3 | NR_NTN_Ph3 | 1 | Rel-19 |  | 2023-12-13 08:00 | 2025-03-03 17:00 | 53% | RP-251954 |  | Thales |  | 2/4/24: WID:RP-234078->RP-240775; 23/7/24: WID:RP-240775->RP-241667; 26/9/24: WID:RP-241667->RP-241789; 24/1/25: WID:RP-241789->RP-243300; 29/9/25: WID:RP-243300->RP-251954 |  | 102 | 52 |  |  | Tue 02/01/24 | Mon 29/09/25
286 | 1021097 | Core part: Non-Terrestrial Networks (NTN) for NR Phase 3 | NR_NTN_Ph3-Core | 2 | Rel-19 | R2 | 2023-12-13 08:00 | 2025-09-09 17:00 | 100% | RP-251954 | RP-251931 | Nicolas Chuberre, Thales | Nicolas.chuberre@thalesaleniaspace.com | 14/3/24: Compl:0%->5%; Stat Rep: ->RP-240091; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com; ; 13/6/24: Compl:5%->25%; Stat Rep: RP-240091->RP-240923; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:25%->45% |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
287 | 1022097 | Perf. part: Non-Terrestrial Networks (NTN) for NR Phase 3 | NR_NTN_Ph3-Perf | 2 | Rel-19 | R4 | 2024-08-18 16:00 | 2026-03-03 17:00 | 0% | RP-251954 | RP-251931 | Nicolas Chuberre, Thales | Nicolas.chuberre@thalesaleniaspace.com | 14/3/24: Stat Rep: ->RP-240091; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com; ; 13/6/24: Stat Rep: RP-240091->RP-240923; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-240923->RP-241742; ; 6/12/24: |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
288 | 1020096 | Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 (for LTE) | IoT_NTN_Ph3 | 1 | Rel-19 |  | 2023-12-13 08:00 | 2025-03-03 17:00 | 78% | RP-252504 |  | Mediatek |  | 2/4/24: WID:RP-234077->RP-240776; 23/7/24: WID:RP-240776->RP-241624; 26/9/24: WID:RP-241624->RP-242397; 24/1/25: WID:RP-242397->RP-243278; 3/4/25: WID:RP-243278->RP-250472; 29/9/25: WID:RP-250472->RP-252504 |  | 102 | 52 |  |  | Tue 02/01/24 | Mon 29/09/25
289 | 1021096 | Core part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 | IoT_NTN_Ph3-Core | 2 | Rel-19 | R2 | 2023-12-13 08:00 | 2025-09-09 17:00 | 100% | RP-252504 | RP-252503 | Mediatek |  | 13/6/24: Compl:0%->15%; Stat Rep: ->RP-241356; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:15%->30%; Stat Rep: RP-241356->RP-242050; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:30%->50%; Stat Rep: RP-242050->RP-242996; ; 6/3/25: FCD:26/02/2025->09/09/202 |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
290 | 1032087 | Perf. part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 | IoT_NTN_Ph3-Perf | 2 | Rel-19 | R4 | 2024-10-13 16:00 | 2026-03-03 17:00 | 50% | RP-252504 | RP-252503 | Mediatek |  | 13/6/24: FCD:03/03/2026->12/12/2025; Stat Rep: ->RP-241356; ; 4/9/24: FCD:12/12/2025->26/03/2025; Stat Rep: RP-241356->RP-242050; ; 6/12/24: Stat Rep: RP-242050->RP-242996; ; 6/3/25: WID: RP-243278->RP-242397; Stat Rep: RP-242996->RP-250470; ; 6/6/25: Com |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
291 | 1030076 | Inter-RAT mode mobility support from E-UTRAN TN to NR NTN | LTE_TN_NR_NTN_mob | 1 | Rel-19 |  | 2024-03-03 08:00 | 2024-09-09 17:00 | 100% | RP-240924 |  | Thales |  | 23/7/24: WID:RP-240846->RP-240924 |  | 103 | 52 |  |  | Tue 02/04/24 | Tue 23/07/24
292 | 1031076 | Core part: Inter-RAT mode mobility support from E-UTRAN TN to NR NTN | LTE_TN_NR_NTN_mob-Core | 2 | Rel-19 | R2 | 2024-03-03 08:00 | 2025-09-09 17:00 | 100% | RP-240924 | RP-251932 | Thales |  | 13/6/24: Compl:0%->70%; Stat Rep: ->RP-240925; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:70%->95%; WID: RP-240924->RP-240846; Stat Rep: RP-240925->RP-241741; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:95%->96%; Stat Rep: RP-241741->RP-242463; ; 6/3/25 |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
293 | 1030086 | Enhanced requirements and test methodology for NR NTN and IoT NTN | NR_IoT_NTN_req_test_enh | 1 | Rel-19 |  | 2024-03-03 08:00 | 2025-03-03 17:00 | 61% | RP-252076 |  | Samsung |  | 23/7/24: WID:RP-240857->RP-241281; 26/9/24: WID:RP-241281->RP-241985; 24/1/25: WID:RP-241985->RP-242901; 29/9/25: WID:RP-242901->RP-252076 |  | 103 | 52 |  |  | Tue 02/04/24 | Mon 29/09/25
294 | 1031086 | Core part: Enhanced requirements and conductive test methodology for NR NTN and IoT NTN | NR_IoT_NTN_req_test_enh-Core | 2 | Rel-19 | R4 | 2024-03-03 08:00 | 2025-09-09 17:00 | 100% | RP-252076 | RP-252074 | Samsung |  | 13/6/24: Stat Rep: ->RP-241280; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->16%; Stat Rep: RP-241280->RP-241984; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:16%->50%; Stat Rep: RP-241984->RP-242592; ; 6/3/25: FCD:23/03/2025->09/09/2025; Compl:50%->65 |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
295 | 1032086 | Perf. Part: Enhanced requirements and conductive test methodology for NR NTN and IoT NTN | NR_IoT_NTN_req_test_enh-Perf | 2 | Rel-19 | R4 | 2024-03-03 08:00 | 2026-03-03 17:00 | 70% | RP-252076 | RP-252074 | Samsung |  | 13/6/24: Stat Rep: ->RP-241280; ; 4/9/24: FCD:03/03/2026->26/03/2025; Compl:0%->10%; Stat Rep: RP-241280->RP-241984; ; 6/12/24: FCD:03/03/2025->03/03/2026; Compl:10%->30%; Stat Rep: RP-241984->RP-242592; ; 6/3/25: FCD:22/07/2025->03/03/2026; Compl:30%->35 |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
296 | 1090063 | UE Conformance - Enhanced requirements and conductive test methodology for NR NTN and IoT NTN | NR_IoT_NTN_req_test_enh-UEConTest | 2 | Rel-19 | R5 | 2025-09-09 08:00 | 2026-12-12 17:00 | 0% | RP-252575 |  | Xiaomi |  | tested: REL-19 WI NR_IoT_NTN_req_test_enh |  | 109 | 55 |  |  | Mon 29/09/25 | NA
297 | 1040129 | Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | NR_NTN_Sband | 1 | Rel-19 |  | 2024-06-06 08:00 | 2025-06-06 17:00 | 100% | RP-250488 |  | Qualcomm |  | 26/9/24: WID:RP-241661->RP-241885; 3/4/25: WID:RP-241885->RP-250488 |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 03/04/25
298 | 1041129 | Core part: Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | NR_NTN_Sband-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-06-06 17:00 | 100% | RP-250488 | RP-251476 | Qualcomm |  | 4/9/24: FCD:03/03/2025->25/06/2025; Compl:0%->20%; Stat Rep: ->RP-241884; ; 6/12/24: FCD:06/06/2025->03/03/2025; Compl:20%->50%; Stat Rep: RP-241884->RP-242615; ; 6/3/25: FCD:09/12/2024->06/06/2025; Compl:50%->70%; Stat Rep: RP-242615->RP-250487; ; 6/6/2 |  | 104 | 53 |  |  | Tue 23/07/24 | Fri 06/06/25
299 | 1042129 | Perf. part: Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | NR_NTN_Sband-Perf | 2 | Rel-19 | R4 | 2024-09-26 16:00 | 2025-06-06 17:00 | 100% | RP-250488 | RP-251476 | Qualcomm |  | 4/9/24: FCD:06/06/2025->25/06/2025; Stat Rep: ->RP-241884; ; 6/12/24: Stat Rep: RP-241884->RP-242615; ; 6/3/25: Stat Rep: RP-242615->RP-250487; ; 6/6/25: Compl:0%->100%; Stat Rep: RP-250487->RP-251476; |  | 104 | 53 |  |  | Tue 23/07/24 | Fri 06/06/25
300 | 1040130 | Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | IoT_NTN_FDD_S_band | 1 | Rel-19 |  | 2024-06-06 08:00 | 2025-06-06 17:00 | 78% | RP-251820 |  | Mediatek |  | 26/9/24: WID:RP-241662->RP-242062; 3/4/25: WID:RP-242062->RP-250474; 18/7/25: WID:RP-250474->RP-251820 |  | 104 | 53 |  |  | Tue 23/07/24 | Fri 18/07/25
301 | 1041130 | Core part: Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | IoT_NTN_FDD_S_band-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-06-06 17:00 | 100% | RP-251820 | RP-251290 | Mediatek |  | 4/9/24: FCD:03/03/2025->25/06/2025; Compl:0%->20%; Stat Rep: ->RP-242061; ; 6/12/24: FCD:06/06/2025->03/03/2025; Compl:20%->50%; WID: RP-241662->RP-242062; Stat Rep: RP-242061->RP-242999; ; 6/3/25: FCD:09/12/2024->06/06/2025; Compl:50%->70%; Stat Rep: RP |  | 104 | 53 |  |  | Tue 23/07/24 | Fri 06/06/25
302 | 1042130 | Perf. part: Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | IoT_NTN_FDD_S_band-Perf | 2 | Rel-19 | R4 | 2024-09-26 16:00 | 2025-06-06 17:00 | 100% | RP-251820 | RP-251290 | Mediatek |  | 4/9/24: FCD:06/06/2025->25/06/2025; Stat Rep: ->RP-242061; ; 6/12/24: WID: RP-241662->RP-242062; Stat Rep: RP-242061->RP-242999; ; 6/3/25: Stat Rep: RP-242999->RP-250473; ; 6/6/25: Compl:0%->100%; Stat Rep: RP-250473->RP-251290; |  | 104 | 53 |  |  | Tue 23/07/24 | Fri 06/06/25
303 | 1090061 | UE Conformance - Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) | IoT_NTN_FDD_S_band-UEConTest | 2 | Rel-19 | R5 | 2025-09-09 08:00 | 2026-03-03 17:00 | 0% | RP-252507 |  | Mediatek |  | tested: REL-19 WI IoT_NTN_FDD_S_band |  | 109 | 55 |  |  | Mon 29/09/25 | NA
304 | 1040135 | Introduction of Ku bands for NR NTN | NR_NTN_Ku_bands | 1 | Rel-19 |  | 2024-06-06 08:00 | 2025-03-03 17:00 | 51% | RP-252911 |  | Intelsat |  | 24/1/25: WID:RP-241690->RP-243314; 3/4/25: WID:RP-243314->RP-250799; 29/9/25: WID:RP-250799->RP-252911 |  | 104 | 53 |  |  | Tue 23/07/24 | Mon 29/09/25
305 | 1041135 | Core part: Introduction of Ku bands for NR NTN | NR_NTN_Ku_bands-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-09-09 17:00 | 100% | RP-252911 | RP-252582 | Intelsat |  | 4/9/24: FCD:09/09/2025->24/09/2024; Compl:0%->15%; Stat Rep: ->RP-241788; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->30%; Stat Rep: RP-241788->RP-242946; ; 6/3/25: FCD:19/04/2025->09/09/2025; Compl:30%->50%; Stat Rep: RP-242946->RP-250466; ; 6/6/2 |  | 104 | 53 |  |  | Tue 23/07/24 | Tue 30/09/25
306 | 1042135 | Perf. part: Introduction of Ku bands for NR NTN | NR_NTN_Ku_bands-Perf | 2 | Rel-19 | R4 | 2024-12-20 14:00 | 2026-03-03 17:00 | 0% | RP-252911 | RP-252582 | Intelsat |  | 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: ->RP-241788; ; 6/12/24: FCD:03/03/2025->03/03/2026; Stat Rep: RP-241788->RP-242946; ; 6/3/25: Stat Rep: RP-242946->RP-250466; ; 6/6/25: Compl:0%->50%; WID: RP-250799->RP-243314; Stat Rep: RP-250466->RP-251271 |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 11/09/25
307 | 1040134 | New NR NTN bands to support Extended L-band and combined MSS L-band and Extended L-band ranges | NR_NTN_combinedLband | 1 | Rel-19 |  | 2024-06-06 08:00 | 2025-06-06 17:00 | 100% | RP-252893 |  | Aalyria |  | 26/9/24: WID:RP-241689->RP-241856; 3/4/25: WID:RP-241856->RP-250752; rapporteur: Inmarsat=> Aalyria; 18/7/25: WID:RP-250752->RP-250983; 29/9/25: WID:RP-250983->RP-252893 |  | 104 | 53 |  |  | Tue 23/07/24 | Mon 29/09/25
308 | 1041134 | Core part: Introduction of new NR NTN bands to support the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) and the combined MSS L-band and Extended L-band ranges (UL 1626.5-1660.5 MHz and 1668-1675 MHz, DL 1518-1559 MHz) | NR_NTN_combinedLband-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-09-09 17:00 | 100% | RP-252893 | RP-250982 | Aalyria |  | 4/9/24: FCD:03/03/2025->25/03/2025; Compl:0%->15%; Stat Rep: ->RP-241782; ; 6/12/24: Compl:15%->35%; Stat Rep: RP-241782->RP-242601; ; 6/3/25: FCD:09/12/2024->06/06/2025; Compl:35%->70%; Stat Rep: RP-242601->RP-250751; ; 6/6/25: FCD:Fri 06/06/25->Tue 09/ |  | 104 | 53 |  |  | Tue 23/07/24 | Tue 30/09/25
309 | 1042134 | STOPPED - Perf. part: Introduction of new NR NTN bands to support the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) and the combined MSS L-band and Extended L-band ranges (UL 1626.5-1660.5 MHz and 1668-1675 MHz, DL 1518-1559 MHz) | NR_NTN_combinedLband-Perf | 2 | Rel-19 | R4 | 2024-09-26 16:00 | 2025-09-09 17:00 | 100% | RP-252893 | RP-250982 | Aalyria |  | 4/9/24: FCD:06/06/2025->25/06/2025; Stat Rep: ->RP-241782; ; 6/12/24: Stat Rep: RP-241782->RP-242601; ; 6/3/25: Stat Rep: RP-242601->RP-250751; ; 6/6/25: FCD:Fri 06/06/25->Tue 09/09/25; Compl:0%->90%; Stat Rep: RP-250751->RP-250982; 29/9/25: Stopped at 9 |  | 104 | 53 |  |  | Tue 23/07/24 | Mon 29/09/25
310 | 1050127 | Introduction of additional operating NR bands for HAPS (High Altitude Platform Station) | NR_HAPS_bands | 1 | Rel-19 |  | 2024-09-09 08:00 | 2025-03-03 17:00 | 100% | RP-242891 |  | SoftBank |  | 24/1/25: WID:RP-242373->RP-242891 |  | 105 | 53 |  |  | Thu 26/09/24 | Fri 24/01/25
311 | 1051127 | Core part: Introduction of additional operating NR bands for HAPS (High Altitude Platform Station) | NR_HAPS_bands-Core | 2 | Rel-19 | R4 | 2024-09-09 08:00 | 2025-03-03 17:00 | 100% | RP-242891 | RP-250407 | SoftBank |  | 6/12/24: FCD:12/12/2024->03/03/2025; Compl:0%->99%; Stat Rep: ->RP-242890; ; 6/3/25: FCD:08/01/2025->03/03/2025; Compl:99%->100%; Stat Rep: RP-242890->RP-250407; |  | 105 | 53 |  |  | Thu 26/09/24 | Thu 06/03/25
312 | 1052127 | Stopped - Perf. part: Introduction of additional operating NR bands for HAPS (High Altitude Platform Station) | NR_HAPS_bands-Perf | 2 | Rel-19 | R4 | 2024-09-09 08:00 | 2024-12-12 17:00 | 100% | RP-242891 |  | SoftBank |  | 24/1/25: Stopped at 0% |  | 105 | 53 |  |  | Thu 26/09/24 | Fri 24/01/25
313 | 0 | Rel-19 XR (eXtended Reality), Metaverse | - | 1 | Rel-19 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
314 | 1020056 | Localized Mobile Metaverse Services | Metaverse | 1 | Rel-19 |  | 2022-03-10 08:00 | 2025-09-09 17:00 | 94% | SP-230509 |  | Guttman, Erik, Samsung | erik.guttman@samsung.com | ; 6/9/23: 0%->80; 21/9/23: 22.156 added;; 8/12/23: 80%->100 | new 22.156, 22.261 ; 22.156 | 100 | 51 |  |  | Thu 08/06/23 | Fri 08/12/23
315 | 950005 | Study on Localized Mobile Metaverse Services | FS_Metaverse | 2 | Rel-19 | S1 | 2022-03-10 08:00 | 2023-09-09 17:00 | 100% | SP-220353 |  | Guttman, Erik, Samsung | erik.guttman@samsung.com | 5/4/22: 22.856 added;; 4/6/22: 0%->15; 9/9/22: 15%->40; 10/12/22: 40%->55; 17/3/23: 55%->75; 8/6/23: 75%->90; 8/6/23: FCD:03/03/2023->09/20; 8/12/23: 90%->100 | 22.856 | 95 | 48 |  |  | Thu 10/03/22 | Fri 08/12/23
316 | 1000028 | Stage 1 of Localized Mobile Metaverse Services | Metaverse | 2 | Rel-19 | S1 | 2023-06-08 08:00 | 2023-12-12 17:00 | 100% | SP-230509 |  | Guttman, Erik, Samsung | erik.guttman@samsung.com | ; 6/9/23: 0%->80; 21/9/23: 22.156 added;; 8/12/23: 80%->100 | new 22.156, 22.261 ; 22.156 | 100 | 51 |  |  | Thu 08/06/23 | Fri 08/12/23
317 | 1040076 | Application enablement for mobile metaverse services | Metaverse_App | 2 | Rel-19 | S6 | 2024-07-16 08:00 | 2024-10-28 10:00 | 100% | SP-241390 |  | Shah, Sapan, Samsung | <sapan.shah@samsung.com> | ; 4/9/24: 0%->25; 26/9/24: WID:SP-241009->SP-241390; 26/9/24: 23.437 added;; 5/12/24: 25%->80; 6/3/25: 80%->100; 26/3/25: 23.438 added; | 23.434; 23.542; 23.558; 23.436 ; 23.437; 23.438 | 104 | 53 |  |  | Wed 12/06/24 | Wed 26/03/25
318 | 1020052 | Study on application enablement for Localized Mobile Metaverse Services | FS_Metaverse_App | 2 | Rel-19 | S6 | 2024-01-03 08:00 | 2024-09-09 17:00 | 100% | SP-231806 |  | Shah, Sapan, Samsung | sapan.shah@samsung.com | 8/12/23: 0%->10; 14/3/24: 0%->30; 3/4/24: 23.700-21 added;; 13/6/24: 30%->70; 4/9/24: 70%->100 | 23.700-21 | 102 | 52 |  |  | Thu 07/12/23 | Wed 04/09/24
319 | 1030039 | Study on security aspects of 5G Mobile Metaverse services | FS_Metaverse_Sec | 2 | Rel-19 | S3 | 2024-04-02 08:00 | 2025-06-06 17:00 | 100% | SP-240508 |  | Rohini Rajendran, | r.rohini@samsung.com | 3/4/24: 33.721 added;; 13/6/24: 0%->20; 5/9/24: 20%->50; 5/12/24: 50%->70; 6/3/25: 70%->79; 6/3/25: FCD:12/12/2024->/25; 5/6/25: 79%->100; 5/6/25: FCD:Sat 25/01/->/25 | 33.721 | 103 | 52 |  |  | Thu 14/03/24 | Thu 05/06/25
320 | 1050025 | CT aspects of Application enablement for mobile metaverse services | Metaverse_App | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 83% | CP-251132 |  | Vijay Sangameshwara, Samsung | s.vijay@samsung.com |  | 24.583, 24.545, 29.549 | 105 | 53 |  |  | Wed 12/06/24 | NA
321 | 1050060 | CT1 aspects of Application enablement for mobile metaverse services | Metaverse_App | 3 | Rel-19 | C1 | 2024-09-09 08:00 | 2025-09-09 17:00 | 85% | CP-251132 |  | Vijay Sangameshwara, Samsung | s.vijay@samsung.com | ; 26/9/24: 24.437 added; |  | 105 | 53 |  |  | Wed 12/06/24 | Thu 26/09/24
322 | 1050061 | CT3 aspects of Application enablement for mobile metaverse services | Metaverse_App | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2025-09-09 17:00 | 80% | CP-251132 |  | Vijay Sangameshwara, Samsung | s.vijay@samsung.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
323 | 1060060 | Security aspects of 5G Mobile Metaverse services | Metaverse_Sec | 2 | Rel-19 | S3 | 2025-01-02 09:00 | 2025-03-03 17:00 | 100% | SP-250075 |  | Rohini Rajendran, r.rohini@samsung.com | Lihui Xiong, xionglihui@oppo.com | ; 26/3/25: WID:SP-241775->SP-250075; 17/9/25: 0%->100 | 33.434 | 106 | 54 |  |  | Thu 05/12/24 | Wed 17/09/25
324 | 1060034 | Extended Reality and Media |  | 1 | Rel-19 |  | 2023-03-16 08:00 | 2026-01-13 17:00 | 99% |  |  |  |  | 29/9/25: FCD:Sun 06/06/27->Tue 13/01/26; Compl:67%->99%; |  | 104 | 53 |  |  | Wed 12/06/24 | Mon 29/09/25
325 | 990052 | Supporting UE Mobility for XR Services | XRMobility | 2 | Rel-19 | S1 | 2023-03-16 08:00 | 2023-05-11 17:00 | 99% | SP-230233 |  | Xiaonan Shi, ChinaMobile | shixiaonan@chinamobile.com | ; 17/3/23: 0%->50; 6/9/23: 50%->100 | 22.261 | 99 | 50 |  |  | Thu 16/03/23 | Wed 06/09/23
326 | 1010032 | Study on Extended Reality and Media service (XRM) Phase 2 | FS_XRM_Ph2 | 2 | Rel-19 | S2 | 2024-01-03 08:00 | 2024-06-25 17:00 | 99% | SP-231671 |  | Primary Rapporteur: Devaki Chandramouli (Nokia) | devaki.chandramouli@nokia.com. | 9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-70 added;; 8/12/23: 0%->13; 14/3/24: 0%->45; 13/6/24: FCD:05/06/2024->/24; 13/6/24: 45%->90; 4/9/24: 90%->100 | 23.700-70 | 101 | 51 |  |  | Wed 20/09/23 | Wed 04/09/24
327 | 1040032 | Extended Reality and Media service (XRM) Phase 2 | XRM_Ph2 | 2 | Rel-19 | S2 | 2024-06-12 08:00 | 2024-10-17 12:00 | 99% | SP-241385 |  | Georgios Gkellas (Nokia), | Georgios.Gkellas@nokia.com. | ; 4/9/24: 0%->5; 26/9/24: WID:SP-240990->SP-241322; 26/9/24: WID:SP-241322->SP-241385; 5/12/24: 5%->65; 6/3/25: 65%->100 | 23.501; 23.502; 23.503; 23.316 | 104 | 53 |  |  | Wed 12/06/24 | Thu 06/03/25
328 | 1060027 | CT aspects of Extended Reality and Media service (XRM) Phase 2 | XRM_Ph2 | 2 | Rel-19 |  | 2024-12-02 08:00 | 2026-01-13 17:00 | 99% | CP-252058 |  | Ravindran, Parthasarathi, Nokia | parthasarathi.ravindran@nokia.com | 29/9/25: FCD:Tue 09/09/25->Tue 13/01/26; WID: CP-251135->CP-252058; List of Impacted TS & TR updated; | 24.501, 29.122, 29.508, 29.512, 29.514, 29.522, 29.561, 29.281, 29.244, 29.502, 29.564, 29.571 | 104 | 53 |  |  | Wed 12/06/24 | Mon 29/09/25
329 | 1060035 | CT1 aspects of Extended Reality and Media service (XRM) Phase 2 | XRM_Ph2 | 3 | Rel-19 | C1 | 2024-12-02 08:00 | 2026-01-13 17:00 | 100% | CP-252058 |  | Ravindran, Parthasarathi, Nokia | parthasarathi.ravindran@nokia.com | 29/9/25: FCD:Tue 09/09/25->Tue 13/01/26; WID: CP-251135->CP-252058; |  | 104 | 53 |  |  | Wed 12/06/24 | Mon 29/09/25
330 | 1060036 | CT3 aspects of Extended Reality and Media service (XRM) Phase 2 | XRM_Ph2 | 3 | Rel-19 | C3 | 2024-12-02 08:00 | 2026-01-13 17:00 | 96% | CP-252058 |  | Ravindran, Parthasarathi, Nokia | parthasarathi.ravindran@nokia.com | 29/9/25: FCD:Tue 09/09/25->Tue 13/01/26; WID: CP-251135->CP-252058; |  | 104 | 53 |  |  | Wed 12/06/24 | Mon 29/09/25
331 | 1060037 | CT4 aspects of Extended Reality and Media service (XRM) Phase 2 | XRM_Ph2 | 3 | Rel-19 | C4 | 2024-12-02 08:00 | 2026-01-13 17:00 | 100% | CP-252058 |  | Ravindran, Parthasarathi, Nokia | parthasarathi.ravindran@nokia.com | 29/9/25: FCD:Tue 09/09/25->Tue 13/01/26; WID: CP-251135->CP-252058; |  | 104 | 53 |  |  | Wed 12/06/24 | Mon 29/09/25
332 | 1090012 | Charging Aspects for XRM phase 2 | XRM_PH2-CH | 2 | Rel-20 | S5 | 2025-09-10 08:00 | 2027-06-06 17:00 | 99% | SP-251214 |  | Xiaoqian Jia (China Telecom) | jiaxq1@chinatelecom.cn |  | 32.255; 32.291; 32.298 | 109 | 55 |  |  | Wed 10/09/25 | NA
333 | 1020051 | Study on Application enabler for XR Services | FS_XRApp | 2 | Rel-19 | S6 | 2024-01-03 08:00 | 2024-12-12 17:00 | 99% | SP-2315739 |  | Zheng, Shaowen, CMCC | zhengshaowen@chinamobile.com | 8/12/23: 0%->10; 14/3/24: 0%->20; 3/4/24: 23.700-23 added;; 13/6/24: 20%->65; 4/9/24: 65%->90; 5/12/24: 90%->100; 5/12/24: FCD:09/09/2024->12/24 | 23.700-23 | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/12/24
334 | 1040074 | Application enablement for XRM Services Phase 2 | XRM_Ph2_App | 2 | Rel-19 | S6 | 2024-07-16 08:00 | 2024-10-28 10:00 | 99% | SP-241207 |  | Zheng, Shaowen, CMCC | zhengshaowen@chinamobile.com | ; 4/9/24: 0%->15; 26/9/24: WID:SP-241007->SP-241207; 5/12/24: 15%->90; 6/3/25: 90%->100 | 23.433; 23.558 | 104 | 53 |  |  | Wed 12/06/24 | Thu 06/03/25
335 | 1060024 | CT aspects of Application enablement for XRM Services Phase 2 | XRM_Ph2_App | 2 | Rel-19 |  | 2024-12-02 08:00 | 2025-09-09 17:00 | 99% | CP-243072 |  | Zhenning, Huang, China Mobile | huangzhenning@chinamobile.com |  | 24.543, 24.548, 29.548, 29.549, 29.558 | 104 | 53 |  |  | Wed 12/06/24 | Thu 26/09/24
336 | 1060038 | CT1 aspects of Application enablement for XRM Services Phase 2 | XRM_Ph2_App | 3 | Rel-19 | C1 | 2025-02-27 08:00 | 2025-09-09 17:00 | 99% | CP-243072 |  | Zhenning, Huang, China Mobile | huangzhenning@chinamobile.com |  |  | 104 | 53 |  |  | Wed 12/06/24 | Thu 26/09/24
337 | 1060039 | CT3 aspects of Application enablement for XRM Services Phase 2 | XRM_Ph2_App | 3 | Rel-19 | C3 | 2024-12-02 08:00 | 2025-09-09 17:00 | 99% | CP-243072 |  | Zhenning, Huang, China Mobile | huangzhenning@chinamobile.com |  |  | 104 | 53 |  |  | Wed 12/06/24 | Thu 26/09/24
338 | 1070021 | Protection of XRM Media related information | XRM_Ph2-SEC | 2 | Rel-19 | S3 | 2025-02-11 15:00 | 2025-03-03 17:00 | 99% | SP-250361 |  | Daniel Cho | daniel.cho@ericsson.com | ; 17/9/25: 0%->100 | 33.501 | 107 | 54 |  |  | Wed 05/03/25 | Wed 17/09/25
339 | 1080016 | OAM support for Extended Reality and Media service (XRM) phase 2 | XRM_Ph2-OAM | 2 | Rel-20 | S5 | 2025-06-05 08:00 | 2026-06-06 17:00 | 99% | SP-250880 |  | Xie Pengxiang (ZTE), | xie.pengxiang@zte.com.cn | ; 12/9/25: 0%->15 | 28.540; 28.541; 28.552; 28.554 | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
340 | 1020098 | XR (eXtended Reality) for NR Phase 3 | NR_XR_Ph3 | 1 | Rel-19 |  | 2023-12-13 08:00 | 2025-03-03 17:00 | 58% | RP-250107 |  | Nokia |  | 2/4/24: WID:RP-234080->RP-240791; 26/9/24: WID:RP-240791->RP-241771; 24/1/25: WID:RP-241771->RP-243318; 3/4/25: WID:RP-243318->RP-250107 |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 03/04/25
341 | 1021098 | Core part: XR (eXtended Reality) for NR Phase 3 | NR_XR_Ph3-Core | 2 | Rel-19 | R2 | 2023-12-13 08:00 | 2025-09-09 17:00 | 100% | RP-250107 | RP-252160 | Benoist Sebire, Nokia | benoist.sebire@nokia.com | 14/3/24: Compl:0%->2%; Stat Rep: ->RP-240081; Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com; ; 13/6/24: Compl:2%->18%; Stat Rep: RP-240081->RP-240927; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:18%->30%; Stat Rep: RP-240 |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
342 | 1022098 | Perf. part: XR (eXtended Reality) for NR Phase 3 | NR_XR_Ph3-Perf | 2 | Rel-19 | R4 | 2024-08-18 16:00 | 2026-03-03 17:00 | 10% | RP-250107 | RP-252160 | Benoist Sebire, Nokia | benoist.sebire@nokia.com | 14/3/24: Stat Rep: ->RP-240081; Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com; ; 13/6/24: Stat Rep: RP-240081->RP-240927; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-240927->RP-241770; ; 6/12/24: FCD:03/03/2025->03 |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
343 | 1030045 | Indirect Network Sharing | TEI19_NetShare | 1 | Rel-19 |  | 2022-03-10 08:00 | 2025-09-09 17:00 | 100% | [6 empty] | 103 | 52 |  |  | Wed 13/03/24 | NA
344 | 950006 | Study on Network Sharing Aspects | FS_NetShare | 2 | Rel-19 | S1 | 2022-03-10 08:00 | 2023-09-09 17:00 | 100% | SP-220087 |  | Wei, Qun, China Unicom | Weiqun5 <at> chinaunicom.cn | 5/4/22: 22.851 added;; 4/6/22: 0%->10; 9/9/22: 10%->20; 10/12/22: 20%->75; 17/3/23: 75%->80; 17/3/23: FCD:12/12/2022->/23; 8/6/23: 80%->95; 8/6/23: FCD:03/03/2023->09/20; 6/9/23: 95%->100 | 22.851 | 95 | 48 |  |  | Thu 10/03/22 | Wed 06/09/23
345 | 1000029 | (Stage 1 of) Indirect Network Sharing | NetShare | 2 | Rel-19 | S1 | 2023-06-08 08:00 | 2023-12-12 17:00 | 100% | SP-230511 |  | Wei, Qun, China Unicom | Weiqun5 <at> chinaunicom.cn | ; 6/9/23: 0%->100 | 22.261 | 100 | 51 |  |  | Thu 08/06/23 | Wed 06/09/23
346 | 1030011 | (Stage 2 of) Indirect Network Sharing | TEI19_NetShare | 2 | Rel-19 | S2 | 2024-04-02 08:00 | 2024-06-06 17:00 | 100% | SP-240488 |  | Xing, Tianqi, China Unicom, | xingtq@chinaunicom.cn | ; 13/6/24: FCD:12/12/2024->06/24; 13/6/24: 0%->100 | 23.501; 23.502 | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
347 | 1040019 | Charging enhancement for indirect network sharing | NetShare_CH | 2 | Rel-19 | S5 | 2024-06-12 08:00 | 2024-12-12 17:00 | 100% | SP-241004 |  | Robert Törnkvist, Ericsson, | robert.tornkvist@ericsson.com | ; 5/12/24: 0%->100 | 32.240; 32.255; 32.256 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/12/24
348 | 1050004 | CT aspects of indirect network sharing | TEI19_NetShare | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-250019 |  | Xing Tianqi, China Unicom | xingtq@chinaunicom.cn |  | 24.501,29.507,29.525,29.531,29.510,29.502,29.509,29.503,29.536 | 105 | 53 |  |  | Wed 12/06/24 | NA
349 | 1050074 | CT1 aspects of indirect network sharing | TEI19_NetShare | 3 | Rel-19 | C1 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-250019 |  | Xing Tianqi, China Unicom | xingtq@chinaunicom.cn |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
350 | 1070048 | CT3 aspects of indirect network sharing | TEI19_NetShare | 3 | Rel-19 | C3 | 2025-03-03 08:00 | 2025-09-09 17:00 | 100% | CP-250019 |  | Xing Tianqi, China Unicom | xingtq@chinaunicom.cn |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
351 | 1050075 | CT4 aspects of indirect network sharing | TEI19_NetShare | 3 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-250019 |  | Xing Tianqi, China Unicom | xingtq@chinaunicom.cn |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
352 | 1060017 | Management of Network Sharing Phase 3 | NetShare_OAM_Ph3 | 1 | Rel-19 | S5 | 2025-01-30 11:00 | 2025-06-06 17:00 | 100% | SP-241950 |  | ZhaoNing Wang (China Unicom) | wangzn18@chinaunicom.cn | ; 6/3/25: 0%->50; 6/6/25: 50%->95; 12/9/25: 95%->100 | 28.552; 32.130; 28.541 | 106 | 54 |  |  | Thu 05/12/24 | Fri 12/09/25
353 | 1030046 | Roaming Value-Added Services | TEI19_RVAS | 1 | Rel-19 |  | 2022-06-02 08:00 | 2025-06-06 17:00 | 100% | [6 empty] | 103 | 52 |  |  | Wed 13/03/24 | NA
354 | 960015 | Study on roaming value added services | FS_RVAS | 2 | Rel-19 | S1 | 2022-06-02 08:00 | 2022-12-12 17:00 | 100% | SP-220442 |  | Peter Bleckert, Ericsson |  | 13/7/22: 22.877 added;; 9/9/22: 0%->60; 10/12/22: FCD:10/03/2023->12/22; 10/12/22: 60%->100 | 22.877 | 96 | 49 |  |  | Thu 02/06/22 | Sat 10/12/22
355 | 990051 | Roaming Value-Added Services | RVAS | 2 | Rel-19 | S1 | 2023-02-02 08:00 | 2023-03-03 17:00 | 100% | SP-230231 |  | Peter Bleckert, Ericsson |  | ; 17/3/23: 0%->100 | 22.261 | 99 | 50 |  |  | Thu 16/03/23 | Fri 17/03/23
356 | 1030013 | Architecture support of roaming value-added services | TEI19_RVAS | 2 | Rel-19 | S2 | 2024-03-13 08:00 | 2024-06-06 17:00 | 100% | SP-240119 |  | Qian Chen, Ericsson, | qian.xb.chen@ericsson.com | ; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100 | 23.501; 23.502 | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
357 | 1050002 | CT aspects of Architecture support of roaming value-added services | TEI19_RVAS | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-06-06 17:00 | 100% | CP-242022 |  | Frank Yong, Yang, Ericsson | frank.yong.yang@ericsson.com |  |  | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
358 | 1050087 | CT3 aspects of Architecture support of roaming value-added services | TEI19_RVAS | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2025-06-06 17:00 | 100% | CP-242022 |  | Frank Yong, Yang, Ericsson | frank.yong.yang@ericsson.com |  |  | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
359 | 1050088 | CT4 aspects of Architecture support of roaming value-added services | TEI19_RVAS | 3 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-06-06 17:00 | 100% | CP-242022 |  | Frank Yong, Yang, Ericsson | frank.yong.yang@ericsson.com |  |  | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
360 | 0 | Rel-19 user plane | - | 1 | Rel-19 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
361 | 1080048 | Media Messaging Enhancements | MeME-MED | 1 | Rel-19 | S4 | 2025-06-05 08:00 | 2025-09-09 17:00 | 100% | SP-250632 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | ; 12/9/25: 0%->100 | 26.143 | 108 | 55 |  |  | Thu 05/06/25 | Fri 12/09/25
362 | 1070056 | Avatar Communications in AR Calls | AvCall-MED | 1 | Rel-19 | S4 | 2025-03-06 08:00 | 2025-09-09 17:00 | 100% | SP-250264 |  | Bouazizi, Imed, Qualcomm, | bouazizi AT qti dot qualcomm dot com | ; 5/6/25: 0%->15; 12/9/25: 15%->100 | 26.264 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
363 | 1050037 | Study on immersive Real-Time Communication for WebRTC, Phase 2 | FS_iRTCW_Ph2 | 1 | Rel-19 | S4 | 2024-09-09 08:00 | 2025-06-06 17:00 | 100% | SP-241374 |  | Hakju Ryan Lee, Samsung Electronics, CO., LTD, | hakju00.lee@samsung.com | 5/12/24: 0%->15; 6/3/25: 15%->35; 26/3/25: 26.830 added;; 5/6/25: 35%->100; 5/6/25: FCD:Mon 03/03/->/25 | 26.830 | 105 | 53 |  |  | Wed 12/06/24 | Thu 05/06/25
364 | 1050113 | Terminal Audio quality performance and Test methods for Immersive Audio Services, Phase 2 | ATIAS_Ph2 | 1 | Rel-19 | S4 | 2024-09-09 08:00 | 2025-12-12 17:00 | 75% | SP-241314 |  | Jan Reimes, HEAD acoustics GmbH, | jan.reimes@head-acoustics.com | ; 6/3/25: 0%->25; 5/6/25: 25%->65; 5/6/25: FCD:Fri 06/06/->/25; 12/9/25: 65%->75; 12/9/25: FCD:Tue 09/09/->12/20 | 26.259; 26.260; 26.261 | 105 | 53 |  |  | Wed 12/06/24 | Fri 12/09/25
365 | 1040022 | Study on Spatial Computing for AR Services | FS_ARSpatial | 1 | Rel-19 | S4 | 2024-06-06 08:00 | 2025-09-09 17:00 | 100% | SP-240927 |  | Hamza, Ahmed, InterDigital Canada | <Ahmed.Hamza@InterDigital.com> | 4/9/24: 0%->10; 26/9/24: 26.819 added;; 5/12/24: 10%->25; 6/3/25: 25%->45; 5/6/25: 45%->45; 5/6/25: FCD:Fri 14/02/->/25; 12/9/25: 45%->100 | 26.819 | 104 | 53 |  |  | Wed 12/06/24 | Fri 12/09/25
366 | 1040021 | EVS Codec Extension for Immersive Voice and Audio Services, Phase 2 | IVAS_Codec_Ph2 | 1 | Rel-19 | S4 | 2024-06-06 08:00 | 2025-12-12 17:00 | 80% | SP-250262 |  | Su, Huan-yu, Huawei Technologies Co Ltd., | su.huanyu@huawei.com | ; 4/9/24: 0%->5; 5/12/24: 5%->20; 5/12/24: FCD:06/06/2025->/25; 6/3/25: 20%->35; 26/3/25: WID:SP-241000->SP-250262; 26/3/25: FCD:19/04/2025->12/25; 5/6/25: 35%->65; 5/6/25: FCD:Fri 12/12/->/25; 12/9/25: 65%->80; 12/9/25: FCD:Tue 09/09/->12/20 | 26.114; 26.117; 26.119; 26.249; 26.250; 26.252; 26.253; 26.258; 26.997 | 104 | 53 |  |  | Wed 12/06/24 | Fri 12/09/25
367 | 1040020 | Study on Haptics in 5G Media Services | FS_HapticsMedia | 1 | Rel-19 | S4 | 2024-06-12 08:00 | 2025-03-03 17:00 | 100% | SP-241121 |  | Gaëlle Martin-Cocher, InterDigital | (Gaelle.Martin-Cocher@InterDigital.com) | 4/9/24: WID:SP-240979->SP-241121; acron.: FS_HapticsMed-> FS_HapticsMedia; 4/9/24: 0%->15; 26/9/24: 26.854 added;; 5/12/24: 15%->60; 6/3/25: 60%->100 | 26.854 | 104 | 53 |  |  | Wed 12/06/24 | Thu 06/03/25
368 | 1050097 | UPF enhancement for Exposure And SBA Phase 2 | UPEAS_Ph2 | 1 | Rel-19 | S2 | 2024-01-04 08:00 | 2025-09-09 17:00 | 100% | SP-240995 |  | Zhu Jinguo, ZTE | zhu.jinguo@zte.com.cn |  | 23.501; 23.502; 23.503 | 105 | 53 |  |  | Wed 12/06/24 | NA
369 | 1020003 | Study on UPF enhancement for Exposure And SBA Phase 2 | FS_UPEAS_Ph2 | 2 | Rel-19 | S2 | 2024-01-04 08:00 | 2024-06-06 17:00 | 100% | SP-231795 |  | Zhu Jinguo, ZTE | zhu.jinguo@zte.com.cn | 14/3/24: 0%->45; 13/6/24: 45%->100 |  | 102 | 52 |  |  | Wed 03/01/24 | Thu 13/06/24
370 | 1040035 | Stage 2 of UPF enhancement for Exposure And SBA Phase 2 | UPEAS_Ph2 | 2 | Rel-19 | S2 | 2024-06-12 08:00 | 2024-12-12 17:00 | 100% | SP-240995 |  | Zhu Jinguo, ZTE | zhu.jinguo@zte.com.cn | ; 4/9/24: 0%->65; 5/12/24: 65%->100 | 23.501; 23.502; 23.503 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/12/24
371 | 1050001 | CT aspects of UPF enhancement for Exposure And SBA Phase 2 | UPEAS_Ph2 | 2 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-250018 |  | Shuang Liang, ZTE | liang.shuang3@zte.com.cn |  | 29.244,29.503,29.504,29.510,29.564,29.571,29.508,29.512,29.513,29.514,29.519,29.522 | 105 | 53 |  |  | Wed 12/06/24 | NA
372 | 1050098 | CT3 aspects of UPF enhancement for Exposure And SBA Phase 2 | UPEAS_Ph2 | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-250018 |  | Shuang Liang, ZTE | liang.shuang3@zte.com.cn |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
373 | 1050099 | CT4 aspects of UPF enhancement for Exposure And SBA Phase 2 | UPEAS_Ph2 | 3 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-250018 |  | Shuang Liang, ZTE | liang.shuang3@zte.com.cn |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
374 | 1030002 | Video Operating Points - Harmonization and Stereo MV-HEVC | VOPS | 1 | Rel-19 | S4 | 2024-03-13 08:00 | 2025-12-12 17:00 | 95% | SP-250818 |  | Waqar Zia | waqar_zia (at) apple.com | 14/5/24: 26.265 added;; 13/6/24: 0%->15; 4/9/24: 15%->20; 4/9/24: 20%->; 5/12/24: 20%->45; 5/12/24: FCD:03/03/2025->/25; 6/3/25: 45%->70; 5/6/25: 70%->70; 5/6/25: FCD:Sat 18/01/->12/20; 5/6/25: WID:SP-240060->SP-250633; 27/6/25: WID:SP-250633->SP-250818; | 26.265; 26.116; 26.118; 26.119; 26.143; 26.511 | 103 | 52 |  |  | Wed 13/03/24 | Fri 12/09/25
375 | 1030003 | Split rendering over IMS | SR_IMS | 1 | Rel-19 | S4 | 2024-04-02 08:00 | 2025-09-09 17:00 | 100% | SP-240492 |  | He, Shane, Nokia Corporation | shane.he@nokia.com | ; 14/5/24: 26.567 added;; 13/6/24: 0%->10; 4/9/24: 10%->25; 5/12/24: 25%->45; 5/12/24: FCD:03/03/2025->/25; 6/3/25: 45%->65; 5/6/25: 65%->95; 5/6/25: FCD:Sat 25/01/->/2025; 12/9/25: 95%->100 | 26.264 ; 26.567 | 103 | 52 |  |  | Wed 13/03/24 | Fri 12/09/25
376 | 1030005 | Study on Media Messaging | FS_MeMe | 1 | Rel-19 | S4 | 2024-04-02 08:00 | 2025-06-06 17:00 | 100% | SP-240477 |  | Thomas Stockhammer, Qualcomm Incorporated, | tsto@qti.qualcomm.com | 13/6/24: 0%->10; 13/6/24: FCD:12/12/2024->/25; 4/9/24: 10%->30; 5/12/24: 30%->60; 6/3/25: 60%->65; 6/3/25: FCD:03/03/2025->/25; 5/6/25: 65%->100; 5/6/25: FCD:Sat 25/01/->/25 |  | 103 | 52 |  |  | Wed 13/03/24 | Thu 05/06/25
377 | 1030006 | Study on Advanced Media Delivery | FS_AMD | 1 | Rel-19 | S4 | 2024-04-02 08:00 | 2024-12-12 17:00 | 100% | SP-241011 |  | Thomas Stockhammer, Qualcomm Incorporated, | tsto@qti.qualcomm.com | ; 13/6/24: 0%->15; 16/7/24: WID:SP-240478->SP-241011; 4/9/24: 15%->30; 5/12/24: 30%->75; 6/3/25: 75%->100 | 26.802; 26.804 | 103 | 52 |  |  | Wed 13/03/24 | Thu 06/03/25
378 | 1060069 | Stage 2 for Advanced Media Delivery | AMD-ARCH-MED | 1 | Rel-19 | S4 | 2024-12-05 08:00 | 2025-03-03 17:00 | 100% | SP-241963 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | ; 6/3/25: 0%->100 | 26.501; 26.502 | 106 | 54 |  |  | Thu 05/12/24 | Thu 06/03/25
379 | 1070057 | Stage 3 for Advanced Media Delivery | AMD_PRO-MED | 1 | Rel-19 | S4 | 2025-03-05 08:00 | 2025-09-09 17:00 | 85% | SP-250265 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com, for all topics except OpenAPI | ; 5/6/25: 0%->40; 12/9/25: 40%->85 | 26.510; 26.511; 26.512; 26.517; 26.532; 26.247; 26.510; 26.512; 26.517; 26.532 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
380 | 1080004 | CT aspects of Advanced Media Delivery | AMD_PRO-MED-CT | 1 | Rel-19 |  | 2025-06-06 08:00 | 2025-10-23 17:00 | 100% | CP-252191 |  | Hanna Lim, Qualcomm Incorporated | hannalim@qti.qualcomm.com | ; 29/9/25: FCD:Tue 09/09/25->Thu 23/10/25; WID: CP-251037->CP-252191; List of Impacted TS & TR updated; | 29.581 | 107 | 54 |  |  | Wed 05/03/25 | Mon 29/09/25
381 | 1080033 | DELETED - CT3 aspects of Advanced Media Delivery | AMD_PRO-MED-CT | 2 | Rel-19 | C3 | 2025-06-06 08:00 | 2025-10-23 17:00 | 100% | CP-252191 |  | Hanna Lim, Qualcomm Incorporated | hannalim@qti.qualcomm.com | ; 29/9/25: FCD:Tue 09/09/25->Thu 23/10/25; WID: CP-251037->CP-252191; | 29.522, 29.580, 29.581 | 107 | 54 |  |  | Wed 05/03/25 | Mon 29/09/25
382 | 1080034 | CT4 aspects of Advanced Media Delivery | AMD_PRO-MED-CT | 2 | Rel-19 | C4 | 2025-06-06 08:00 | 2025-10-23 17:00 | 100% | CP-252191 |  | Hanna Lim, Qualcomm Incorporated | hannalim@qti.qualcomm.com | ; 29/9/25: FCD:Tue 09/09/25->Thu 23/10/25; WID: CP-251037->CP-252191; | 29.522, 29.580, 29.581 | 107 | 54 |  |  | Wed 05/03/25 | Mon 29/09/25
383 | 1030007 | Study of 5G Real-time Transport Protocol Configurations, Phase 2 | FS_5G_RTP_Ph2 | 1 | Rel-19 | S4 | 2024-04-02 08:00 | 2024-12-12 17:00 | 100% | SP-240482 |  | Igor Curcio, Nokia Corporation | igor.curcio@nokia.com | 14/5/24: 26.822 added;; 13/6/24: 0%->40; 4/9/24: 40%->65; 5/12/24: 65%->100 | 26.822 | 103 | 52 |  |  | Wed 13/03/24 | Thu 05/12/24
384 | 1060021 | 5G Real-time Transport Protocol Configurations, Phase 2 | 5G_RTP_Ph2 | 1 | Rel-19 | S4 | 2024-12-05 08:00 | 2025-09-09 17:00 | 100% | SP-241961 |  | Igor Curcio, Nokia Corporation | igor.curcio@nokia.com | ; 6/3/25: 0%->35; 5/6/25: 35%->75; 5/6/25: FCD:Sun 15/06/->/25; 12/9/25: 75%->100 | 26.522; 26.510; 26.113 | 106 | 54 |  |  | Thu 05/12/24 | Fri 12/09/25
385 | 1030008 | Study on Beyond 2D Video | FS_Beyond2D | 1 | Rel-19 | S4 | 2024-04-02 08:00 | 2025-09-09 17:00 | 100% | SP-240479 |  | Jiayi Xu, | xujiayi@chinamobile.com | 14/5/24: 26.956 added;; 13/6/24: 0%->10; 4/9/24: 10%->17; 5/12/24: 17%->28; 6/3/25: 28%->50; 6/3/25: FCD:06/06/2025->/25; 5/6/25: 50%->70; 5/6/25: FCD:Fri 06/06/->/25; 12/9/25: 70%->100 | 26.956 | 103 | 52 |  |  | Wed 13/03/24 | Fri 12/09/25
386 | 0 | Rel-19 Verticals and Non Public Network | - | 1 | Rel-19 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
387 | 1060040 | Common API Framework (CAPIF) Phase 3 | CAPIF_Ph3 | 1 | Rel-19 |  | 2024-01-04 08:00 | 2026-01-13 17:00 | 96% | SP-241381 |  | Niranth Amogh, Nokia | niranth.amogh@nokia.com | ; 29/9/25: FCD:Tue 03/03/26->Tue 13/01/26; Compl:83%->96%; | 23.222 | 105 | 53 |  |  | Wed 04/09/24 | Mon 29/09/25
388 | 1020062 | Study on CAPIF Phase 3 | FS_CAPIF_Ph3 | 2 | Rel-19 | S6 | 2024-01-04 08:00 | 2024-12-12 17:00 | 96% | SP-231741 |  | Preciado Rojas, Diego, Nokia | diego.preciado_rojas@nokia.com | 14/3/24: 0%->20; 3/4/24: 23.700-22 added;; 13/6/24: 20%->55; 4/9/24: 55%->90; 5/12/24: 90%->100; 5/12/24: FCD:09/09/2024->12/24 | 23.700-22 | 102 | 52 |  |  | Wed 03/01/24 | Thu 05/12/24
389 | 1050035 | Stage 2 of Common API Framework (CAPIF) Phase 3 | CAPIF_Ph3 | 2 | Rel-19 | S6 | 2024-10-04 13:00 | 2024-12-12 17:00 | 96% | SP-241694 |  | Niranth Amogh, Nokia | niranth.amogh@nokia.com | ; 8/1/25: WID:SP-241381->SP-241694; 9/6/25: 0%->100 | 23.222 | 105 | 53 |  |  | Wed 04/09/24 | Mon 09/06/25
390 | 1060026 | CT aspects of Common API Framework (CAPIF) Phase 3 | CAPIF_Ph3 | 2 | Rel-19 |  | 2024-12-02 08:00 | 2025-09-09 17:00 | 96% | CP-252059 |  | Paul, Bhaskar, Nokia | bhaskar.paul@nokia.com | ; 29/9/25: WID: CP-243074->CP-252059; | 29.222 | 105 | 53 |  |  | Wed 04/09/24 | Mon 29/09/25
391 | 1060041 | CT3 aspects of Common API Framework (CAPIF) Phase 3 | CAPIF_Ph3 | 3 | Rel-19 | C3 | 2024-12-02 08:00 | 2026-01-13 17:00 | 96% | CP-252059 |  | Paul, Bhaskar, Nokia | bhaskar.paul@nokia.com | ; 29/9/25: FCD:Tue 09/09/25->Tue 13/01/26; WID: CP-243074->CP-252059; | 29.222 | 105 | 53 |  |  | Wed 04/09/24 | Mon 29/09/25
392 | 1040025 | Study on security aspects of CAPIF Phase 3 | FS_CAPIF_Ph3-sec | 2 | Rel-19 | S3 | 2024-06-12 08:00 | 2025-06-06 17:00 | 96% | SP-240654 |  | Henry Leung ( Xiaomi) | lianghaoran@xiaomi.com | 5/9/24: 0%->20; 26/9/24: 33.700-22 added;; 5/12/24: 20%->60; 6/3/25: 60%->60; 5/6/25: 60%->100; 5/6/25: FCD:Thu 17/10/->/25 | 33.700-22 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/06/25
393 | 1060061 | Security aspects of CAPIF Phase3 | CAPIF_Ph3_sec | 2 | Rel-19 | S3 | 2025-01-30 11:00 | 2025-06-06 17:00 | 96% | SP-250076 |  | 1st rapporteur: Henry Leung (Xiaomi), | lianghaoran@xiaomi.com | ; 26/3/25: WID:SP-241776->SP-250076; 5/6/25: 0%->100 | 33.122 | 106 | 54 |  |  | Thu 05/12/24 | Thu 05/06/25
394 | 1040015 | Study on Charging Aspects of CAPIF | FS_CAPIF_Ph2_CH | 2 | Rel-19 | S5 | 2024-06-12 08:00 | 2024-09-09 17:00 | 96% | SP-240981 |  | João Rodrigues, Nokia, | joao.a.rodrigues@nokia.com | 13/6/24: 0%->15; 4/9/24: 15%->35; 26/9/24: 28.849 added;; 5/12/24: 35%->75; 6/3/25: 75%->100; 12/9/25: FCD:Thu 17/10/->/24 | 28.849 | 104 | 53 |  |  | Wed 12/06/24 | Fri 12/09/25
395 | 1070015 | Charging aspects of CAPIF | CH_CAPIF_EXT | 2 | Rel-19 | S5 | 2025-03-26 08:00 | 2025-09-09 17:00 | 96% | SP-250820 |  | João Rodrigues, Nokia | joao.a.rodrigues@nokia.com | ; 6/6/25: 0%->70; 27/6/25: WID:SP-250366->SP-250820; 12/9/25: 70%->100 | 32.240; 32.254; 32.291; 32.298 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
396 | 1080014 | Study on Charging Aspects of CAPIF phase 3 | FS_CAPIF_Ph3_CH | 2 | Rel-20 | S5 | 2025-06-05 08:00 | 2026-03-03 17:00 | 96% | SP-250869 |  | ur: João Rodrigues (Nokia), | joao.a.rodrigues@nokia.com | 18/7/25: 28.891 added; | 28.891 | 108 | 55 |  |  | Thu 05/06/25 | Fri 18/07/25
397 | 1080019 | Converged Charging aspects of CAPIF Phase 3 | CAPIF_Ph3_con-CH | 2 | Rel-19 | S5 | 2025-06-05 08:00 | 2025-09-09 17:00 | 96% | SP-251027 |  |  |  | ; 12/9/25: 0%->100; 29/9/25: WID:SP-250509->SP- 251027 | 32.254; 32.291; 32.298 | 108 | 55 |  |  | Thu 05/06/25 | Mon 29/09/25
398 | 1060009 | Enhanced OAM for management service exposure to external consumers through CAPIF | MExpo | 1 | Rel-19 | S5 | 2025-03-01 16:00 | 2025-09-09 17:00 | 100% | SP-241942 |  | Winnie Nakimuli (Nokia) | winnie.nakimuli@nokia.com | 6/3/25: 0%->15; 6/6/25: 15%->80; 12/9/25: 80%->100 |  | 106 | 54 |  |  | Thu 05/12/24 | Fri 12/09/25
399 | 1000027 | Non-Public Network (NPN) security considerations | SecNPN | 1 | Rel-19 | S1 | 2023-05-22 08:00 | 2023-06-06 17:00 | 100% | SP-230523 |  | Yinglin Chen, China Telecom | chenyl37@chinatelecom.cn |  | 22.261 | 100 | 51 |  |  | Thu 08/06/23 | NA
400 | 1020039 | Study on security for PLMN hosting a NPN | PLMNNPN_SEC | 1 | Rel-19 | S3 | 2024-01-03 08:00 | 2024-09-09 17:00 | 100% | SP-231786 |  | Jun Shen | shenjun6@chinatelecom.cn | 4/1/24: 33.757 added;; 14/3/24: 0%->25; 13/6/24: 25%->70; 5/9/24: 70%->75; 5/12/24: 75%->95; 6/3/25: 95%->100; 5/6/25: 100%->100 | 33.757 | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/06/25
401 | 1060067 | Security for PLMN hosting a NPN | PLMNNPN | 1 | Rel-19 | S3 | 2024-12-05 08:00 | 2025-06-06 17:00 | 100% | SP-241782 |  | Jun Shen | shenjun6@chinatelecom.cn | ; 6/3/25: 0%->90; 5/6/25: 90%->100 | 33.501 | 106 | 54 |  |  | Thu 05/12/24 | Thu 05/06/25
402 | 1050080 | ProSe support in NPN | TEI19_ProSe_NPN | 1 | Rel-19 |  | 2024-03-13 08:00 | 2025-09-09 17:00 | 100% | SP-240122 |  | Walter Dees, Philips International B.V., | walter.dees@philips.com | ; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100 | 23.304; 23.501 | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
403 | 1030016 | Stage 2 of ProSe support in NPN | TEI19_ProSe_NPN | 2 | Rel-19 | S2 | 2024-03-13 08:00 | 2024-06-06 17:00 | 100% | SP-240122 |  | Walter Dees, Philips International B.V., | walter.dees@philips.com | ; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100 | 23.304; 23.501 | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
404 | 1050021 | CT aspects of ProSe support in NPN | TEI19_ProSe_NPN | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-251224 |  | Li, Mingxue, China Telecom | limx36@chinatelecom.cn |  | 23.122, 24.501, 24.554, 24.555, 29.525, 23.003 | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
405 | 1050081 | CT1 aspects of ProSe support in NPN | TEI19_ProSe_NPN | 3 | Rel-19 | C1 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-251224 |  | Li, Mingxue, China Telecom | limx36@chinatelecom.cn |  |  | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
406 | 1060042 | CT3 aspects of ProSe support in NPN | TEI19_ProSe_NPN | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-251224 |  | Li, Mingxue, China Telecom | limx36@chinatelecom.cn |  |  | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
407 | 1050082 | CT4 aspects of ProSe support in NPN | TEI19_ProSe_NPN | 3 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-251224 |  | Li, Mingxue, China Telecom | limx36@chinatelecom.cn |  |  | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
408 | 1050083 | DELETED - CT6 aspects of ProSe support in NPN | TEI19_ProSe_NPN | 3 | Rel-19 | C6 | 2024-12-30 16:00 | 2025-09-09 17:00 | 100% | CP-251224 |  | Li, Mingxue, China Telecom | limx36@chinatelecom.cn |  |  | 103 | 52 | 108 |  | Wed 13/03/24 | Thu 13/06/24
409 | 1040009 | Rel-19 Enhancements of 3GPP Northbound and Application Layer Interfaces and APIs | NBI19 | 1 | Rel-19 |  | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-243079 |  | Abdessamad El Moatamid, Huawei | abdessamad.el.moatamid@huawei.com |  | 24.558, 24.559, 24.549, 29.116, 29.122, 29.222, 29.255, 29.257, 29.343, 29.435, 29.486, 29.522, 29.538, 29.548, 29.549, 29.558, 29.583 | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
410 | 1040060 | CT1 aspects of Rel-19 Enhancements of 3GPP Northbound and Application Layer Interfaces and APIs | NBI19 | 2 | Rel-19 | C1 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-243079 |  | Abdessamad El Moatamid, Huawei | abdessamad.el.moatamid@huawei.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
411 | 1040061 | CT3 aspects of Rel-19 Enhancements of 3GPP Northbound and Application Layer Interfaces and APIs | NBI19 | 2 | Rel-19 | C3 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-243079 |  | Abdessamad El Moatamid, Huawei | abdessamad.el.moatamid@huawei.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
412 | 0 | Rel-19 Radio: NR-only, band-related |  | 1 | Rel-19 |  | 2019-03-07 08:00 | 2019-03-07 17:00 | 0% | [10 empty] | Thu 07/12/23 | NA
413 | 1060083 | 7MHz Channel Bandwidth for n26 and n5 | NR_FR1_7MHz_BW | 1 | Rel-19 | R4 | 2024-05-19 08:00 | 2025-09-08 17:00 | 88% | RP-251453 |  | China Telecom |  | 3/4/25: WID:RP-243323->RP-250373; rapporteur: T-Mobile => China Telecom; 18/7/25: WID:RP-250373->RP-251453 |  | 106 | 54 |  |  | Fri 24/01/25 | Fri 18/07/25
414 | 1061083 | Core part: 7MHz Channel Bandwidth for n26 and n5 | NR_FR1_7MHz_BW-Core | 2 | Rel-19 | R4 | 2024-10-14 14:00 | 2025-09-09 17:00 | 100% | RP-251453 | RP-252543 | China Telecom |  | 6/3/25: FCD:07/09/2025->09/09/2025; Compl:0%->10%; Stat Rep: ->RP-250374; ; 6/6/25: Compl:10%->55%; Stat Rep: RP-250374->RP-251454; ; 11/9/25: Compl:55%->100%; Stat Rep: RP-251454->RP-252543; |  | 106 | 54 |  |  | Fri 24/01/25 | Thu 11/09/25
415 | 1062083 | Perf. Part: 7MHz Channel Bandwidth for n26 and n5 | NR_FR1_7MHz_BW-Perf | 2 | Rel-19 | R4 | 2024-10-14 14:00 | 2026-03-03 17:00 | 80% | RP-251453 | RP-252543 | China Telecom |  | 6/3/25: FCD:07/09/2025->03/03/2026; Stat Rep: ->RP-250374; ; 6/6/25: Compl:0%->20%; Stat Rep: RP-250374->RP-251454; ; 11/9/25: Compl:20%->80%; Stat Rep: RP-251454->RP-252543; |  | 106 | 54 |  |  | Fri 24/01/25 | Thu 11/09/25
416 | 1040127 | Introduction of the NR FDD 1.4 GHz band | NR_FDD_1400MHz | 1 | Rel-19 | R4 | 2024-06-06 08:00 | 2024-12-12 17:00 | 100% | RP-250760 |  | MidWave Wireless |  | 26/9/24: WID:RP-241648->RP-242120; 3/4/25: WID:RP-242120->RP-250760 |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 03/04/25
417 | 1041127 | Core part: Introduction of the NR FDD 1.4 GHz band | NR_FDD_1400MHz-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-03-03 17:00 | 100% | RP-250760 | RP-250403 | MidWave Wireless |  | 4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->40%; Stat Rep: ->RP-242117; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:40%->99%; WID: RP-242120->RP-241648; Stat Rep: RP-242117->RP-242494; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:99%->100%; Stat Rep: R |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 06/03/25
418 | 1042127 | Perf. part: Introduction of the NR FDD 1.4 GHz band | NR_FDD_1400MHz-Perf | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-03-03 17:00 | 100% | RP-250760 | RP-250403 | MidWave Wireless |  | 4/9/24: FCD:03/03/2025->24/12/2024; Compl:0%->40%; Stat Rep: ->RP-242117; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:40%->99%; WID: RP-242120->RP-241648; Stat Rep: RP-242117->RP-242494; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:99%->100%; Stat Rep: R |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 06/03/25
419 | 1040131 | Introduction of NR bands n87 and n88 | NR_bands_n87_n88 | 1 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-03-03 17:00 | 100% | RP-242501 |  | Nokia |  | 26/9/24: WID:RP-241663->RP-242338; 24/1/25: WID:RP-242338->RP-242501 |  | 104 | 53 |  |  | Tue 23/07/24 | Fri 24/01/25
420 | 1041131 | Core part: Introduction of NR bands n87 and n88 | NR_bands_n87_n88-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-03-03 17:00 | 100% | RP-242501 | RP-250149 | Nokia |  | 4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->33%; Stat Rep: ->RP-241816; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:33%->66%; Stat Rep: RP-241816->RP-242500; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:66%->100%; Stat Rep: RP-242500->RP-250149; |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 06/03/25
421 | 1042131 | Perf. part: Introduction of NR bands n87 and n88 | NR_bands_n87_n88-Perf | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-03-03 17:00 | 100% | RP-242501 | RP-250149 | Nokia |  | 4/9/24: FCD:03/03/2025->25/03/2025; Compl:0%->33%; Stat Rep: ->RP-241816; ; 6/12/24: Compl:33%->66%; Stat Rep: RP-241816->RP-242500; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:66%->100%; Stat Rep: RP-242500->RP-250149; |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 06/03/25
422 | 1040132 | Introduction of NR band n68 | NR_band_n68 | 1 | Rel-19 | R4 | 2024-06-06 08:00 | 2024-12-12 17:00 | 100% | RP-250763 |  | Ericsson |  | 24/1/25: WID:RP-241664->RP-242606; 3/4/25: WID:RP-242606->RP-250763 |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 03/04/25
423 | 1041132 | Core part: Introduction of NR band n68 | NR_band_n68-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-03-03 17:00 | 100% | RP-250763 | RP-250525 | Ericsson |  | 4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->25%; WID: RP-241664->RP-231664; Stat Rep: ->RP-241861; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:25%->60%; WID: RP-231664->RP-241664; Stat Rep: RP-241861->RP-242605; ; 6/3/25: FCD:09/12/2024->03/03/2025; C |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 06/03/25
424 | 1042132 | Perf. part: Introduction of NR band n68 | NR_band_n68-Perf | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-03-03 17:00 | 100% | RP-250763 | RP-250525 | Ericsson |  | 4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->25%; WID: RP-241664->RP-231664; Stat Rep: ->RP-241861; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:25%->60%; WID: RP-231664->RP-241664; Stat Rep: RP-241861->RP-242605; ; 6/3/25: FCD:09/12/2024->03/03/2025; C |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 06/03/25
425 | 1040121 | Additional NR bands for NR features in Rel-19 | NR_bands_xFeature_R19 | 1 | Rel-19 | R4 | 2024-06-06 08:00 | 2024-09-09 17:00 | 46% | RP-252463 |  | ZTE |  | 26/9/24: WID:RP-241677->RP-241922; 24/1/25: WID:RP-241922->RP-242572; 3/4/25: WID:RP-242572->RP-250211; 18/7/25: WID:RP-250211->RP-251250; 29/9/25: WID:RP-251250->RP-252463 |  | 104 | 53 |  |  | Tue 23/07/24 | Mon 29/09/25
426 | 1041121 | Core part: Additional NR bands for NR features in Rel-19 | NR_bands_xFeature_R19-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-12-12 17:00 | 85% | RP-252463 | RP-252464 | ZTE |  | 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->15%; Stat Rep: ->RP-241923; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->35%; Stat Rep: RP-241923->RP-242573; ; 6/3/25: FCD:19/04/2025->09/09/2025; Compl:35%->50%; Stat Rep: RP-242573->RP-250212; ; 6/6/2 |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 11/09/25
427 | 1090060 | UE Conformance - Additional NR bands for NR features in Rel-19 | NR_bands_xFeature_R19-UEConTest | 2 | Rel-19 | R5 | 2025-09-09 08:00 | 2026-12-12 17:00 | 0% | RP-252139 |  | ZTE |  | tested: basket REL-19 WI NR_bands_xFeature_R19 which got exception in RP-252462 to complete by Dec.25; dependency to REL-18 WI NR_ENDC_RF_FR1_enh2-UEConTest |  | 109 | 55 |  |  | Mon 29/09/25 | NA
428 | 1040120 | Rel-19 NR CA/DC for x bands DL with y bands UL (x<7, y<3) and SUL/CA band combinations with a single SUL or two SUL cells | NR_CADC_SUL_R19 | 1 | Rel-19 | R4 | 2024-06-06 08:00 | 2024-09-09 17:00 | 88% | RP-252440 |  | Ericsson |  | 26/9/24: WID:RP-241674->RP-241833; 3/4/25: WID:RP-241833->RP-250214; 18/7/25: WID:RP-250214->RP-251806; 29/9/25: WID:RP-251806->RP-252440 |  | 104 | 53 |  |  | Tue 23/07/24 | Mon 29/09/25
429 | 1041120 | Core part: Rel-19 NR Carrier Aggregation (CA)/Dual Connectivity (DC) for x bands DL with y bands UL (x<7, y<3) and Supplementary Uplink (SUL) band combinations/CA band combinations with a single SUL or two SUL cells | NR_CADC_SUL_R19-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-12-12 17:00 | 88% | RP-252440 | RP-252439 | Ericsson |  | 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->20%; Stat Rep: ->RP-241832; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:20%->34%; Stat Rep: RP-241832->RP-242753; ; 6/3/25: FCD:19/04/2025->09/09/2025; Compl:34%->35%; WID: RP-241833->RP-242754; Stat Rep: RP |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 11/09/25
430 | 1050120 | Multi-carrier enhancements for NR Phase 3 | NR_MC_enh2 | 1 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | RP-252564 |  | Lenovo |  | 24/1/25: WID:RP-242408->RP-242904; 29/9/25: WID:RP-242904->RP-252564 |  | 105 | 53 |  |  | Thu 26/09/24 | Mon 29/09/25
431 | 1051120 | Core part: Multi-carrier enhancements for NR Phase 3 | NR_MC_enh2-Core | 2 | Rel-19 | R1 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | RP-252564 | RP-252563 | Lenovo |  | 6/12/24: FCD:09/09/2025->06/06/2025; Compl:0%->40%; Stat Rep: ->RP-242903; ; 6/3/25: FCD:16/03/2025->09/09/2025; Compl:40%->80%; Stat Rep: RP-242903->RP-250413; ; 6/6/25: Compl:80%->90%; Stat Rep: RP-250413->RP-251421; ; 11/9/25: Compl:90%->100%; Stat Re |  | 105 | 53 |  |  | Thu 26/09/24 | Thu 11/09/25
432 | 0 | Rel-19 Radio: NR-only, topics other than band |  | 1 | Rel-19 |  | 2019-03-07 08:00 | 2019-03-07 17:00 | 0% | [10 empty] | Thu 07/12/23 | NA
433 | 1080080 | UE Conformance - New Rel-19 NR licensed bands and extension of existing NR bands | NR_lic_bands_BW_R19-UEConTest | 1 | Rel-19 | R5 | 2025-06-06 08:00 | 2027-06-06 17:00 | 10% | RP-252651 | RP-252650 | Huawei |  | tested: REL-19 WIs NR_FDD_1400MHz, NR_bands_n87_n88, NR_band_n68, NR_NTN_Sband, NR_NTN_combinedLband, NR_NTN_Ku_bands, NR_bands_CA_ENDC_R19_BWs, NR_FR1_7MHz_BW; compare NR_lic_bands_BW_R18-UEConTest; ; 11/9/25: FCD:Sun 06/06/27->Thu 03/06/27; Compl:0%->10 |  | 108 | 55 |  |  | Fri 18/07/25 | Mon 29/09/25
434 | 1060082 | Low band carrier aggregation via switching | NR_LBCA_Sw | 1 | Rel-19 |  | 2025-03-06 08:00 | 2026-03-03 17:00 | 34% | RP-252694 |  | Telus |  | 3/4/25: WID:RP-243317->RP-250247; 18/7/25: WID:RP-250247->RP-251315; AT&T => Telus; 29/9/25: WID:RP-251315->RP-252694 |  | 106 | 54 |  |  | Fri 24/01/25 | Mon 29/09/25
435 | 1061082 | Core part: Low band carrier aggregation via switching | NR_LBCA_Sw-Core | 2 | Rel-19 | R4 | 2025-03-06 15:00 | 2025-09-09 17:00 | 100% | RP-252694 | RP-252695 | Telus |  | 6/3/25: Compl:0%->10%; Stat Rep: ->RP-250246; ; 26/3/25: 38.768 added;; 6/6/25: Compl:10%->60%; Stat Rep: RP-250246->RP-251316; List of Impacted TS & TR updated; ; 11/9/25: Compl:60%->100%; Stat Rep: RP-251316->RP-252695; List of Impacted TS & TR updated; | 38.768 | 106 | 54 |  |  | Fri 24/01/25 | Thu 11/09/25
436 | 1062082 | Perf. part: Low band carrier aggregation via switching | NR_LBCA_Sw-Perf | 2 | Rel-19 | R4 | 2025-03-06 08:00 | 2026-03-03 17:00 | 0% | RP-252694 | RP-252695 | Telus |  | 6/3/25: Stat Rep: ->RP-250246; ; 6/6/25: Stat Rep: RP-250246->RP-251316; ; 11/9/25: Stat Rep: RP-251316->RP-252695; |  | 106 | 54 |  |  | Fri 24/01/25 | Thu 11/09/25
437 | 1050126 | mmWave in NR: UE spurious emissions and EESS (Earth Exploration Satellite Service) protection | NR_mmWave_protect | 1 | Rel-19 |  | 2024-09-09 08:00 | 2026-06-06 17:00 | 69% | RP-251811 |  | China Unicom |  | 24/1/25: WID:RP-242371->RP-242611; 3/4/25: WID:RP-242611->RP-250818; 18/7/25: WID:RP-250818->RP-251811 |  | 105 | 53 |  |  | Thu 26/09/24 | Fri 18/07/25
438 | 1051126 | Core part: mmWave in NR: UE spurious emissions and EESS (Earth Exploration Satellite Service) protection | NR_mmWave_protect-Core | 2 | Rel-19 | R4 | 2024-09-09 08:00 | 2025-06-06 17:00 | 100% | RP-251811 | RP-251593 | China Unicom |  | 6/12/24: Compl:0%->40%; Stat Rep: ->RP-242612; ; 6/3/25: FCD:16/03/2025->06/06/2025; Compl:40%->80%; Stat Rep: RP-242612->RP-250429; ; 6/6/25: Compl:80%->100%; Stat Rep: RP-250429->RP-251593; |  | 105 | 53 |  |  | Thu 26/09/24 | Fri 06/06/25
439 | 1052126 | Perf. part: mmWave in NR: UE spurious emissions and EESS (Earth Exploration Satellite Service) protection | NR_mmWave_protect-Perf | 2 | Rel-19 | R4 | 2024-09-09 08:00 | 2025-06-06 17:00 | 100% | RP-251811 | RP-251593 | China Unicom |  | 6/12/24: Compl:0%->40%; Stat Rep: ->RP-242612; ; 6/3/25: FCD:16/03/2025->06/06/2025; Compl:40%->80%; Stat Rep: RP-242612->RP-250429; ; 6/6/25: Compl:80%->100%; Stat Rep: RP-250429->RP-251593; |  | 105 | 53 |  |  | Thu 26/09/24 | Fri 06/06/25
440 | 1080082 | UE Conformance - mmWave in NR UE spurious emissions and EESS (Earth Exploration Satellite Service) protection | NR_mmWave_protect-UEConTest | 2 | Rel-19 | R5 | 2025-06-06 08:00 | 2026-06-06 17:00 | 22% | RP-251514 | RP-251981 | China Unicom |  | tested: REL-19 WI NR_mmWave_protect ; 11/9/25: Compl:0%->22%; Stat Rep: ->RP-251981; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
441 | 1040100 | Study on spatial channel model for demodulation performance requirements for NR | FS_NR_demod_SCM | 1 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-09-09 17:00 | 100% | RP-251040 | RP-252355 | Nokia |  | 4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->15%; Stat Rep: ->RP-241844; ; 26/9/24: WID:RP-241610->RP-241848; 26/9/24: 38.753 added;; 6/12/24: Compl:15%->40%; WID: RP-241848->RP-241610; Stat Rep: RP-241844->RP-242465; ; 6/3/25: FCD:14/02/2025->06/06/202 | 38.753 | 104 | 53 |  |  | Tue 23/07/24 | Thu 11/09/25
442 | 1040101 | Study on NR FR1 DL fragmented carriers | FS_NR_FR1_DL_Frag_Carrier | 1 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-06-06 17:00 | 100% | RP-243002 | RP-251287 | Mediatek |  | 4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->5%; Stat Rep: ->RP-242054; ; 26/9/24: WID:RP-241669->RP-242404; 26/9/24: 38.755 added;; 6/12/24: Compl:5%->25%; Stat Rep: RP-242054->RP-243001; ; 24/1/25: WID:RP-242404->RP-243002; 6/3/25: FCD:14/02/2025->06/ | 38,755 | 104 | 53 |  |  | Tue 23/07/24 | Fri 06/06/25
443 | 1020081 | Study on channel modelling enhancements for 7-24GHz for NR | FS_NR_7_24GHz_CHmod | 1 | Rel-19 | R1 | 2023-12-13 08:00 | 2025-06-06 17:00 | 100% | RP-234018 | RP-251240 | LEE Daewon, Intel Corporation | daewon.lee@intel.com | 14/3/24: Stat Rep: ->RP-240265; Rapporteur: Intel->LEE Daewon, Intel Corporation; Rap eMail: ->daewon.lee@intel.com; ; 13/6/24: Compl:0%->15%; Stat Rep: RP-240265->RP-241099; ; 4/9/24: FCD:06/06/2025->25/06/2025; Compl:15%->35%; Stat Rep: RP-241099->RP-24 |  | 102 | 52 |  |  | Tue 02/01/24 | Fri 06/06/25
444 | 1050125 | Additional topological enhancements for NR | NR_WAB_5GFemto | 1 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | RP-252479 |  | NTT DOCOMO |  | 24/1/25: WID:RP-242395->RP-243009; 29/9/25: WID:RP-243009->RP-252479 |  | 105 | 53 |  |  | Thu 26/09/24 | Mon 29/09/25
445 | 1051125 | Core part: Additional topological enhancements for NR | NR_WAB_5GFemto-Core | 2 | Rel-19 | R3 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | RP-252479 | RP-252481 | NTT DOCOMO |  | 6/12/24: Compl:0%->30%; Stat Rep: ->RP-243006; ; 6/3/25: FCD:20/05/2025->09/09/2025; Compl:30%->60%; Stat Rep: RP-243006->RP-250357; ; 6/6/25: Compl:60%->85%; Stat Rep: RP-250357->RP-251410; ; 11/9/25: Compl:85%->100%; Stat Rep: RP-251410->RP-252481; |  | 105 | 53 |  |  | Thu 26/09/24 | Thu 11/09/25
446 | 1020082 | Study on additional topological enhancements for NR | FS_NR_WAB_5GFemto | 1 | Rel-19 | R3 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | RP-241264 | RP-241963 | Min, Tianyang, NTT DOCOMO | tianyang.min.ex@nttdocomo.com | 14/3/24: FCD:28/05/2021->09/09/2024; Stat Rep: ->RP-240320; Rapporteur: NTT DOCOMO->Min, Tianyang, NTT DOCOMO; Rap eMail: ->tianyang.min.ex@nttdocomo.com; ; 2/4/24: WID:RP-234041->RP-240319; 3/4/24: 38.799 added;; 13/6/24: Compl:0%->70%; Stat Rep: RP-2... | 38.799 | 102 | 52 |  |  | Tue 02/01/24 | Thu 26/09/24
447 | 1030084 | NR Sidelink: Intra-band Carrier Aggregation in ITS band | NR_SL_intraB_CA_ITS | 1 | Rel-19 |  | 2024-03-03 08:00 | 2024-09-09 17:00 | 100% | RP-250997 |  | OPPO |  | 18/7/25: WID:RP-240840->RP-250997 |  | 103 | 52 |  |  | Tue 02/04/24 | Fri 18/07/25
448 | 1031084 | Core part: NR Sidelink: Intra-band Carrier Aggregation in ITS band | NR_SL_intraB_CA_ITS-Core | 2 | Rel-19 | R4 | 2024-03-03 08:00 | 2025-06-06 17:00 | 100% | RP-250997 | RP-250996 | OPPO |  | 14/5/24: 38.787 added;; 13/6/24: Compl:0%->15%; Stat Rep: ->RP-241152; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:15%->25%; Stat Rep: RP-241152->RP-241843; ; 6/12/24: FCD:09/09/2024->04/03/2024; Compl:25%->0%; Stat Rep: RP-241843->RP-242789; ; 6/3/25: FC | 38,787 | 103 | 52 |  |  | Tue 02/04/24 | Fri 06/06/25
449 | 1040114 | NR sidelink multi-hop relay | NR_SL_relay_multihop | 1 | Rel-19 |  | 2024-06-06 08:00 | 2024-09-09 17:00 | 100% | RP-250188 |  | LG Electronics |  | 26/9/24: WID:RP-241609->RP-242349; 3/4/25: WID:RP-242349->RP-250188 |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 03/04/25
450 | 1041114 | Core part: NR sidelink multi-hop relay | NR_SL_relay_multihop-Core | 2 | Rel-19 | R2 | 2024-06-06 08:00 | 2025-09-09 17:00 | 100% | RP-250188 | RP-251941 | LG Electronics |  | 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->15%; Stat Rep: ->RP-241750; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->40%; Stat Rep: RP-241750->RP-242529; ; 6/3/25: FCD:19/04/2025->09/09/2025; Compl:40%->60%; Stat Rep: RP-242529->RP-250187; ; 6/6/2 |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 11/09/25
451 | 1020089 | NR MIMO Phase 5 | NR_MIMO_Ph5 | 1 | Rel-19 |  | 2023-12-13 08:00 | 2025-03-03 17:00 | 72% | RP-242394 |  | Samsung |  | 2/4/24: WID:RP-234007->RP-240087; 26/9/24: WID:RP-240087->RP-242394 |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 26/09/24
452 | 1021089 | Core part: NR MIMO Phase 5 | NR_MIMO_Ph5-Core | 2 | Rel-19 | R1 | 2023-12-13 08:00 | 2025-09-09 17:00 | 100% | RP-242394 | RP-252065 | Eko Onggosanusi, Samsung | eko.o@samsung.com | 14/3/24: Compl:0%->15%; Stat Rep: ->RP-240086; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com; ; 13/6/24: Compl:15%->35%; WID: RP-240087->RP-234007; Stat Rep: RP-240086->RP-241051; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
453 | 1022089 | Perf. part: NR MIMO Phase 5 | NR_MIMO_Ph5-Perf | 2 | Rel-19 | R4 | 2024-08-18 16:00 | 2026-03-03 17:00 | 40% | RP-242394 | RP-252065 | Eko Onggosanusi, Samsung | eko.o@samsung.com | 14/3/24: Stat Rep: ->RP-240086; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com; ; 13/6/24: WID: RP-240087->RP-234007; Stat Rep: RP-240086->RP-241051; ; 4/9/24: FCD:03/03/2026->26/03/2025; WID: RP-234007->RP-240087; Stat Rep: |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
454 | 1020090 | Evolution of NR duplex operation: Sub-band full duplex (SBFD) | NR_duplex_evo | 1 | Rel-19 |  | 2023-12-13 08:00 | 2025-03-03 17:00 | 65% | RP-251874 |  | Huawei |  | 2/4/24: WID:RP-234035->RP-240789; 23/7/24: WID:RP-240789->RP-241614; 18/7/25: WID:RP-241614->RP-251874 |  | 102 | 52 |  |  | Tue 02/01/24 | Fri 18/07/25
455 | 1021090 | Core part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) | NR_duplex_evo-Core | 2 | Rel-19 | R1 | 2023-12-13 08:00 | 2025-09-09 17:00 | 100% | RP-251874 | RP-252364 | Xinghua Song, He (Jackson) Wang, Huawei, Samsung | songxinghua@huawei.com, h0809.wang@samsung.com | 14/3/24: Compl:0%->7%; Stat Rep: ->RP-240171; Rapporteur: Huawei->Xinghua Song, He (Jackson) Wang, Huawei, Samsung; Rap eMail: ->songxinghua@huawei.com, h0809.wang@samsung.com; ; 13/6/24: Compl:7%->18%; Stat Rep: RP-240171->RP-241286; ; 4/9/24: FCD:09/09/ |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
456 | 1022090 | Perf. part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) | NR_duplex_evo-Perf | 2 | Rel-19 | R4 | 2024-08-18 16:00 | 2026-03-03 17:00 | 25% | RP-251874 | RP-252364 | Xinghua Song, He (Jackson) Wang, Huawei, Samsung | songxinghua@huawei.com, h0809.wang@samsung.com | 14/3/24: Stat Rep: ->RP-240171; Rapporteur: Huawei->Xinghua Song, He (Jackson) Wang, Huawei, Samsung; Rap eMail: ->songxinghua@huawei.com, h0809.wang@samsung.com; ; 13/6/24: Stat Rep: RP-240171->RP-241286; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: R |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
457 | 1020091 | NR mobility enhancements Phase 4 | NR_Mob_Ph4 | 1 | Rel-19 |  | 2023-12-13 08:00 | 2025-03-03 17:00 | 67% | RP-252111 |  | Apple |  | 2/4/24: WID:RP-234036->RP-240299; 23/7/24: WID:RP-240299->RP-241515; 26/9/24: WID:RP-241515->RP-242356; 3/4/25: WID:RP-242356->RP-250339; 29/9/25: WID:RP-250339->RP-252111 |  | 102 | 52 |  |  | Tue 02/01/24 | Mon 29/09/25
458 | 1021091 | Core part: NR mobility enhancements Phase 4 | NR_Mob_Ph4-Core | 2 | Rel-19 | R2 | 2023-12-13 08:00 | 2025-09-09 17:00 | 100% | RP-252111 | RP-252108 | Naveen Palle, Apple Inc. | naveen.palle@apple.com | 14/3/24: Stat Rep: ->RP-240298; Rapporteur: Apple->Naveen Palle, Apple Inc.; Rap eMail: ->naveen.palle@apple.com; ; 13/6/24: Compl:0%->5%; Stat Rep: RP-240298->RP-241514; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:5%->20%; Stat Rep: RP-241514->RP-241915; |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
459 | 1022091 | Perf. part: NR mobility enhancements Phase 4 | NR_Mob_Ph4-Perf | 2 | Rel-19 | R4 | 2024-08-18 16:00 | 2026-03-03 17:00 | 10% | RP-252111 | RP-252108 | Naveen Palle, Apple Inc. | naveen.palle@apple.com | 14/3/24: Stat Rep: ->RP-240298; Rapporteur: Apple->Naveen Palle, Apple Inc.; Rap eMail: ->naveen.palle@apple.com; ; 13/6/24: Stat Rep: RP-240298->RP-241514; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241514->RP-241915; ; 6/12/24: FCD:03/03/2025->0 |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
460 | 1040023 | Security aspects of NR mobility enhancement Phase 4 | NR_Mob_Ph4_Sec | 2 | Rel-19 | S3 | 2024-07-16 08:00 | 2025-06-06 17:00 | 100% | SP-240652 |  | Rajavelsamy R | rajvel@samsung.com | ; 6/3/25: 0%->70; 6/3/25: FCD:03/03/2025->/25; 5/6/25: 70%->100; 5/6/25: FCD:Thu 27/02/->/25 | 33.501 | 104 | 53 |  |  | Tue 16/07/24 | Thu 05/06/25
461 | 1020092 | Data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) Phase 4 | NR_ENDC_SON_MDT_Ph4 | 1 | Rel-19 |  | 2023-12-13 08:00 | 2024-09-09 17:00 | 100% | RP-252557 |  | China Unicom |  | 29/9/25: WID:RP-234038->RP-252557 |  | 102 | 52 |  |  | Tue 02/01/24 | Mon 29/09/25
462 | 1021092 | Core part: Data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) Phase 4 | NR_ENDC_SON_MDT_Ph4-Core | 2 | Rel-19 | R3 | 2023-12-13 08:00 | 2025-09-09 17:00 | 100% | RP-252557 | RP-252558 | Xufei Dong, China Unicom | dongxf37@chinaunicom.cn | 14/3/24: Stat Rep: ->RP-240118; Rapporteur: China Unicom->Xufei Dong, China Unicom; Rap eMail: ->dongxf37@chinaunicom.cn; ; 13/6/24: Compl:0%->15%; Stat Rep: RP-240118->RP-241081; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:15%->30%; Stat Rep: RP-241081-> |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
463 | 780060 | Study on 6 GHz for LTE and NR | FS_6GHz_LTE_NR | 1 | Rel-19 | RP | 2017-12-15 08:00 | 2024-03-03 17:00 | 100% | RP-234033 | RP-231702 | Dominique Everaere, Ericsson | dominique.everaere@ericsson.com | 27/3/18: Compl:0%->25%27/3/18: WID: RP-172804->RP-180168¦27/3/18: 37.890 added;¦27/3/18: 37.107 added;¦27/6/18: Compl:25%->30%¦27/6/18: CD:Fri 15/¦26/3/19: WID:RP-181019->RP-190681; 26/6/19: WID:RP-190681->RP-190957¦01/24: Rel-18->Rel-19; 2/1/24: WID:R... | 37.890; 37.107 | 78 | 40 |  |  | Mon 08/01/18 | Tue 02/04/24
464 | 1030074 | Study on NR FR2 OTA (Over the Air) testing Phase 3 | FS_NR_FR2_OTA_Ph3 | 1 | Rel-19 | R4 | 2024-03-03 08:00 | 2025-09-09 17:00 | 100% | RP-242833 | RP-252375 | Qualcomm |  | 13/6/24: Compl:0%->30%; Stat Rep: SI ->RP-241157; ; 23/7/24: WID:RP-240856->RP-241158; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:30%->70%; Stat Rep: RP-241157->RP-241845; ; 26/9/24: WID:RP-241158->RP-242400; 26/9/24: 38.771 added;; 6/12/24: FCD:09/09/2024 | 38.771 | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
465 | 1030075 | Study on IMT parameters for NR for 4400 to 4800 MHz, 7125 to 8400 MHz and 14800 to 15350 MHz | FS_NR_IMT_4400_7125_14800MHz | 1 | Rel-19 | R4 | 2019-03-07 08:00 | 2025-03-03 17:00 | 100% | RP-242944 | RP-250538 | Ericsson |  | 14/5/24: 38.922 added;; 23/7/24: WID:RP-240787->RP-241326; 4/9/24: FCD:09/03/2021->24/12/2024; Compl:0%->50%; Stat Rep: SI ->RP-241840; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:50%->95%; Stat Rep: RP-241840->RP-242943; ; 24/1/25: WID:RP-241326->RP-242 | 38.922 | 103 | 52 |  |  | Tue 02/04/24 | Thu 06/03/25
466 | 1030078 | NR base station (BS) RF requirement evolution for FR1/FR2 and testing | NR_BS_RF_req_evo | 1 | Rel-19 |  | 2024-03-03 08:00 | 2025-03-03 17:00 | 72% | RP-252578 |  | ZTE |  | 23/7/24: WID:RP-240829->RP-241284; 26/9/24: WID:RP-241284->RP-242010; 24/1/25: WID:RP-242010->RP-243270; 29/9/25: WID:RP-243270->RP-252578 |  | 103 | 52 |  |  | Tue 02/04/24 | Mon 29/09/25
467 | 1031078 | Core part: NR base station (BS) RF requirement evolution for FR1/FR2 and testing | NR_BS_RF_req_evo-Core | 2 | Rel-19 | R4 | 2024-03-03 08:00 | 2025-12-12 17:00 | 85% | RP-252578 | RP-252577 | ZTE |  | 13/6/24: Compl:0%->10%; Stat Rep: ->RP-241285; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:10%->20%; Stat Rep: RP-241285->RP-242011; ; 26/9/24: 38.908 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:20%->30%; Stat Rep: RP-242011->RP-242831; ; 6/3/25: F | 38.908 | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
468 | 1032078 | Perf. part: NR base station (BS) RF requirement evolution for FR1/FR2 and testing | NR_BS_RF_req_evo-Perf | 2 | Rel-19 | R4 | 2024-03-03 08:00 | 2026-03-03 17:00 | 60% | RP-252578 | RP-252577 | ZTE |  | 13/6/24: Stat Rep: ->RP-241285; ; 4/9/24: FCD:03/03/2026->26/03/2025; Compl:0%->5%; Stat Rep: RP-241285->RP-242011; ; 6/12/24: FCD:03/03/2025->03/03/2026; Compl:5%->10%; Stat Rep: RP-242011->RP-242831; ; 6/3/25: FCD:22/07/2025->03/03/2026; Compl:10%->30%; |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
469 | 1030079 | NR Radio Resource Management (RRM) Phase 5 | NR_RRM_Ph5 | 1 | Rel-19 |  | 2024-03-03 08:00 | 2025-03-03 17:00 | 71% | RP-252494 |  | Apple |  | 26/9/24: WID:RP-240830->RP-242380; 29/9/25: WID:RP-242380->RP-252494 |  | 103 | 52 |  |  | Tue 02/04/24 | Mon 29/09/25
470 | 1031079 | Core part: NR Radio Resource Management (RRM) Phase 5 | NR_RRM_Ph5-Core | 2 | Rel-19 | R4 | 2024-03-03 08:00 | 2025-09-09 17:00 | 100% | RP-252494 | RP-252493 | Apple |  | 13/6/24: Compl:0%->5%; Stat Rep: ->RP-241268; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:5%->25%; Stat Rep: RP-241268->RP-241971; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:25%->60%; Stat Rep: RP-241971->RP-242569; ; 6/3/25: FCD:23/03/2025->09/09/2025; |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
471 | 1032079 | Perf. part: NR Radio Resource Management (RRM) Phase 5 | NR_RRM_Ph5-Perf | 2 | Rel-19 | R4 | 2024-10-13 16:00 | 2026-03-03 17:00 | 40% | RP-252494 | RP-252493 | Apple |  | 13/6/24: Stat Rep: ->RP-241268; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241268->RP-241971; ; 6/12/24: FCD:03/03/2025->03/03/2026; Stat Rep: RP-241971->RP-242569; ; 6/3/25: Stat Rep: RP-242569->RP-250320; ; 6/6/25: Compl:0%->20%; Stat Rep: RP-25 |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
472 | 1030080 | NR demodulation performance Phase 5 | NR_demod_Ph5 | 1 | Rel-19 |  | 2024-03-03 08:00 | 2024-09-09 17:00 | 100% | RP-252538 |  | China Telecom |  | 23/7/24: WID:RP-240831->RP-241297; 29/9/25: WID:RP-251448->RP-252538 |  | 103 | 52 |  |  | Tue 02/04/24 | Mon 29/09/25
473 | 1032080 | Perf. part: NR demodulation performance Phase 5 | NR_demod_Ph5-Perf | 2 | Rel-19 | R4 | 2024-03-03 08:00 | 2025-09-09 17:00 | 100% | RP-252538 | RP-252537 | China Telecom |  | 13/6/24: FCD:03/03/2026->09/09/2025; Stat Rep: ->RP-241296; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->14%; Stat Rep: RP-241296->RP-241996; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:14%->43%; Stat Rep: RP-241996->RP-242855; ; 6/3/25: FCD:23/03/202 |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
474 | 1030081 | NR channel BW less than 5MHz for FR1 Phase 2 | NR_FR1_lessthan_5MHz_BW_Ph2 | 1 | Rel-19 |  | 2024-03-03 08:00 | 2026-12-12 17:00 | 52% | RP-251670 |  | Intel |  | 23/7/24: WID:RP-240832->RP-241622; 24/1/25: WID:RP-241622->RP-243309; 3/4/25: WID:RP-243309->RP-250781; 18/7/25: WID:RP-250781->RP-251670 |  | 103 | 52 |  |  | Tue 02/04/24 | Fri 18/07/25
475 | 1031081 | Core part: NR channel BW less than 5MHz for FR1 Phase 2 | NR_FR1_lessthan_5MHz_BW_Ph2-Core | 2 | Rel-19 | R4 | 2024-03-03 08:00 | 2025-03-03 17:00 | 100% | RP-251670 | RP-250462 | Intel |  | 13/6/24: Compl:0%->25%; Stat Rep: ->RP-241496; ; 4/9/24: FCD:12/12/2024->24/12/2024; Compl:25%->70%; Stat Rep: RP-241496->RP-242031; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:73%->99%; Stat Rep: RP-242031->RP-243146; ; 6/3/25: FCD:12/11/2024->03/03/202 |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 06/03/25
476 | 1032081 | Perf. part: NR channel BW less than 5MHz for FR1 Phase 2 | NR_FR1_lessthan_5MHz_BW_Ph2-Perf | 2 | Rel-19 | R4 | 2024-07-21 10:00 | 2025-06-06 17:00 | 100% | RP-251670 | RP-251669 | Intel |  | 13/6/24: Stat Rep: ->RP-241496; ; 6/12/24: Stat Rep: RP-241496->RP-243146; ; 6/3/25: Compl:0%->30%; Stat Rep: RP-243146->RP-250462; ; 6/6/25: Compl:30%->100%; Stat Rep: RP-250462->RP-251669; |  | 103 | 52 |  |  | Tue 02/04/24 | Fri 06/06/25
477 | 1080077 | UE Conformance - NR channel BW less than 5MHz for FR1 Phase 2 | NR_FR1_lessthan_5MHz_BW_Ph2-UEConTest | 2 | Rel-19 | R5 | 2025-06-06 08:00 | 2026-12-12 17:00 | 5% | RP-252552 | RP-252551 | China Telecom |  | tested: REL-19 WI NR_FR1_lessthan_5MHz_BW_Ph2 ; 11/9/25: FCD:Sat 12/12/26->Thu 10/12/26; Compl:0%->5%; Stat Rep: ->RP-252551; ; 29/9/25: WID:RP-251455->RP-252552 |  | 108 | 55 |  |  | Fri 18/07/25 | Mon 29/09/25
478 | 1030083 | Enhancements for Air-to-ground network for NR | NR_ATG_enh | 1 | Rel-19 |  | 2024-03-03 08:00 | 2025-03-03 17:00 | 76% | RP-243285 |  | CMCC |  | 23/7/24: WID:RP-240839->RP-241213; 26/9/24: WID:RP-241213->RP-242381; 24/1/25: WID:RP-242381->RP-243285 |  | 103 | 52 |  |  | Tue 02/04/24 | Fri 24/01/25
479 | 1031083 | Core part: Enhancements for Air-to-ground network for NR | NR_ATG_enh-Core | 2 | Rel-19 | R4 | 2024-03-03 08:00 | 2025-09-09 17:00 | 100% | RP-243285 | RP-252602 | CMCC |  | 13/6/24: Compl:0%->10%; Stat Rep: ->RP-241214; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:10%->25%; Stat Rep: RP-241214->RP-241933; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:25%->55%; Stat Rep: RP-241933->RP-242960; ; 6/3/25: FCD:23/03/2025->09/09/202 |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
480 | 1032083 | Perf. part: Enhancements for Air-to-ground network for NR | NR_ATG_enh-Perf | 2 | Rel-19 | R4 | 2024-10-13 16:00 | 2026-03-03 17:00 | 50% | RP-243285 | RP-252602 | CMCC |  | 13/6/24: Stat Rep: ->RP-241214; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241214->RP-241933; ; 6/12/24: FCD:03/03/2025->03/03/2026; Stat Rep: RP-241933->RP-242960; ; 6/3/25: Stat Rep: RP-242960->RP-250271; ; 6/6/25: Compl:0%->33%; Stat Rep: RP-25 |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
481 | 1040123 | Rel-19 High power UE (power class 1.5 or 2) for NR intra-band Carrier Aggregation (CA) or NR inter-band CA/Dual connectivity (DC) band combinations with/without NR Supplementary Uplink (UL) | HPUE_NR_CADC_SUL_R19 | 1 | Rel-19 |  | 2024-06-06 08:00 | 2024-09-09 17:00 | 85% | RP-252540 |  | China Telecom |  | 26/9/24: WID:RP-241679->RP-242003; 24/1/25: WID:RP-242003->RP-242754; 24/1/25: WID:RP-242754->RP-242865; 3/4/25: WID:RP-242865->RP-250806; 18/7/25: WID:RP-250806->RP-251450; 29/9/25: WID:RP-251450->RP-252540 |  | 104 | 53 |  |  | Tue 23/07/24 | Mon 29/09/25
482 | 1041123 | Core part: Rel-19 High power UE (power class 1.5 or 2) for NR intra-band Carrier Aggregation (CA) or NR inter-band CA/Dual connectivity (DC) band combinations with/without NR Supplementary Uplink (UL) | HPUE_NR_CADC_SUL_R19-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-12-12 17:00 | 85% | RP-252540 | RP-252541 | China Telecom |  | 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-242004; ; 26/9/24: 38.794 added;; 26/9/24: 38.746 added;; 26/9/24: 38.750 added;; 26/9/24: 38.792 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:10%->30%; Stat Rep: RP-242004->RP-24286 | 38.794; 38.746; 38.750; 38.792 | 104 | 53 |  |  | Tue 23/07/24 | Thu 11/09/25
483 | 1040124 | Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band for handheld/FWA UEs, and high power UE operation (power class 1) for FWVM (fixed-wireless/vehicle-mounted) use cases in a single NR band | HPUE_NR_FR1_bands_R19 | 1 | Rel-19 |  | 2024-06-06 08:00 | 2024-09-09 17:00 | 75% | RP-252606 |  | CMCC |  | 26/9/24: WID:RP-241680->RP-241932; 18/7/25: WID:RP-241932->RP-251402; 29/9/25: WID:RP-251402->RP-252606 |  | 104 | 53 |  |  | Tue 23/07/24 | Mon 29/09/25
484 | 1041124 | Core part: Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band for handheld/FWA Ues, and high power UE operation (power class 2, 1.5 and 1) for FWVM (fixed-wireless/vehicle-mounted) use cases in a single NR band | HPUE_NR_FR1_bands_R19-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-12-12 17:00 | 88% | RP-252606 | RP-252604 | CMCC |  | 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->15%; Stat Rep: ->RP-241931; ; 26/9/24: 38.795 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->30%; Stat Rep: RP-241931->RP-242959; ; 6/3/25: FCD:19/04/2025->09/09/2025; Compl:30%->55%; Stat Rep: RP-24 | 38.795 | 104 | 53 |  |  | Tue 23/07/24 | Thu 11/09/25
485 | 1080076 | UE Conformance - Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band for handheld/FWA UEs, and high power UE operation (power class 2, 1.5 and 1) for FWVM (fixed-wireless/vehicle-mounted) use cases in a single NR band | HPUE_NR_FR1_bands_R19-UEConTest | 2 | Rel-19 | R5 | 2025-06-06 08:00 | 2026-06-06 17:00 | 56% | RP-252598 | RP-252599 | CMCC |  | tested: REL-19 WI HPUE_NR_FR1_bands_R19-Core ; 11/9/25: Compl:0%->56%; Stat Rep: ->RP-252599; ; 29/9/25: WID:RP-251374->RP-252598 |  | 108 | 55 |  |  | Fri 18/07/25 | Mon 29/09/25
486 | 1040128 | Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28 | NR_n28_PC2_40MHz_CBW | 1 | Rel-19 |  | 2024-06-06 08:00 | 2024-12-12 17:00 | 96% | RP-243321 |  | CMCC |  | 26/9/24: WID:RP-241660->RP-241930; 24/1/25: WID:RP-241930->RP-243321 |  | 104 | 53 |  |  | Tue 23/07/24 | Fri 24/01/25
487 | 1041128 | Core part: Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28 | NR_n28_PC2_40MHz_CBW-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-06-06 17:00 | 100% | RP-243321 | RP-250273 | CMCC |  | 4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->20%; Stat Rep: ->RP-241929; ; 6/12/24: Compl:20%->99%; Stat Rep: RP-241929->RP-242957; ; 6/3/25: FCD:15/10/2024->06/06/2025; Compl:99%->100%; Stat Rep: RP-242957->RP-250273; |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 06/03/25
488 | 1070062 | UE Conformance - Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28 | NR_n28_PC2_40MHz_CBW-UEConTest | 2 | Rel-19 | R5 | 2025-03-03 08:00 | 2026-03-03 17:00 | 92% | RP-250249 | RP-252597 | CMCC |  | 6/6/25: Compl:0%->54%; Stat Rep: ->RP-251380; ; 11/9/25: Compl:54%->92%; Stat Rep: RP-251380->RP-252597; |  | 107 | 54 |  |  | Wed 26/03/25 | Thu 11/09/25
489 | 0 | Rel-19 Radio: NR and LTE | - | 1 | Rel-19 |  | 2019-03-07 07:00 | 2019-03-07 07:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
490 | 1040118 | Rel-19 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink | DL_intrpt_combos_TxSW_R19 | 1 | Rel-19 |  | 2024-06-06 08:00 | 2024-09-09 17:00 | 100% | RP-250369 |  | China Telecom |  | basket WI; no Perf. part; compare DL_intrpt_combos_TxSW_R18; TR 37.8xx ; 3/4/25: WID:RP-241672->RP-250369 |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 03/04/25
491 | 1041118 | Core part: Rel-19 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink | DL_intrpt_combos_TxSW_R19-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-09-09 17:00 | 100% | RP-250369 | RP-252539 | China Telecom |  | basket WI; no Perf. part; compare DL_intrpt_combos_TxSW_R18; TR 37.8xx ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-241999; ; 26/9/24: 37.887 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:10%->20%; Stat Rep: RP-241999->RP-2428 | 37.887 | 104 | 53 |  |  | Tue 23/07/24 | Thu 11/09/25
492 | 1040126 | Adding channel bandwidth(s) support to existing NR bands and CA/ENDC combinations in REL-19 | NR_bands_CA_ENDC_R19_BWs | 1 | Rel-19 |  | 2024-06-06 08:00 | 2024-09-09 17:00 | 100% | RP-252020 |  | Ericsson |  | basket WI; no Perf. part; compare: NR_bands_R18_BWs; TR 37.8xx ; 26/9/24: WID:RP-241684->RP-242402; 24/1/25: WID:RP-242402->RP-242604; 3/4/25: WID:RP-242604->RP-250524; 18/7/25: WID:RP-250524->RP-251160; 29/9/25: WID:RP-251160->RP-252020 |  | 104 | 53 |  |  | Tue 23/07/24 | Mon 29/09/25
493 | 1041126 | Core part: Adding channel bandwidth(s) support to existing NR bands and CA/ENDC combinations in REL-19 | NR_bands_CA_ENDC_R19_BWs-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-09-09 17:00 | 100% | RP-252020 | RP-252019 | Ericsson |  | basket WI; no Perf. part; compare: NR_bands_R18_BWs; TR 37.8xx ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->5%; WID: RP-241684->RP-231684; Stat Rep: ->RP-241757; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:5%->15%; Stat Rep: RP-241757->RP-242603; ; 6 |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 11/09/25
494 | 1040122 | Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s) | HPUE_DC_LTE_NR_R19 | 1 | Rel-19 |  | 2024-06-06 08:00 | 2024-09-09 17:00 | 43% | RP-252336 |  | China Unicom |  | basket WI; no Perf. part; compare HPUE_FR1_DC_LTE_NR_R18 and DC_R19_xBLTE_yBNR ; 26/9/24: WID:RP-241678->RP-242341; 24/1/25: WID:RP-242341->RP-242609; 3/4/25: WID:RP-242609->RP-250424; 18/7/25: WID:RP-250424->RP-251595; 29/9/25: WID:RP-251595->RP-252336 |  | 104 | 53 |  |  | Tue 23/07/24 | Mon 29/09/25
495 | 1041122 | Core part: Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s) | HPUE_DC_LTE_NR_R19-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-12-12 17:00 | 80% | RP-252336 | RP-252338 | China Unicom |  | basket WI; no Perf. part; compare HPUE_FR1_DC_LTE_NR_R18 and DC_R19_xBLTE_yBNR ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->15%; Stat Rep: ->RP-242019; ; 26/9/24: 37.898 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->30%; Stat Rep: RP-242019- | 37.898 | 104 | 53 |  |  | Tue 23/07/24 | Thu 11/09/25
496 | 1080081 | UE Conformance - Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s) | HPUE_DC_LTE_NR_R19-UEConTest | 2 | Rel-19 | R5 | 2025-06-06 08:00 | 2026-12-12 17:00 | 6% | RP-251512 | RP-251980 | China Unicom |  | tested: REL-19 WI HPUE_DC_LTE_NR_R19-Core ; 11/9/25: FCD:Sat 12/12/26->Thu 10/12/26; Compl:0%->6%; Stat Rep: ->RP-251980; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
497 | 1040125 | Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-19 | LTE_NR_R19_Simult_RxTx | 1 | Rel-19 |  | 2024-06-06 08:00 | 2024-09-09 17:00 | 80% | RP-251536 |  | Huawei |  | basket WI; no Perf. part; compare REL-18 WI LTE_NR_Simult_RxTx_R18 and REL-17 WI LTE_NR_Simult_RxTx; TR 37.8xx ; 26/9/24: WID:RP-241682->RP-242088; 18/7/25: WID:RP-242088->RP-251536 |  | 104 | 53 |  |  | Tue 23/07/24 | Fri 18/07/25
498 | 1041125 | Core part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-19 | LTE_NR_R19_Simult_RxTx-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-12-12 17:00 | 80% | RP-251536 | RP-252736 | Huawei |  | basket WI; no Perf. part; compare REL-18 WI LTE_NR_Simult_RxTx_R18 and REL-17 WI LTE_NR_Simult_RxTx; TR 37.8xx ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-242087; ; 26/9/24: 38.793 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Comp | 38.793 | 104 | 53 |  |  | Tue 23/07/24 | Tue 30/09/25
499 | 1040119 | Rel-19 Dual connectivity (DC) of x LTE band(s), y NR band(s) (1<=x<6, 1<=y<6, x+y<=6) and single or two NR Supplementary Uplink (SUL) bands | DC_R19_xBLTE_yBNR | 1 | Rel-19 |  | 2024-06-06 08:00 | 2024-09-09 17:00 | 80% | RP-252016 |  | Nokia |  | 26/9/24: WID:RP-241673->RP-241786; 24/1/25: WID:RP-241786->RP-243257; 3/4/25: WID:RP-243257->RP-250143; 18/7/25: WID:RP-250143->RP-250966; 29/9/25: WID:RP-250966->RP-252016 |  | 104 | 53 |  |  | Tue 23/07/24 | Mon 29/09/25
500 | 1041119 | Core part: Rel-19 Dual connectivity (DC) of x LTE band(s), y NR band(s) (1<=x<6, 1<=y<6, x+y<=6) and single or two NR Supplementary Uplink (SUL) bands | DC_R19_xBLTE_yBNR-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-12-12 17:00 | 80% | RP-252016 | RP-252015 | Nokia |  | 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-241785; ; 26/9/24: 37.719-11-11 added;; 26/9/24: 37.719-21-11 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:10%->15%; Stat Rep: RP-241785->RP-242535; ; 6/3/25: FCD:19/04/2025->09/09/2 | 37.719-11-10; 37.719-11-11; 37.719-21-11 | 104 | 53 |  |  | Tue 23/07/24 | Tue 30/09/25
501 | 1030077 | UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 | NR_ENDC_RF_Ph4 | 1 | Rel-19 |  | 2024-03-03 08:00 | 2025-03-03 17:00 | 83% | RP-251816 |  | Huawei |  | 23/7/24: WID:RP-240828->RP-241656; 3/4/25: WID:RP-241656->RP-250780; 18/7/25: WID:RP-250780->RP-251816 |  | 103 | 52 |  |  | Tue 02/04/24 | Fri 18/07/25
502 | 1031077 | Core part: UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 | NR_ENDC_RF_Ph4-Core | 2 | Rel-19 | R4 | 2024-03-03 08:00 | 2025-09-09 17:00 | 100% | RP-251816 | RP-252731 | Huawei |  | 13/6/24: Compl:0%->20%; Stat Rep: ->RP-241236; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:20%->35%; Stat Rep: RP-241236->RP-242084; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:35%->50%; Stat Rep: RP-242084->RP-243011; ; 6/3/25: FCD:23/03/2025->09/09/202 |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
503 | 1032077 | Perf. part: UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 | NR_ENDC_RF_Ph4-Perf | 2 | Rel-19 | R4 | 2024-03-03 08:00 | 2026-03-03 17:00 | 70% | RP-251816 | RP-252731 | Huawei |  | 4/9/24: FCD:03/03/2026->26/03/2025; Compl:0%->15%; Stat Rep: ->RP-242084; ; 6/12/24: FCD:03/03/2025->03/03/2026; Compl:15%->20%; Stat Rep: RP-242084->RP-243011; ; 6/3/25: FCD:22/07/2025->03/03/2026; Stat Rep: RP-243011->RP-250280; ; 6/6/25: Compl:20%->60% |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
504 | 1030082 | Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) | NonCol_intraB_ENDC_NR_CA_Ph2 | 1 | Rel-19 |  | 2024-03-03 08:00 | 2025-03-03 17:00 | 52% | RP-242083 |  | KDDI |  | 26/9/24: WID:RP-240838->RP-242083 |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 26/09/24
505 | 1031082 | Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) | NonCol_intraB_ENDC_NR_CA_Ph2-Core | 2 | Rel-19 | R4 | 2024-03-03 08:00 | 2025-09-09 17:00 | 100% | RP-242083 | RP-252366 | KDDI |  | 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->35%; Stat Rep: ->RP-242079; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:35%->45%; Stat Rep: RP-242079->RP-242842; ; 6/3/25: FCD:23/03/2025->09/09/2025; Compl:45%->50%; Stat Rep: RP-242842->RP-250279; ; 6/6/25 |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
506 | 1032082 | Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) | NonCol_intraB_ENDC_NR_CA_Ph2-Perf | 2 | Rel-19 | R4 | 2024-10-13 16:00 | 2026-03-03 17:00 | 0% | RP-242083 | RP-252366 | KDDI |  | 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: ->RP-242079; ; 6/12/24: FCD:03/03/2025->03/03/2026; Stat Rep: RP-242079->RP-242842; ; 6/3/25: Stat Rep: RP-242842->RP-250279; ; 6/6/25: Stat Rep: RP-250279->RP-251278; ; 11/9/25: Stat Rep: RP-251278->RP-252366 |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
507 | 1030085 | FR1 TRP, TRS and MIMO OTA testing enhancement Phase 3 | TRP_TRS_MIMO_OTA_Ph3 | 1 | Rel-19 |  | 2024-03-03 08:00 | 2025-03-03 17:00 | 86% | RP-252187 |  | Vivo |  | 23/7/24: WID:RP-240841->RP-241623; 24/1/25: WID:RP-241623->RP-243277; 3/4/25: WID:RP-243277->RP-250197; 29/9/25: WID:RP-250197->RP-252187 |  | 103 | 52 |  |  | Tue 02/04/24 | Mon 29/09/25
508 | 1031085 | Core part: FR1 TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 | TRP_TRS_MIMO_OTA_Ph3-Core | 2 | Rel-19 | R4 | 2024-03-03 08:00 | 2025-09-09 17:00 | 100% | RP-252187 | RP-252010 | Vivo |  | 13/6/24: Compl:0%->10%; Stat Rep: ->RP-241043; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:10%->20%; Stat Rep: RP-241043->RP-241828; ; 26/9/24: 38.762 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:20%->45%; Stat Rep: RP-241828->RP-242623; ; 6/3/25: F | 38.762 | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
509 | 1032085 | Perf. Part: FR1 TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 | TRP_TRS_MIMO_OTA_Ph3-Perf | 2 | Rel-19 | R4 | 2024-03-03 08:00 | 2026-03-03 17:00 | 75% | RP-252187 | RP-252010 | Vivo |  | 13/6/24: Stat Rep: ->RP-241043; ; 4/9/24: FCD:03/03/2026->26/03/2025; Compl:0%->5%; Stat Rep: RP-241043->RP-241828; ; 6/12/24: FCD:03/03/2025->03/03/2026; Compl:5%->25%; Stat Rep: RP-241828->RP-242623; ; 6/3/25: FCD:22/07/2025->03/03/2026; Compl:25%->35%; |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
510 | 1070063 | UE Conformance - Rel-19 NR CA and DC; and NR and LTE DC Configurations | NR_CADC_NR_LTE_DC_R19-UEConTest | 1 | Rel-19 | R5 | 2025-03-03 08:00 | 2026-12-12 17:00 | 5% | RP-250452 | RP-252649 | Huawei |  | 6/6/25: FCD:Sat 12/12/26->Fri 11/12/26; Compl:0%->5%; Stat Rep: ->RP-251492; ; 11/9/25: FCD:Fri 11/12/26->Thu 10/12/26; Stat Rep: RP-251492->RP-252649; |  | 107 | 54 |  |  | Wed 26/03/25 | Thu 11/09/25
511 | 0 | Rel-19 Radio: LTE | - | 1 | Rel-19 |  | 2019-03-07 07:00 | 2019-03-07 07:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
512 | 1070064 | New LTE band for 5G broadcast for region 3 utilizing a geosynchronous satellite | LTE_band_5G_bcast_GSO | 1 | Rel-19 | R4 | 2025-03-03 08:00 | 2026-03-03 17:00 | 34% | RP-251419 |  | Astrum Mobile |  | 18/7/25: WID:RP-250788->RP-251419 |  | 107 | 54 |  |  | Wed 26/03/25 | Fri 18/07/25
513 | 1071064 | Core part: New LTE band for 5G broadcast for region 3 utilizing a geosynchronous satellite | LTE_band_5G_bcast_GSO-Core | 2 | Rel-19 | R4 | 2025-03-03 08:00 | 2025-09-09 17:00 | 100% | RP-251419 | RP-251943 | Astrum Mobile |  | 6/6/25: Compl:0%->75%; WID: RP-250788->RP-251419; Stat Rep: ->RP-251276; ; 11/9/25: Compl:75%->100%; Stat Rep: RP-251276->RP-251943; |  | 107 | 54 |  |  | Wed 26/03/25 | Thu 11/09/25
514 | 1072064 | Perf. part: New LTE band for 5G broadcast for region 3 utilizing a geosynchronous satellite | LTE_band_5G_bcast_GSO-Perf | 2 | Rel-19 | R4 | 2025-03-03 08:00 | 2026-03-03 17:00 | 0% | RP-251419 | RP-251943 | Astrum Mobile |  | 6/6/25: WID: RP-250788->RP-251419; Stat Rep: ->RP-251276; ; 11/9/25: Stat Rep: RP-251276->RP-251943; |  | 107 | 54 |  |  | Wed 26/03/25 | Thu 11/09/25
515 | 1060081 | LTE-based 5G Broadcast Phase 2 | LTE_terr_bcast_Ph2 | 1 | Rel-19 |  | 2024-05-19 08:00 | 2025-12-12 17:00 | 59% | RP-250794 |  | EBU |  | 3/4/25: WID:RP-243290->RP-250794 |  | 106 | 54 |  |  | Fri 24/01/25 | Thu 03/04/25
516 | 1061081 | Core part: LTE-based 5G Broadcast Phase 2 | LTE_terr_bcast_Ph2-Core | 2 | Rel-19 | R1 | 2024-10-14 14:00 | 2025-09-09 17:00 | 100% | RP-250794 | RP-251975 | EBU |  | 6/3/25: FCD:07/09/2025->09/09/2025; Compl:0%->40%; Stat Rep: ->RP-250238; ; 6/6/25: Compl:40%->95%; Stat Rep: RP-250238->RP-251143; ; 11/9/25: Compl:95%->100%; Stat Rep: RP-251143->RP-251975; |  | 106 | 54 |  |  | Fri 24/01/25 | Thu 11/09/25
517 | 1062081 | Perf. part: LTE-based 5G Broadcast Phase 2 | LTE_terr_bcast_Ph2-Perf | 2 | Rel-19 | R4 | 2024-11-11 16:00 | 2025-12-12 17:00 | 25% | RP-250794 | RP-251975 | EBU |  | 6/3/25: Stat Rep: ->RP-250238; ; 6/6/25: Stat Rep: RP-250238->RP-251143; ; 11/9/25: Compl:0%->25%; Stat Rep: RP-251143->RP-251975; |  | 106 | 54 |  |  | Fri 24/01/25 | Thu 11/09/25
518 | 1060080 | New bands for LTE based 5G terrestrial broadcast for early deployments | LTE_terr_bcast_bands_sub_108 | 1 | Rel-19 |  | 2024-05-19 08:00 | 2025-06-06 17:00 | 100% | RP-250793 |  | EBU |  | 3/4/25: WID:RP-243268->RP-250793 |  | 106 | 54 |  |  | Fri 24/01/25 | Thu 03/04/25
519 | 1061080 | New bands for LTE based 5G terrestrial broadcast for early deployments | LTE_terr_bcast_bands_sub_108-Core | 2 | Rel-19 | R4 | 2024-09-14 11:00 | 2025-06-06 17:00 | 100% | RP-250793 | RP-251141 | EBU |  | 6/3/25: Compl:0%->40%; Stat Rep: ->RP-250235; ; 6/6/25: Compl:40%->100%; Stat Rep: RP-250235->RP-251141; |  | 106 | 54 |  |  | Fri 24/01/25 | Fri 06/06/25
520 | 1040117 | Introduction of LTE FDD band in 1800–1830 MHz for Canada | LTE_FDD_1800_1830MHz_CAN | 1 | Rel-19 |  | 2024-06-06 08:00 | 2025-03-03 17:00 | 100% | RP-242461 |  | Novamint |  | ; 26/9/24: WID:RP-241649->RP-241739; 24/1/25: WID:RP-241739->RP-242461 |  | 104 | 53 |  |  | Tue 23/07/24 | Fri 24/01/25
521 | 1041117 | Core part: Introduction of LTE FDD band in 1800–1830 MHz for Canada | LTE_FDD_1800_1830MHz_CAN-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-03-03 17:00 | 100% | RP-242461 | RP-250105 | Novamint |  | ; 4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->25%; Stat Rep: ->RP-241738; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:25%->99%; Stat Rep: RP-241738->RP-242460; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:99%->100%; Stat Rep: RP-242460->RP-250105; |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 06/03/25
522 | 1042117 | Perf.part: Introduction of LTE FDD band in 1800–1830 MHz for Canada | LTE_FDD_1800_1830MHz_CAN-Perf | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-03-03 17:00 | 100% | RP-242461 | RP-250105 | Novamint |  | ; 4/9/24: FCD:03/03/2025->25/03/2025; Stat Rep: ->RP-241738; ; 6/12/24: Compl:0%->99%; Stat Rep: RP-241738->RP-242460; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:99%->100%; Stat Rep: RP-242460->RP-250105; |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 06/03/25
523 | 1040116 | Rel-19 High power UE (power class 2) and high power operation (power class 1) for fixed-wireless/vehicle-mounted use cases in a single LTE band | HPUE_LTE_bands_R19 | 1 | Rel-19 |  | 2024-06-06 08:00 | 2024-09-09 17:00 | 100% | RP-241681 |  | Nokia |  | basket WI; no Perf. part; TR 36.8xx |  | 104 | 53 |  |  | Tue 23/07/24 | NA
524 | 1041116 | Core part: Rel-19 High power UE (power class 2) and high power operation (power class 1) for fixed-wireless/vehicle-mounted use cases in a single LTE band | HPUE_LTE_bands_R19-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-09-09 17:00 | 100% | RP-242086 | RP-250899 | Nokia |  | basket WI; no Perf. part; TR 36.8xx ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-241814; ; 26/9/24: 36.767 added;; 6/12/24: FCD:09/09/2024->09/09/2025; WID: RP-241681->RP-242086; Stat Rep: RP-241814->RP-242499; ; 6/3/25: FCD:19/04/ | 36,767 | 104 | 53 |  |  | Tue 23/07/24 | Tue 30/09/25
525 | 1040115 | Rel-19 LTE-Advanced Carrier Aggregation for x bands (1<=x<= 6) DL with y bands (y=1, 2) UL | LTE_CA_R19_xBDL_yBUL | 1 | Rel-19 |  | 2024-06-06 08:00 | 2025-06-06 17:00 | 85% | RP-252735 |  | Huawei |  | basket WI; no Perf. part; TR 36.8xx; compare REL-18 WI LTE_CA_R18_xBDL_yBUL ; 26/9/24: WID:RP-241676->RP-242086; 24/1/25: WID:RP-242086->RP-243014; 3/4/25: WID:RP-243014->RP-250282; 18/7/25: WID:RP-250282->RP-251534; 29/9/25: WID:RP-251534->RP-252735 |  | 104 | 53 |  |  | Tue 23/07/24 | Mon 29/09/25
526 | 1041115 | Core part: Rel-19 LTE-Advanced Carrier Aggregation for x bands (1<=x<= 6) DL with y bands (y=1, 2) UL | LTE_CA_R19_xBDL_yBUL-Core | 2 | Rel-19 | R4 | 2024-06-06 08:00 | 2025-12-12 17:00 | 85% | RP-252735 | RP-252733 | Huawei |  | basket WI; no Perf. part; TR 36.8xx; compare REL-18 WI LTE_CA_R18_xBDL_yBUL ; 4/9/24: FCD:09/09/2025->24/06/2025; Compl:0%->10%; Stat Rep: ->RP-242085; ; 26/9/24: 36.719-01-01 added;; 6/12/24: FCD:06/06/2025->09/09/2025; Compl:10%->31%; Stat Rep: RP-2420 | 36.719-01-01 | 104 | 53 |  |  | Tue 23/07/24 | Thu 11/09/25
527 | 0 | Rel-19 other topics | - | 1 | Rel-19 |  | 2019-03-07 07:00 | 2019-03-07 07:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
528 | 1070023 | Specification of example algorithm for alternative f5* (f5**) function | Crypto_f5** | 1 | Rel-19 | S3 | 2025-03-06 08:00 | 2025-06-06 17:00 | 100% | SP-250360 |  | Ferhat Karakoc | ferhat.karakoc@ericsson.com | ; 26/3/25: 35.249 added;; 26/3/25: 23.369 added;; 26/3/25: 23.700-14 added;; 17/9/25: 0%->100 | 33.102; 35.205; 35.231 ; 35.249; 23.369; 23.700-14 | 107 | 54 |  |  | Wed 05/03/25 | Wed 17/09/25
529 | 1060056 | Study on 3GPP Cryptographic Inventory | FS_CryptoInv | 1 | Rel-19 | S3 | 2024-12-05 08:00 | 2025-06-06 17:00 | 100% | SP-241955 |  | Stawros Orkopoulos | stawros.orkopoulos@nokia.com | 6/3/25: 0%->25; 5/6/25: 25%->100 |  | 106 | 54 |  |  | Thu 05/12/24 | Thu 05/06/25
530 | 1040012 | CHF Segmentation | CHFSeg | 1 | Rel-19 | S5 | 2024-06-12 08:00 | 2025-09-09 17:00 | 100% | SP-250122 |  | Cetinkaya Egemen Kemal,Verizon | (egemen.cetinkaya@verizon.com) | ; 4/9/24: 5%->25; 5/12/24: 25%->55; 6/3/25: 55%->60; 26/3/25: WID:SP-241001->SP-250122; 26/3/25: FCD:11/12/2024->/25; 6/6/25: 60%->90; 12/9/25: 90%->100 | 32.290; 32.291 | 104 | 53 |  |  | Wed 12/06/24 | Fri 12/09/25
531 | 1050121 | Introduction of BDS (BeiDou Navigation Satellite System) B2b Signal in A-GNSS for LTE and NR | LCS_BDS_B2b_LTE_NR | 1 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | RP-252083 |  | CAICT |  | 24/1/25: WID:RP-242413->RP-242459; 3/4/25: WID:RP-242459->RP-250767; 29/9/25: WID:RP-250767->RP-252083 |  | 105 | 53 |  |  | Thu 26/09/24 | Mon 29/09/25
532 | 1051121 | Core part: Introduction of BDS (BeiDou Navigation Satellite System) B2b Signal in A-GNSS for LTE and NR | LCS_BDS_B2b_LTE_NR-Core | 2 | Rel-19 | R2 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | RP-252083 | RP-252106 | CAICT |  | 6/12/24: FCD:06/06/2025->09/09/2025; Compl:0%->70%; Stat Rep: ->RP-242580; ; 6/3/25: FCD:20/05/2025->09/09/2025; Compl:70%->99%; WID: RP-242459->RP-250330; Stat Rep: RP-242580->RP-250329; ; 6/6/25: Stat Rep: RP-250329->RP-251012; ; 11/9/25: Compl:99%->10 |  | 105 | 53 |  |  | Thu 26/09/24 | Thu 11/09/25
533 | 1052121 | Perf. part: Introduction of BDS (BeiDou Navigation Satellite System) B2b Signal in A-GNSS for LTE and NR | LCS_BDS_B2b_LTE_NR-Perf | 2 | Rel-19 | R4 | 2024-12-30 16:00 | 2025-09-09 17:00 | 100% | RP-252083 | RP-252106 | CAICT |  | 6/12/24: Stat Rep: ->RP-242580; ; 6/3/25: WID: RP-242459->RP-250330; Stat Rep: RP-242580->RP-250329; ; 6/6/25: Compl:0%->99%; Stat Rep: RP-250329->RP-251012; ; 11/9/25: Compl:99%->100%; Stat Rep: RP-251012->RP-252106; |  | 105 | 53 |  |  | Thu 26/09/24 | Thu 11/09/25
534 | 1050122 | Introduction of A-GNSS support for NavIC (Navigation with Indian Constellation) L1 SPS (Standard Positioning Service) in NR & LTE | LCS_NAVIC_L1_SPS_NR_LTE | 1 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | RP-251552 |  | Reliance Jio |  | 24/1/25: WID:RP-242414->RP-243247; 18/7/25: WID:RP-243247->RP-251552 |  | 105 | 53 |  |  | Thu 26/09/24 | Fri 18/07/25
535 | 1051122 | Core part: Introduction of A-GNSS support for NavIC (Navigation with Indian Constellation) L1 SPS (Standard Positioning Service) in NR & LTE | LCS_NAVIC_L1_SPS_NR_LTE-Core | 2 | Rel-19 | R2 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | RP-251552 | RP-251554 | Reliance Jio |  | 6/12/24: Compl:0%->50%; Stat Rep: ->RP-243246; ; 6/3/25: FCD:16/03/2025->06/06/2025; Compl:50%->80%; Stat Rep: RP-243246->RP-250047; ; 6/6/25: FCD:Fri 06/06/25->Tue 09/09/25; Compl:80%->99%; Stat Rep: RP-250047->RP-251554; ; 30/9/25: 99%->100 |  | 105 | 53 |  |  | Thu 26/09/24 | Tue 30/09/25
536 | 1052122 | Perf. part: Introduction of A-GNSS support for NavIC (Navigation with Indian Constellation) L1 SPS (Standard Positioning Service) in NR & LTE | LCS_NAVIC_L1_SPS_NR_LTE-Perf | 2 | Rel-19 | R4 | 2024-12-30 16:00 | 2025-06-06 17:00 | 100% | RP-251552 | RP-251554 | Reliance Jio |  | 6/12/24: Stat Rep: ->RP-243246; ; 6/3/25: Stat Rep: RP-243246->RP-250047; ; 6/6/25: FCD:Tue 09/09/25->Fri 06/06/25; Compl:0%->100%; Stat Rep: RP-250047->RP-251554; |  | 105 | 53 |  |  | Thu 26/09/24 | Fri 06/06/25
537 | 1050033 | Data management regarding subscriptions and reporting | Data_SREP | 1 | Rel-19 | S5 | 2024-12-28 09:00 | 2025-09-09 17:00 | 100% | SP-241380 |  | Robert Petersen (Ericsson) | robert.petersen@ericsson.com | ; 6/6/25: 0%->40; 12/9/25: 40%->100 | 28.537; 28.550; 28.532; 32.421; 32.422; 32.423; 28.404; 28.405; 28.622; 28.623 | 105 | 53 |  |  | Wed 04/09/24 | Fri 12/09/25
538 | 1040071 | Study on MC services support on IOPS mode of operation for 5G | FS_Generic_IOPS | 1 | Rel-19 | S6 | 2024-07-16 08:00 | 2024-12-12 17:00 | 100% | SP-241017 |  | FirstNet, Mark Lipford | mark.lipford@firstnet.gov | 4/9/24: 0%->40; 26/9/24: 23.700-09 added;; 5/12/24: 40%->100; 5/12/24: FCD:06/06/2025->12/24; 5/12/24: 40%->100 | 23.700-09 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/12/24
539 | 1050036 | MC services for generic support on IOPS mode of operation | Generic_IOPS | 1 | Rel-19 | S6 | 2024-09-04 08:00 | 2024-12-12 17:00 | 100% | SP-241382 |  | FirstNet, Mark Lipford | mark.lipford@firstnet.gov | ; 5/12/24: 0%->100; 5/12/24: 100%->65; 6/3/25: 65%->100 | 23.180 | 105 | 53 |  |  | Wed 04/09/24 | Thu 06/03/25
540 | 1050114 | Monitoring of signalling traffic in 5G | MonSTra | 1 | Rel-19 | S1 | 2024-05-06 08:00 | 2024-12-12 17:00 | 99% | SP-240793 |  | Cristina Romaguera | cristina.romaguera@vodafone.com | ; 12/6/24: 0%->100 | 22.261 | 105 | 53 |  |  | Wed 12/06/24 | Wed 12/06/24
541 | 1040082 | Stage 1 for MonSta | MonSTra | 2 | Rel-19 | S1 | 2024-05-06 08:00 | 2024-06-06 17:00 | 100% | SP-240793 |  | Cristina Romaguera | cristina.romaguera@vodafone.com | ; 12/6/24: 0%->100 | 22.261 | 104 | 53 |  |  | Wed 12/06/24 | Wed 12/06/24
542 | 1050028 | Security for MonStra | MonStra-Sec | 2 | Rel-19 | S3 | 2024-10-04 13:00 | 2024-12-12 17:00 | 100% | SP-241376 |  | Vodafone, Susana Sabater | susana.sabatr@vodafone.com | ; 17/9/25: 0%->100 | 33.501 | 105 | 53 |  |  | Wed 04/09/24 | Wed 17/09/25
543 | 1060012 | Management for MonStra | Monstra-OAM | 2 | Rel-19 | S5 | 2024-12-05 08:00 | 2024-12-10 15:00 | 100% | SP-241945 |  | Susana Sabater (Vodafone) | susana.sabater@vodafone.com | 5/12/24: 0%->80; 6/6/25: 80%->100 |  | 106 | 54 |  |  | Thu 05/12/24 | Fri 06/06/25
544 | 1040036 | Enhancement of support for Edge Computing in 5G Core network - Phase 3 | eEDGE_5GC_Ph3 | 1 | Rel-19 |  | 2024-01-04 08:00 | 2025-09-09 17:00 | 99% | SP-241284 |  | Changhong Shan (Intel) | chang.hong.shan@intel.com | ; 26/9/24: WID:SP-240996->SP-241284; 6/3/25: 82%-> | 23.501; 23.502; 23.548; 23.503 | 104 | 53 |  |  | Wed 12/06/24 | Thu 06/03/25
545 | 1020004 | Study on Enhancement of support for Edge Computing in 5G Core network - Phase 3 | FS_eEDGE_5GC_Ph3 | 2 | Rel-19 | S2 | 2024-01-04 08:00 | 2024-09-09 17:00 | 100% | SP-240962 |  | Changhong Shan (Intel) | chang.hong.shan@intel.com | 14/3/24: 0%->50; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 50%->90; 16/7/24: WID:SP-231796->SP-240962; 4/9/24: 90%->100 |  | 102 | 52 |  |  | Wed 03/01/24 | Wed 04/09/24
546 | 1030036 | Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC phase 3 | FS_EDGE_Ph3 | 2 | Rel-19 | S3 | 2024-04-02 08:00 | 2024-12-12 17:00 | 100% | SP-240510 |  | Ge Yao, | yaog9@chinaunicom.cn | 3/4/24: 33.749 added;; 13/6/24: 0%->30; 5/9/24: 30%->60; 5/12/24: 60%->95; 6/3/25: 95%->100; 5/6/25: 100%->100 | 33.749 | 103 | 52 |  |  | Thu 14/03/24 | Thu 05/06/25
547 | 1060064 | Security Aspects of Enhancement of Support for Edge Computing in 5GC phase 3 | EDGE_Ph3 | 2 | Rel-19 | S3 | 2025-01-02 09:00 | 2025-03-03 17:00 | 100% | SP-241959 |  | TBD |  | 17/9/25: 0%->100 | 33.501; 33.558 | 106 | 54 |  |  | Thu 05/12/24 | Wed 17/09/25
548 | 1050050 | Stage 2 of Enhancement of support for Edge Computing in 5G Core network - Phase 3 | eEDGE_5GC_Ph3 | 2 | Rel-19 | S2 | 2024-06-12 08:00 | 2024-12-12 17:00 | 100% | SP-241505 |  | Meghashree Dattatri Kedalagudde (Intel); | meghashree.dattatri.kedalagudde@intel.com | ; 4/9/24: 0%->30; 5/12/24: 30%->97; 8/1/25: WID:SP-240996->SP-241505 (Rapp change); 6/3/25: 97%->100 | 23.501; 23.502; 23.548; 23.503 | 105 | 53 |  |  | Wed 12/06/24 | Thu 06/03/25
549 | 1050006 | CT aspects of Enhancement of support for Edge Computing in 5G Core network - Phase 3 | eEDGE_5GC_Ph3 | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 99% | CP-250016 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com |  | 29.244, 29.502, 29.503, 29.504, 29.510, 29.556 , 29.571, 29.512, 29.513, 29.514, 29.519, 29.522, 29.591, 29.244, 29.502, 29.503, 29.504, 29.510, 29.556 , 29.571, 29.512, 29.513, 29.514, 29.519, 29.522, 29.591, 29.518 | 105 | 53 |  |  | Wed 12/06/24 | NA
550 | 1050051 | CT3 aspects of Enhancement of support for Edge Computing in 5G Core network - Phase 3 | eEDGE_5GC_Ph3 | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2025-09-09 17:00 | 98% | CP-250016 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
551 | 1050052 | CT4 aspects of Enhancement of support for Edge Computing in 5G Core network - Phase 3 | eEDGE_5GC_Ph3 | 3 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-250016 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
552 | 1050056 | Multi-Access (ATSSS_Ph4) | MASSS | 1 | Rel-19 |  | 2024-01-04 08:00 | 2025-09-09 17:00 | 100% | SP-240994 |  | Krisztian Kiss (Apple), | krisztian@apple.com |  | 23.501; 23.502; 23.503 | 105 | 53 |  |  | Wed 12/06/24 | NA
553 | 1020070 | Study on Multi-Access (DualSteer and ATSSS_Ph4) | FS_MASSS | 2 | Rel-19 | S2 | 2024-01-04 08:00 | 2024-09-09 17:00 | 100% | SP-240467 |  | Krisztian Kiss (Apple) | krisztian@apple.com | 14/3/24: 0%->30; 2/4/24: WID:SP-231802->SP-240467; 2/4/24: FCD:09/09/2024->/24; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 30%->70; 4/9/24: 70%->100 |  | 102 | 52 |  |  | Wed 03/01/24 | Wed 04/09/24
554 | 1030037 | Study on security aspects for Multi-Access (DualSteer + ATSSS Ph-4) | FS_MASSS_Sec | 2 | Rel-19 | S3 | 2024-04-02 08:00 | 2024-12-12 17:00 | 100% | SP-240511 |  | Kolekar, Abhijeet (Intel) | abhijeet.kolekar@intel.com | 3/4/24: 33.754 added;; 13/6/24: 0%->45; 5/9/24: 45%->95; 5/12/24: 95%->100; 6/3/25: 100%->100 | 33.754 | 103 | 52 |  |  | Thu 14/03/24 | Thu 06/03/25
555 | 1040034 | Stage 2 of Multi-Access (ATSSS_Ph4) | MASSS | 2 | Rel-19 | S2 | 2024-06-12 08:00 | 2024-12-12 17:00 | 100% | SP-241331 |  | Krisztian Kiss (Apple), | krisztian@apple.com | ; 4/9/24: 0%->50; 26/9/24: WID:SP-240994->SP-241331; 5/12/24: 50%->100 | 23.501; 23.502; 23.503 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/12/24
556 | 1050020 | CT aspects of Multi-Access (ATSSS_Ph4) | MASSS | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-251226 |  | Gupta, Vivek, Apple | vivek_g_gupta@apple.com |  | 24.193, 24.501, 24.302, 27.007, 29.512, 29.244, 29.571 | 105 | 53 |  |  | Wed 12/06/24 | NA
557 | 1050057 | CT1 aspects of Multi-Access (ATSSS_Ph4) | MASSS | 3 | Rel-19 | C1 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-251226 |  | Gupta, Vivek, Apple | vivek_g_gupta@apple.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
558 | 1050058 | CT3 aspects of Multi-Access (ATSSS_Ph4) | MASSS | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-251226 |  | Gupta, Vivek, Apple | vivek_g_gupta@apple.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
559 | 1050059 | CT4 aspects of Multi-Access (ATSSS_Ph4) | MASSS | 3 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-251226 |  | Gupta, Vivek, Apple | vivek_g_gupta@apple.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
560 | 1050066 | System architecture for Next Generation Real time Communication services Phase 2 | NG_RTC_Ph2 | 1 | Rel-19 |  | 2023-09-20 08:00 | 2025-09-09 17:00 | 98% | SP-240985 |  | Yi Jiang, China Mobile | jiangyi at chinamobile dot com | ; 16/7/24: WID:SP-240625->SP-240985 | 23.228; 23.502 | 105 | 53 |  |  | Wed 12/06/24 | Tue 16/07/24
561 | 1010030 | Study on system architecture for next generation real time communication services phase 2 | FS_NG_RTC_Ph2 | 2 | Rel-19 | S2 | 2023-09-20 08:00 | 2024-09-09 17:00 | 100% | SP-231196 |  | Yi Jiang (China Mobile) | jiangyi@chinamobile.com | 9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-77 added;; 8/12/23: 0%->15; 14/3/24: 15%->45; 13/6/24: FCD:05/06/2024->/24; 13/6/24: 45%->95; 5/12/24: 95%->100 | 23.700-77 | 101 | 51 |  |  | Wed 20/09/23 | Thu 05/12/24
562 | 1040016 | Study on Charging aspects of next generation real time communication services phase 2 | FS_NG_RTC_Ph2_CH | 2 | Rel-19 | S5 | 2024-06-12 08:00 | 2024-12-11 12:00 | 100% | SP-240982 |  | Chen Ai, China Mobile | chenai@chinamobile.com | 13/6/24: 0%->10; 4/9/24: 10%->45; 26/9/24: 28.851 added;; 5/12/24: 45%->75; 5/12/24: FCD:12/12/2024->/25; 6/3/25: 75%->100 | 28.851 | 104 | 53 |  |  | Wed 12/06/24 | Thu 06/03/25
563 | 1040026 | Stage 2 of System architecture for Next Generation Real time Communication services Phase 2 | NG_RTC_Ph2 | 2 | Rel-19 | S2 | 2024-06-12 08:00 | 2024-10-17 12:00 | 99% | SP-241384 |  | Yi Jiang, China Mobile | jiangyi at chinamobile dot com | ; 16/7/24: WID:SP-240625->SP-240985; 4/9/24: 0%->10; 26/9/24: WID:SP-240985->SP-241384; 5/12/24: 10%->70; 6/3/25: 70%->98; 5/6/25: 98%->99 | 23.228; 23.502 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/06/25
564 | 1050022 | CT aspects of System architecture for Next Generation Real time Communication services Phase 2 | NG_RTC_Ph2 | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 96% | CP-242250 |  | Chen Xu, China Mobile | chenxu@chinamobile.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | Tue 16/07/24
565 | 1050067 | CT1 aspects of System architecture for Next Generation Real time Communication services Phase 2 | NG_RTC_Ph2 | 3 | Rel-19 | C1 | 2024-09-09 08:00 | 2025-09-09 17:00 | 95% | CP-242250 |  | Chen Xu, China Mobile | chenxu@chinamobile.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | Tue 16/07/24
566 | 1050068 | CT3 aspects of System architecture for Next Generation Real time Communication services Phase 2 | NG_RTC_Ph2 | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2025-09-09 17:00 | 97% | CP-242250 |  | Chen Xu, China Mobile | chenxu@chinamobile.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | Tue 16/07/24
567 | 1050069 | CT4 aspects of System architecture for Next Generation Real time Communication services Phase 2 | NG_RTC_Ph2 | 3 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-09-09 17:00 | 95% | CP-242250 |  | Chen Xu, China Mobile | chenxu@chinamobile.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | Tue 16/07/24
568 | 1050070 | CT6 aspects of System architecture for Next Generation Real time Communication services Phase 2 | NG_RTC_Ph2 | 3 | Rel-19 | C6 | 2024-12-30 16:00 | 2025-09-09 17:00 | 100% | CP-242250 |  | Chen Xu, China Mobile | chenxu@chinamobile.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | Tue 16/07/24
569 | 1070016 | Charging aspects of next generation real time communication services phase 2 | NG_RTC_Ph2-CH | 2 | Rel-19 | S5 | 2025-03-26 08:00 | 2025-09-09 17:00 | 100% | SP-250513 |  | Chen Ai, China Mobile | chenai@chinamobile.com | ; 6/6/25: 0%->70; 27/6/25: WID:SP-250367->SP-250513; 12/9/25: 70%->100 | 32.254; 32.255; 32.260; 32.291; 32.298 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
570 | 1070044 | Rel-19 Application Data Analytics Enablement Service | TEI19_ADAES | 1 | Rel-19 |  | 2024-12-07 10:00 | 2025-09-09 17:00 | 96% | SP-241695 |  | Yue, Jing, Ericsson | jing.yue@ericsson.com |  | 23.436 | 107 | 54 |  |  | Thu 05/12/24 | NA
571 | 1060068 | Stage 2 of Rel-19 Application Data Analytics Enablement Service | TEI19_ADAES | 2 | Rel-19 | S6 | 2024-12-07 10:00 | 2024-12-12 17:00 | 100% | SP-241695 |  | Yue, Jing, Ericsson | jing.yue@ericsson.com | ; 3/4/25: 0%->100 | 23.436 | 106 | 54 |  |  | Thu 05/12/24 | Thu 03/04/25
572 | 1070004 | CT aspects of Rel-19 Application Data Analytics Enablement Service | TEI19_ADAES | 2 | Rel-19 |  | 2025-03-06 08:00 | 2025-09-09 17:00 | 96% | CP-250074 |  | Pastushok, Igor, Ericsson | igor.pastushok@ericsson.com |  | 29.549 | 107 | 54 |  |  | Thu 05/12/24 | NA
573 | 1070045 | CT3 aspects of Rel-19 Application Data Analytics Enablement Service | TEI19_ADAES | 3 | Rel-19 | C3 | 2025-03-06 08:00 | 2025-09-09 17:00 | 96% | CP-250074 |  | Pastushok, Igor, Ericsson | igor.pastushok@ericsson.com |  | 29.549 | 107 | 54 |  |  | Thu 05/12/24 | NA
574 | 1070046 | MSISDN verification operation support to Nnef_UEId Service | TEI19_MVOSNS | 1 | Rel-19 |  | 2024-12-07 10:00 | 2025-06-06 17:00 | 100% | SP-241498 |  | Rohit Abhishek (AT&T) | ra503n@att.com |  | 23.502; 23.501 | 107 | 54 |  |  | Thu 05/12/24 | NA
575 | 1060028 | Stage 2 of MSISDN verification operation support to Nnef_UEId Service | TEI19_MVOSNS | 2 | Rel-19 | S2 | 2024-12-07 10:00 | 2024-12-12 17:00 | 100% | SP-241498 |  | Rohit Abhishek (AT&T) | ra503n@att.com | ; 26/3/25: 0%->100 | 23.502; 23.501 | 106 | 54 |  |  | Thu 05/12/24 | Wed 26/03/25
576 | 1070007 | CT aspects of MSISDN verification operation support to Nnef_UEId Service | TEI19_MVOSNS | 2 | Rel-19 |  | 2025-03-03 08:00 | 2025-06-06 17:00 | 100% | CP-250077 |  | Shahram Mohajeri, AT&T | sm7084@att.com |  | 29.522 | 107 | 54 |  |  | Thu 05/12/24 | NA
577 | 1070047 | CT3 aspects of MSISDN verification operation support to Nnef_UEId Service | TEI19_MVOSNS | 3 | Rel-19 | C3 | 2025-03-03 08:00 | 2025-06-06 17:00 | 100% | CP-250077 |  | Shahram Mohajeri, AT&T | sm7084@att.com |  | 29.522 | 107 | 54 |  |  | Thu 05/12/24 | NA
578 | 1070041 | Network Controlled Network Slice Selection | TEI19_SliceSel | 1 | Rel-19 |  | 2024-12-07 10:00 | 2025-09-09 17:00 | 100% | SP-241502 |  | Saito, Koji, KDDI | kj-saitou_at_kddi_dot_com |  | 23.501; 23.502; 23.503 | 107 | 54 |  |  | Thu 05/12/24 | NA
579 | 1060030 | Stage 2 of Network Controlled Network Slice Selection | TEI19_SliceSel | 2 | Rel-19 | S2 | 2024-12-07 10:00 | 2024-12-12 17:00 | 100% | SP-241502 |  | Saito, Koji, KDDI | kj-saitou_at_kddi_dot_com | ; 26/3/25: 0%->100 | 23.501; 23.502; 23.503 | 106 | 54 |  |  | Thu 05/12/24 | Wed 26/03/25
580 | 1070003 | CT aspects of Network Controlled Network Slice Selection | TEI19_SliceSel | 2 | Rel-19 |  | 2025-03-03 08:00 | 2025-09-09 17:00 | 100% | CP-251133 |  | Xiaojian Yan, ZTE | yan.xiaojian@zte.com.cn |  | 29.522, 29.534, 29.519, 29.507, 29.523, 29.502, 29.504, 29.518 | 107 | 54 |  |  | Thu 05/12/24 | NA
581 | 1070042 | CT3 aspects of Network Controlled Network Slice Selection | TEI19_SliceSel | 3 | Rel-19 | C3 | 2025-03-03 08:00 | 2025-09-09 17:00 | 100% | CP-251133 |  | Xiaojian Yan, ZTE | yan.xiaojian@zte.com.cn |  |  | 107 | 54 |  |  | Thu 05/12/24 | NA
582 | 1070043 | CT4 aspects of Network Controlled Network Slice Selection | TEI19_SliceSel | 3 | Rel-19 | C4 | 2025-03-03 08:00 | 2025-09-09 17:00 | 100% | CP-251133 |  | Xiaojian Yan, ZTE | yan.xiaojian@zte.com.cn |  |  | 107 | 54 |  |  | Thu 05/12/24 | NA
583 | 1070039 | PRU Usage Extension supported by Core Network | TEI19_PRUE | 1 | Rel-19 |  | 2024-12-07 10:00 | 2025-06-06 17:00 | 100% | SP-241504 |  | Hou, Yunjing, CATT | houyunjing@catt.cn |  |  | 107 | 54 |  |  | Thu 05/12/24 | NA
584 | 1060031 | Stage 2 of PRU Usage Extension supported by Core Network | TEI19_PRUE | 2 | Rel-19 | S2 | 2024-12-07 10:00 | 2024-12-12 17:00 | 100% | SP-241504 |  | Hou, Yunjing, CATT | houyunjing@catt.cn | 26/3/25: 0%->100 |  | 106 | 54 |  |  | Thu 05/12/24 | Wed 26/03/25
585 | 1070001 | CT aspects of PRU Usage Extension supported by Core Network | TEI19_PRUE | 2 | Rel-19 |  | 2025-03-03 08:00 | 2025-06-06 17:00 | 100% | CP-250017 |  | Wang, Baixiao, CATT | wangbaixiao@cictmobile.com |  | 29.572 | 107 | 54 |  |  | Thu 05/12/24 | NA
586 | 1070040 | CT4 aspects of PRU Usage Extension supported by Core Network | TEI19_PRUE | 3 | Rel-19 | C4 | 2025-03-03 08:00 | 2025-06-06 17:00 | 100% | CP-250017 |  | Wang, Baixiao, CATT | wangbaixiao@cictmobile.com |  | 29.572 | 107 | 54 |  |  | Thu 05/12/24 | NA
587 | 1050078 | On-demand broadcast of GNSS assistance data | TEI19_OBGAD | 1 | Rel-19 |  | 2024-04-02 08:00 | 2025-09-09 17:00 | 100% | SP-240487 |  | Aihua Li, China Mobile | <liaihua@chinamobile.com> |  | 23.502; 23.273 | 103 | 52 |  |  | Wed 13/03/24 | NA
588 | 1030010 | Stage 2 of On-demand broadcast of GNSS assistance data | TEI19_OBGAD | 2 | Rel-19 | S2 | 2024-04-02 08:00 | 2024-12-12 17:00 | 100% | SP-240487 |  | Aihua Li, China Mobile | <liaihua@chinamobile.com> | ; 4/9/24: 0%->100 | 23.502; 23.273 | 103 | 52 |  |  | Wed 13/03/24 | Wed 04/09/24
589 | 1050003 | CT aspects of On-demand broadcast of GNSS assistance data | TEI19_OBGAD | 2 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-242023 |  | Rong Wang, China Mobile | wangrongyjy@chinamobile.com |  |  | 103 | 52 |  |  | Wed 13/03/24 | NA
590 | 1050079 | CT4 aspects of On-demand broadcast of GNSS assistance data | TEI19_OBGAD | 3 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-242023 |  | Rong Wang, China Mobile | wangrongyjy@chinamobile.com |  |  | 103 | 52 |  |  | Wed 13/03/24 | NA
591 | 1080039 | ATSSS Rule Provisioning via 3GPP access connected to EPC | TEI19_ARP3E | 1 | Rel-19 | S2 | 2024-12-07 10:00 | 2025-06-06 17:00 | 100% | SP-241500 |  | Chunhui Zhu (NEC) | zhu_chunhui@nec.cn | ; 26/3/25: 0%->100 | 23.502 | 106 | 54 |  |  | Thu 05/12/24 | Wed 26/03/25
592 | 1060029 | Stage 2 of ATSSS Rule Provisioning via 3GPP access connected to EPC | TEI19_ARP3E | 2 | Rel-19 | S2 | 2024-12-07 10:00 | 2024-12-12 17:00 | 100% | SP-241500 |  | Chunhui Zhu (NEC) | zhu_chunhui@nec.cn | ; 26/3/25: 0%->100 | 23.502 | 106 | 54 |  |  | Thu 05/12/24 | Wed 26/03/25
593 | 1080020 | CT aspects of ATSSS Rule Provisioning via 3GPP access connected to EPC | TEI19_ARP3E-CT | 2 | Rel-19 | C1 | 2025-06-06 08:00 | 2025-06-06 17:00 | 100% | CP-251217 |  | Chunhui Zhu (NEC) | zhu_chunhui@nec.cn | ; 26/3/25: 0%->100 | 24.193 | 106 | 54 |  |  | Thu 05/12/24 | Wed 26/03/25
594 | 1080040 | CT1 aspects of ATSSS Rule Provisioning via 3GPP access connected to EPC | TEI19_ARP3E-CT | 3 | Rel-19 | C1 | 2025-06-06 08:00 | 2025-06-06 17:00 | 100% | CP-251217 |  | Chunhui Zhu (NEC) | zhu_chunhui@nec.cn | ; 26/3/25: 0%->100 | 24.193 | 106 | 54 |  |  | Thu 05/12/24 | Wed 26/03/25
595 | 1030012 | Minimize the Number of Policy Associations | TEI19_MINPA | 1 | Rel-19 |  | 2024-06-17 08:00 | 2025-03-03 17:00 | 100% | SP-240118 |  | Ericsson, Belen Pancorbo | belen . pancorbo {@} ericsson . com) |  | 23.502; 23.501; 23.503 | 103 | 52 |  |  | Wed 13/03/24 | NA
596 | 1040078 | Stage 2 of Minimize the Number of Policy Associations | TEI19_MINPA | 2 | Rel-19 | S2 | 2024-06-17 08:00 | 2025-03-03 17:00 | 100% | SP-240118 |  | Ericsson, Belen Pancorbo | belen . pancorbo {@} ericsson . com) | 13/6/24: 0%->100 |  | 101 | 51 |  |  | Wed 06/09/23 | Thu 13/06/24
597 | 1040004 | CT Aspects on Minimize the Number of Policy Associations | TEI19_MINPA | 2 | Rel-19 |  | 2024-06-17 08:00 | 2025-03-03 17:00 | 100% | CP-241295 |  | Jones Lu, Ericsson | jones.lu@ericsson.com |  | TS 29.503,TS 29.507,TS 29.513,TS 29.518,TS 29.525 | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
598 | 1040052 | CT3 Aspects on Minimize the Number of Policy Associations | TEI19_MINPA | 3 | Rel-19 | C3 | 2024-06-17 08:00 | 2025-03-03 17:00 | 100% | CP-241295 |  | Jones Lu, Ericsson | jones.lu@ericsson.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
599 | 1040053 | CT4 Aspects on Minimize the Number of Policy Associations | TEI19_MINPA | 3 | Rel-19 | C4 | 2024-06-17 08:00 | 2025-03-03 17:00 | 100% | CP-241295 |  | Jones Lu, Ericsson | jones.lu@ericsson.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
600 | 1050089 | Spending Limits for UE Policies in Roaming scenario | TEI19_SLUPiR | 1 | Rel-19 |  | 2024-03-13 08:00 | 2024-12-12 17:00 | 100% | SP-240486 |  | uri baniel, oracle | uri dot baniel at oracle dot com | ; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100 | 23.502; 23.501; 23.503 | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
601 | 1030014 | Stage 2 of Spending Limits for UE Policies in Roaming scenario | TEI19_SLUPiR | 2 | Rel-19 | S2 | 2024-03-13 08:00 | 2024-06-06 17:00 | 100% | SP-240486 |  | uri baniel, oracle | uri dot baniel at oracle dot com | ; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100 | 23.502; 23.501; 23.503 | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
602 | 1050011 | CT aspects of Spending Limits for UE Policies in Roaming scenario | TEI19_SLUPiR | 2 | Rel-19 |  | 2024-09-09 08:00 | 2024-12-12 17:00 | 100% | CP-242060 |  | SUN, Yue, China Telecom | suny20@chinatelecom.cn |  |  | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
603 | 1050090 | CT3 aspects of Spending Limits for UE Policies in Roaming scenario | TEI19_SLUPiR | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2024-12-12 17:00 | 100% | CP-242060 |  | SUN, Yue, China Telecom | suny20@chinatelecom.cn |  |  | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
604 | 1030015 | Enhancing Parameter Provisioning with static UE IP address and UP security policy | TEI19_IP_SP_EXP | 1 | Rel-19 |  | 2023-12-26 08:00 | 2025-06-06 17:00 | 100% | SP-240121 |  | Stefan Rommer, Ericsson | stefan . rommer @ ericsson . com) |  | 23.501; 23.502 | 103 | 52 |  |  | Wed 13/03/24 | NA
605 | 1040079 | Stage 2 of Enhancing Parameter Provisioning with static UE IP address and UP security policy | TEI19_IP_SP_EXP | 2 | Rel-19 | S2 | 2023-12-26 08:00 | 2024-12-12 17:00 | 100% | SP-240121 |  | Stefan Rommer, Ericsson | stefan . rommer @ ericsson . com) | 19/6/24: FCD:06/06/2025->12/20; 4/9/24: 0%->100 |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 04/09/24
606 | 1040007 | CT aspects of Enhancing Parameter Provisioning with static UE IP address and UP security policy | TEI19_IP_SP_EXP | 2 | Rel-19 |  | 2024-06-17 08:00 | 2025-06-06 17:00 | 100% | CP-243076 |  | Maria Tianmei, Liang, Ericsson | maria.liang@ericsson.co |  | 29.503,29.522,29.503,29.522 | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
607 | 1040056 | CT3 aspects of Enhancing Parameter Provisioning with static UE IP address and UP security policy | TEI19_IP_SP_EXP | 3 | Rel-19 | C3 | 2024-06-17 08:00 | 2025-06-06 17:00 | 100% | CP-243076 |  | Maria Tianmei, Liang, Ericsson | maria.liang@ericsson.co |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
608 | 1040057 | CT4 aspects of Enhancing Parameter Provisioning with static UE IP address and UP security policy | TEI19_IP_SP_EXP | 3 | Rel-19 | C4 | 2024-06-17 08:00 | 2025-06-06 17:00 | 100% | CP-243076 |  | Maria Tianmei, Liang, Ericsson | maria.liang@ericsson.co |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
609 | 1030017 | Multiple Location Procedure for Emergency LCS Routing | TEI19_MLR4RTR | 1 | Rel-19 | S2 | 2024-03-13 08:00 | 2024-12-12 17:00 | 100% | SP-240123 |  | Simon Cai (Nokia Shanghai-Bell)Simon<dot>Ca<at> nokia<dash>sbell<dot>com | Simon<dot>Ca<at> nokia<dash>sbell<dot>com | ; 5/12/24: 0%->100 | 23.273 | 103 | 52 |  |  | Wed 13/03/24 | Thu 05/12/24
610 | 1030018 | Roaming traffic offloading via session breakout in HPLMN | TEI19_HSBO | 1 | Rel-19 | S2 | 2024-04-02 08:00 | 2024-12-12 17:00 | 100% | SP-240491 |  | Hyesung Kim, Samsung | hs1207.kim@samsung.com | ; 5/12/24: 0%->100 | 23.501 | 103 | 52 |  |  | Wed 13/03/24 | Thu 05/12/24
611 | 1060043 | Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports | TEI19_DLPMR | 1 | Rel-19 |  | 2024-03-13 08:00 | 2025-03-03 17:00 | 100% | SP-240125 |  | Richard, Batorfi, Ericsson, | richard.batorfi@ericsson.com |  | 23.273 | 103 | 52 |  |  | Wed 13/03/24 | NA
612 | 1030019 | Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports | TEI19_DLPMR | 2 | Rel-19 | S2 | 2024-03-13 08:00 | 2024-12-12 17:00 | 100% | SP-240125 |  | Richard, Batorfi, Ericsson, | richard.batorfi@ericsson.com | ; 5/12/24: 0%->100 | 23.273 | 103 | 52 |  |  | Wed 13/03/24 | Thu 05/12/24
613 | 1060004 | CT aspects of Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports | TEI19_DLPMR | 2 | Rel-19 | C4 | 2024-12-02 08:00 | 2025-02-03 16:00 | 100% | CP-243048 |  | Jones Lu, Ericsson | jones.lu@ericsson.com |  | 29.515, 29.518, 29.572 | 103 | 52 |  |  | Wed 13/03/24 | NA
614 | 1060044 | CT4 aspects of Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports | TEI19_DLPMR | 3 | Rel-19 | C4 | 2024-12-02 08:00 | 2025-03-03 17:00 | 100% | CP-243048 |  | Jones Lu, Ericsson | jones.lu@ericsson.com |  |  | 103 | 52 |  |  | Wed 13/03/24 | NA
615 | 1050084 | QoS monitoring enhancement | TEI19_QME | 1 | Rel-19 |  | 2024-04-02 08:00 | 2025-06-06 17:00 | 100% | SP-240961 |  | Aihua Li, China Mobile | <liaihua@chinamobile.com> | ; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100; 16/7/24: WID:SP-240489->SP-240961 | 23.501; 23.502 | 103 | 52 |  |  | Wed 13/03/24 | Tue 16/07/24
616 | 1030020 | Stage 2 of QoS monitoring enhancement | TEI19_QME | 2 | Rel-19 | S2 | 2024-04-02 08:00 | 2024-06-06 17:00 | 100% | SP-240961 |  | Aihua Li, China Mobile | <liaihua@chinamobile.com> | ; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100; 16/7/24: WID:SP-240489->SP-240961 | 23.501; 23.502 | 103 | 52 |  |  | Wed 13/03/24 | Tue 16/07/24
617 | 1050012 | CT aspects of QoS monitoring enhancement | TEI19_QME | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-06-06 17:00 | 100% | CP-243312 |  | Huang, Zhenning, China Mobile | huangzhenning@chinamobile.com |  | 29.122, 29.502, 29.512, 29.514, 29.522, 29.565 | 103 | 52 |  |  | Wed 13/03/24 | Tue 16/07/24
618 | 1050085 | CT3 aspects of QoS monitoring enhancement | TEI19_QME | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2025-06-06 17:00 | 100% | CP-243312 |  | Huang, Zhenning, China Mobile | huangzhenning@chinamobile.com |  |  | 103 | 52 |  |  | Wed 13/03/24 | Tue 16/07/24
619 | 1050086 | CT4 aspects of QoS monitoring enhancement | TEI19_QME | 3 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-06-06 17:00 | 100% | CP-243312 |  | Huang, Zhenning, China Mobile | huangzhenning@chinamobile.com |  |  | 103 | 52 |  |  | Wed 13/03/24 | Tue 16/07/24
620 | 1060045 | Subscription control for reference time distribution in EPS | TEI19_TIME_SUB_EPS | 1 | Rel-19 |  | 2024-03-13 08:00 | 2024-12-12 17:00 | 100% | SP-240127 |  | Sebastian Speicher, Qualcomm | speicher AT qti DOT qualcomm DOT com) | ; 4/9/24: 0%->100 |  | 103 | 52 |  |  | Wed 13/03/24 | Wed 04/09/24
621 | 1030021 | Stage 2 of Subscription control for reference time distribution in EPS | TEI19_TIME_SUB_EPS | 2 | Rel-19 | S2 | 2024-03-13 08:00 | 2024-12-12 17:00 | 100% | SP-240127 |  | Sebastian Speicher, Qualcomm | speicher AT qti DOT qualcomm DOT com) | ; 4/9/24: 0%->100 | 23.401 | 103 | 52 |  |  | Wed 13/03/24 | Wed 04/09/24
622 | 1060001 | CT aspects of Subscription control for reference time distribution in EPS | TEI19_TIME_SUB_EPS | 2 | Rel-19 |  | 2024-12-02 08:00 | 2024-12-12 17:00 | 100% | CP-243017 |  | Hanna Lim, Qualcomm Incorporated | hannalim@qti.qualcomm.com |  | 29.272, 29.274, 29.230, 23.008 | 103 | 52 |  |  | Wed 13/03/24 | Wed 04/09/24
623 | 1060046 | CT4 aspects of Subscription control for reference time distribution in EPS | TEI19_TIME_SUB_EPS | 3 | Rel-19 | C4 | 2024-12-02 08:00 | 2024-12-12 17:00 | 100% | CP-243017 |  | Hanna Lim, Qualcomm Incorporated | hannalim@qti.qualcomm.com |  |  | 103 | 52 |  |  | Wed 13/03/24 | Wed 04/09/24
624 | 1030022 | Providing per-subscriber VLAN instructions from UDM and DN-AAA | TEI19_VLANSUB | 1 | Rel-19 |  | 2023-12-26 08:00 | 2025-06-06 17:00 | 100% | SP-240128 |  | Stefan Rommer, Ericsson | stefan . rommer @ ericsson . com) |  | 23.501; 23.502 | 103 | 52 |  |  | Wed 13/03/24 | NA
625 | 1040080 | Stage 2 of Providing per-subscriber VLAN instructions from UDM and DN-AAA | TEI19_VLANSUB | 2 | Rel-19 | S2 | 2023-12-26 08:00 | 2024-12-12 17:00 | 100% | SP-240128 |  | Stefan Rommer, Ericsson | stefan . rommer @ ericsson . com) | 19/6/24: FCD:06/06/2025->12/20; 5/12/24: 0%->100 |  | 101 | 51 |  |  | Wed 06/09/23 | Thu 05/12/24
626 | 1040006 | CT aspects of Providing per-subscriber VLAN instructions from UDM and DN-AAA | TEI19_VLANSUB | 2 | Rel-19 |  | 2024-06-17 08:00 | 2025-06-06 17:00 | 100% | CP-250078 |  | Maria Tianmei, Liang, Ericsson | maria.liang@ericsson.co |  | 29.503,29.561,29.230,29.244 | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
627 | 1040054 | CT3 aspects of Providing per-subscriber VLAN instructions from UDM and DN-AAA | TEI19_VLANSUB | 3 | Rel-19 | C3 | 2024-06-17 08:00 | 2025-06-06 17:00 | 100% | CP-250078 |  | Maria Tianmei, Liang, Ericsson | maria.liang@ericsson.co |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
628 | 1040055 | CT4 aspects of Providing per-subscriber VLAN instructions from UDM and DN-AAA | TEI19_VLANSUB | 3 | Rel-19 | C4 | 2024-06-17 08:00 | 2025-06-06 17:00 | 100% | CP-250078 |  | Maria Tianmei, Liang, Ericsson | maria.liang@ericsson.co |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
629 | 1050076 | NF discovery and selection by target PLMN | TEI19_NFsel_by_tPLMN | 1 | Rel-19 |  | 2024-04-02 08:00 | 2025-09-09 17:00 | 100% | SP-240490 |  | Dr. Thomas Belling, Nokia, | thomas (dot) belling (at) nokia (dot) com | ; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100 | 23.501; 23.502 | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
630 | 1030023 | Stage 2 of NF discovery and selection by target PLMN | TEI19_NFsel_by_tPLMN | 2 | Rel-19 | S2 | 2024-04-02 08:00 | 2024-06-06 17:00 | 100% | SP-240490 |  | Dr. Thomas Belling, Nokia, | thomas (dot) belling (at) nokia (dot) com | ; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100 | 23.501; 23.502 | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
631 | 1050005 | CT aspects of NF discovery and selection by target PLMN | TEI19_NFsel_by_tPLMN | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-242025 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com |  |  | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
632 | 1050077 | CT4 aspects of NF discovery and selection by target PLMN | TEI19_NFsel_by_tPLMN | 3 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-242025 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com |  |  | 103 | 52 |  |  | Wed 13/03/24 | Thu 13/06/24
633 | 1020057 | Integrated Sensing and Communication | Sensing | 1 | Rel-19 |  | 2022-03-10 08:00 | 2023-12-12 17:00 | 100% | SP-230750 |  | Aleksiev, Vasil, Deutsche Telekom AG | vasil.aleksiev@magenta.at | 6/9/23: 0%->80; 8/12/23: 80%->100 | 22.137 | 100 | 51 |  |  | Thu 08/06/23 | Fri 08/12/23
634 | 950003 | Study on Integrated Sensing and Communication | FS_Sensing | 2 | Rel-19 | S1 | 2022-03-10 08:00 | 2023-09-09 17:00 | 100% | SP-220717 |  | Aleksiev, Vasil, Deutsche Telekom | Vasil.Aleksiev@magenta.at | 5/4/22: 22.837 added;; 4/6/22: 0%->10; 21/6/22: WID:SP-220084->SP-220717; 9/9/22: 10%->40; 10/12/22: 40%->65; 17/3/23: 65%->80; 8/6/23: 80%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->100 | 22.837 | 95 | 48 |  |  | Thu 10/03/22 | Wed 06/09/23
635 | 1000026 | Stage 1 of Integrated Sensing and Communication | Sensing | 2 | Rel-19 | S1 | 2023-06-08 08:00 | 2023-12-12 17:00 | 100% | SP-230750 |  | Aleksiev, Vasil, Deutsche Telekom AG | vasil.aleksiev@magenta.at | 6/9/23: 0%->80; 8/12/23: 80%->100 | 22.137 | 100 | 51 |  |  | Thu 08/06/23 | Fri 08/12/23
636 | 1020086 | Study on channel modelling for Integrated Sensing And Communication (ISAC) for NR | FS_Sensing_NR | 1 | Rel-19 | R1 | 2023-12-13 08:00 | 2025-06-06 17:00 | 100% | RP-242348 | RP-251474 | Yingyang Li, Jerome Vogedes, Xiaomi, AT&T | liyingyang@xiaomi.com, jerome.vogedes@att.com | 14/3/24: Compl:0%->6%; Stat Rep: ->RP-240114; Rapporteur: Xiaomi->Yingyang Li, Jerome Vogedes, Xiaomi, AT&T; Rap eMail: ->liyingyang@xiaomi.com, jerome.vogedes@att.com; ; 2/4/24: WID:RP-234069->RP-240799; 13/6/24: Compl:6%->22%; Stat Rep: RP-240114->RP... |  | 102 | 52 |  |  | Tue 02/01/24 | Fri 06/06/25
637 | 1020059 | Uncrewed Aerial System Phase 3 | UAS_Ph3 | 1 | Rel-19 |  | 2022-06-02 08:00 | 2025-09-09 17:00 | 100% | SP-230518 |  | Pengtai Qin , China Mobile | qinpengtai@chinamobile.com | 6/9/23: 0%->95; 8/12/23: 95%->100 |  | 100 | 51 |  |  | Thu 08/06/23 | Fri 08/12/23
638 | 960017 | Study on (Stage 1 of) UAV Phase 3 | FS_UAV_Ph3 | 2 | Rel-19 | S1 | 2022-06-02 08:00 | 2023-09-09 17:00 | 100% | SP-220954 |  | Pengtai Qin , China Mobile | qinpengtai@chinamobile.com | 17/8/22: WID:SP-220444->SP-220680; 9/9/22: 0%->20; 23/9/22: WID:SP-220680->SP-220954; 10/12/22: 20%->45; 17/3/23: 45%->65; 8/6/23: 65%->95; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 95%->100 |  | 96 | 49 |  |  | Thu 02/06/22 | Wed 06/09/23
639 | 1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 2 | Rel-19 | S2 | 2024-01-04 08:00 | 2024-09-09 17:00 | 100% | SP-231801 |  | LaeYoung Kim (LG Electronics) | laeyoung.kim@lge.com | 14/3/24: 0%->50; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 50%->90; 4/9/24: 90%->100 |  | 102 | 52 |  |  | Wed 03/01/24 | Wed 04/09/24
640 | 1000032 | Stage 1 of Uncrewed Aerial System Phase 3 | UAS_Ph3 | 2 | Rel-19 | S1 | 2023-06-08 08:00 | 2023-12-12 17:00 | 100% | SP-230518 |  | Pengtai Qin , China Mobile | qinpengtai@chinamobile.com | 6/9/23: 0%->95; 8/12/23: 95%->100 |  | 100 | 51 |  |  | Thu 08/06/23 | Fri 08/12/23
641 | 1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 2 | Rel-19 | S2 | 2024-06-12 08:00 | 2024-12-12 17:00 | 100% | SP-241287 |  | LaeYoung Kim (LG Electronics) | laeyoung.kim@lge.com | ; 4/9/24: 0%->65; 26/9/24: WID:SP-240997->SP-241287; 5/12/24: 65%->99; 6/3/25: 99%->100; 5/6/25: 100%->100 | 23.256; 23.288; 23.503; 23.502; 23.401 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/06/25
642 | 1050013 | CT aspects of UAS, UAV and UAM Phase 3 | UAS_Ph3 | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-251136 |  | Sunhee Kim, LG Electronics | sunhee.kim@lge.com |  | 24.501, 24.301, 27.007, 29.122, 29.255, 29.256, 29.503, 29.518, 29.520, 29.522 | 105 | 53 |  |  | Wed 12/06/24 | NA
643 | 1050091 | CT1 aspects of UAS, UAV and UAM Phase 3 | UAS_Ph3 | 3 | Rel-19 | C1 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-251136 |  | Sunhee Kim, LG Electronics | sunhee.kim@lge.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
644 | 1050092 | CT3 aspects of UAS, UAV and UAM Phase 3 | UAS_Ph3 | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-251136 |  | Sunhee Kim, LG Electronics | sunhee.kim@lge.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
645 | 1060047 | CT4 aspects of UAS, UAV and UAM Phase 3 | UAS_Ph3 | 3 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-251136 |  | Sunhee Kim, LG Electronics | sunhee.kim@lge.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
646 | 1060058 | Security of Uncrewed Aerial System Phase 3 | UAS_Ph3_Sec | 2 | Rel-19 | S3 | 2025-01-02 09:00 | 2025-03-03 17:00 | 100% | SP-241773 |  | Markus Hanhisalo, Ericsson | markus.hanhisalo@ericsson.com | ; 17/9/25: 0%->100 | 33.256 | 106 | 54 |  |  | Thu 05/12/24 | Wed 17/09/25
647 | 1070017 | Charging for Uncrewed Aerial Systems Phase 3 | UAS_Ph3-CH | 2 | Rel-19 | S5 | 2025-03-26 08:00 | 2025-09-09 17:00 | 100% | SP-250512 |  | Jia Dong, China Mobile | dongjia@chinamobile.com | ; 6/6/25: 0%->45; 27/6/25: WID:SP-250396->SP-250512; 12/9/25: 45%->100 | 32.240; 32.255; 32.256; 32.291; 32.298 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
648 | 1010008 | Application Architecture for UAS applications Phase 3 | UASAPP_Ph3 | 2 | Rel-19 | S6 | 2023-09-07 08:00 | 2024-12-12 17:00 | 100% | SP-240741 |  | Roy, Michel, InterDigital | michel.roy@interdigital.com | ; 8/12/23: 0%->20; 14/3/24: 20%->40; 13/6/24: 40%->60; 16/7/24: WID:SP-230991->SP-240741; 4/9/24: 60%->75; 5/12/24: 75%->100 | 23.255; 23.434 | 101 | 51 |  |  | Thu 07/09/23 | Thu 05/12/24
649 | 1040043 | CT Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS), Phase 3 | UASAPP_Ph3 | 2 | Rel-19 |  | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-241281 |  | Taimoor Abbas, InterDigital | taimoor.abbas@interdigital.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
650 | 1040069 | CT1 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS), Phase 3 | UASAPP_Ph3 | 3 | Rel-19 | C1 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-241281 |  | Taimoor Abbas, InterDigital | taimoor.abbas@interdigital.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
651 | 1040070 | CT3 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS), Phase 3 | UASAPP_Ph3 | 3 | Rel-19 | C3 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-241281 |  | Taimoor Abbas, InterDigital | taimoor.abbas@interdigital.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
652 | 1030033 | UAS security enhancements | FS_UAS_Ph3_Sec | 2 | Rel-19 | S3 | 2024-04-02 08:00 | 2024-12-12 17:00 | 100% | SP-240504 |  | Markus Hanhisalo, | markus.hanhisalo@ericsson.com | 3/4/24: 33.759 added;; 13/6/24: 0%->50; 5/12/24: 50%->100; 6/3/25: 100%->100 | 33.759 | 103 | 52 |  |  | Thu 14/03/24 | Thu 06/03/25
653 | 960018 | Study on Upper layer traffic steering, switching and split over dual 3GPP access | FS_DualSteer | 1 | Rel-19 | S1 | 2022-06-02 08:00 | 2023-09-09 17:00 | 100% | SP-220445 |  | Francesco Pica; Qualcomm |  | 13/7/22: 22.841 added;; 9/9/22: 0%->30; 10/12/22: 30%->60; 17/3/23: 60%->75; 8/6/23: 75%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->95; 8/12/23: 95%->100 | 22.841 | 96 | 49 |  |  | Thu 02/06/22 | Fri 08/12/23
654 | 1040017 | Study on Charging aspects of Uncrewed Aerial Systems | FS_UAS_CH | 1 | Rel-19 | S5 | 2024-06-12 08:00 | 2024-12-11 12:00 | 100% | SP-240983 |  | Jia Dong, China Mobile, | dongjia@chinamobile.com | 4/9/24: 0%->40; 26/9/24: 28.853 added;; 5/12/24: 40%->75; 5/12/24: FCD:12/12/2024->/25; 6/3/25: 75%->100 | 28.853 | 104 | 53 |  |  | Wed 12/06/24 | Thu 06/03/25
655 | 1020031 | Upper layer traffic steering and switching over dual 3GPP access | DualSteer | 1 | Rel-19 | S1 | 2023-12-07 08:00 | 2023-12-10 15:00 | 95% | SP-231412 |  | Pica Francesco, Qualcomm | fpica<at>qti.qualcomm.com | ; 8/12/23: 0%->95 | 22.261 | 102 | 52 |  |  | Thu 07/12/23 | Fri 08/12/23
656 | 1010022 | Edge Computing Considering the Operational Needs of Service Hosting Environment | EdgeOpNeeds | 1 | Rel-19 | S1 | 2023-08-21 08:00 | 2023-09-09 17:00 | 100% | SP-231037 |  | Yuying Zhang, China Telecom | zhangyy45@chinatelecom.cn | ; 6/9/23: 0%->100 | 22.261 | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
657 | 1060048 | 5G NR Femto | 5G_Femto | 1 | Rel-19 |  | 2024-01-04 08:00 | 2025-09-09 17:00 | 100% | SP-241327 |  | Malla Reddy Sama | sama@docomolab-euro.com | ; 4/9/24: 0%->30; 26/9/24: WID:SP-240629->SP-241327 | 23.501; 23.502 | 104 | 53 |  |  | Wed 12/06/24 | Thu 26/09/24
658 | 1020002 | Study on System aspects of 5G NR Femto | FS_5G_Femto | 2 | Rel-19 | S2 | 2024-01-04 08:00 | 2024-09-09 17:00 | 100% | SP-231797 |  | Malla Reddy Sama (NTT DOCOMO) | sama@docomolab-euro.com | 14/3/24: 0%->40; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 40%->90; 4/9/24: 90%->100; 4/9/24: 100%-> |  | 102 | 52 |  |  | Wed 03/01/24 | Wed 04/09/24
659 | 1040028 | System aspects of 5G NR Femto | 5G_Femto | 2 | Rel-19 | S2 | 2024-06-12 08:00 | 2024-12-12 17:00 | 100% | SP-241327 |  | Malla Reddy Sama | sama@docomolab-euro.com | ; 4/9/24: 0%->30; 26/9/24: WID:SP-240629->SP-241327; 5/12/24: 30%->100 | 23.501; 23.502 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/12/24
660 | 1060002 | CT aspects of 5G NR Femto | 5G_Femto | 2 | Rel-19 | C4 | 2024-12-12 08:00 | 2025-09-09 17:00 | 100% | CP-250020 |  | Dojiri, Shunsuke, NTT DOCOMO | dojiri@nttdocomo.com |  | 29.503, 29.504, 29.505, 29.522, 29.571 | 104 | 53 |  |  | Wed 12/06/24 | Thu 26/09/24
661 | 1060049 | CT3 aspects of 5G NR Femto | 5G_Femto | 3 | Rel-19 | C3 | 2024-12-12 08:00 | 2025-09-09 17:00 | 100% | CP-250020 |  | Dojiri, Shunsuke, NTT DOCOMO | dojiri@nttdocomo.com |  |  | 104 | 53 |  |  | Wed 12/06/24 | Thu 26/09/24
662 | 1060050 | CT4 aspects of 5G NR Femto | 5G_Femto | 3 | Rel-19 | C4 | 2024-12-12 08:00 | 2025-09-09 17:00 | 100% | CP-250020 |  | Dojiri, Shunsuke, NTT DOCOMO | dojiri@nttdocomo.com |  |  | 104 | 53 |  |  | Wed 12/06/24 | Thu 26/09/24
663 | 1030028 | Study on security aspects of 5G NR Femto Document for: Approval | FS_5G_Femto_Sec | 2 | Rel-19 | S3 | 2024-04-02 08:00 | 2024-12-12 17:00 | 100% | SP-240505 |  | Peilin LIU (ZTE) | liu.peilin@zte.com.cn , | 3/4/24: 33.745 added;; 13/6/24: 0%->30; 5/9/24: 30%->60; 5/12/24: 60%->98; 6/3/25: 98%->100; 5/6/25: 100%->100 | 33.745 | 103 | 52 |  |  | Thu 14/03/24 | Thu 05/06/25
664 | 1060062 | Security aspects of 5G NR Femto | 5G_Femto_Sec | 2 | Rel-19 | S3 | 2025-01-30 11:00 | 2025-06-06 17:00 | 100% | SP-241958 |  | Liu,Peilin liu.peilin@zte.com.cn | Song,Hua songhua@chinamobile.com | 17/9/25: 0%->100 |  | 106 | 54 |  |  | Thu 05/12/24 | Wed 17/09/25
665 | 1050115 | Proximity-based Services in 5GS Phase 3 | 5G_ProSe_Ph3 | 1 | Rel-19 |  | 2024-01-04 08:00 | 2025-09-09 17:00 | 99% | SP-231037 |  | Hugh Shieh (AT&T) | hs6220@att.com |  |  | 102 | 52 |  |  | Wed 06/09/23 | Wed 06/09/23
666 | 1020066 | Study on Proximity-based Services in 5GS Phase 3 | FS_5G_ProSe_Ph3 | 2 | Rel-19 | S2 | 2024-01-04 08:00 | 2024-09-09 17:00 | 100% | SP-231798 |  | Hugh Shieh (AT&T) | hs6220@att.com | 14/3/24: 0%->45; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 45%->90; 4/9/24: 90%->100 |  | 102 | 52 |  |  | Wed 03/01/24 | Wed 04/09/24
667 | 1040030 | Proximity-based Services in 5GS Phase 3 | 5G_ProSe_Ph3 | 2 | Rel-19 | S2 | 2024-06-12 08:00 | 2024-12-12 17:00 | 100% | SP-240988 |  | Nassima Toumi (KPN N.V.) | nassima.toumi@tno.nl | ; 4/9/24: 0%->70; 5/12/24: 70%->100 | 23.304 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/12/24
668 | 1050023 | CT aspects of Proximity-based Services in 5GS Phase 3 | 5G_ProSe_Ph3 | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 99% | CP-243266 |  | Zhao, Xiaoxue (CATT) | zhaoxiaoxue@cictmobile.com | ; 26/9/24: WID:CP-242108->SP-241290 | 24.554, 24.555, 24.501, 24.587, 29.519, 29.522, 29.525, 29.503, 29.504, 29.518, 29.510, 29.555, 29.559, 29.571, 31.102 | 105 | 53 |  |  | Wed 12/06/24 | Thu 26/09/24
669 | 1050038 | CT1 aspects of Proximity-based Services in 5GS Phase 3 | 5G_ProSe_Ph3 | 3 | Rel-19 | C1 | 2024-09-09 08:00 | 2025-09-09 17:00 | 98% | CP-243266 |  | Zhao, Xiaoxue (CATT) | zhaoxiaoxue@cictmobile.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
670 | 1050116 | CT3 aspects of Proximity-based Services in 5GS Phase 3 | 5G_ProSe_Ph3 | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-243266 |  | Zhao, Xiaoxue (CATT) | zhaoxiaoxue@cictmobile.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
671 | 1050039 | CT4 aspects of Proximity-based Services in 5GS Phase 3 | 5G_ProSe_Ph3 | 3 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-243266 |  | Zhao, Xiaoxue (CATT) | zhaoxiaoxue@cictmobile.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
672 | 1050040 | CT6 aspects of Proximity-based Services in 5GS Phase 3 | 5G_ProSe_Ph3 | 3 | Rel-19 | C6 | 2024-12-30 16:00 | 2025-09-09 17:00 | 100% | CP-243266 |  | Zhao, Xiaoxue (CATT) | zhaoxiaoxue@cictmobile.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
673 | 1060057 | Security Aspects of Proximity Based Services in 5GS Phase 3 | 5G_ProSe_Sec_Ph3 | 2 | Rel-19 | S3 | 2024-12-05 08:00 | 2025-03-03 17:00 | 100% | SP-241956 |  | Primary Rapporteur: Ao Lei (Huawei) | leiao@huawei.com | ; 6/3/25: 0%->95; 6/3/25: FCD:03/03/2025->/25; 5/6/25: 95%->100 | 33.503 | 106 | 54 |  |  | Thu 05/12/24 | Thu 05/06/25
674 | 1050030 | Charging for 5G ProSe Ph3 | 5G_ProSe_Ph3-CH | 2 | Rel-19 | S5 | 2024-12-28 09:00 | 2025-06-06 17:00 | 100% | SP-241377 |  | Xiaoqian Jia (China Telecom) | jiaxq1@chinatelecom.cn | ; 6/3/25: 0%->100; 12/9/25: 100%->100; 12/9/25: FCD:Tue 09/09/->/25 | 32.277; 32.291; 32.298 | 105 | 53 |  |  | Wed 04/09/24 | Fri 12/09/25
675 | 1030034 | Study on Security Aspects of Enhancement for Proximity Based Services in 5GS Phase 3 | FS_5G_ProSe_Ph3_SEC | 1 | Rel-19 | S3 | 2024-04-02 08:00 | 2024-12-12 17:00 | 100% | SP-240513 |  | Lei, Ao (Huawei) | leiao@huawei.com | 3/4/24: 33.743 added;; 13/6/24: 0%->30; 5/9/24: 30%->60; 5/12/24: 60%->100 | 33.743 | 103 | 52 |  |  | Thu 14/03/24 | Thu 05/12/24
676 | 1050100 | Vehicle Mounted Relays Phase 2 | VMR_Ph2 | 1 | Rel-19 |  | 2024-01-04 08:00 | 2025-06-06 17:00 | 100% | SP-240989 |  | Hong Cheng (Qualcomm) | hongc@qti.qualcomm.com |  | 23.501; 23.502; 23.273 | 105 | 53 |  |  | Wed 12/06/24 | NA
677 | 1020067 | Study on Vehicle Mounted Relays Phase 2 | FS_VMR_Ph2 | 2 | Rel-19 | S2 | 2024-01-04 08:00 | 2024-09-09 17:00 | 100% | SP-240493 |  | Primary Rapporteur: Hong Cheng (Qualcomm) | hongc@qti.qualcomm.com | 14/3/24: 0%->40; 2/4/24: WID:SP-231799->SP-240493; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 40%->95; 5/12/24: 95%->100 |  | 102 | 52 |  |  | Wed 03/01/24 | Thu 05/12/24
678 | 1040031 | Stage 2 of Vehicle Mounted Relays Phase 2 | VMR_Ph2 | 2 | Rel-19 | S2 | 2024-06-12 08:00 | 2024-12-12 17:00 | 100% | SP-240989 |  | Hong Cheng (Qualcomm) | hongc@qti.qualcomm.com | ; 4/9/24: 0%->40; 5/12/24: 40%->100 | 23.501; 23.502; 23.273 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/12/24
679 | 1050026 | CT aspects of Vehicle Mounted Relays Phase 2 | VMR_Ph2 | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-06-06 17:00 | 100% | CP-251221 |  | Kim, Sunghoon, Qualcomm Incorporated | sunghoon@qti.qualcomm.com |  | 24.501, 23.041, 29.515 | 105 | 53 |  |  | Wed 12/06/24 | NA
680 | 1050101 | CT1 aspects of Vehicle Mounted Relays Phase 2 | VMR_Ph2 | 3 | Rel-19 | C1 | 2024-09-09 08:00 | 2025-06-06 17:00 | 100% | CP-251221 |  | Kim, Sunghoon, Qualcomm Incorporated | sunghoon@qti.qualcomm.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
681 | 1050102 | CT4 aspects of Vehicle Mounted Relays Phase 2 | VMR_Ph2 | 3 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-06-06 17:00 | 100% | CP-251221 |  | Kim, Sunghoon, Qualcomm Incorporated | sunghoon@qti.qualcomm.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
682 | 1050093 | Identifying non-3GPP Devices Connecting behind a UE or 5G-RG | UIA_ARC | 1 | Rel-19 |  | 2024-01-04 08:00 | 2025-09-09 17:00 | 100% | SP-240971 |  | Michael Starsinic, Interdigital | Michael.Starsinic@Interdigital.com |  |  | 105 | 53 |  |  | Thu 20/06/24 | NA
683 | 1020063 | Study on User Identities and Authentication Architecture | FS_UIA_ARC | 2 | Rel-19 | S2 | 2024-01-04 08:00 | 2024-09-09 17:00 | 100% | SP-231804 |  | Michael Starsinic, Interdigital | Michael.Starsinic@Interdigital.com | 14/3/24: 0%->35; 14/3/24: 23.700-32 added;; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 35%->90; 4/9/24: 90%->93; 5/12/24: 93%->100 | 23.700-32 | 102 | 52 |  |  | Wed 03/01/24 | Thu 05/12/24
684 | 1040085 | Stage 2 of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG | UIA_ARC | 2 | Rel-19 | S2 | 2024-06-20 08:00 | 2024-12-12 17:00 | 100% | SP-240971 |  | Michael Starsinic, Interdigital | Michael.Starsinic@Interdigital.com | 4/9/24: 0%->15; 5/12/24: 15%->90; 6/3/25: 90%->100; 5/6/25: 100%->100 |  | 104 | 53 |  |  | Thu 20/06/24 | Thu 05/06/25
685 | 1050009 | CT aspects of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG | UIA_ARC | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-242029 |  | Sethi, Anuj, InterDigital | anuj.sethi@interdigital.com |  |  | 105 | 53 |  |  | Thu 20/06/24 | NA
686 | 1050094 | CT1 aspects of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG | UIA_ARC | 3 | Rel-19 | C1 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-242029 |  | Sethi, Anuj, InterDigital | anuj.sethi@interdigital.com |  |  | 105 | 53 |  |  | Thu 20/06/24 | NA
687 | 1050095 | CT3 aspects of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG | UIA_ARC | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-242029 |  | Sethi, Anuj, InterDigital | anuj.sethi@interdigital.com |  |  | 105 | 53 |  |  | Thu 20/06/24 | NA
688 | 1050096 | CT4 aspects of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG | UIA_ARC | 3 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-242029 |  | Sethi, Anuj, InterDigital | anuj.sethi@interdigital.com |  |  | 105 | 53 |  |  | Thu 20/06/24 | NA
689 | 1030032 | Study on security aspects of User Identities and Authentication | FS_UIA_Sec | 1 | Rel-19 | S3 | 2024-04-02 08:00 | 2024-12-12 17:00 | 100% | SP-240507 |  | Samir Ferdi, | Samir.Ferdi@InterDigital.com | 3/4/24: 33.700-32 added;; 13/6/24: 0%->35; 5/9/24: 35%->65; 5/12/24: 65%->100 | 33.700-32 | 103 | 52 |  |  | Thu 14/03/24 | Thu 05/12/24
690 | 950007 | Study on FRMCS Phase 5 | FS_FRMCS_Ph5 | 1 | Rel-19 | S1 | 2022-03-10 08:00 | 2023-12-12 17:00 | 100% | SP-241693 |  | Patrick WIMART, UIC | wimart@uic.org | ; 4/6/22: 0%->15; 21/6/22: WID:SP-220088->SP-220437. FS_FRMCS_Ph3->FS_FRMCS_Ph5; 9/9/22: 15%->30; 10/12/22: 30%->50; 8/6/23: 50%->80; 8/6/23: FCD:09/09/2023->12/20; 6/9/23: 80%->90; 8/12/23: 90%->100; 8/1/25: WID:SP-220437->SP-241693 | 22.989 | 95 | 48 |  |  | Thu 10/03/22 | Wed 08/01/25
691 | 1000031 | FRMCS Phase 5 | FRMCS_Ph5 | 1 | Rel-19 | S1 | 2023-06-08 08:00 | 2025-09-09 17:00 | 99% | SP-230512 |  | Nikolopoulou, Vassiliki, UIC | nikolopoulou@uic.org | ; 6/9/23: 0%->50; 8/12/23: 50%->100 | 22.280; 22.179; 22.289; 22.261 | 100 | 51 |  |  | Thu 08/06/23 | Fri 08/12/23
692 | 1000038 | Stage 2 of Railways specific Enhancements to Mission Critical Services | FRMCS_Ph5 | 2 | Rel-19 | S6 | 2023-06-08 08:00 | 2024-12-12 17:00 | 100% | SP-230780 |  | Oettl, Martin, Nokia, | martin.oettl@nokia.com | ; 7/9/23: 0%->10; 8/12/23: 10%->30; 14/3/24: 30%->40. 14/5/24: acronym: enh4FRMCS ->FRMCS_Ph5 ; 13/6/24: 40%->55; 4/9/24: 55%->70; 5/12/24: 70%->100 | 23.280; 23.281; 23.282; 23.379; 23.283; 23.289 | 100 | 51 |  |  | Thu 08/06/23 | Thu 05/12/24
693 | 1050018 | CT aspects of Railways specific Enhancements to Mission Critical Services | FRMCS_Ph5 | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 98% | CP-242102 |  | Won, Sung Hwan, Nokia | sung.won@nokia.com |  |  | 100 | 51 |  |  | Thu 08/06/23 | Thu 13/06/24
694 | 1050103 | CT1 aspects of Railways specific Enhancements to Mission Critical Services | FRMCS_Ph5 | 3 | Rel-19 | C1 | 2024-09-09 08:00 | 2025-09-09 17:00 | 98% | CP-242102 |  | Won, Sung Hwan, Nokia | sung.won@nokia.com |  |  | 100 | 51 |  |  | Thu 08/06/23 | Thu 13/06/24
695 | 850044 | Study on Supporting of Railway Smart Station Services | FS_RAILSS | 1 | Rel-19 | S1 | 2019-09-19 08:00 | 2022-09-08 17:00 | 100% | SP-190838 |  | Han, Andrew Min-gyu, Hansung University | andyhan(at)hansung(dot)ac(dot)kr | ; 8/10/19: 22.890 added;; 6/12/19: 0%->5; 5/12/20: 5%->15; 19/3/21: FCD:12/06/2020->09/21; 19/3/21: 15%->30; 13/9/21: 30%->35; 10/12/21: 35%->45; 11/03/22: Rel-18->Rel-19; 9/9/22: 45%->100 | New ; 22.890 | 85 | 43 |  |  | Fri 13/09/19 | Fri 09/09/22
696 | 960020 | Study on Network of Service Robots with Ambient Intelligence | FS_SOBOT | 1 | Rel-19 | S1 | 2022-06-02 08:00 | 2023-12-12 17:00 | 100% | SP-220447 |  | LEE, Ki-Dong, LG Electronics | kidong.lee@lge.com | 13/7/22: 22.916 added;; 9/9/22: 0%->10; 10/12/22: 10%->40; 17/3/23: FCD:03/03/2023->9/9/23; 17/3/23: 40%->70; 8/6/23: 70%->80; 8/6/23: FCD:09/09/2023->12/20; 6/9/23: 80%->90; 8/12/23: 90%->100 | 22.916 | 96 | 49 |  |  | Thu 02/06/22 | Fri 08/12/23
697 | 990053 | Study on Interconnect of SNPN | FS_ISN | 1 | Rel-19 | S1 | 2023-06-08 08:00 | 2024-06-27 14:00 | 40% | SP-230236 |  | Thierry Bérisot, Novamint | tberisot@novamint.com | 8/6/23: 0%->30; 6/9/23: 30%->60; 8/12/23: FCD:12/12/2023->/2024; 8/12/23: 60%->65 | 22.848 | 99 | 50 |  |  | Thu 16/03/23 | Fri 08/12/23
698 | 1030041 | Interconnect of SNPN | ISN | 1 | Rel-19 | S1 | 2024-03-13 08:00 | 2024-03-29 17:00 | 100% | SP-240194 |  | Thierry Bérisot, Novamint, | tberisot@novamint.com | ; 14/3/24: 0%->100 | 22.261 | 103 | 52 |  |  | Wed 13/03/24 | Thu 14/03/24
699 | 990050 | Edge Computing for Industrial Scenarios | EDGINDUS | 1 | Rel-19 | S1 | 2023-02-02 08:00 | 2023-03-03 17:00 | 100% | SP-230229 |  | Bruno Tossou, Orange | bruno.tossou@orange.com | ; 17/3/23: 0%->100 | 22.104 | 99 | 50 |  |  | Thu 16/03/23 | Fri 17/03/23
700 | 990049 | PS Data Off for IMS Data Channel Service | IMSDCDataOff | 1 | Rel-19 | S1 | 2023-02-02 08:00 | 2023-03-03 17:00 | 100% | SP-230227 |  | Yue Hu, China Mobile | huyueyjy@chinamobile.com | ; 9/8/23: 0%->100 | 22.011 | 99 | 50 |  |  | Thu 16/03/23 | Wed 09/08/23
701 | 970044 | Multi-path relay | MultiRelay | 1 | Rel-19 | S1 | 2022-09-01 08:00 | 2022-09-19 17:00 | 100% | SP-220943 |  | Yuying Zhang, China Telecom | zhangyy45@chinatelecom.cn | ; 9/9/22: 0%->100 | 22.261 | 97 | 49 |  |  | Fri 09/09/22 | Fri 09/09/22
702 | 1000025 | UE-to-UE multi-hop relay | UEMHopRelay | 1 | Rel-19 | S1 | 2023-05-22 08:00 | 2023-06-06 17:00 | 100% | SP-230521 |  | Lipford, Mark, FirstNet Authority, | mark.lipford@firstnet.gov | ; 8/6/23: 100%-> | 22.261; 22.280 | 100 | 51 |  |  | Thu 08/06/23 | Thu 08/06/23
703 | 970043 | Interworking of Non-3GPP Digital Terrestrial Broadcast Networks with 5GS Multicast Broadcast Services | DTT4MBS | 1 | Rel-19 | S1 | 2022-09-01 08:00 | 2022-09-19 17:00 | 100% | SP-220941 |  | Saha, Anindya, Saankhya Labs | anindya@saankhyalabs.com | ; 9/9/22: 0%->100 | 22.261 | 97 | 49 |  |  | Fri 09/09/22 | Fri 09/09/22
704 | 1040083 | MPS for Messaging services | MPS4msg | 1 | Rel-19 |  | 2022-09-01 08:00 | 2025-05-20 09:00 | 97% | SP-220939 |  | Singh, Ray, Peraton Labs | rsingh@peratonlabs.com | ; 9/9/22: 0%->100 | 22.153 | 97 | 49 |  |  | Fri 09/09/22 | Fri 09/09/22
705 | 970042 | (stage 1 of) MPS for Messaging services | MPS4msg | 2 | Rel-19 | S1 | 2022-09-01 08:00 | 2022-09-19 17:00 | 100% | SP-220939 |  | Singh, Ray, Peraton Labs | rsingh@peratonlabs.com | ; 9/9/22: 0%->100 | 22.153 | 97 | 49 |  |  | Fri 09/09/22 | Fri 09/09/22
706 | 1040029 | (stage 2 of) MPS for IMS Messaging and SMS services | MPS4msg | 2 | Rel-19 | S2 | 2024-06-12 08:00 | 2024-12-12 17:00 | 100% | SP-240987 |  | Robert Streijl (Peraton Labs), | rstreijl@peratonlabs.com | ; 4/9/24: 0%->80; 5/12/24: 80%->100 | 23.401; 23.203; 23.501; 23.502; 23.503; 23.682; 23.204; 23.272; 23.228 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/12/24
707 | 1010031 | Study on MPS for IMS Messaging and SMS services | FS_MPS4msg | 2 | Rel-19 | S2 | 2024-01-03 08:00 | 2024-06-06 17:00 | 100% | SP-231197 |  | Robert Streijl (Peraton Labs) | rstreijl@peratonlabs.com | 9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-75 added;; 8/12/23: 0%->20; 14/3/24: 0%->70; 13/6/24: 70%->100; 4/9/24: 99%->100 | 23.700-75 | 101 | 51 |  |  | Wed 20/09/23 | Wed 04/09/24
708 | 1050007 | CT aspects of MPS for IMS Messaging and SMS services | MPS4msg | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-05-20 09:00 | 96% | CP-243047 |  | Monnes, Peter (Peraton Labs) | pmonnes@peratonlabs.com |  | 23.540, 24.229, 24.247, 24.301, 24.341, 29.122, 29.128, 29.213, 29.214, 29.228, 29.272, 29.336, 29.338, 24.501, 29.503, 29.513, 29.514, 29.518, 29.522, 29.562, 29.577, 23.540, 24.229, 24.247, 24.301, 24.341, 29.122, 29.128, 29.213, 29.214, 29.228, 29.272, | 105 | 53 |  |  | Wed 12/06/24 | NA
709 | 1050063 | CT1 aspects of MPS for IMS Messaging and SMS services | MPS4msg | 3 | Rel-19 | C1 | 2024-09-09 08:00 | 2025-05-20 09:00 | 96% | CP-243047 |  | Monnes, Peter (Peraton Labs) | pmonnes@peratonlabs.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
710 | 1050064 | CT3 aspects of MPS for IMS Messaging and SMS services | MPS4msg | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2025-05-20 09:00 | 96% | CP-243047 |  | Monnes, Peter (Peraton Labs) | pmonnes@peratonlabs.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
711 | 1050065 | CT4 aspects of MPS for IMS Messaging and SMS services | MPS4msg | 3 | Rel-19 | C4 | 2024-09-09 08:00 | 2025-05-20 09:00 | 95% | CP-243047 |  | Monnes, Peter (Peraton Labs) | pmonnes@peratonlabs.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
712 | 1050104 | Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2 | 1 | Rel-19 | S1 | 2022-09-01 08:00 | 2025-10-23 17:00 | 59% | SP-220992 |  | Yinglin Chen, China Telecom | chenyl37@chinatelecom.cn | ; 9/9/22: 0%->100; 29/9/25: FCD:Tue 09/09/25->Thu 23/10/25; Compl:58%->30%; | 22.261 | 97 | 49 |  |  | Fri 09/09/22 | Mon 29/09/25
713 | 1050029 | Study on MINT support in EPS for 5G-only national roaming UE | FS_MINT_Ph2 | 2 | Rel-19 | C1 | 2024-09-09 08:00 | 2025-03-03 17:00 | 100% | CP-251227 |  | Li Mingxue, China Telecom | limx36@chinatelecom.cn | 3/4/25: WID:CP-242249->CP-243260 |  | 97 | 49 |  |  | Fri 09/09/22 | Thu 03/04/25
714 | 970041 | Stage 2 of Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2 | 2 | Rel-19 | S1 | 2022-09-01 08:00 | 2022-09-13 12:00 | 30% | SP-220992 |  | Yinglin Chen, China Telecom | chenyl37@chinatelecom.cn | ; 9/9/22: 0%->100 | 22.261 | 97 | 49 |  |  | Fri 09/09/22 | Fri 09/09/22
715 | 1080022 | CT aspects of Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2 | 2 | Rel-19 | C1 | 2025-06-06 08:00 | 2025-10-23 17:00 | 38% | CP-252193 |  | Li Mingxue, China Telecom | limx36@chinatelecom.cn | ; 9/9/22: 0%->100; 29/9/25: FCD:Tue 09/09/25->Thu 23/10/25; WID: CP-251282->CP-252193; List of Impacted TS & TR updated; | 23.122, 24.301, 24.501, 29.272, 29.274, 31.102 | 97 | 49 |  |  | Fri 09/09/22 | Mon 29/09/25
716 | 1080037 | CT1 aspects of Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2 | 3 | Rel-19 | C1 | 2025-06-06 08:00 | 2025-10-23 17:00 | 90% | CP-252193 |  | Li Mingxue, China Telecom | limx36@chinatelecom.cn | ; 9/9/22: 0%->100; 29/9/25: FCD:Tue 09/09/25->Thu 23/10/25; WID: CP-251282->CP-252193; | 23.122, 24.301, 31.102 | 97 | 49 |  |  | Fri 09/09/22 | Mon 29/09/25
717 | 1090035 | CT4 aspects of Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2 | 3 | Rel-19 | C4 | 2025-06-06 08:00 | 2025-09-09 17:00 | 0% | CP-252193 |  | Li Mingxue, China Telecom | limx36@chinatelecom.cn | ; 9/9/22: 0%->100; 29/9/25: WID: CP-251282->CP-252193; | 23.122, 24.301, 31.102 | 97 | 49 |  |  | Mon 08/09/25 | Mon 29/09/25
718 | 1080038 | CT6 aspects of Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2 | 3 | Rel-19 | C6 | 2025-06-06 08:00 | 2025-09-09 17:00 | 0% | CP-252193 |  | Li Mingxue, China Telecom | limx36@chinatelecom.cn | ; 9/9/22: 0%->100; 29/9/25: WID: CP-251282->CP-252193; | 23.122, 24.301, 31.102 | 97 | 49 |  |  | Fri 09/09/22 | Mon 29/09/25
719 | 1090014 | Charging aspects of MINT | MINT-CH | 2 | Rel-19 | S5 | 2025-09-09 08:00 | 2025-09-09 17:00 | 30% | SP-251262 |  | Robert Törnkvist, Ericsson | robert.tornkvist@ericsson.com |  | 32.240; 32.255; 32.256; 32.291; 32.298 | 109 | 55 |  |  | Wed 10/09/25 | NA
720 | 980108 | Measurement Data Collection | MeasureData | 1 | Rel-19 | S1 | 2022-12-09 08:00 | 2022-12-20 17:00 | 100% | SP-221263 |  | Yingjun Zhou, ZTE Corporation | zhou.yingjun@zte.com.cn | ; 10/12/22: 0%->100 | 22.261 | 98 | 50 |  |  | Fri 09/12/22 | Sat 10/12/22
721 | 1010025 | Local traffic routing for multi-access UE | LTR_MA | 1 | Rel-19 | S1 | 2023-08-21 08:00 | 2023-09-09 17:00 | 100% | SP-231035 |  | Yinglin Chen, China Telecom | chenyl37@chinatelecom.cn | ; 6/9/23: 0%->100 | 22.261 | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
722 | 980008 | Study on Diverse audio Capturing system for End-user Devices | FS_DaCED | 1 | Rel-19 | S4 | 2022-12-13 08:00 | 2024-12-12 17:00 | 100% | SP-221330 |  | Wang Bin, Xiaomi | wangbin23@xiaomi.com | ; 17/3/23: 0%->5; 17/3/23: 26.933 added;; 8/6/23: 5%->30; 7/9/23: 30%->35; 8/12/23: 35%->45; 14/3/24: 45%->70; 13/6/24: 70%->85; 4/9/24: 85%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100 | 26.933 | 98 | 50 |  |  | Fri 09/12/22 | Thu 05/12/24
723 | 1000034 | Study on Service aspects for supporting the eMMTel service | FS_eMMTelAPP | 1 | Rel-19 | S6 | 2023-06-08 08:00 | 2024-12-12 17:00 | 100% | SP-230779 |  | Liu, Yue, China Mobile | liuyueyjy@chinamobile.com | ; 30/6/23: 23.700-92 added;; 7/9/23: 0%->10; 8/12/23: 10%->20; 14/3/24: 20%->35; 13/6/24: 35%->70; 4/9/24: 70%->80; 5/12/24: 80%->100; 5/12/24: FCD:09/09/2024->12/24 | 23.222 ; 23.700-92 | 100 | 51 |  |  | Thu 08/06/23 | Thu 05/12/24
724 | 1070036 | Application enablement aspects for MMTel | MMTel_App | 1 | Rel-19 |  | 2024-07-16 08:00 | 2025-09-09 17:00 | 82% | SP-241019 |  | Liu, Yue, China Mobile | liuyueyjy@chinamobile.com | 4/9/24: 0%->10; 26/9/24: 23.792 added;; 5/12/24: 10%->60 | 23.792 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/12/24
725 | 1040073 | Stage 2 of Application enablement aspects for MMTel | MMTel_App | 2 | Rel-19 | S6 | 2024-07-16 08:00 | 2024-10-28 10:00 | 100% | SP-241019 |  | Liu, Yue, China Mobile | liuyueyjy@chinamobile.com | 4/9/24: 0%->10; 26/9/24: 23.792 added;; 5/12/24: 10%->60; 6/3/25: 60%->100 | 23.792 | 104 | 53 |  |  | Wed 12/06/24 | Thu 06/03/25
726 | 1070008 | CT aspects of Application enablement aspects for MMTel | MMTel_App | 2 | Rel-19 |  | 2025-03-06 08:00 | 2025-09-09 17:00 | 78% | CP-250249 |  | Liu, Yue, China Mobile | liuyueyjy@chinamobile.com |  | 24.542 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/12/24
727 | 1070037 | CT1 aspects of Application enablement aspects for MMTel | MMTel_App | 3 | Rel-19 | C1 | 2025-03-06 08:00 | 2025-09-09 17:00 | 80% | CP-250249 |  | Liu, Yue, China Mobile | liuyueyjy@chinamobile.com |  | 24.542 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/12/24
728 | 1070038 | CT3 aspects of Application enablement aspects for MMTel | MMTel_App | 3 | Rel-19 | C3 | 2025-03-06 08:00 | 2025-09-09 17:00 | 75% | CP-250249 |  | Liu, Yue, China Mobile | liuyueyjy@chinamobile.com |  | 24.542 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/12/24
729 | 1050053 | Enhanced application layer support for location services | eLSAPP | 1 | Rel-19 |  | 2023-06-08 08:00 | 2025-09-09 17:00 | 99% | SP-241005 |  | Liping Wu, CATT | wuliping@cictmobile.com |  | 23.434; 23.436 | 105 | 53 |  |  | Wed 12/06/24 | NA
730 | 1000035 | Study on enhanced application layer support for location services | FS_eLSAPP | 2 | Rel-19 | S6 | 2023-06-08 08:00 | 2024-09-09 17:00 | 100% | SP-230778 |  | Liping Wu, CATT | wuliping@cictmobile.com | ; 30/6/23: 23.700-72 added;; 7/9/23: 0%->15; 8/12/23: 15%->25; 14/3/24: 25%->40; 2/4/24: WID:SP-230778->SP-240295; 2/4/24: FCD:05/06/2024->/24; 13/6/24: 40%->85; 13/6/24: WID:SP-240295->SP-230778; 4/9/24: 85%->100 | 23.434 ; 23.700-72 | 100 | 51 |  |  | Thu 08/06/23 | Wed 04/09/24
731 | 1040072 | Stage 2 of Enhanced application layer support for location services | eLSAPP | 2 | Rel-19 | S6 | 2024-06-12 08:00 | 2024-12-12 17:00 | 100% | SP-241005 |  | Liping Wu, CATT | wuliping@cictmobile.com | ; 4/9/24: 0%->30; 5/12/24: 30%->100 | 23.434; 23.436 | 104 | 53 |  |  | Wed 12/06/24 | Thu 05/12/24
732 | 1050015 | CT aspects of Enhanced application layer support for location services | eLSAPP | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 99% | CP-242064 |  | Wang, Baixiao (CATT) | wangbaixiao@cictmobile.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
733 | 1050054 | CT1 aspects of Enhanced application layer support for location services | eLSAPP | 3 | Rel-19 | C1 | 2024-09-09 08:00 | 2025-09-09 17:00 | 98% | CP-242064 |  | Wang, Baixiao (CATT) | wangbaixiao@cictmobile.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
734 | 1050055 | CT3 aspects of Enhanced application layer support for location services | eLSAPP | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-242064 |  | Wang, Baixiao (CATT) | wangbaixiao@cictmobile.com |  |  | 105 | 53 |  |  | Wed 12/06/24 | NA
735 | 1000036 | Sharing of administrative configuration between interconnected MC service systems | MCShAC | 1 | Rel-19 | S6 | 2023-06-08 08:00 | 2024-12-12 17:00 | 100% | SP-230692 |  | andreas.flander@bdbos.bund.de | andreas.flander@bdbos.bund.de | ; 7/9/23: 0%->5; 8/12/23: 5%->40; 14/3/24: 40%->90; 13/6/24: 90%->90; 4/9/24: 90%->100 | 23.280; 23.379; 23.281; 23.282 | 100 | 51 |  |  | Thu 08/06/23 | Wed 04/09/24
736 | 1060051 | 5GMSG Service phase 3 | 5GMARCH_Ph3 | 1 | Rel-19 |  | 2023-06-08 08:00 | 2025-09-09 17:00 | 99% | SP-230781 |  | Liu, Yue, China Mobile, | liuyueyjy@chinamobile.com | 7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50 |  | 100 | 51 |  |  | Thu 08/06/23 | Wed 04/09/24
737 | 1000037 | Stage 2 of GMSG Service phase 3 | 5GMARCH_Ph3 | 2 | Rel-19 | S6 | 2023-06-08 08:00 | 2024-12-12 17:00 | 100% | SP-230781 |  | Liu, Yue, China Mobile, | liuyueyjy@chinamobile.com | 7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50; 5/12/24: 50%->100; 5/12/24: FCD:09/09/2024->12/24 |  | 100 | 51 |  |  | Thu 08/06/23 | Thu 05/12/24
738 | 1060019 | CT aspects for enabling MSGin5G Service phase 3 | 5GMARCH_Ph3 | 2 | Rel-19 |  | 2024-12-02 08:00 | 2025-09-09 17:00 | 98% | CP-251225 |  | Liu, Yue, China Mobile | liuyueyjy@chinamobile.com | 7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50 | 24.538, 24.544, 24.546, 29.538 | 100 | 51 |  |  | Thu 08/06/23 | Wed 04/09/24
739 | 1060052 | CT1 aspects for enabling MSGin5G Service phase 3 | 5GMARCH_Ph3 | 3 | Rel-19 | C1 | 2024-12-02 08:00 | 2025-09-09 17:00 | 95% | CP-251225 |  | Liu, Yue, China Mobile | liuyueyjy@chinamobile.com | 7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50 | 24.538, 24.544, 24.546, 29.538 | 100 | 51 |  |  | Thu 08/06/23 | Wed 04/09/24
740 | 1060053 | CT3 aspects for enabling MSGin5G Service phase 3 | 5GMARCH_Ph3 | 3 | Rel-19 | C3 | 2024-12-02 08:00 | 2025-09-09 17:00 | 100% | CP-251225 |  | Liu, Yue, China Mobile | liuyueyjy@chinamobile.com | 7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50 | 24.538, 24.544, 24.546, 29.538 | 100 | 51 |  |  | Thu 08/06/23 | Wed 04/09/24
741 | 1030030 | Security aspects for MSGin5G Service Phase 3 | 5GMARCH_SEC_Ph3 | 2 | Rel-19 | S3 | 2024-04-02 08:00 | 2024-12-12 17:00 | 100% | SP-240516 |  | Xiaoting Huang, | huangxiaoting@chinamobile.com | ; 13/6/24: 0%->70; 5/9/24: 70%->100 | 33.501 | 103 | 52 |  |  | Thu 14/03/24 | Thu 05/09/24
742 | 1000039 | Enhanced Mission Critical Architecture | enhMC | 1 | Rel-19 | S6 | 2023-06-08 08:00 | 2024-12-12 17:00 | 100% | SP-241691 |  | Negalaguli, Harish, Motorola Solutions, | harish.negalaguli@motorolasolutions.com | ; 7/9/23: WID:SP-230695->SP-230988; 7/9/23: 0%->5; 8/12/23: 5%->30; 14/3/24: 30%->40; 13/6/24: 40%->60; 4/9/24: 60%->75; 5/12/24: 75%->100; 8/1/25: WID:SP-230988->SP-241691 | 23.280; 23.379; 23.281; 23.282; 23.283; 23.289 | 100 | 51 |  |  | Thu 08/06/23 | Wed 08/01/25
743 | 1050071 | SEAL DD (Data Delivery) Phase 2 | SEALDD_Ph2 | 1 | Rel-19 |  | 2023-09-07 08:00 | 2025-09-09 17:00 | 99% | SP-230989 |  | Cuili Ge, Huawei | gecuili@huawei.com | 8/12/23: 0%->25; 14/3/24: 25%->35; 13/6/24: 35%->70 |  | 101 | 51 |  |  | Thu 07/09/23 | Thu 13/06/24
744 | 1010006 | Stage 2 of SEAL DD (Data Delivery) Phase 2 | SEALDD_Ph2 | 2 | Rel-19 | S6 | 2023-09-07 08:00 | 2024-12-12 17:00 | 100% | SP-230989 |  | Cuili Ge, Huawei | gecuili@huawei.com | 8/12/23: 0%->25; 14/3/24: 25%->35; 13/6/24: 35%->70; 4/9/24: 70%->80; 5/12/24: 80%->100 |  | 101 | 51 |  |  | Thu 07/09/23 | Thu 05/12/24
745 | 1050017 | CT aspects of SEAL DD (Data Delivery) Phase 2 | SEALDD_Ph2 | 2 | Rel-19 |  | 2024-09-09 08:00 | 2025-09-09 17:00 | 99% | CP-243261 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  | 24.543, 24.548, 29.548, 29.549 | 101 | 51 |  |  | Thu 07/09/23 | Thu 13/06/24
746 | 1050072 | CT1 aspects of SEAL DD (Data Delivery) Phase 2 | SEALDD_Ph2 | 3 | Rel-19 | C1 | 2024-09-09 08:00 | 2025-09-09 17:00 | 97% | CP-243261 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  |  | 101 | 51 |  |  | Thu 07/09/23 | Thu 13/06/24
747 | 1050073 | CT3 aspects of SEAL DD (Data Delivery) Phase 2 | SEALDD_Ph2 | 3 | Rel-19 | C3 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-243261 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  |  | 101 | 51 |  |  | Thu 07/09/23 | Thu 13/06/24
748 | 1040081 | Architecture for enabling Edge Applications Phase 3 | EDGEAPP_Ph3 | 1 | Rel-19 |  | 2023-09-07 08:00 | 2025-09-09 17:00 | 99% | SP-231160 |  | Hyesung Kim, Samsung | hs1207.kim@samsung.com | ; 8/12/23: 0%->15; 14/3/24: 15%->35 | 23.558 | 101 | 51 |  |  | Thu 07/09/23 | Thu 14/03/24
749 | 1010007 | Stage 2 of enabling Edge Applications Phase 3 | EDGEAPP_Ph3 | 2 | Rel-19 | S6 | 2023-09-07 08:00 | 2024-12-12 17:00 | 100% | SP-231160 |  | Hyesung Kim, Samsung | hs1207.kim@samsung.com | ; 8/12/23: 0%->15; 14/3/24: 15%->35; 13/6/24: 35%->80; 4/9/24: 80%->85; 5/12/24: 85%->100 | 23.558 | 101 | 51 |  |  | Thu 07/09/23 | Thu 05/12/24
750 | 1040008 | CT aspects for Enabling Edge Applications Phase 3 | EDGEAPP_Ph3 | 2 | Rel-19 |  | 2024-06-17 08:00 | 2025-09-09 17:00 | 99% | CP-241074 |  | Narendranath Durga Tangudu, Samsung | n.tangudu@samsung.com |  | 24.558,29.558 | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
751 | 1040058 | CT1 aspects for Enabling Edge Applications Phase 3 | EDGEAPP_Ph3 | 3 | Rel-19 | C1 | 2024-06-17 08:00 | 2025-09-09 17:00 | 98% | CP-241074 |  | Narendranath Durga Tangudu, Samsung | n.tangudu@samsung.com | 16/7/24: FCD:06/06/2025->/25 |  | 101 | 51 |  |  | Wed 06/09/23 | Tue 16/07/24
752 | 1040059 | CT3 aspects for Enabling Edge Applications Phase 3 | EDGEAPP_Ph3 | 3 | Rel-19 | C3 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-241074 |  | Narendranath Durga Tangudu, Samsung | n.tangudu@samsung.com | 16/7/24: 0%->100 |  | 101 | 51 |  |  | Wed 06/09/23 | Tue 16/07/24
753 | 0 | Rel-19 miscellaneous Security |  | 1 | Rel-19 |  | 2019-03-07 08:00 | 2019-03-07 17:00 | 0% | [10 empty] | Thu 07/12/23 | NA
754 | 1030029 | Security Assurance Specification for maintenance of 5G features | SCAS_5G_Maint | 1 | Rel-19 | S3 | 2024-04-02 08:00 | 2025-03-03 17:00 | 100% | SP-240515 |  | Rong Wu (Huawei) | raina.wu@huawei.com | 5/9/24: 0%->50; 5/12/24: 50%->100 |  | 103 | 52 |  |  | Thu 14/03/24 | Thu 05/12/24
755 | 1010010 | 5G Security Assurance Specification (SCAS) for the Unified Data Repository (UDR) | SCAS_5G_UDR | 1 | Rel-19 | S3 | 2023-09-06 08:00 | 2024-05-21 09:00 | 80% | SP-230864 |  | Andreas, Joerg, BSI Germany | joerg.andreas@bsi.bund.de | ; 8/12/23: 0%->10; 3/4/24: 33.530 added;; 13/6/24: 10%->50; 5/9/24: 50%->60; 5/12/24: 60%->80 | 33.926 ; 33.530 | 101 | 51 |  |  | Wed 06/09/23 | Thu 05/12/24
756 | 1010011 | 5G Security Assurance Specification (SCAS) for the Short Message Service Function (SMSF) | SCAS_5G_SMSF | 1 | Rel-19 | S3 | 2023-09-06 08:00 | 2024-09-09 17:00 | 100% | SP-231158 |  | Manjesh K. Hanawal, IIT Bombay | mhanawal@iitb.ac.in | 8/12/23: 0%->10; 4/1/24: 33.529 added;; 14/3/24: 10%->40; 13/6/24: 40%->70; 5/9/24: 70%->40; 5/9/24: 40%->100; 5/12/24: 100%->100 | 33.529 | 101 | 51 |  |  | Wed 06/09/23 | Thu 05/12/24
757 | 1010012 | Addition of 256-bit security Algorithms | 256_Algo | 1 | Rel-19 | S3 | 2023-09-06 08:00 | 2024-03-03 17:00 | 100% | SP-240476 |  | Orkopoulos, Stawros | stawros.orkopoulos@nokia.com | 8/12/23: 0%->10; 4/1/24: 35.248 added;; 14/3/24: 10%->100; 2/4/24: WID:SP-231159->SP-240476 | 35.248; 35.247; 35.246; 35.245; 35.244; 35.243; 35.242; 35.241; 35.240 | 101 | 51 |  |  | Wed 06/09/23 | Tue 02/04/24
758 | 1020036 | Addition of Milenage-256 algorithm | Milenage_256 | 1 | Rel-19 | S3 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-241087 |  | Mireille Pauliac | mireille.pauliac@thalesgroup.com | 4/1/24: 35.237 added;; 4/1/24: 35.236 added;; 4/1/24: 35.235 added;; 4/1/24: 35.234 added;; 14/3/24: 0%->5; 5/9/24: 5%->65; 26/9/24: WID:SP-231792->SP-241087; 5/12/24: 65%->100 | 35.237; 35.236; 35.235; 35.234 | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/12/24
759 | 1020041 | Study on enabling a cryptographic algorithm transition to 256-bits | FS_CAT256 | 1 | Rel-19 | S3 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-231788 |  | Yuto Nakano | yt-nakano@kddi.com | 4/1/24: 33.700-41 added;; 14/3/24: 0%->10; 13/6/24: 10%->90; 5/9/24: 90%->100 | 33.700-41 | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/09/24
760 | 1020034 | Study on enablers for Zero Trust Security | FS_eZTS | 1 | Rel-19 | S3 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-231784 |  | Sheeba Backia Mary Baskaran | smary@lenovo.com | 4/1/24: 33.794 added;; 14/3/24: 0%->20; 13/6/24: 20%->50; 5/9/24: 50%->75; 5/12/24: 75%->95; 6/3/25: 95%->100; 5/6/25: 100%->100 | 33.794 | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/06/25
761 | 1020035 | Mission critical security enhancements for release 19 | MCXSec4 | 1 | Rel-19 | S3 | 2024-01-04 08:00 | 2024-08-30 15:00 | 99% | SP-231783 |  | Woodward, Tim, Motorola Solutions, Inc. | tim.woodward@motorolasolutions.com | ; 14/3/24: 0%->10; 5/9/24: 10%->50; 5/12/24: 50%->90; 6/3/25: 90%->95; 5/6/25: 95%->99 | 33.180 | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/06/25
762 | 1020038 | Study on the security support for the Next Generation Real Time Communication services phase 2 | FS_NG_RTC_SEC_Ph2 | 1 | Rel-19 | S3 | 2024-01-03 08:00 | 2024-12-30 10:00 | 100% | SP-240233 |  | Vlasios Tsiatsis | vlasios.tsiatsis@ericsson.com | 4/1/24: 33.790 added;; 14/3/24: 0%->17; 2/4/24: WID:SP-231785->SP-240233; 13/6/24: 17%->40; 5/9/24: 40%->60; 5/12/24: 60%->80; 6/3/25: 80%->80; 6/3/25: FCD:12/12/2024->/25; 5/6/25: 80%->100 | 33.790 | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/06/25
763 | 1060063 | Security support for the Next Generation Real Time Communication services Phase 2 | NG_RTC_SEC_Ph2 | 1 | Rel-19 | S3 | 2025-01-02 09:00 | 2025-03-03 17:00 | 100% | SP-250649 |  | Vlasios Tsiatsis, Ericsson | vlasios.tsiatsis@ericsson.com | ; 26/3/25: WID:SP-241778->SP-250078; 27/6/25: WID:SP-250078->SP-250649; 17/9/25: 0%->100 | 33.203 | 106 | 54 |  |  | Thu 05/12/24 | Wed 17/09/25
764 | 1020040 | Study of ACME for Automated Certificate Management in SBA | FS_ACME_SBA | 1 | Rel-19 | S3 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-231787 |  | Charles Eckel | eckelcu(at)cisco.com | 4/1/24: 33.776 added;; 14/3/24: 0%->15; 13/6/24: 15%->45; 13/6/24: FCD:06/06/2024->12/24; 5/9/24: 45%->55; 5/12/24: 55%->100; 6/3/25: 100%->100; 5/6/25: 100%->100 | 33.776 | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/06/25
765 | 1060066 | Automatic Certificate Management Environment (ACME) for the Service Based Architecture (SBA) | ACME_SBA | 1 | Rel-19 | S3 | 2024-12-05 08:00 | 2025-06-06 17:00 | 100% | SP-241960 |  | Charles Eckel (Cisco) | eckelcu(at)cisco.com | ; 6/3/25: 0%->55; 5/6/25: 55%->100 | 33.310 | 106 | 54 |  |  | Thu 05/12/24 | Thu 05/06/25
766 | 1080043 | Roaming and interconnect authorization aspects in indirect communication | SBA_RoamInt-SEC | 1 | Rel-19 | S3 | 2025-06-27 08:00 | 2025-07-07 17:00 | 100% | SP-250815 |  | Anja Jerichow | anja.jerichow@nokia.com | ; 17/9/25: 0%->100 | 33.501 | 108 | 55 |  |  | Thu 05/06/25 | Wed 17/09/25
767 | 1080046 | Public key distribution and Issuer claim verification of the Access Token | SBA_KDATV-SEC | 1 | Rel-19 | S3 | 2025-06-05 08:00 | 2025-06-06 17:00 | 100% | SP-250816 |  | Mohsin Khan | mohsin.a.khan@ericsson.com | ; 17/9/25: 0%->100 | 33.501 | 108 | 55 |  |  | Thu 05/06/25 | Wed 17/09/25
768 | 1020042 | 3GPP profiles for cryptographic algorithms and security protocols | CryptoSP | 1 | Rel-19 | S3 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-231793 |  | Mohsin Khan A | mohsin.a.khan@ericsson.com | ; 14/3/24: 0%->20; 13/6/24: 20%->50; 5/9/24: 50%->80; 5/12/24: 80%->100; 6/3/25: 100%->100; 5/6/25: 100%->100 | 33.127; 33.203; 33.210; 33.222; 33.246; 33.259; 33.303; 33.310; 33.401; 33.402; 33.434; 33.501 | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/06/25
769 | 1020043 | Study on mitigations against bidding down attacks | FS_MiBiDA | 1 | Rel-19 | S3 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-231789 |  | Noamen Ben Henda | noamen.ben.henda@huawei.com | 4/1/24: 33.701 added;; 14/3/24: 0%->20; 13/6/24: 20%->85; 13/6/24: FCD:05/06/2024->12/24; 5/9/24: 85%->100 | 33.701 | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/09/24
770 | 1060054 | Mobility over non-3GPP access to avoid full primary authentication | Non3GPPMob_Sec | 1 | Rel-19 |  | 2024-01-03 08:00 | 2025-09-09 17:00 | 72% | SP-241088 |  | Khare, Saurabh | saurabh.khare@nokia.com | ; 26/9/24: WID:SP-240653->SP-241088 | 33.501 | 104 | 53 |  |  | Wed 12/06/24 | Thu 26/09/24
771 | 1020045 | Study on Security for mobility over non-3GPP access to avoid full primary authentication | FS_Non3GPPMob_Sec | 2 | Rel-19 | S3 | 2024-01-03 08:00 | 2024-08-30 15:00 | 25% | SP-231791 |  | Saurabh Khare, Nokia | Saurabh.Khare@nokia.com | 4/1/24: 33.702 added;; 14/3/24: 0%->25 | 33.702 | 102 | 52 |  |  | Thu 07/12/23 | Thu 14/03/24
772 | 1040024 | Security for mobility over non-3GPP access to avoid full primary authentication | Non3GPPMob_Sec | 2 | Rel-19 | S3 | 2024-08-07 13:00 | 2024-12-12 17:00 | 100% | SP-241088 |  | Khare, Saurabh | saurabh.khare@nokia.com | ; 26/9/24: WID:SP-240653->SP-241088; 17/9/25: 0%->100 | 33.501 | 104 | 53 |  |  | Wed 12/06/24 | Wed 17/09/25
773 | 1060020 | CT aspects of security for mobility over non-3GPP access to avoid full primary authentication | Non3GPPMob_Sec | 2 | Rel-19 | C1 | 2024-12-02 08:00 | 2025-09-09 17:00 | 100% | CP-250133 |  | Nassar, Mohamed Amin, Nokia | mohamed.a.nassar@nokia.com |  | 24.502 | 104 | 53 |  |  | Wed 12/06/24 | Thu 26/09/24
774 | 0 | Rel-19 miscellaneous OAM&charging |  | 1 | Rel-19 |  | 2019-03-07 08:00 | 2019-03-07 17:00 | 0% | [10 empty] | Thu 07/12/23 | NA
775 | 1040013 | Charging Aspects of Ranging and Sidelink Positioning | Ranging_SL_CH | 1 | Rel-19 | S5 | 2024-05-06 08:00 | 2025-03-03 17:00 | 100% | SP-241002 |  | Zhiwei Mo, China Telecom, | mozw@chinatelecom.cn | ; 4/9/24: 20%->50; 5/12/24: 50%->100. 12/09/25: Rel-18->Rel-19; 12/9/25: FCD:Sat 30/11/->03/25 | 32.240; 32.290; 32.271; 32.291; 32.298 | 104 | 53 |  |  | Thu 13/06/24 | Fri 12/09/25
776 | 1070020 | Charging aspects for Multi-Operator Core Network (MOCN) Network Sharing | CH_MOCN_NetShare | 1 | Rel-19 | S5 | 2025-03-26 08:00 | 2025-09-09 17:00 | 100% | SP-250819 |  | Robert Törnkvist, Ericsson, | robert.tornkvist@ericsson.com | ; 6/6/25: 0%->75; 27/6/25: WID:SP-250371->SP-250819; 12/9/25: 75%->100 | 32.130; 32.240; 32.255; 32.291; 32.298 ; 28.201 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
777 | 1060006 | Service Based Management Architecture enhancement phase 3 | SBMA_Ph3 | 1 | Rel-19 | S5 | 2025-03-01 16:00 | 2025-09-09 17:00 | 100% | SP-241939 |  | Kai Zhang (Huawei) | kai.zhangkai@huawei.com | ; 6/3/25: 0%->40; 6/6/25: 40%->90; 12/9/25: 90%->100 | 32.156; 28.532; 28.533; 28.537; 28.622; 28.623; 28.530; 28.550; 32.421; 32.422; 32.423; 28.404; 28.405; 28.406; 28.552; 28.554; 28.558; 32.130; 28.313; 28.314; 28.623; 28.310; 28.530; 28.531; 28.111; 28.550; 28.621; 28.623; 32.421; 32.422; 28.404; 28.405; | 106 | 54 |  |  | Thu 05/12/24 | Fri 12/09/25
778 | 1020019 | Study on Management Data Analytics (MDA) Phase 3 | FS_eMDAS_Ph3 | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-241157 |  | Brendan T Hassett (Huawei) | brendan.t.hassett@huawei.com | 13/6/24: 0%->70; 16/7/24: WID:SP-231726->SP-240968; 4/9/24: 70%->90; 4/9/24: FCD:09/09/2024->12/24; 26/9/24: WID:SP-240968->SP-241157; 5/12/24: 90%->100 |  | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/12/24
779 | 1060014 | Management Data Analytics phase 3 | eMDAS_Ph3 | 1 | Rel-19 | S5 | 2025-03-01 16:00 | 2025-09-09 17:00 | 100% | SP-241947 |  | Brendan T Hassett (Huawei) | brendan.t.hassett@huawei.com | ; 6/3/25: 0%->30; 6/6/25: 30%->85; 12/9/25: 85%->100 | 28.104 | 106 | 54 |  |  | Thu 05/12/24 | Fri 12/09/25
780 | 1020008 | Study on intent driven management services for mobile network phase 3 | FS_IDMS_MN_Ph3 | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-231737 |  | Ruiyue Xu (Huawei) | xuruiyue@huawei.com | 14/3/24: 0%->5; 13/6/24: 5%->70; 4/9/24: 70%->95; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 95%->100 |  | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/12/24
781 | 1060013 | Intent driven management services for mobile network phase 3 | IDMS_MN_Ph3 | 1 | Rel-19 | S5 | 2025-01-30 11:00 | 2025-06-06 17:00 | 100% | SP-241946 |  | Ruiyue Xu (Huawei) | xuruiyue@huawei.com | ; 6/3/25: 0%->65; 6/6/25: 65%->100 | 28.312 | 106 | 54 |  |  | Thu 05/12/24 | Fri 06/06/25
782 | 1020009 | Study on closed control loop management | FS_CCLM | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-231735 |  | Deepanshu Gautam (Samsung) | deepanshu.g@samsung.com | 14/3/24: 0%->5; 13/6/24: 5%->40; 4/9/24: 40%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100 |  | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/12/24
783 | 1020018 | Study on management aspects of Network Digital Twin | FS_NDT | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-231727 |  | Yushuang Hu (China Mobile) | huyushuang@chinamobile.com | 4/1/24: 28.915 added;; 14/3/24: 0%->5; 13/6/24: 5%->65; 13/6/24: WID:SP-231428->SP-231727; 4/9/24: 65%->95; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 95%->100 | 28.915 | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/12/24
784 | 1060005 | Management aspects of Network Digital Twins | NDT | 1 | Rel-19 | S5 | 2025-03-01 16:00 | 2025-09-09 17:00 | 100% | SP-241938 |  | Yushuang Hu (China Mobile) | huyushuang@chinamobile.com | 6/3/25: 0%->10; 6/6/25: 10%->95; 12/9/25: 95%->100 |  | 106 | 54 |  |  | Thu 05/12/24 | Fri 12/09/25
785 | 1020016 | Study on Enablers for Security Monitoring | FS_SECM | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-231736 |  | Clifton Fernandes (Nokia) | clifton.fernandes@nokia.com | 4/1/24: 28.870 added;; 4/9/24: 0%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100 | 28.870 | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/12/24
786 | 1020011 | Study on Service Based Management Architecture enhancement phase 3 | FS_SBMA_Ph3 | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-241569 |  | Kai Zhang (Huawei) | kai.zhangkai@huawei.com | 13/6/24: 0%->45; 4/9/24: 45%->75; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 75%->100; 8/1/25: WID:SP-231725->SP-241569 |  | 102 | 52 |  |  | Thu 07/12/23 | Wed 08/01/25
787 | 1020033 | Study on Management of planned configurations | FS_PlanM | 1 | Rel-19 | S5 | 2024-01-04 08:00 | 2024-09-09 17:00 | 100% | SP-231721 |  | Olaf Pollakowski (Nokia) | olaf.pollakowski@nokia.com | 4/1/24: 28.872 added;; 13/6/24: 0%->60; 4/9/24: 60%->100 | 28.872 | 102 | 52 |  |  | Wed 03/01/24 | Wed 04/09/24
788 | 1050032 | Management of planned configurations | PlanM | 1 | Rel-19 | S5 | 2024-09-04 08:00 | 2025-09-09 17:00 | 100% | SP-241379 |  | Olaf Pollakowski (Nokia) | olaf.pollakowski@nokia.com | 26/9/24: 28.572 added;; 5/12/24: 0%->60; 6/3/25: 60%->75; 6/6/25: 75%->75; 6/6/25: FCD:Fri 06/06/->/25; 12/9/25: 75%->100 | 28.572 | 105 | 53 |  |  | Wed 04/09/24 | Fri 12/09/25
789 | 1060010 | Closed Control Loop Management | CCLM | 1 | Rel-19 | S5 | 2025-03-01 16:00 | 2025-09-09 17:00 | 100% | SP-241943 |  | Deepanshu Gautam (Samsung) | deepanshu.g@samsung.com | ; 6/3/25: 0%->10; 6/6/25: 10%->80; 12/9/25: 80%->100 | 28.535; 28.536; 28.622; 32.161 | 106 | 54 |  |  | Thu 05/12/24 | Fri 12/09/25
790 | 1020025 | Data management phase 2 | MADCOL_Ph2 | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2025-09-09 17:00 | 100% | SP-250116 |  | Sreekumar Pothera Kalloor (Nokia) | sreekumar.pk@nokia.com | ; 13/6/24: 0%->50; 16/7/24: WID:SP-231746->SP-240877; 4/9/24: 50%->80; 5/12/24: 80%->88. 03/25: Rapporteur updated from sivaramakrishnan.swaminathan@nokia.com; 26/3/25: WID:SP-240877->SP-250116; 26/3/25: FCD:30/12/2024->/25; 6/6/25: 88%->88; 6/6/25: FCD: | 28.622; 28.623 | 102 | 52 |  |  | Thu 07/12/23 | Fri 12/09/25
791 | 1020012 | Study on data management regarding subscriptions and reporting | FS_Data_SREP | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2024-09-09 17:00 | 100% | SP-231732 |  | Robert Petersen (Ericsson) | robert.petersen@ericsson.com | 13/6/24: 0%->60; 4/9/24: 60%->100 |  | 102 | 52 |  |  | Thu 07/12/23 | Wed 04/09/24
792 | 1020026 | 5G performance measurements and KPIs phase 4 | PM_KPI_5G_Ph4 | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2025-09-09 17:00 | 100% | SP-250511 |  | XiuMin Chen (China Telecom) | chenxiumin@chinatelecom.cn | ; 13/6/24: 0%->20; 4/9/24: 20%->30; Rapporteur update: Xiebaoguo->Ruan bang qiu (ruan.bangqiu@zte.com.cn); 26/9/24: WID:SP-231747->SP-241155; 5/12/24: 30%->65; 6/3/25: 65%->75; 6/6/25: 75%->90; 6/6/25: FCD:Mon 30/12/->/25; 27/6/25: WID:SP-241155->SP-2505 | 28.552; 32.425; 28.554; 28.532; 28.550; 28.558; 32.404; 32.401 | 102 | 52 |  |  | Thu 07/12/23 | Fri 12/09/25
793 | 1020027 | 5G Advanced NRM features phase 3 | AdNRM_Ph3 | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2025-06-06 17:00 | 100% | SP-250123 |  | Sean Sun (Nokia) | sean.sun@nokia-sbell.com | ; 13/6/24: 0%->15; 16/7/24: WID:SP-231745->SP-240875; 4/9/24: 15%->30; 5/12/24: 30%->60; 8/1/25: WID:SP-240875->SP-241565; 6/3/25: 60%->75; 26/3/25: WID:SP-241565->SP-250123; 26/3/25: FCD:30/12/2024->/25; 6/6/25: 75%->100 | 28.540; 28.541; 28.622; 28.623 | 102 | 52 |  |  | Thu 07/12/23 | Fri 06/06/25
794 | 1020028 | Subscriber and Equipment Trace and QoE collection management | TraceQoE_OAM | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2025-09-09 17:00 | 100% | SP-250115 |  | Zu Qiang (Ericsson) | zu.qiang@ericsson.com | ; 13/6/24: 0%->20; 4/9/24: 20%->40; 5/12/24: 40%->75; 6/3/25: 75%->80; 26/3/25: WID:SP-231748->SP-250115; 6/6/25: FCD:Mon 30/12/->/25; 12/9/25: 80%->100 | 32.421; 32.422; 32.423; 28.404; 28.405; 28.406; 28.622; 28.623 | 102 | 52 |  |  | Thu 07/12/23 | Fri 12/09/25
795 | 1020013 | Study on Management Aspects of NTN Phase 2 | FS_NTN_OAM_Ph2 | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-231733 |  | MingRui Sun (China Unicom) | sunmr19@chinaunicom.cn | 13/6/24: 0%->65; 4/9/24: 65%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100 |  | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/12/24
796 | 1020014 | Study on management of IAB nodes | FS_NR_mobile_IAB_OAM | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-231729 |  | JunFeng Wang (Ericsson) | junfeng.a.wang@ericsson.com | 13/6/24: 0%->40; 13/6/24: FCD:09/09/2024->12/24; 4/9/24: 40%->90; 5/12/24: 90%->100 |  | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/12/24
797 | 1060015 | Management of IAB nodes | NR_mobile_IAB_OAM | 1 | Rel-19 | S5 | 2025-03-01 16:00 | 2025-12-12 17:00 | 90% | SP-241948 |  | JunFeng Wang (Ericsson) | junfeng.a.wang@ericsson.com | ; 6/6/25: 0%->70; 12/9/25: 70%->90; 12/9/25: FCD:Tue 09/09/->12/25 | 28.541; 28.540; 28.531; 28.314; 28.315 | 106 | 54 |  |  | Thu 05/12/24 | Fri 12/09/25
798 | 1020017 | Study on management aspects of RedCap feature | FS_NR_RedCap_OAM | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-231734 |  | Zhen Xing (China Unicom) | xingz12@chinaunicom.cn | 13/6/24: 0%->50; 4/9/24: 50%->75; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 75%->100 |  | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/12/24
799 | 1020020 | Study on Enhancement of Management Aspects related to NWDAF Phase 2 | FS_NWDAF_OAM_Ph2 | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2024-09-09 17:00 | 100% | SP-231724 |  | Primary Rapporteur: Song Zhao (China Telecom) | zhaosong1@chinatelecom.cn | 13/6/24: 0%->75; 4/9/24: 75%->100 |  | 102 | 52 |  |  | Thu 07/12/23 | Wed 04/09/24
800 | 1050031 | Enhancement of Management Aspects Related of NWDAF Phase 2 | NWDAF_OAM_Ph2 | 1 | Rel-19 | S5 | 2024-09-04 08:00 | 2025-06-06 17:00 | 100% | SP-241378 |  | Song Zhao (China Telecom) | zhaosong1@chinatelecom.cn | ; 5/12/24: 0%->60; 6/3/25: 60%->65; 6/6/25: 65%->100 | 28.552; 28.541 | 105 | 53 |  |  | Wed 04/09/24 | Fri 06/06/25
801 | 1020015 | Study on Management of Network Sharing Phase3 | FS_NetShare_OAM_Ph3 | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-240966 |  | ZhaoNing Wang (China Unicom) | wangzn18@chinaunicom.cn | 13/6/24: 0%->50; 16/7/24: WID:SP-231731->SP-240966; 4/9/24: 50%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100 |  | 102 | 52 |  |  | Thu 07/12/23 | Thu 05/12/24
802 | 1020022 | Study on Enhanced OAM for management exposure to external consumers | FS_MExpo | 1 | Rel-19 | S5 | 2024-01-03 08:00 | 2024-12-12 17:00 | 100% | SP-241570 |  | Srilakshmi Srinivasaraju (Nokia) | srilakshmi.s@nokia.com | 14/3/24: 0%->5; 13/6/24: 5%->50; 16/7/24: WID:SP-231728->SP-240967; 4/9/24: 50%->60; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 60%->100; 8/1/25: WID:SP-240967->SP-241570 |  | 102 | 52 |  |  | Thu 07/12/23 | Wed 08/01/25
803 | 0 | Rel-19 other |  | 1 | Rel-19 |  | 2019-03-07 08:00 | 2019-03-07 17:00 | 0% | [10 empty] | Thu 07/12/23 | NA
804 | 1060055 | Reducing Information Exposure over SBI | RedInfExp_SBI | 1 | Rel-19 |  | 2023-06-07 08:00 | 2025-09-09 17:00 | 100% | CP-243308 |  | Nivedya P S, Samsung | nivedya.ps@samsung.com | 30/6/23: 29.857 added;; 3/4/25: WID:CP-243019->CP-243308 |  | 100 | 51 |  |  | Wed 07/06/23 | Thu 03/04/25
805 | 1000001 | Study on Reducing Information Exposure over SBI | FS_RedInfExp_SBI | 2 | Rel-19 | C4 | 2023-06-07 08:00 | 2023-12-12 17:00 | 100% | CP-231350 |  | Varini Gupta, Samsung | varini.gupta@samsung.com | 30/6/23: 29.857 added; | 29.857 | 100 | 51 |  |  | Wed 07/06/23 | Fri 30/06/23
806 | 1060003 | Reducing Information Exposure over SBI | RedInfExp_SBI | 2 | Rel-19 | C4 | 2024-12-02 08:00 | 2025-09-09 17:00 | 100% | CP-243308 |  | Nivedya P S, Samsung | nivedya.ps@samsung.com | 30/6/23: 29.857 added; | 29.510, 29.500 | 100 | 51 |  |  | Wed 07/06/23 | Fri 30/06/23
807 | 1010003 | Study on IMS Disaster Prevention and Restoration Enhancement | FS_IMS_RES | 1 | Rel-19 | C4 | 2022-08-25 08:00 | 2024-03-03 17:00 | 100% | CP-232281 |  | Liu, Liu, China Telecom | liuliu66@chinatelecom.cn | 21/9/23: 29.866 added; | 29.xxx; 29.866 | 96 | 49 |  |  | Fri 03/06/22 | Thu 21/09/23
808 | 1080001 | IMS Disaster Prevention and Restoration Enhancement | IMS_RES-CT | 1 | Rel-19 |  | 2024-06-06 08:00 | 2025-09-09 17:00 | 47% | CP-251016 |  | Liu, Liu, China Telecom | liuliu66@chinatelecom.cn |  | 23.380, 24.229, 23.334, 29.244, 29.500, 29.562, 29.213, 29.513 | 96 | 49 |  |  | Fri 03/06/22 | Thu 21/09/23
809 | 1090034 | CT1 aspects of IMS Disaster Prevention and Restoration Enhancement | IMS_RES-CT | 2 | Rel-19 | C1 | 2025-06-06 08:00 | 2025-09-09 17:00 | 0% | CP-251016 |  | Liu, Liu, China Telecom | liuliu66@chinatelecom.cn |  | 23.380, 24.229, 23.334, 29.244, 29.500, 29.562, 29.213, 29.513 | 96 | 49 |  |  | Mon 08/09/25 | NA
810 | 1080035 | CT3 aspects of IMS Disaster Prevention and Restoration Enhancement | IMS_RES-CT | 2 | Rel-19 | C3 | 2025-06-06 08:00 | 2025-09-09 17:00 | 70% | CP-251016 |  | Liu, Liu, China Telecom | liuliu66@chinatelecom.cn |  | 23.380, 24.229, 23.334, 29.244, 29.500, 29.562, 29.213, 29.513 | 96 | 49 |  |  | Mon 08/09/25 | NA
811 | 1080036 | CT4 aspects of IMS Disaster Prevention and Restoration Enhancement | IMS_RES-CT | 2 | Rel-19 | C4 | 2025-06-06 08:00 | 2025-09-09 17:00 | 70% | CP-251016 |  | Liu, Liu, China Telecom | liuliu66@chinatelecom.cn |  | 23.380, 24.229, 23.334, 29.244, 29.500, 29.562, 29.213, 29.513 | 96 | 49 |  |  | Mon 08/09/25 | NA
812 | 1000016 | Study on Film Grain Synthesis | FS_FGS | 1 | Rel-19 | S4 | 2023-06-08 08:00 | 2024-09-09 17:00 | 100% | SP-241389 |  | Brian Lee (Dolby Laboratories) | Brian.Lee@dolby.com | ; 7/9/23: 0%->10; 8/12/23: 10%->20; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 20%->30; 14/3/24: FCD:03/03/2024->3/3/25; Rel-18->Rel-19; 13/6/24: 30%->; 4/9/24: 30%->100; 4/9/24: FCD:03/03/2025->09/24; 4/9/24: WID:SP-230539->SP-241120 ; 26/9/24: WID:SP-... | 26.955 ; 26.855 | 100 | 51 |  |  | Thu 08/06/23 | Thu 26/09/24
813 | 1000019 | Study of Avatars in Real-Time Communication Services | FS_AVATAR | 1 | Rel-19 | S4 | 2023-06-08 08:00 | 2025-03-03 17:00 | 100% | SP-230544 |  | Bouazizi, Imed, Qualcomm Incorporated | bouazizi AT qti DOT qualcomm DOT com | 7/9/23: 0%->5; 21/9/23: 26.813 added;; 8/12/23: 5%->20; 14/3/24: 20%->30; 14/3/24: FCD:03/03/2024->12/24; ; Rel-18->Rel-19; 13/6/24: 30%->50; 4/9/24: 50%->55; 5/12/24: 55%->60; 5/12/24: FCD:12/12/2024->/25; 6/3/25: 60%->100 | 26.813 | 100 | 51 |  |  | Thu 08/06/23 | Thu 06/03/25
814 | 1040001 | Service Based Interface Protocol Improvements Release 19 | SBIProtoc19 | 1 | Rel-19 |  | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-241021 |  | Wang Rong, China Mobile | wangrongyjy@chinamobile.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
815 | 1040050 | CT3 aspects of Service Based Interface Protocol Improvements Release 19 | SBIProtoc19 | 2 | Rel-19 | C3 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-241021 |  | Wang Rong, China Mobile | wangrongyjy@chinamobile.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
816 | 1040051 | CT4 aspects of Service Based Interface Protocol Improvements Release 19 | SBIProtoc19 | 2 | Rel-19 | C4 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-241021 |  | Wang Rong, China Mobile | wangrongyjy@chinamobile.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
817 | 1090031 | Lower Selection-priority for PLMN Selection | LoSePLMN | 1 | Rel-19 |  | 2024-06-06 08:00 | 2025-09-09 17:00 | 54% |  |  | Wang Rong, China Mobile | wangrongyjy@chinamobile.com | 29/9/25: Compl:54%->52%; |  | 101 | 51 |  |  | Mon 08/09/25 | Mon 29/09/25
818 | 1090040 | Stage 1 for Lower Selection-priority for PLMN Selection | LoSePLMN-REQ | 2 | Rel-19 | S1 | 2025-08-08 08:00 | 2025-09-09 17:00 | 100% | SP-251194 |  | Cristina Romaguera, Vodafone | cristina.romaguera@vodafone.com | ; 12/9/25: 0%->100; 12/9/25: 100%->100 | 22.011 | 109 | 55 |  |  | Wed 10/09/25 | Fri 12/09/25
819 | 1090009 | CT aspects of Lower Selection-priority for PLMN Selection | LoSePLMN-CT | 2 | Rel-19 |  | 2024-06-06 08:00 | 2025-09-09 17:00 | 52% | CP-252194 |  | Yang Lu; Vodafone | yang.lu@vodafone.com | 29/9/25: List of Impacted TS & TR updated; | 23.122, 24.368, 31.102 | 101 | 51 |  |  | Mon 08/09/25 | Mon 29/09/25
820 | 1090032 | CT aspects of Lower Selection-priority for PLMN Selection | LoSePLMN-CT | 3 | Rel-19 | C1 | 2024-06-06 08:00 | 2025-09-09 17:00 | 5% | CP-252194 |  | Yang Lu; Vodafone | yang.lu@vodafone.com |  |  | 101 | 51 |  |  | Mon 08/09/25 | Wed 06/09/23
821 | 1090033 | CT aspects of Lower Selection-priority for PLMN Selection | LoSePLMN-CT | 3 | Rel-19 | C6 | 2024-06-06 08:00 | 2025-09-09 17:00 | 100% | CP-252194 |  | Yang Lu; Vodafone | yang.lu@vodafone.com |  |  | 101 | 51 |  |  | Mon 08/09/25 | Wed 06/09/23
822 | 1040003 | Subscriber Data Migration | SUBDMIG | 1 | Rel-19 | C4 | 2024-06-17 08:00 | 2025-09-09 17:00 | 98% | CP-251038 |  | Jesus de Gregorio, Ericsson | Jesus de Gregorio, jesus.de.gregorio@ericsson.com |  | 23.527,29.503,29.504,29.510,29.571 | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
823 | 1050010 | Rel-19 Enhancements of Network Automation Enablers | eNetAE19 | 1 | Rel-19 | C3 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-243078 |  | Xuefei Zhang (Huawei) | summer.xuefei@huawei.com |  | 29.508, 29.517, 29.520, 29.522, 29.552, 29.574, 29.575, 29.576, 29.591 | 101 | 51 |  |  | Wed 06/09/23 | Thu 26/09/24
824 | 1040005 | Protocol for AI Data Collection from UPF | PAIDC_UPF | 1 | Rel-19 |  | 2024-06-17 08:00 | 2026-03-30 17:00 | 98% |  |  | Huang Zhenning, China Mobile | huangzhenning@chinamobile.com | 29/9/25: FCD:Tue 09/09/25->Mon 30/03/26; Compl:97%->98%; |  | 101 | 51 |  |  | Wed 06/09/23 | Mon 29/09/25
825 | 1040999 | Study on Protocol for AI Data Collection from UPF | FS_PAIDC_UPF | 2 | Rel-19 | C4 | 2024-06-17 08:00 | 2025-09-09 17:00 | 98% | CP-251039 |  | Huang Zhenning, China Mobile | huangzhenning@chinamobile.com |  |  | 101 | 51 |  |  | Mon 08/09/25 | Wed 06/09/23
826 | 1090001 | CT aspects of PAIDC_UPF | PAIDC_UPF | 2 | Rel-19 |  | 2024-06-17 08:00 | 2026-03-30 17:00 | 98% | CP-252243 |  | Wang Rong, China Mobile | wangrongyjy@chinamobile.com | 29/9/25: FCD:Tue 09/09/25->Mon 30/03/26; WID: CP-252016->CP-252243; | 29.564, 29.508 | 101 | 51 |  |  | Mon 08/09/25 | Mon 29/09/25
827 | 1090036 | CT3 aspects of PAIDC_UPF | PAIDC_UPF | 3 | Rel-19 | C3 | 2024-06-17 08:00 | 2026-03-30 17:00 | 100% | CP-252243 |  | Wang Rong, China Mobile | wangrongyjy@chinamobile.com | 29/9/25: FCD:Tue 09/09/25->Mon 30/03/26; WID: CP-252016->CP-252243; | 29.564, 29.508 | 101 | 51 |  |  | Mon 08/09/25 | Mon 29/09/25
828 | 1090037 | CT4 aspects of PAIDC_UPF | PAIDC_UPF | 3 | Rel-19 | C4 | 2024-06-17 08:00 | 2026-03-30 17:00 | 95% | CP-252243 |  | Wang Rong, China Mobile | wangrongyjy@chinamobile.com | 29/9/25: FCD:Tue 09/09/25->Mon 30/03/26; WID: CP-252016->CP-252243; | 29.564, 29.508 | 101 | 51 |  |  | Mon 08/09/25 | Mon 29/09/25
829 | 1080002 | Study on IMS resiliency | FS_IMSResil | 1 | Rel-19 | C4 | 2025-06-06 08:00 | 2025-09-09 17:00 | 40% | CP-251280 |  | Kenichi Yamamoto, KDDI | kc-yamamoto@kddi.com | 18/7/25: 29.867 added; | 29.867 | 101 | 51 |  |  | Wed 06/09/23 | Fri 18/07/25
830 | 1040039 | IMS Stage-3 IETF Protocol Alignment | IMSProtoc19 | 1 | Rel-19 |  | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-251219 |  | Won, Sung Hwan, Nokia | sung.won@nokia.com |  | 23.218, 24.229, 24.930, 24.186, 29.163, 29.165, 29.292 | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
831 | 1040062 | CT1 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc19 | 2 | Rel-19 | C1 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-251219 |  | Won, Sung Hwan, Nokia | sung.won@nokia.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
832 | 1040063 | CT3 aspects of IMS Stage-3 IETF Protocol Alignment | IMSProtoc19 | 2 | Rel-19 | C3 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-251219 |  | Won, Sung Hwan, Nokia | sung.won@nokia.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
833 | 1040041 | Protocol enhancements for Mission Critical Services | MCProtoc19 | 1 | Rel-19 |  | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-241283 |  | Magnus Tränk, Ericsson | magnus.trank@ericsson.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
834 | 1040064 | CT1 aspects of Protocol enhancements for Mission Critical Services | MCProtoc19 | 2 | Rel-19 | C1 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-241283 |  | Magnus Tränk, Ericsson | magnus.trank@ericsson.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
835 | 1040065 | CT3 aspects of Protocol enhancements for Mission Critical Services | MCProtoc19 | 2 | Rel-19 | C3 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-241283 |  | Magnus Tränk, Ericsson | magnus.trank@ericsson.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
836 | 1040066 | CT4 aspects of Protocol enhancements for Mission Critical Services | MCProtoc19 | 2 | Rel-19 | C4 | 2024-11-03 08:00 | 2025-09-09 17:00 | 100% | CP-241283 |  | Magnus Tränk, Ericsson | magnus.trank@ericsson.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
837 | 1040042 | Enhancement of controlling RAT utilization | ECRATU | 1 | Rel-19 |  | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-251220 |  | Yang Lu, Vodafone | yang.lu@vodafone.com |  | 24.301, 24.501, 23.122, 29.272, 29.503 | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
838 | 1040067 | CT1 aspects of Enhancement of controlling RAT utilization | ECRATU | 2 | Rel-19 | C1 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-251220 |  | Yang Lu, Vodafone | yang.lu@vodafone.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
839 | 1040068 | CT4 aspects of Enhancement of controlling RAT utilization | ECRATU | 2 | Rel-19 | C4 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-251220 |  | Yang Lu, Vodafone | yang.lu@vodafone.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
840 | 1040045 | Enhanced Mission Critical Location Management | enhMCLoc | 1 | Rel-19 | C1 | 2024-06-17 08:00 | 2025-09-09 17:00 | 98% | CP-241288 |  | Magnus Tränk, Ericsson | magnus.trank@ericsson.com |  | 24.281,24.282,24.283,24.379,24.481,24.482,24.483,24.484,29.379 | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
841 | 1050027 | Alignment of eCall over IMS with CEN | eCallCEN | 1 | Rel-19 | C1 | 2024-09-09 08:00 | 2025-06-06 17:00 | 100% | CP-251223 |  | Osama Lotfallah, Qualcomm Incorporated | osamal@qti.qualcomm.com |  | 24.229 | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
842 | 1060075 | UE Conformance - Alignment of eCall over IMS with CEN | eCallCEN-UEConTest | 1 | Rel-19 | R5 | 2024-09-14 11:00 | 2026-03-03 17:00 | 94% | RP-251963 | RP-251962 | Qualcomm |  | 6/3/25: Compl:0%->80%; Stat Rep: ->RP-250112; ; 6/6/25: FCD:Fri 06/06/25->Fri 12/12/25; Compl:80%->90%; Stat Rep: RP-250112->RP-251190; ; 11/9/25: FCD:Fri 12/12/25->Tue 03/03/26; Compl:90%->94%; Stat Rep: RP-251190->RP-251962; ; 29/9/25: WID:RP-242495->RP |  | 106 | 54 |  |  | Fri 24/01/25 | Mon 29/09/25
843 | 1060025 | Rel-19 Enhancements of UE Policy | UEP19 | 1 | Rel-19 | C3 | 2024-12-02 08:00 | 2025-09-09 17:00 | 100% | CP-243073 |  | Susana Fernández, Ericsson | Susana.fernandez@ericsson.com |  | 29.525, 29.523, 29.519, 29.522, 29.513 | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
844 | 1070005 | Rel-19 Enhancements of SM Policy | SMPC19 | 1 | Rel-19 | C3 | 2025-03-03 08:00 | 2025-09-09 17:00 | 100% | CP-250075 |  | Chi Zhang, Huawei | margo.zhangchi@huawei.com |  | 29.512, 29.513 | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
845 | 1070006 | CT Aspects for IP Domain usage | IPD | 1 | Rel-19 | C3 | 2025-03-03 08:00 | 2025-09-09 17:00 | 100% | CP-250248 |  | Zhenning Huang, China Mobile | huangzhenning@chinamobile.com |  | 29.213, 29.513 | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
846 | 1060018 | NAS layer overhead reduction for data transfer using CP CIoT | NORDAT_CP | 1 | Rel-19 | C1 | 2024-12-02 08:00 | 2026-01-13 17:00 | 100% | CP-252195 |  | Amer Catovic | amerc@qti.qualcomm.com | 29/9/25: FCD:Tue 09/09/25->Tue 13/01/26; WID: CP-250251->CP-252195; | 24.301, 24.007 | 101 | 51 |  |  | Wed 06/09/23 | Mon 29/09/25
847 | 1070009 | Support for PWS in Satellite E-UTRAN and Satellite NG-RAN | PWS_NTN | 1 | Rel-19 |  | 2025-03-03 08:00 | 2025-09-09 17:00 | 100% | CP-251222 |  | Amer Catovic | amerc@qti.qualcomm.com |  | 23.041 | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
848 | 1070049 | CT1 aspects of Support for PWS in Satellite E-UTRAN and Satellite NG-RAN | PWS_NTN | 2 | Rel-19 | C1 | 2025-03-03 08:00 | 2025-09-09 17:00 | 100% | CP-251222 |  | Amer Catovic | amerc@qti.qualcomm.com |  |  | 101 | 51 |  |  | Wed 06/09/23 | Wed 06/09/23
849 | 1070050 | DELETED - CT4 aspects of Support for PWS in Satellite E-UTRAN and Satellite NG-RAN | PWS_NTN | 2 | Rel-19 | C4 | 2025-03-06 08:00 | 2025-09-09 17:00 | 100% | CP-251222 |  | Amer Catovic | amerc@qti.qualcomm.com |  |  | 101 | 51 | 108 |  | Wed 06/09/23 | Wed 06/09/23
850 | 1040044 | Stage-3 5GS NAS protocol development 18 | 5GProtoc19 | 1 | Rel-19 |  | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-241280 |  | Sedlacek, Ivo, Ericsson, | ivo <dot> sedlacek <at> ericsson <dot> com |  |  | 96 | 49 |  |  | Fri 03/06/22 | Tue 06/06/23
851 | 1040046 | Stage-3 5GS NAS protocol development 18 general aspects | 5GProtoc19 | 2 | Rel-19 | C1 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-241280 |  | Sedlacek, Ivo, Ericsson, | ivo <dot> sedlacek <at> ericsson <dot> com |  |  | 96 | 49 |  |  | Fri 03/06/22 | NA
852 | 1040047 | Stage-3 5GS NAS protocol development 18 non 3GPP aspects | 5GProtoc19-non3GPP | 2 | Rel-19 | C1 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-241280 |  | Sedlacek, Ivo, Ericsson, | ivo <dot> sedlacek <at> ericsson <dot> com |  |  | 96 | 49 |  |  | Fri 03/06/22 | NA
853 | 1040040 | Stage-3 SAE Protocol Development | SAES19 | 1 | Rel-19 |  | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-241284 |  | Sethi, Anuj, InterDigital |  |  |  | 96 | 49 |  |  | Fri 03/06/22 | Tue 06/06/23
854 | 1040048 | Stage-3 SAE Protocol Development general | SAES19 | 2 | Rel-19 | C1 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-241284 |  | Sethi, Anuj, InterDigital |  |  |  | 96 | 49 |  |  | Fri 03/06/22 | NA
855 | 1040049 | Stage-3 SAE Protocol Development non 3GPP | SAES19-non3GPP | 2 | Rel-19 | C1 | 2024-06-17 08:00 | 2025-09-09 17:00 | 100% | CP-241284 |  | Sethi, Anuj, InterDigital |  |  |  | 96 | 49 |  |  | Fri 03/06/22 | NA
856 | 970002 | Lawful Interception Rel-19 | LI19 | 1 | Rel-19 | S3LI | 2023-03-24 08:00 | 2024-03-30 09:00 | 15% | SP-250817 |  | Koen Jaspers, PIDS | kbj@xs4all.nl | ; 16/3/23: WID:SP-220752->SP-230242; 16/3/23: FCD:03/03/2024->9/9/2024. Rapporteur changed from Alex Leadbeater; 5/9/24: 0%->10; 5/12/24: 10%->15; 26/3/25: WID:SP-230242->SP-250372; 27/6/25: WID:SP-250372->SP-250817; 18/7/25: 33.129-2 added;; 18/7/25: 33 | 33.107; 33.108; 33.126; 33.127; 33.128 ; 33.129-2; 33.129-2; 33.129-1 | 97 | 49 |  |  | Sun 11/09/22 | Fri 18/07/25
857 | 1040010 | Lawful Interception Guidance Rel-19 | LI19_Guide | 1 | Rel-19 | S3LI | 2024-07-16 08:00 | 2024-12-22 11:00 | 52% | SP-240562 |  | Nag Rao, Nokia, | nagaraja.rao@nokia.com | 5/12/24: 0%->52 |  | 104 | 53 |  |  | Tue 16/07/24 | Thu 05/12/24
858 | 1080003 | Harmonization of test case definitions for cross-RAT usability | TestHarmon_CrossRAT | 1 | Rel-19 | C6 | 2025-06-06 08:00 | 2026-03-03 17:00 | 0% | CP-251036 |  | Arne Marquordt, COMPRION GmbH | amarquordt@comprion.com |  | 31.117, 31.121, 31.124, 31.127 | 106 | 54 |  |  | Fri 24/01/25 | Thu 06/03/25
859 | 980130 | (Small) Technical Enhancements and Improvements for Rel-19 | TEI19 | 1 | Rel-19 |  | 2022-09-09 08:00 | 2022-11-12 14:00 | 0% | [6 empty] | 92 | 47 |  |  | Mon 15/06/15 | Mon 15/06/15
860 | 1080051 | LI Handling of Protected Services | FS_LIHOPES | 1 | Rel-19 | S3LI | 2025-06-05 08:00 | 2026-03-03 17:00 | 0% | SP-250813 |  | Mats Näslund, NDRE | mats.naslund@fra.se | 27/6/25: WID:SP-250445->SP-250813; 18/7/25: 33.727 added; | 33.727 | 108 | 55 |  |  | Thu 05/06/25 | Fri 18/07/25
861 | 0 | --- RELEASE 18 --- | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
862 | 0 | Rel-18 Satellite (5GSAT), NTN | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
863 | 970056 | 5G system with satellite backhaul | 5GSATB | 1 | Rel-18 |  | 2021-06-11 08:00 | 2023-12-12 17:00 | 100% | SP-230111 |  | Xu Hui, CATT | xuhui@catt.cn | ; 11/6/21: 0%->100; | 22.261 | 92 | 47 |  |  | Fri 11/06/21 | Fri 10/12/21
864 | 920035 | Stage 1 of 5GSATB | 5GSATB | 2 | Rel-18 | S1 | 2021-06-11 08:00 | 2021-06-18 17:00 | 100% | SP-210528 |  | Xu Hui, CATT | xuhui@catt.cn | ; 11/6/21: 0%->100; | 22.261 | 92 | 47 |  |  | Fri 11/06/21 | Fri 10/12/21
865 | 940060 | Study on Support of Satellite Backhauling in 5GS | FS_5GSATB | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2023-03-03 17:00 | 100% | SP-211639 |  | Hucheng Wang, CATT | wanghucheng@catt.cn | 21/1/22: 23.700-27 added;; 12/3/22: 0%->15; 4/6/22: 15%->60; 12/9/22: 60%->80; 10/12/22: 80%->100 | 23.700-27 | 94 | 48 |  |  | Sun 19/12/21 | Sat 10/12/22
866 | 970018 | Stage 2 of 5GSATB | 5GSATB | 2 | Rel-18 | S2 | 2022-09-12 08:00 | 2023-06-06 17:00 | 100% | SP-230111 |  | Hucheng Wang, CATT | wanghucheng@catt.cn | ; 10/12/22: 0%->30; 15/3/23: FCD:03/03/2023->06/23; 15/3/23: 30%->65; 15/3/23: WID:SP-220808->SP-230111; 8/6/23: 65%->100 | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Sun 11/09/22 | Thu 08/06/23
867 | 980053 | CT3 aspects of 5GSATB | 5GSATB | 2 | Rel-18 | C3 | 2022-12-16 08:00 | 2023-12-12 17:00 | 100% | CP-232131 |  | Hou, Yunjing, CATT | houyunjing@catt.cn | 6/6/23: Compl:30%->60% | 29.512; 29.514; 29.522; 29.525; 29.513; 29.502; 29.244; 29.564 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
868 | 980054 | CT4 aspects of 5GSATB | 5GSATB | 2 | Rel-18 | C4 | 2022-12-16 08:00 | 2023-12-12 17:00 | 100% | CP-232131 |  | Hou, Yunjing, CATT | houyunjing@catt.cn |  | 29.512; 29.514; 29.522; 29.525; 29.513; 29.502; 29.244; 29.564 | 97 | 49 |  |  | Sun 11/09/22 | NA
869 | 1020024 | Charging aspects of Satellite Backhaul in 5GS | 5GSATB_CH | 1 | Rel-18 | S5 | 2023-12-07 08:00 | 2024-03-03 17:00 | 100% | SP-240266 |  | Yingying, Liu, CATT | liuyingying@cictmobile.com | SP-231707 shows UID 1020023 but this duplicates with SP-231706, so changed here to 1020024.; 15/3/24: 0%->100; 2/4/24: WID:SP-231707->SP-240266 | 32.240; 32.255; 32.256; 32.254; 32.257; 32.291; 32.298 | 102 | 52 |  |  | Thu 07/12/23 | Tue 02/04/24
870 | 1020029 | Management aspects of 5G system supporting satellite backhaul | 5GSATB_OAM | 1 | Rel-18 | S5 | 2023-12-07 08:00 | 2024-03-03 17:00 | 100% | SP-231708 |  | Wen Qi, China Telecom | qiw@chinatelecom.cn | ; 14/3/24: 0%->100 | 28.541; 28.552 | 102 | 52 |  |  | Wed 03/01/24 | Thu 14/03/24
871 | 920034 | 5G system with satellite access to Support Control and/or Video Surveillance | SCVS | 1 | Rel-18 | S1 | 2021-06-11 08:00 | 2021-09-08 17:00 | 100% | SP-210527 |  | Dong Chen, Xiaomi | chendong7@xiaomi.com | ; 10/12/21: 0%->100 | 22.261 | 92 | 47 |  |  | Fri 11/06/21 | Fri 10/12/21
872 | 940074 | Study on 5GC enhancement for satellite access Phase 2 | FS_5GSAT_Ph2 | 1 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-211651 |  | Fine, Jean-Yves, Thales | jean-yves.fine@thalesgroup.com. | 21/1/22: 23.700-28 added;; 12/3/22: 0%->12; 4/6/22: 12%->50; 12/9/22: 50%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100 | 23.700-28 | 94 | 48 |  |  | Sun 19/12/21 | Sat 10/12/22
873 | 989998 | Satellite access Phase 2 | 5GSAT_Ph2 | 1 | Rel-18 |  | 2022-12-09 08:00 | 2024-03-03 17:00 | 100% | SP-230109 |  | Rapporteur: Jean-Yves Fine, Thales | jean-yves.fine@thalesgroup.com |  | 23.501; 23.502; 23.503; 23.401 | 98 | 50 |  |  | Fri 09/12/22 | NA
874 | 980014 | (Stage 2 of 5GSAT_Ph2) 5GC/EPC enhancement for satellite access Phase 2 | 5GSAT_Ph2 | 2 | Rel-18 | S2 | 2022-12-09 08:00 | 2023-06-06 17:00 | 100% | SP-230109 |  | Rapporteur: Jean-Yves Fine, Thales | jean-yves.fine@thalesgroup.com | ; 15/3/23: 0%->70; 15/3/23: WID:SP-221344->SP-230109; 8/6/23: 70%->100 | 23.501; 23.502; 23.503; 23.401 | 98 | 50 |  |  | Fri 09/12/22 | Thu 08/06/23
875 | 990024 | CT1 aspects of 5GSAT_Ph2 | 5GSAT_Ph2 | 2 | Rel-18 | C1 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240269 |  | Amer Catovic, Qualcomm Incorporated | amerc@qti.qualcomm.com | 6/6/23: Compl:0%->10% | 24.501.24.301.23.122.27.007.29.122.29.522.31.102 | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
876 | 990056 | deleted - CT6 aspects of 5GSAT_Ph2 | 5GSAT_Ph2 | 2 | Rel-18 | C6 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240269 |  | Amer Catovic, Qualcomm Incorporated | amerc@qti.qualcomm.com | ; 15/3/24: 0%->100 | 24.501.24.301.23.122.27.007.29.122.29.522.31.102 | 99 | 50 |  |  | Fri 09/12/22 | Fri 15/03/24
877 | 1010018 | Charging aspects of 5GSAT | 5GSAT_Ph2_CH | 2 | Rel-18 | S5 | 2023-09-07 08:00 | 2024-03-03 17:00 | 100% | SP-231152 |  | Yingying, Liu, CATT | liuyingying@cictmobile.com | ; 8/12/23: 0%->35; 14/3/24: 35%->100 | 32.255; 32.256; 32.291; 32.298 | 101 | 51 |  |  | Thu 07/09/23 | Thu 14/03/24
878 | 941006 | NR NTN (Non-Terrestrial Networks) enhancements | NR_NTN_enh | 1 | Rel-18 |  | 2021-12-13 08:00 | 2025-12-12 17:00 | 79% | RP-240779 |  | Thales |  | compare REL-17 WI NR_NTN_solutions; 5/4/22: WID:RP-213690->RP-220953; 12/7/22: WID:RP-220953->RP-221819; 23/9/22: WID:RP-221819->RP-222654; 9/1/23: WID:RP-222654->RP-223534; 29/3/23: WID:RP-223534->RP-230809; 6/10/23: WID:RP-230809->RP-232669; 2/1/24: ... |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 02/04/24
879 | 941106 | Core part: NR NTN (Non-Terrestrial Networks) enhancements | NR_NTN_enh-Core | 2 | Rel-18 | R2 | 2021-12-13 08:00 | 2024-06-06 17:00 | 100% | RP-232669 | RP-240921 | Nicolas Chuberre, Thales | Nicolas.chuberre@thalesaleniaspace.com | compare REL-17 WI NR_NTN_solutions; 22/3/22: Stat Rep: ->RP-220383; 20/6/22: FCD:12/12/2023->23/12/2022; Compl:0%->5%; Stat Rep: RP-220383->RP-221170 / 1746; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.... |  | 94 | 48 |  |  | Thu 06/01/22 | Thu 13/06/24
880 | 941206 | Perf. part: NR NTN (Non-Terrestrial Networks) enhancements | NR_NTN_enh-Perf | 2 | Rel-18 | R2 | 2021-12-15 08:00 | 2024-06-06 17:00 | 100% | RP-232669 | RP-240921 | Nicolas Chuberre, Thales | Nicolas.chuberre@thalesaleniaspace.com | ; ; 20/6/22: WG: R4->R2; FCD:12/06/2024->24/06/2022; Stat Rep: RP-220383->RP-221170 / 1746; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com13/7/22: FCD:24/06/2022->06/20 ...; 9/12/22: FCD:24/06/2023->0... |  | 94 | 48 |  |  | Thu 06/01/22 | Thu 13/06/24
881 | 1050130 | UE Conformance - NR NTN (non-Terrestrial Networks) enhancements plus CT aspects | NR_NTN_enh_plus_CT-UEConTest | 2 | Rel-18 | R5 | 2024-09-09 08:00 | 2025-12-12 17:00 | 20% | RP-251230 | RP-252049 | Qualcomm |  | 6/12/24: Compl:0%->6%; Stat Rep: ->RP-242899; ; 6/3/25: FCD:24/07/2025->12/12/2025; Compl:6%->10%; Stat Rep: RP-242899->RP-250397; ; 6/6/25: Compl:10%->15%; Stat Rep: RP-250397->RP-251231; ; 18/7/25: WID:RP-242024->RP-251230; 11/9/25: Compl:15%->20%; Sta |  | 105 | 53 |  |  | Thu 26/09/24 | Thu 11/09/25
882 | 941004 | IoT (Internet of Things) NTN (non-terrestrial network) enhancements | IoT_NTN_enh | 1 | Rel-18 |  | 2021-12-13 08:00 | 2024-12-12 17:00 | 95% | RP-241351 |  | MediaTek |  | no Perf. part; 5/4/22: WID:RP-213596->RP-220979; 12/7/22: WID:RP-220979->RP-221806; 9/1/23: WID:RP-221806->RP-223519; 2/1/24: WID:RP-223519->RP-234073; 23/7/24: WID:RP-234073->RP-241351 |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 23/07/24
883 | 940104 | Core part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements | IoT_NTN_enh-Core | 2 | Rel-18 | R2 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-241351 | RP-233260 | Abhishek Roy, MediaTek | abhishek.roy@mediatek.com | no Perf. Part. Slight misalignment in UID numberring scheme (940104 instead of 941104) but it was decided to leave it as such to avoid further potential problems by changing a UID; 20/6/22: FCD:12/12/2023->23/12/2022; Compl:0%->3%; Stat Rep: ->RP-22155... |  | 94 | 48 |  |  | Thu 06/01/22 | Fri 08/12/23
884 | 950284 | Perf. Part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements | IoT_NTN_enh-Perf | 2 | Rel-18 | R4 | 2022-03-07 08:00 | 2024-06-06 17:00 | 100% | RP-241351 | RP-241350 | Abhishek Roy, MediaTek | abhishek.roy@mediatek.com | 20/6/22: WG: R4->R2; FCD:07/06/2024->24/06/2022; Stat Rep: ->RP-221553 / 1759; Rapporteur: MediaTek->Abhishek Roy, MediaTek; Rap eMail: ->abhishek.roy@mediatek.com ...; 17/3/23: FCD:23/12/2022->06/06/2024; Stat Rep: ->RP-230633; Rapporteur: MediaTek... |  | 95 | 48 |  |  | Sat 04/06/22 | Thu 13/06/24
885 | 1030073 | UE Conformance - IoT (Internet of Things) NTN (non-terrestrial network) enhancements plus CT1 aspects | IoT_NTN_enh_plus_CT1-UEConTest | 2 | Rel-18 | R5 | 2024-03-03 08:00 | 2025-12-12 17:00 | 87% | RP-241949 | RP-252594 | CMCC |  | 13/6/24: Compl:0%->16%; WID: RP-240784->RP-240144; Stat Rep: ->RP-241198; ; 23/7/24: WID:RP-240144->RP-241197; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:16%->27%; Stat Rep: RP-241198->RP-241950; ; 26/9/24: WID:RP-241197->RP-241949; 6/12/24: FCD:12/12/2024 |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
886 | 981043 | Introduction of the satellite L-/S-band for NR | NR_NTN_LSband | 1 | Rel-18 |  | 2022-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-234043 |  | Apple |  | 29/3/23: WID:RP-223485->RP-230706; 8/6/23: 38.741 added;; 2/1/24: WID:RP-230706->RP-234043 | 38.741 | 98 | 50 |  |  | Mon 09/01/23 | Tue 02/01/24
887 | 981143 | Core part: Introduction of the satellite L-/S-band for NR | NR_NTN_LSband-Core | 2 | Rel-18 | R4 | 2022-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-234043 | RP-233306 | Alexander Sayenko, Apple Inc. | asayenko@apple.com | 17/3/23: FCD:12/12/2023->08/09/2023; Compl:0%->10%; Stat Rep: ->RP-230154; Rapporteur: Apple->Alexander Sayenko, Apple Inc.; Rap eMail: ->asayenko@apple.com; 31/3/23: FCD:08/09/2023->12/12/2023; Stat Rep: RP-230154->RP-230707; ...; 6/9/23: Compl:50%->... |  | 98 | 50 |  |  | Mon 09/01/23 | Fri 08/12/23
888 | 981243 | Perf. part: Introduction of the satellite L-/S-band for NR | NR_NTN_LSband-Perf | 2 | Rel-18 | R4 | 2022-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-234043 | RP-233306 | Alexander Sayenko, Apple Inc. | asayenko@apple.com | 17/3/23: Compl:0%->50%; Stat Rep: ->RP-230154; Rapporteur: Apple->Alexander Sayenko, Apple Inc.; Rap eMail: ->asayenko@apple.com; 31/3/23: Stat Rep: RP-230154->RP-230707; ...; 6/9/23: Compl:90%->95%; WID: RP-230706->RP-231179; Stat Rep: RP-230707->RP-... |  | 98 | 50 |  |  | Mon 09/01/23 | Fri 08/12/23
889 | 970028 | Study on Security Aspects of Satellite Access | FS_5GSAT_Sec | 1 | Rel-18 | S3 | 2022-09-12 08:00 | 2023-03-03 17:00 | 100% | SP-220875 |  | Wei Lu, Xiaomi | luwei10@xiaomi.com | 23/9/22: 33.700-28 added;; 11/12/22: 0%->15; 17/3/23: 15%->25; 8/6/23: 25%->100; 7/9/23: 100%-> | 33.700-28 | 97 | 49 |  |  | Sun 11/09/22 | Thu 07/09/23
890 | 960026 | Study on Management Aspects of IoT NTN Enhancements | FS_IoT_NTN | 1 | Rel-18 | S5 | 2022-06-02 08:00 | 2023-06-06 17:00 | 100% | SP-220490 |  | Sun Mingrui, China Unicom | sunmr19@chinaunicom.cn | 12/9/22: 0%->30; 11/12/22: 30%->75; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 75%->95; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100 |  | 96 | 49 |  |  | Thu 02/06/22 | Thu 08/06/23
891 | 960091 | Study on requirements and use cases for network verified UE location for Non-Terrestrial-Networks (NTN) in NR | FS_NR_NTN_netw_verif_UE_loc | 1 | Rel-18 | RP | 2022-06-01 08:00 | 2022-06-15 17:00 | 100% | RP-221820 |  | Thales |  |  |  | 96 | 49 |  |  | Tue 12/07/22 | NA
892 | 980028 | Study on charging aspects of Satellite in 5GS | FS_5GSAT_CH | 1 | Rel-18 | S5 | 2022-06-01 08:00 | 2023-12-12 17:00 | 100% | SP-221162 |  | Yingying, Liu, CATT | liuyingying@cictmobile.com | 17/3/23: 0%->5; 17/3/23: 22.844 added;; 8/6/23: 5%->30; 7/9/23: 0%->80; 8/12/23: 80%->100; 8/12/23: 99%->100 | 22.844 | 98 | 50 |  |  | Fri 09/12/22 | Fri 08/12/23
893 | 1000060 | 30 MHz Channel Bandwidth for NR NTN (non-terrestrial networks) in FR1 (frequency range 1) | NR_NTN_CBW_30MHz | 1 | Rel-18 | R4 | 2023-06-07 08:00 | 2023-09-08 17:00 | 100% | RP-232647 |  | Thales |  | 6/10/23: WID:RP-231499->RP-232647 |  | 100 | 51 |  |  | Thu 29/06/23 | Fri 06/10/23
894 | 1001060 | Core part: 30 MHz Channel Bandwidth for NR NTN (non-terrestrial networks) in FR1 (frequency range 1) | NR_NTN_CBW_30MHz-Core | 2 | Rel-18 | R4 | 2023-06-07 08:00 | 2023-09-08 17:00 | 100% | RP-232647 | RP-232646 | Dorin Panaitopol, THALES | dorin.panaitopol@thalesgroup.com | 6/9/23: Compl:0%->50%; Stat Rep: ->RP-231568; Rapporteur: Thales->Dorin Panaitopol, THALES; Rap eMail: ->dorin.panaitopol@thalesgroup.com; ; 21/9/23: FCD:12/12/2023->08/09/2023; Compl:50%->100%; Stat Rep: RP-231568->RP-232646; |  | 100 | 51 |  |  | Thu 29/06/23 | Thu 21/09/23
895 | 991041 | Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN | IoT_NTN_extLband | 1 | Rel-18 | R4 | 2023-03-03 08:00 | 2025-06-06 17:00 | 100% | RP-240741 |  | Inmarsat |  | 7/9/23: WID:RP-230790->RP-231487; 6/10/23: WID:RP-231487->RP-232686; 2/1/24: WID:RP-232686->RP-233856; 2/4/24: WID:RP-233856->RP-240741 |  | 99 | 50 |  |  | Wed 29/03/23 | Tue 02/04/24
896 | 991141 | Core part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN | IoT_NTN_extLband-Core | 2 | Rel-18 | R4 | 2023-03-03 08:00 | 2024-03-03 17:00 | 100% | RP-240741 | RP-232609 | Luca Lodigiani, Inmarsat | Luca.lodigiani@inmarsat.com | ; 7/6/23: Compl:0%->11%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:11%->30%; WID: RP-230790->RP-231487; Stat Rep: ->RP-232459; Rapporteur: Inmarsat->Luca Lodigiani, Inmarsat; Rap eMail: ->Luca.lodigiani@inmarsat.com; ; 21/9/23: FCD:22/09/2023->12/12/2... |  | 99 | 50 |  |  | Wed 29/03/23 | Tue 02/04/24
897 | 991241 | Perf. part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN | IoT_NTN_extLband-Perf | 2 | Rel-18 | R4 | 2023-03-03 08:00 | 2024-06-06 17:00 | 100% | RP-240741 | RP-232609 | Luca Lodigiani, Inmarsat | Luca.lodigiani@inmarsat.com | 6/9/23: WID: RP-230790->RP-231487; Stat Rep: ->RP-232459; Rapporteur: Inmarsat->Luca Lodigiani, Inmarsat; Rap eMail: ->Luca.lodigiani@inmarsat.com; ; 21/9/23: FCD:12/12/2023->06/06/2024; Stat Rep: RP-232459->RP-232609; ; 8/12/23: FCD:06/06/2024->12/12... |  | 99 | 50 |  |  | Wed 29/03/23 | Tue 23/07/24
898 | 1040110 | UE Conformance - Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN | IoT_NTN_extLband-UEConTest | 2 | Rel-18 | R5 | 2024-06-06 08:00 | 2025-06-06 17:00 | 100% | RP-241355 | RP-251292 | Mediatek |  | 4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->5%; Stat Rep: ->RP-242049; ; 6/12/24: Compl:5%->95%; Stat Rep: RP-242049->RP-242993; ; 6/3/25: FCD:14/02/2025->06/06/2025; Stat Rep: RP-242993->RP-250476; ; 6/6/25: Compl:95%->100%; Stat Rep: RP-250476->RP-25 |  | 104 | 53 |  |  | Tue 23/07/24 | Fri 06/06/25
899 | 991043 | Introduction of FDD LTE band (L+S band) for IoT NTN operation | IoT_NTN_FDD_LS_band | 1 | Rel-18 | R4 | 2023-03-03 08:00 | 2025-03-03 17:00 | 100% | RP-241353 |  | MediaTek |  | 2/1/24: WID:RP-230792->RP-234060; 2/4/24: WID:RP-234060->RP-240451; 23/7/24: WID:RP-240451->RP-241353 |  | 99 | 50 |  |  | Wed 29/03/23 | Tue 23/07/24
900 | 991143 | Core part: Introduction of FDD LTE band (L+S band) for IoT NTN operation | IoT_NTN_FDD_LS_band-Core | 2 | Rel-18 | R4 | 2023-03-03 08:00 | 2023-12-12 17:00 | 100% | RP-241353 | RP-241352 | Huanren FU, MediaTek Inc. | huanren.fu@mediatek.com | ; 7/6/23: Compl:0%->30%; 6/9/23: Compl:30%->60%; WID: RP-230792->RP-231479; Stat Rep: ->RP-232313; Rapporteur: MediaTek->Aijun CAO, MediaTek Inc.; Rap eMail: ->aijun.cao@mediatek.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-232313->RP-233258; ; 4/1/2... | 36.764 | 99 | 50 |  |  | Wed 29/03/23 | Thu 13/06/24
901 | 991243 | Perf. part: Introduction of FDD LTE band (L+S band) for IoT NTN operation | IoT_NTN_FDD_LS_band-Perf | 2 | Rel-18 | R4 | 2023-03-06 08:00 | 2024-06-06 17:00 | 100% | RP-241353 | RP-241352 | Huanren FU, MediaTek Inc. | huanren.fu@mediatek.com | ; 7/6/23: CD:06/06/2024->06/06/2023; 6/9/23: FCD:06/06/2023->06/06/2024; WID: RP-230792->RP-231479; Stat Rep: ->RP-232313; Rapporteur: MediaTek->Aijun CAO, MediaTek Inc.; Rap eMail: ->aijun.cao@mediatek.com; ; 8/12/23: Stat Rep: RP-232313->RP-233258; ... |  | 99 | 50 |  |  | Wed 29/03/23 | Thu 13/06/24
902 | 1040109 | UE Conformance - Introduction of FDD LTE band (L+S band) for IoT NTN operation | IoT_NTN_FDD_LS_band-UEConTest | 2 | Rel-18 | R5 | 2024-06-06 08:00 | 2024-12-12 17:00 | 100% | RP-242992 | RP-242991 | Mediatek |  | 4/9/24: FCD:03/03/2025->25/03/2025; Compl:0%->95%; Stat Rep: ->RP-242048; ; 6/12/24: FCD:03/03/2025->12/12/2024; Compl:95%->99%; Stat Rep: RP-242048->RP-242991; ; 24/1/25: WID:RP-241354->RP-242992; 24/1/25: 99%->100 |  | 104 | 53 |  |  | Tue 23/07/24 | Fri 24/01/25
903 | 950074 | NB-IoT/eMTC Core and Perf requirements for NTN | LTE_NBIOT_eMTC_NTN_req | 1 | Rel-18 |  | 2022-03-15 08:00 | 2024-03-03 17:00 | 100% | RP-223437 |  | MediaTek |  | TS 36.10x, TS 36.10y; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 12/7/22: WID:RP-220938->RP-221556; 9/1/23: WID:RP-221556->RP-223437; 23/7/24: 99%->100 |  | 95 | 48 |  |  | Tue 05/04/22 | Tue 23/07/24
904 | 950174 | Core part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) | LTE_NBIoT_eMTC_NTN_req-Core | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2022-12-01 17:00 | 100% | RP-221556 | RP-223231 | Tim Frost, MediaTek Inc. | Tim.frost@mediatek.com | TS 36.10x, TS 36.10y; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 20/6/22: FCD:15/12/2022->22/12/2022; Stat Rep: ->RP-221555; Rapporteur: MediaTek->Tim Frost, MediaTek Inc.; Rap eMail: ->tim dot frost at mediatek dot com13/7/22: 36.1...;... | 36.102; 36.105; 36.108 | 95 | 48 |  |  | Tue 05/04/22 | Mon 09/01/23
905 | 950274 | Perf. part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) | LTE_NBIoT_eMTC_NTN_req-Perf | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2023-06-06 17:00 | 100% | RP-223437 | RP-230634 | Hsuanli Lin, MediaTek Inc. | hsuanli.lin@mediatek.com | TS 36.1XX; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 6/6/22: CD:15/06/2023->23/06/2022; 6/6/22: Stat Rep: ->RP-221555; 20/6/22: Rapporteur: MediaTek->Tim Frost, MediaTek Inc.; Rap eMail: ->tim dot frost at mediatek dot com13/7/22: ...;... | 36.181 | 95 | 48 |  |  | Tue 05/04/22 | Wed 07/06/23
906 | 981034 | UE Conformance - NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) | LTE_NBIOT_eMTC_NTN_req-UEConTest | 2 | Rel-18 | R5 | 2022-12-13 08:00 | 2024-03-03 17:00 | 100% | RP-240147 | RP-240146 | Dan SONG, Danbo Fu (MediaTek), CMCC, MediaTek Inc. | songdan@chinamobile.com, Danbo.Fu@mediatek.com | 17/3/23: Compl:0%->30%; Stat Rep: ->RP-230284; Rapporteur: CMCC->Dan SONG, Danbo Fu (MediaTek), CMCC, MediaTek Inc.; Rap eMail: ->songdan@chinamobile.com, Danbo.Fu@mediatek.com; 17/3/23: 36.521-4 added;; 29/3/23: WID:RP-223064->RP-230285; ...; 21/9/23... | 36.521-4 | 98 | 50 |  |  | Mon 09/01/23 | Tue 02/04/24
907 | 0 | Rel-18 Internet of Things (IoT), MTC, Energy, complexity saving | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
908 | 930029 | Personal IoT and Residential networks | PIRates | 1 | Rel-18 |  | 2020-06-25 08:00 | 2024-03-03 17:00 | 100% | SP-211505 |  | Xiaowan Ke, vivo Mobile Communications Ltd | xiaowan.ke@vivo.com | ; 10/12/21: WID:SP-211055->SP-211505 (chg rapporteur) | 22.261 | 93 | 47 |  |  | Fri 10/09/21 | Fri 10/12/21
909 | 880041 | Study on Personal IoT Networks | FS_PIN | 2 | Rel-18 | S1 | 2020-06-25 08:00 | 2021-06-11 17:00 | 100% | SP-200592 |  | Adrian Buckley, vivo Mobile Communications | adrian.buckley@vivo.com | 28/7/20: 22.859 added;; 12/9/20: 0%->15; 5/12/20: 15%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->90; 13/9/21: 90%->100 | 22.859 | 88 | 45 |  |  | Thu 25/06/20 | Mon 13/09/21
910 | 880040 | Study on Enhancements for Residential 5G | FS_Resident | 2 | Rel-18 | S1 | 2020-06-25 08:00 | 2021-06-11 17:00 | 100% | SP-200576 |  | Toon Norp, KPN | toon.norp@tno.nl | 28/7/20: 22.858 added;; 12/9/20: 0%->30; 5/12/20: 30%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->85; 13/9/21: 85%->100 | 22.858 | 88 | 45 |  |  | Thu 25/06/20 | Mon 13/09/21
911 | 930022 | Stage 1 of PIRates | PIRates | 2 | Rel-18 | S1 | 2021-09-10 08:00 | 2021-12-10 17:00 | 100% | SP-211505 |  | Xiaowan Ke, vivo Mobile Communications Ltd | xiaowan.ke@vivo.com | ; 13/9/21: 0%->85; 10/12/21: 85%->100; 10/12/21: WID:SP-211055->SP-211505 | 22.261 | 93 | 47 |  |  | Fri 10/09/21 | Fri 10/12/21
912 | 940065 | Study on Personal IoT Networks | FS_PIN | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2023-03-03 17:00 | 100% | SP-230089 |  | Zhenhua Xie, vivo Mobile Communications Ltd | zhenhua.xie@vivo.com | 21/1/22: 23.700-88 added;; 12/3/22: 0%->20; 4/6/22: 20%->60; 12/9/22: 60%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->95; 15/3/23: FCD:12/12/2022->03/23; 15/3/23: 95%->100; 15/3/23: WID:SP-211643->SP-230089 | 23.700-88 | 94 | 48 |  |  | Sun 19/12/21 | Wed 15/03/23
913 | 980011 | (Stage 2 of) Personal IoT Networks | PIN | 2 | Rel-18 | S2 | 2022-12-09 08:00 | 2023-06-06 17:00 | 100% | SP-221343 |  | Zhenhua Xie, vivo | zhenhua.xie@vivo.com | 10/1/23: FCD clarified to be June (and not March) by e-mail; 15/3/23: 0%->60; 8/6/23: 60%->100 | 23.501; 23.502; 23.503 | 98 | 50 |  |  | Fri 09/12/22 | Thu 08/06/23
914 | 990018 | CT1 aspects of PIN | PIN | 2 | Rel-18 | C1 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-233216 |  | Hui Wang, vivo | wanghui.wh@vivo.com | 6/6/23: Compl:0%->50% | 24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244 | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
915 | 990058 | CT3 aspects of PIN | PIN | 2 | Rel-18 | C3 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-233216 |  | Hui Wang, vivo | wanghui.wh@vivo.com | 9/6/23: 0%->20 | 24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244 | 99 | 50 |  |  | Fri 09/12/22 | Fri 09/06/23
916 | 990059 | CT4 aspects of PIN | PIN | 2 | Rel-18 | C4 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-233216 |  | Hui Wang, vivo | wanghui.wh@vivo.com |  | 24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244 | 99 | 50 |  |  | Fri 09/12/22 | NA
917 | 990106 | Application layer support for Personal IoT Network | PINAPP | 1 | Rel-18 |  | 2021-12-13 08:00 | 2024-03-03 17:00 | 100% | SP-221236 |  | Huazhang Lv, vivo Mobile Communications Ltd, | huazhang.lv@vivo.com |  |  | 99 | 50 |  |  | Fri 09/12/22 | NA
918 | 940021 | Study on Application layer support for Personal IoT Networks | FS_PINAPP | 2 | Rel-18 | S6 | 2021-12-13 08:00 | 2022-12-12 17:00 | 100% | SP-220095 |  | Huazhang Lv, vivo Mobile Communications Ltd | huazhang.lv@vivo.com | 7/1/22: 23.700-78 added;; 12/3/22: WID:SP-211515->SP-220095; 12/3/22: 0%->15; 4/6/22: 15%->40; 12/9/22: 40%->60; 12/9/22: FCD:12/09/2022->12/20; 11/12/22: 60%->100; 31/3/23: 24.583 added; | 23.700-78; 24.583 | 94 | 48 |  |  | Mon 13/12/21 | Fri 31/03/23
919 | 980052 | Stage 2 of PINAPP | PINAPP | 2 | Rel-18 | S6 | 2022-12-09 08:00 | 2023-06-06 17:00 | 100% | SP-221236 |  | Huazhang Lv, vivo Mobile Communications Ltd, | huazhang.lv@vivo.com | 17/3/23: FCD:03/03/2023->/23; 17/3/23: 0%->50; 17/3/23: 23.542 added;; 8/6/23: 50%->100 | 23.542 | 98 | 50 |  |  | Fri 09/12/22 | Thu 08/06/23
920 | 990017 | CT1 aspects of PINAPP | PINAPP | 2 | Rel-18 | C1 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-233218 |  | Yizhong ZHANG, vivo | yizhong.zhang@vivo.com | 6/6/23: Compl:0%->40% | 27.007 | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
921 | 990061 | CT3 aspects of PINAPP | PINAPP | 2 | Rel-18 | C3 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-233218 |  | Yizhong ZHANG, vivo | yizhong.zhang@vivo.com | 31/3/23: 29.583 added;; 9/6/23: 5%->10 | 27.007; 29.583 | 99 | 50 |  |  | Fri 09/12/22 | Fri 09/06/23
922 | 960027 | Study on Personal IoT Networks Security Aspects | FS_PIN_Sec | 1 | Rel-18 | S3 | 2022-06-02 08:00 | 2023-03-03 17:00 | 100% | SP-220525 |  | Zhenhua Xie, vivo Mobile Communications Co. Ltd | zhuenhua.xie@vivo.com | 13/7/22: 33.882 added;; 12/9/22: 0%->20; 11/12/22: 20%->50; 17/3/23: 50%->60; 8/6/23: 60%->100 | 33.882 | 96 | 49 |  |  | Thu 02/06/22 | Thu 08/06/23
923 | 920016 | Study on Application Capability Exposure for IoT Platforms | FS_ACE_IOT | 1 | Rel-18 | S6 | 2021-06-11 08:00 | 2022-06-09 17:00 | 100% | SP-220093 |  | Mladin, Catalina; Convida Wireless | Mladin.Catalina@convidawireless.com | 2/7/21: 23.700-97 added;; 13/9/21: 0%->15; 13/12/21: 15%->40; 12/3/22: 40%->55; 12/3/22: FCD:11/03/2022->6/22; 12/3/22: WID:SP-210478->SP-220093; 4/6/22: 55%->60; 12/9/22: 60%->75; 11/12/22: 75%->75; 17/3/23: 75%->95; 8/6/23: 95%->100 | 23.700-97 | 92 | 47 |  |  | Fri 11/06/21 | Thu 08/06/23
924 | 0 | See also IoT_NTN_en under Satellite and LPHP under Verticals | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
925 | 0 | See also " NB-IoT/eMTC requirements for NTN" (UID 950074) under Satellite | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
926 | 940085 | Study on low-power wake-up signal and receiver for NR | FS_NR_LPWUS | 1 | Rel-18 | R1 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-232672 | RP-233067 | Xueming Pan, vivo | panxueming@vivo.com | 21/1/22: 38.869 added;; 22/3/22: Stat Rep: ->RP-2205966/6/22: CD:12/12/2023->23/12/20226/6/22: Stat Rep: RP-220596->RP-221270; 20/6/22: Rapporteur: vivo->Xiaodong Shen, vivo Communication Technology; Rap eMail: ->shenxiaodong@vivo.com12/7/22: WID:R...;... | 38.869 | 94 | 48 |  |  | Thu 06/01/22 | Fri 08/12/23
927 | 970080 | Enhanced support of reduced capability NR devices | NR_redcap_enh | 1 | Rel-18 |  | 2021-12-12 08:00 | 2024-12-12 17:00 | 93% | RP-233637 |  | Ericsson |  | 9/1/23: WID:RP-222675->RP-223544; 6/10/23: WID:RP-223544->RP-232671; 2/1/24: WID:RP-232671->RP-233637 |  | 97 | 49 |  |  | Fri 23/09/22 | Tue 02/01/24
928 | 970180 | Core part: Enhanced support of reduced capability NR devices | NR_redcap_enh-Core | 2 | Rel-18 | R1 | 2022-09-08 08:00 | 2023-12-12 17:00 | 100% | RP-233637 | RP-233636 | Johan BERGMAN, Ericsson | johan.bergman@ericsson.com | 9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-222827; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-222827->RP-230111; ;..... |  | 97 | 49 |  |  | Fri 23/09/22 | Fri 08/12/23
929 | 970280 | Perf. part: Enhanced support of reduced capability NR devices | NR_redcap_enh-Perf | 2 | Rel-18 | R1 | 2022-09-13 08:00 | 2024-06-06 17:00 | 100% | RP-233637 | RP-241124 | Johan BERGMAN, Ericsson | johan.bergman@ericsson.com | 9/12/22: WG: R4->R1; FCD:10/06/2023->01/06/2024; Stat Rep: ->RP-222827; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; 17/3/23: Stat Rep: RP-222827->RP-230111; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Stat Rep:... |  | 97 | 49 |  |  | Fri 23/09/22 | Tue 23/07/24
930 | 940086 | Study on further NR RedCap (reduced capability) UE complexity reduction | FS_NR_redcap_enh | 2 | Rel-18 | R1 | 2021-12-12 08:00 | 2022-09-09 17:00 | 100% | RP-221161 | RP-221160 | Johan BERGMAN, Ericsson | johan.bergman@ericsson.com | TR 38.8xx; compare REL-17 SI FS_NR_redcap and REL-17 WI NR_redcap; 21/1/22: 38.865 added;; 22/3/22: Stat Rep: ->RP-220470 ; 6/6 ; 20/6/22: Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com12/7/22: WID:RP-213661-...; 23 | 38.865 | 94 | 48 |  |  | Thu 06/01/22 | Fri 23/09/22
931 | 1030062 | UE Conformance - Enhanced support of reduced capability NR devices plus CT1 aspects | NR_redcap_enh_plus_CT1-UEConTest | 2 | Rel-18 | R5 | 2024-03-03 08:00 | 2025-12-12 17:00 | 83% | RP-242487 | RP-251976 | China Unicom |  | 13/6/24: Compl:0%->5%; Stat Rep: ->RP-240919; ; 23/7/24: WID:RP-240054->RP-240920; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->28%; Stat Rep: RP-240919->RP-241883; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:28%->53%; Stat Rep: RP-241883->RP-242486; ; |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
932 | 940056 | Study on RedCap Phase 2 | FS_REDCAP_Ph2 | 1 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-220074 |  | Qian, Chen, Ericsson | qian.xb.chen@ericsson.com | 21/01/22: name corrected; 21/1/22: 23.700-68 added;; 12/3/22: 0%->30; 12/3/22: WID:SP-211635->SP-220074; 4/6/22: 30%->70; 12/9/22: 70%->99; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 99%->100 | 23.700-68 | 94 | 48 |  |  | Sun 19/12/21 | Sat 10/12/22
933 | 980113 | NR RedCap UE with long eDRX for RRC_INACTIVE State | NR_REDCAP_Ph2 | 1 | Rel-18 |  | 2022-12-15 08:00 | 2023-12-13 17:00 | 100% | SP-220803 |  | Qian, Chen, Ericsson | qian.xb.chen@ericsson.com |  | 23.501; 23.502 | 97 | 49 |  |  | Sun 11/09/22 | NA
934 | 970013 | (Stage 2 of) NR RedCap UE with long eDRX for RRC_INACTIVE State | NR_REDCAP_Ph2 | 2 | Rel-18 | S2 | 2022-09-12 08:00 | 2023-03-03 17:00 | 100% | SP-230171 |  | Qian, Chen, Ericsson | qian.xb.chen@ericsson.com | ; 10/12/22: 0%->60; 15/3/23: WID:SP-220803->SP-230171; 15/3/23: 60%->95; 8/6/23: 95%->100; 4/1/24: 28.876 added; | 23.501; 23.502 ; 28.876 | 97 | 49 |  |  | Sat 10/12/22 | Thu 04/01/24
935 | 980068 | CT4 aspects of NR_REDCAP_Ph2 | NR_REDCAP_Ph2 | 2 | Rel-18 | C4 | 2022-12-15 08:00 | 2023-12-12 17:00 | 100% | CP-223021 |  | Frank Yong Yang, Ericsson | frank.yong.yang@ericsson.com | 6/6/23: Compl:60%->90% | 24.008; 29.502; 29.518 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
936 | 980069 | CT1 aspects of NR_REDCAP_Ph2 | NR_REDCAP_Ph2 | 2 | Rel-18 | C1 | 2022-12-16 08:00 | 2023-12-12 17:00 | 100% | CP-223021 |  | Frank Yong Yang, Ericsson | frank.yong.yang@ericsson.com |  | 24.008; 29.502; 29.518 | 97 | 49 |  |  | Sun 11/09/22 | NA
937 | 991039 | Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18 | NR_FDD_bands_R18_redcap | 1 | Rel-18 |  | 2023-03-06 08:00 | 2025-03-03 17:00 | 100% | RP-232894 |  | Ericsson |  | 2/1/24: WID:RP-230743->RP-232894 |  | 99 | 50 |  |  | Fri 07/04/23 | Tue 02/01/24
938 | 991139 | Core part: Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18 | NR_FDD_bands_R18_redcap-Core | 2 | Rel-18 | R4 | 2023-03-06 08:00 | 2023-12-12 17:00 | 100% | RP-232894 | RP-232xyz | Chunhui Zhang, Ericsson | Chunhui.Zhang@ericsson.com | ; 7/6/23: Compl:0%->40%; 6/9/23: Compl:40%->50%; WID: RP-230743->RP-231049; Stat Rep: ->RP-231881; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 8/12/23: Compl:50%->100%; Stat Rep: RP-231881->RP-232xyz; |  | 99 | 50 |  |  | Fri 07/04/23 | Fri 08/12/23
939 | 1060076 | UE Conformance - New NR FDD bands for RedCap (Reduced Capability) in Rel-18 | NR_FDD_bands_R18_redcap-UEConTest | 2 | Rel-18 | R5 | 2024-08-28 14:00 | 2025-03-03 17:00 | 100% | RP-250289 | RP-250288 | Ericsson |  | 6/3/25: FCD:09/09/2025->03/03/2025; Compl:0%->100%; Stat Rep: ->RP-250288; ; 3/4/25: WID:RP-242648->RP-250289 |  | 106 | 54 |  |  | Fri 24/01/25 | Thu 03/04/25
940 | 981037 | Network energy savings for NR | Netw_Energy_NR | 1 | Rel-18 |  | 2021-12-13 08:00 | 2025-12-12 17:00 | 99% | RP-234009 |  | Huawei |  | 2/1/24: WID:RP-223540->RP-234009 |  | 98 | 50 |  |  | Mon 09/01/23 | Tue 02/01/24
941 | 981137 | Core part: Network energy savings for NR | Netw_Energy_NR-Core | 2 | Rel-18 | R1 | 2022-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-234009 | RP-233655 | Yi Wang, Huawei | wangyi6@huawei.com | 17/3/23: FCD:12/12/2023->08/09/2023; Compl:0%->15%; Stat Rep: ->RP-230565; Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com; 31/3/23: FCD:08/09/2023->12/12/2023; Stat Rep: RP-230565->RP-230714; ;...; 6/9/23: Compl:55%->75%; Stat Re... |  | 98 | 50 |  |  | Mon 09/01/23 | Fri 08/12/23
942 | 981237 | Perf. part: Network energy savings for NR | Netw_Energy_NR-Perf | 2 | Rel-18 | R4 | 2022-12-14 08:00 | 2024-06-06 17:00 | 100% | RP-234009 | RP-241239 | Yi Wang, Huawei | wangyi6@huawei.com | 17/3/23: Stat Rep: ->RP-230565; Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com; 31/3/23: FCD:06/06/2024->06/06/2023; Stat Rep: RP-230565->RP-230714; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Stat Rep: RP-230714->RP-231926; ; 8/12/... |  | 98 | 50 |  |  | Mon 09/01/23 | Tue 23/07/24
943 | 1030067 | UE Conformance - Network energy savings for NR | Netw_Energy_NR-UEConTest | 2 | Rel-18 | R5 | 2024-03-03 08:00 | 2025-12-12 17:00 | 97% | RP-240291 | RP-252647 | Huawei |  | 13/6/24: Compl:0%->5%; Stat Rep: ->RP-241378; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->24%; Stat Rep: RP-241378->RP-242075; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:24%->54%; Stat Rep: RP-242075->RP-243092; ; 6/3/25: FCD:28/05/2025->12/12/2025; |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
944 | 940080 | Study on network energy savings for NR | FS_Netw_Energy_NR | 2 | Rel-18 | R1 | 2021-12-13 08:00 | 2022-12-01 17:00 | 100% | RP-230566 | RP-223002 | Yi Wang, Huawei | wangyi6@huawei.com | 21/1/22: 38.864 added;; 22/3/22: Stat Rep: ->RP-220296; 5/4/22: WID:RP-213554->RP-220297 ; 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com12/7/22: WID:RP-220297->RP-221443; 9/12/22: FCD:22/12/2022->... | 38.864 | 94 | 48 |  |  | Thu 06/01/22 | Wed 29/03/23
945 | 0 | Rel-18 Uncrewed Aerial Vehicles (UAV), UAS, UAM | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
946 | 990107 | Further Architecture Enhancement for UAV and UAM | UAS_Ph2 | 1 | Rel-18 |  | 2021-12-20 08:00 | 2024-03-03 17:00 | 100% | SP-221323 |  | Faccin, Stefano, Qualcomm Incorporated | sfaccin@qti.qualcomm.com | 10/1/23: FCD clarified to be June (and not March) by e-mail | 23.256 | 99 | 50 |  |  | Fri 09/12/22 | NA
947 | 940051 | Study on Phase 2 of UAS, UAV and UAM | FS_UAS_Ph2 | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-211632 |  | Stefano Faccin | sfaccin@qti.qualcomm.com | ; 21/1/22: 23.700-58 added;; 12/3/22: 0%->20; 4/6/22: 20%->50; 4/6/22: FCD:10/06/2022->09/22; 12/9/22: 50%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->98; 15/3/23: 98%->100 | 23.256 ; 23.700-58 | 94 | 48 |  |  | Sun 19/12/21 | Wed 15/03/23
948 | 980012 | (Stage 2 of UAS Ph2) Further Architecture Enhancement for UAV and UAM | UAS_Ph2 | 2 | Rel-18 | S2 | 2022-12-09 08:00 | 2023-06-06 17:00 | 100% | SP-230091 |  | Faccin, Stefano, Qualcomm Incorporated | sfaccin@qti.qualcomm.com | 10/1/23: FCD clarified to be June (and not March) by e-mail ; 15/3/23: 0%->85; 15/3/23: WID:SP-221323->SP-230091; 8/6/23: 85%->100 | 23.256 | 98 | 50 |  |  | Fri 09/12/22 | Thu 08/06/23
949 | 960034 | Study on Security of Phase 2 for UAS, UAV and UAM | FS_UAS_Ph2_SEC | 2 | Rel-18 | S3 | 2022-06-02 08:00 | 2023-03-03 17:00 | 100% | SP-220532 |  | Escott, Adrian, Qualcomm Incorporated, | aescott@qti.qualcomm.com | 13/7/22: 33.891 added;; 11/12/22: 0%->65; 17/3/23: 65%->100 | 33.891 | 96 | 49 |  |  | Thu 02/06/22 | Fri 17/03/23
950 | 990036 | Security of UAV and UAM Phase 2 | UAS_Ph2 | 2 | Rel-18 | S3 | 2023-03-16 08:00 | 2023-09-09 17:00 | 100% | SP-230149 |  | Escott, Adrian, Qualcomm Incorporated | aescott@qti.qualcomm.com | ; 8/6/23: 0%->60; 7/9/23: 60%->100 | 33.256 | 99 | 50 |  |  | Thu 16/03/23 | Thu 07/09/23
951 | 990012 | CT1 aspects of UAS Ph2 | UAS_Ph2 | 2 | Rel-18 | C1 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-230330 |  | Kim, Sunghoon, Qualcomm Incorporated | sunghoon@qti.qualcomm.com | 31/3/23: 24.578 added;; 31/3/23: 24.577 added;6/6/23: Compl:0%->50% | 24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102; 24.578; 24.577 | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
952 | 990063 | CT3 aspects of UAS Ph2 | UAS_Ph2 | 2 | Rel-18 | C3 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-230330 |  | Kim, Sunghoon, Qualcomm Incorporated | sunghoon@qti.qualcomm.com | 9/6/23: 0%->30 | 24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102 | 99 | 50 |  |  | Fri 09/12/22 | Fri 09/06/23
953 | 990064 | CT4 aspects of UAS Ph2 | UAS_Ph2 | 2 | Rel-18 | C4 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-230330 |  | Kim, Sunghoon, Qualcomm Incorporated | sunghoon@qti.qualcomm.com | 6/6/23: Compl:0%->10% | 24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102 | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
954 | 990105 | CT6 aspects of UAS Ph2 | UAS_Ph2 | 2 | Rel-18 | C6 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-230330 |  | Kim, Sunghoon, Qualcomm Incorporated | sunghoon@qti.qualcomm.com |  | 24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102 | 99 | 50 |  |  | Fri 09/12/22 | NA
955 | 930012 | Study on enhanced architecture for UAS Applications | FS_eUASAPP | 1 | Rel-18 | S6 | 2021-09-13 08:00 | 2022-12-12 17:00 | 100% | SP-220465 |  | Monrad, Atle, InterDigital | atle.monrad@interdigital.com | 13/12/21: 0%->10; 13/12/21: WID:SP-210954->SP-211511; 13/12/21: FCD:Fri 10/06/->09/22; 12/3/22: 10%->30; 12/3/22: WID:SP-211511->SP-22009; 22/3/22: 23.700-55 added;; 4/6/22: 30%->50; 4/6/22: WID:SP-22009->SP-220465; 12/9/22: 50%->80; 12/9/22: FCD:12/09... | 23.700-55 | 93 | 47 |  |  | Mon 13/09/21 | Sun 11/12/22
956 | 980126 | Architecture for UAS Applications, Phase 2 | UASAPP_Ph2 | 1 | Rel-18 |  | 2022-09-09 08:00 | 2023-12-12 17:00 | 100% | SP-220915 |  | Monrad, Atle, InterDigital | atle.monrad@interdigital.com |  | 23.255 | 97 | 49 |  |  | Sun 11/09/22 | NA
957 | 970038 | Stage 2 of UASAPP_Ph2 | UASAPP_Ph2 | 2 | Rel-18 | S6 | 2022-09-09 08:00 | 2023-06-06 17:00 | 100% | SP-221228 |  | Monrad, Atle, InterDigital | atle.monrad@interdigital.com | ; 11/12/22: 0%->25; 9/1/23: WID:SP-220915->SP-221228; 17/3/23: 25%->65; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 65%->100 | 23.255 | 97 | 49 |  |  | Sun 11/12/22 | Thu 08/06/23
958 | 980055 | CT1 aspects of UASAPP_Ph2 | UASAPP_Ph2 | 2 | Rel-18 | C1 | 2022-12-16 08:00 | 2023-12-12 17:00 | 100% | CP-240273 |  | Taimoor Abbas, InterDigital | taimoor.abbas@interdigital.com | 6/6/23: Compl:5%->60% | 27.007; 24.257; 29.257 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
959 | 980056 | CT3 aspects of UASAPP_Ph2 | UASAPP_Ph2 | 2 | Rel-18 | C3 | 2022-12-16 08:00 | 2023-12-12 17:00 | 100% | CP-240273 |  | Taimoor Abbas, InterDigital | taimoor.abbas@interdigital.com | ; 9/6/23: 0%->40 | 27.007; 24.257; 29.257 | 97 | 49 |  |  | Sun 11/09/22 | Fri 09/06/23
960 | 941005 | NR support for UAV (Uncrewed Aerial Vehicles) | NR_UAV | 1 | Rel-18 | R2 | 2021-12-13 08:00 | 2026-03-03 17:00 | 76% | RP-233386 |  | Nokia |  | no Perf. part; no RAN1 spec affected so far; 9/1/23: WID:RP-213600->RP-223545; 29/3/23: WID:RP-223545->RP-230782; 2/1/24: WID:RP-230782->RP-233386 |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 02/01/24
961 | 941105 | Core part: NR support for UAV (Uncrewed Aerial Vehicles) | NR_UAV-Core | 2 | Rel-18 | R2 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-233386 | RP-233385 | Jedrzej Stanczak, Nokia, Nokia Shanghai Bell | jedrzej.stanczak@nokia.com | no Perf. part; no RAN1 spec affected so far; 20/6/22: FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221498; Rapporteur: Nokia->Jedrzej Stanczak, Nokia, Nokia Shanghai Bell; Rap eMail: ->jedrzej.stanczak@nokia.com13/7/22: FCD:23/12/2022->12/20...; 17/3/23:... |  | 94 | 48 |  |  | Thu 06/01/22 | Fri 08/12/23
962 | 1070060 | UE Conformance - NR Support for UAV (Uncrewed Aerial Vehicles) plus CT1 aspects | NR_UAV_plus_CT1-UEConTest | 2 | Rel-18 | R5 | 2025-03-03 08:00 | 2026-03-03 17:00 | 42% | RP-250062 | RP-251977 | China Unicom |  | 6/6/25: Compl:0%->28%; Stat Rep: ->RP-251507; ; 11/9/25: Compl:28%->42%; Stat Rep: RP-251507->RP-251977; |  | 107 | 54 |  |  | Wed 26/03/25 | Thu 11/09/25
963 | 991035 | Enhanced LTE Support for UAV (Uncrewed Aerial Vehicles) | LTE_UAV_enh | 1 | Rel-18 | R2 | 2023-03-03 08:00 | 2023-12-12 17:00 | 100% | RP-233389 |  | Nokia |  | 2/1/24: WID:RP-230783->RP-233389 |  | 99 | 50 |  |  | Wed 29/03/23 | Tue 02/01/24
964 | 991135 | Core part: Enhanced LTE Support for UAV (Uncrewed Aerial Vehicles) | LTE_UAV_enh-Core | 2 | Rel-18 | R2 | 2023-03-03 08:00 | 2023-12-12 17:00 | 100% | RP-233389 | RP-233388 | Jedrzej Stanczak, Nokia, Nokia Shanghai Bell | jedrzej.stanczak@nokia.com | ; 7/6/23: Compl:0%->60%; 6/9/23: Compl:60%->80%; Stat Rep: ->RP-231865; Rapporteur: Nokia->Jedrzej Stanczak, Nokia, Nokia Shanghai Bell; Rap eMail: ->jedrzej.stanczak@nokia.com; ; 8/12/23: Compl:80%->100%; Stat Rep: RP-231865->RP-233388; |  | 99 | 50 |  |  | Wed 29/03/23 | Fri 08/12/23
965 | 0 | Rel-18 Sidelink, Proximity, Location and Positioning | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
966 | 910040 | Ranging-based Service and sidelink positioning | Ranging | 1 | Rel-18 |  | 2020-06-25 08:00 | 2024-03-03 17:00 | 100% | SP-210212 |  | Xiaowei jiang, Xiaomi | jiangxiaowei@xiaomi.com |  | 22.261 | 91 | 46 |  |  | Thu 18/03/21 | NA
967 | 880039 | Study on Ranging | FS_Ranging | 2 | Rel-18 | S1 | 2020-06-25 08:00 | 2021-06-11 17:00 | 100% | SP-200575 |  | Xiaowei jiang | jiangxiaowei@xiaomi.com | 28/7/20: 22.855 added;; 12/9/20: 0%->40; 5/12/20: 40%->80; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 80%->85; 11/6/21: 85%->100 | 22.855 | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
968 | 910034 | Stage 1 for Ranging | Ranging | 2 | Rel-18 | S1 | 2021-03-18 08:00 | 2021-06-11 17:00 | 100% | SP-210212 |  | Xiaowei jiang, Xiaomi | jiangxiaowei@xiaomi.com | ; 11/6/21: 0%->100 | 22.261 | 91 | 46 |  |  | Thu 18/03/21 | Fri 11/06/21
969 | 940069 | Study on Ranging based services and sidelink positioning | FS_Ranging_SL | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-211647 |  | Shen, Sherry (Yang), Xiaomi, | shenyang6@xiaomi.com | 21/1/22: 23.700-86 added;; 12/3/22: 0%->15; 4/6/22: 15%->60; 12/9/22: 60%->70; 10/12/22: 70%->85; 15/3/23: 85%->100 | 23.700-86 | 94 | 48 |  |  | Sun 19/12/21 | Wed 15/03/23
970 | 980015 | Stage 2 of Ranging_SL | Ranging_SL | 2 | Rel-18 | S2 | 2022-12-09 08:00 | 2023-06-06 17:00 | 100% | SP-230106 |  | Shen, Sherry (Yang), Xiaomi | shenyang6@xiaomi.com | "Architecture Enhancement to support Ranging based services and Sidelink Positioning" ; 15/3/23: 0%->50; 15/3/23: WID:SP-221325->SP-230106; 17/3/23: 23.586 added;; 8/6/23: 50%->100 | 23.304; 23.287; 23.273; 23.502; 23.503 ; 23.586 | 98 | 50 |  |  | Fri 09/12/22 | Thu 08/06/23
971 | 960036 | Study on Security Aspects of Ranging Based Services and Sidelink Positioning | FS_Ranging_SL_Sec | 2 | Rel-18 | S3 | 2022-06-02 08:00 | 2023-03-03 17:00 | 100% | SP-220534 |  | Wei Lu, Xiaomi, | luwei10@xiaomi.com | 13/7/22: 33.893 added;; 12/9/22: 0%->20; 11/12/22: 20%->40; 17/3/23: 40%->70; 8/6/23: 70%->100 | 33.893 | 96 | 49 |  |  | Thu 02/06/22 | Thu 08/06/23
972 | 990046 | Security Aspects of Ranging_SL | Ranging_SL_Sec | 2 | Rel-18 | S3 | 2023-03-16 08:00 | 2023-09-09 17:00 | 100% | SP-230769 |  | Lu, Wei, Xiaomi | luwei10@xiaomi.com | 31/3/23: 33.533 added;; 8/6/23: 0%->40; 30/6/23: WID:SP-230159->SP-230769; 7/9/23: 40%->100 | 33.533 | 99 | 50 |  |  | Thu 16/03/23 | Thu 07/09/23
973 | 990014 | CT1 aspects of Ranging_SL | Ranging_SL | 2 | Rel-18 | C1 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240298 |  | Tingfang Tang, Xiaomi | tangtingfang@xiaomi.com | ; 31/3/23: 24.514 added;6/6/23: Compl:0%->15% | 24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572; 24.514 | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
974 | 990066 | CT3 aspects of Ranging_SL | Ranging_SL | 2 | Rel-18 | C3 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240298 |  | Tingfang Tang, Xiaomi | tangtingfang@xiaomi.com | ; 16/7/24: 99%->100 | 24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572 | 99 | 50 |  |  | Fri 09/12/22 | Tue 16/07/24
975 | 990067 | CT4 aspects of Ranging_SL | Ranging_SL | 2 | Rel-18 | C4 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240298 |  | Tingfang Tang, Xiaomi | tangtingfang@xiaomi.com | 6/6/23: Compl:0%->30%; 4/1/24: 29.586 added; | 24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572; 29.586 | 99 | 50 |  |  | Fri 09/12/22 | Thu 04/01/24
976 | 1000009 | Charging Aspects of Ranging and Sidelink Positioning | FS_Ranging_SL_CH | 2 | Rel-18 | S5 | 2023-06-08 08:00 | 2024-03-03 17:00 | 100% | SP-230622 |  | Zhiwei Mo, China Telecom, | mozw<at>chinatelecom<dot>cn | 30/6/23: 28.845 added;; 7/9/23: 0%->15; 8/12/23: 15%->70; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 70%->100 | 28.845 | 100 | 51 |  |  | Thu 08/06/23 | Thu 14/03/24
977 | 980111 | 5GC LoCation Services - Phase 3 | 5G_eLCS_Ph3 | 1 | Rel-18 |  | 2022-09-30 08:00 | 2024-03-03 17:00 | 100% | SP-220811 |  | Ming Ai, CATT | aiming@catt.cn |  | 23.273 | 97 | 49 |  |  | Sun 11/09/22 | NA
978 | 940058 | Study on Enhancement to the 5GC LoCation Services-Phase 3 | FS_eLCS_Ph3 | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-220069 |  | Ming Ai, CATT | aiming@catt.cn, Primary Rapporteur. | 21/1/22: 23.700-71 added;; 12/3/22: 0%->15; 12/3/22: WID:SP-211637->SP-220069; 4/6/22: 15%->55; 4/6/22: FCD:12/09/2022->12/22; 12/9/22: 55%->80; 10/12/22: 80%->100 | 23.700-71 | 94 | 48 |  |  | Sun 19/12/21 | Sat 10/12/22
979 | 970021 | (stage 2 of) 5GC LoCation Services - Phase 3 | 5G_eLCS_Ph3 | 2 | Rel-18 | S2 | 2022-09-30 08:00 | 2023-06-06 17:00 | 100% | SP-230093 |  | Ming Ai, CATT | aiming@catt.cn | ; 10/12/22: WID:SP-220811->SP-221123; 10/12/22: 0%->30; 10/12/22: 0%->30; 9/1/23: WID:SP-221123->SP-221338; 15/3/23: 30%->65; 15/3/23: WID:SP-221338->SP-230093; 15/3/23: FCD:03/03/2023->06/20; 8/6/23: 65%->100 | 23.273 | 97 | 49 |  |  | Sun 11/09/22 | Thu 08/06/23
980 | 980057 | CT1 aspects of 5G_eLCS_Ph3 | 5G_eLCS_Ph3 | 2 | Rel-18 | C1 | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-240233 |  | Wang, Baixiao, CATT | wangbaixiao@cictmobile.com | 6/6/23: Compl:5%->15% | 23.273 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
981 | 980058 | CT3 aspects of 5G_eLCS_Ph3 | 5G_eLCS_Ph3 | 2 | Rel-18 | C3 | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-240233 |  | Wang, Baixiao, CATT | wangbaixiao@cictmobile.com | ; 9/6/23: 20%->30 | 23.273 | 97 | 49 |  |  | Sun 11/09/22 | Fri 09/06/23
982 | 980059 | CT4 aspects of 5G_eLCS_Ph3 | 5G_eLCS_Ph3 | 2 | Rel-18 | C4 | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-240233 |  | Wang, Baixiao, CATT | wangbaixiao@cictmobile.com | ; 9/6/23: 25%->65 | 23.273 | 97 | 49 |  |  | Sun 11/09/22 | Fri 09/06/23
983 | 1070019 | Charging aspects of 5GC LoCation Services | CH_5G_eLCS_Ph3 | 1 | Rel-19 | S5 | 2025-03-26 08:00 | 2025-06-06 17:00 | 100% | SP-250370 |  | Zhiwei Mo, China Telecom | mozw@chinatelecom.cn | ; 6/6/25: 0%->100; 12/9/25: FCD:Tue 09/09/->/25 | 32.271; 32.290; 32.291; 32.298 | 107 | 54 |  |  | Wed 05/03/25 | Fri 12/09/25
984 | 981038 | Expanded and improved NR positioning | NR_pos_enh2 | 1 | Rel-18 |  | 2022-12-13 08:00 | 2026-06-06 17:00 | 72% | RP-241186 |  | Intel |  | 29/3/23: WID:RP-223549->RP-230328; 6/10/23: WID:RP-230328->RP-232670; 2/1/24: WID:RP-232670->RP-233382; 2/4/24: WID:RP-233382->RP-240778; 23/7/24: WID:RP-240778->RP-241186 |  | 98 | 50 |  |  | Mon 09/01/23 | Tue 23/07/24
985 | 981138 | Core part: Expanded and improved NR positioning | NR_pos_enh2-Core | 2 | Rel-18 | R1 | 2022-12-13 08:00 | 2025-03-03 17:00 | 100% | RP-241186 | RP-241919 | Debdeep Chatterjee | debdeep.chatterjee@intel.com | 17/3/23: Compl:0%->15%; Stat Rep: ->RP-230327; Rapporteur: Intel->Debdeep Chatterjee, Intel Corporation; Rap eMail: ->debdeep.chatterjee@intel.com; 17/3/23: 38.355 added;; ;...; 6/9/23: Compl:50%->70%; WID: RP-230328->RP-231460; Stat Rep: RP-230327->R... | 38.355 | 98 | 50 |  |  | Mon 09/01/23 | Wed 04/09/24
986 | 981238 | Perf. part: Expanded and improved NR positioning | NR_pos_enh2-Perf | 2 | Rel-18 | R4 | 2022-12-15 08:00 | 2024-05-04 11:00 | 99% | RP-241186 | RP-242766 | Debdeep Chatterjee | debdeep.chatterjee@intel.com | Study in Rel-17 UID820025; 13/12/21: 0%->15; 12/3/22: 15%->30; 22/3/22: 23.545 added;; 4/6/22: 30%->50; 12/9/22: 50%->55; 11/12/22: 55%->65; 11/12/22: FCD:09/12/2022->/23; 9/1/23: WID:SP-210957->SP-221233; 17/3/23: 65%->75; 8/6/23: 75%->100; 30/6/23: ... |  | 98 | 50 |  |  | Mon 09/01/23 | Fri 06/12/24
987 | 1040107 | UE Conformance - Expanded and improved NR positioning | NR_pos_enh2-UEConTest | 2 | Rel-18 | R5 | 2024-06-06 08:00 | 2026-06-06 17:00 | 16% | RP-252718 | RP-252717 | CATT |  | 4/9/24: FCD:06/06/2026->26/06/2025; Compl:0%->5%; Stat Rep: ->RP-242124; ; 26/9/24: WID:RP-241342->RP-242125; 6/12/24: FCD:06/06/2025->05/06/2026; Compl:5%->6%; WID: RP-242125->RP-241342; Stat Rep: RP-242124->RP-243121; ; 6/3/25: FCD:23/10/2025->05/06/20 |  | 104 | 53 |  |  | Tue 23/07/24 | Mon 29/09/25
988 | 940081 | Study on expanded and improved NR positioning | FS_NR_pos_enh2 | 2 | Rel-18 | R1 | 2022-12-13 08:00 | 2024-06-05 17:00 | 100% | RP-222616 | RP-222982 | Debdeep Chatterjee, Intel Corporation | debdeep.chatterjee@intel.com | compare REL-17 SI FS_NR_pos; TR 38.8xx; 21/1/22: 38.859 added; ; 6/6/22: Compl:0%->12% 20/6/22: Rapporteur: Intel->Alexey Khoryaev, Intel Corporation; Rap eMail: ->alexey.khoryaev@intel.com12/7/22: WID:RP-213588->RP-221814 ;...; 23/9/22: WID:RP-213588... | 38.859 | 94 | 48 |  |  | Thu 06/01/22 | Mon 09/01/23
989 | 940097 | NR sidelink evolution | NR_SL_enh2 | 1 | Rel-18 |  | 2021-12-13 08:00 | 2024-06-06 17:00 | 100% | RP-232789 |  | OPPO |  | TR 38.8xx; compare REL-17 WI NR_SL_enh; 5/4/22: WID:RP-213678->RP-220300; 12/7/22: WID:RP-220300->RP-221798; 23/9/22: WID:RP-221798->RP-221938; 9/1/23: WID:RP-221938->RP-222806; 29/3/23: WID:RP-222806->RP-230077; 2/1/24: WID:RP-230077->RP-232789 |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 02/01/24
990 | 940197 | Core part: NR sidelink evolution | NR_SL_enh2-Core | 2 | Rel-18 | R1 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-232789 | RP-232786 | Kevin Lin, OPPO | Kevin.Lin@oppo.com | TR 38.8xx; compare REL-17 WI NR_SL_enh; 22/3/22: Stat Rep: ->RP-220320 6/6/22: Compl:0%->7% ; ; 20/6/22: Rapporteur: OPPO->Kevin Lin, OPPO; Rap eMail: ->Kevin.Lin@oppo.com13/7/22: FCD:23/12/2022->12/20 ; ...; 9/12/22: FCD:23/12/2022->01/12/2023; Comp... | 38.786 | 94 | 48 |  |  | Thu 06/01/22 | Fri 08/12/23
991 | 940297 | Perf. part: NR sidelink evolution | NR_SL_enh2-Perf | 2 | Rel-18 | R1 | 2021-12-15 08:00 | 2024-06-06 17:00 | 100% | RP-232789 | RP-240928 | Kevin Lin, OPPO | Kevin.Lin@oppo.com | ; 22/3/22: CD:12/09/2023->12/06/2024; 22/3/22: Stat Rep: ->RP-220320 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: ; 20/6/22: WG: R4->R1; Rapporteur: OPPO->Kevin Lin, OPPO; Rap eMail: ->Kevin.Lin@oppo.com13/7/22: FCD:24/06/2022->06/20 ; ...; 9/12/22: FCD... |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 23/07/24
992 | 941002 | NR sidelink relay enhancements | NR_SL_relay_enh | 1 | Rel-18 |  | 2021-12-13 08:00 | 2024-12-12 17:00 | 97% | RP-232972 |  | LG Electronics |  | compare REL-17 WI NR_SL_relay; 6/1/22: WID:RP-213585->RP-212819; 5/4/22: WID:RP-212819->RP-221010; 12/7/22: WID:RP-221010->RP-221262; 9/1/23: WID:RP-221262->RP-223501; 2/1/24: WID:RP-223501->RP-232972 |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 02/01/24
993 | 941102 | Core part: NR sidelink relay enhancements | NR_SL_relay_enh-Core | 2 | Rel-18 | R2 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-232972 | RP-232971 | Youngdae LEE, LG Electronics Inc. | youngdae.lee@lge.com | compare REL-17 WI NR_SL_relay; 22/3/22: WID: RP-212819->RP-213585; 22/3/22: Stat Rep: ->RP-220524 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 20/6/22: Rapporteur: LG Electronics->Youngdae LEE, LG Electronics; Rap eMail: ->youngdae.lee@lge.com13/7/22: ...;... |  | 94 | 48 |  |  | Thu 06/01/22 | Fri 08/12/23
994 | 941202 | Perf. part: NR sidelink relay enhancements | NR_SL_relay_enh-Perf | 2 | Rel-18 | R2 | 2021-12-15 08:00 | 2024-06-06 17:00 | 100% | RP-223501 | RP-241088 | Youngdae LEE, LG Electronics Inc. | youngdae.lee@lge.com | ; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: WID: RP-212819->RP-213585; 22/3/22: Stat Rep: ->RP-220524 6/6/22: CD:12/06/2024->24/06/2022 20/6/22: WG: R4->R2; FCD:24/06/2022->22/06/2022; Rapporteur: LG Electronics->Youngdae LEE, LG Electronics;...;... |  | 94 | 48 |  |  | Thu 06/01/22 | Thu 13/06/24
995 | 960083 | UE Conformance - NR Sidelink Relay | NR_SL_relay-UEConTest | 2 | Rel-17 | R5 | 2022-06-15 08:00 | 2025-12-12 17:00 | 95% | RP-252721 | RP-252722 | Xiaozhong CHEN, CATT | chenxiaozhong@catt.cn | 9/9/22: Comp...; 23/9/22: WID:RP-221447->RP-222378; 9/12/22: FCD:23/09/2022->01/09/2023; WID: RP-222378->RP-221447; Stat Rep: ->RP-223141; Rapporteur: CATT->Xiaozhong CHEN, CATT; Rap eMail: ->chenxiaozhong@catt.cn; 17/3/23: FCD:09/09/2023..... |  | 96 | 49 |  |  | Tue 12/07/22 | Mon 29/09/25
996 | 941000 | Mobile Terminated-Small Data Transmission (MT-SDT) for NR | NR_MT_SDT | 1 | Rel-18 |  | 2021-12-13 08:00 | 2024-12-12 17:00 | 97% | RP-234010 |  | ZTE |  | no Perf. part; 9/1/23: WID:RP-213583->RP-222993; 2/1/24: WID:RP-222993->RP-234010 |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 02/01/24
997 | 941100 | Core part: Mobile Terminated-Small Data Transmission (MT-SDT) for NR | NR_MT_SDT-Core | 2 | Rel-18 | R2 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-234010 | RP-232887 | Eswar Vutukuri, ZTE Corporation | eswar.vutukuri@zte.com.cn | no Perf. part ; 6/6/22: CD:12/09/2023->23/09/2022 6/6/22: Stat Rep: RP-220215->RP-221310; 20/6/22: Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->eswar.vutukuri@zte.com.cn13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/2022->01... |  | 94 | 48 |  |  | Thu 06/01/22 | Fri 08/12/23
998 | 1040103 | UE Conformance - Mobile Terminated-Small Data Transmission (MT-SDT) for NR | NR_MT_SDT-UEConTest | 2 | Rel-18 | R5 | 2024-06-06 08:00 | 2025-12-12 17:00 | 95% | RP-241127 | RP-251961 | Qualcomm |  | 4/9/24: FCD:12/12/2025->25/12/2024; Compl:0%->10%; Stat Rep: ->RP-241914; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:10%->40%; Stat Rep: RP-241914->RP-242496; ; 6/3/25: FCD:24/06/2025->12/12/2025; Compl:40%->65%; Stat Rep: RP-242496->RP-250111; ; 6/6/2 |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 11/09/25
999 | 950048 | Study on Proximity based Services Phase 2 | FS_5G_ProSe_Ph2 | 1 | Rel-18 | S2 | 2021-12-20 08:00 | 2023-03-10 17:00 | 100% | SP-211653 |  | Deng, Qiang, CATT | dengqiang1@catt.cn, Primary Rapporteur. | 21/1/22: 23.700-33 added;; 12/3/22: 0%->20; 14/3/24: 95%->100 | 23.700-33 | 95 | 48 |  |  | Sun 19/12/21 | Thu 14/03/24
1000 | 940077 | Study on Stage 2 for Proximity based Services Phase 2 | FS_5G_ProSe_Ph2 | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-211653 |  | Deng, Qiang, CATT | dengqiang1@catt.cn, Primary Rapporteur. | 21/1/22: 23.700-33 added;; 12/3/22: 0%->20; 4/6/22: 20%->55; 12/9/22: 55%->75; 10/12/22: 75%->100 | 23.700-33 | 94 | 48 |  |  | Sun 19/12/21 | Sat 10/12/22
1001 | 950024 | Study on Security Aspects of Proximity Based Services Phase 2 | FS_5G_ProSe_Ph2 | 2 | Rel-18 | S3 | 2022-03-10 08:00 | 2023-03-10 17:00 | 100% | SP-220202 |  | Wei Zhou, CATT | zhouwei@catt.cn | 4/6/22: 0%->5; 13/7/22: 33.740 added;; 13/7/22: 33.741 added;; 12/9/22: 5%->40; 11/12/22: 40%->75; 17/3/23: 75%->80; 8/6/23: 80%->90 | 33.740; 33.741 | 95 | 48 |  |  | Thu 10/03/22 | Thu 08/06/23
1002 | 980112 | Proximity-based Services in 5GS Phase 2 | 5G_ProSe_Ph2 | 1 | Rel-18 |  | 2022-09-27 08:00 | 2023-12-12 17:00 | 100% | SP-220806 |  | Deng Qiang, CATT | dengqiang1@catt.cn |  | 23.304; 23.501; 23.502; 23.503 | 97 | 49 |  |  | Wed 19/10/22 | NA
1003 | 970016 | (stage 2 of) Proximity-based Services in 5GS Phase 2 | 5G_ProSe_Ph2 | 2 | Rel-18 | S2 | 2022-09-27 08:00 | 2023-06-06 17:00 | 100% | SP-230097 |  | Deng Qiang, CATT | dengqiang1@catt.cn | ; 9/1/23: WID:SP-220806->SP-221206; 15/3/23: WID:SP-221206->SP-230097; 15/3/23: 0%->80; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 80%->100 | 23.304; 23.501; 23.502; 23.503 | 97 | 49 |  |  | Wed 19/10/22 | Thu 08/06/23
1004 | 980060 | CT1 aspects of 5G_ProSe_Ph2 | 5G_ProSe_Ph2 | 2 | Rel-18 | C1 | 2022-12-16 08:00 | 2023-12-12 17:00 | 100% | CP-233220 |  | Duan, Xiaoyan, CATT | duanxiaoyan@catt.cn | ; 9/6/23: 15%->70 | 24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102 | 97 | 49 |  |  | Wed 19/10/22 | Fri 09/06/23
1005 | 980061 | CT3 aspects of 5G_ProSe_Ph2 | 5G_ProSe_Ph2 | 2 | Rel-18 | C3 | 2022-12-16 08:00 | 2023-12-12 17:00 | 100% | CP-233220 |  | Duan, Xiaoyan, CATT | duanxiaoyan@catt.cn | ; 9/6/23: 0%->20 | 24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102 | 97 | 49 |  |  | Wed 19/10/22 | Fri 09/06/23
1006 | 980062 | CT4 aspects of 5G_ProSe_Ph2 | 5G_ProSe_Ph2 | 2 | Rel-18 | C4 | 2022-12-16 08:00 | 2023-12-12 17:00 | 100% | CP-233220 |  | Duan, Xiaoyan, CATT | duanxiaoyan@catt.cn | 6/6/23: Compl:0%->30% | 24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102 | 97 | 49 |  |  | Wed 19/10/22 | Tue 06/06/23
1007 | 980063 | CT6 aspects of 5G_ProSe_Ph2 | 5G_ProSe_Ph2 | 2 | Rel-18 | C6 | 2022-12-16 08:00 | 2023-12-12 17:00 | 100% | CP-233220 |  | Duan, Xiaoyan, CATT | duanxiaoyan@catt.cn |  | 24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102 | 97 | 49 |  |  | Wed 19/10/22 | NA
1008 | 990045 | Security Aspects of Proximity-based Services in 5GS Phase 2 | 5G_ProSe_Ph2 | 2 | Rel-18 | S3 | 2023-03-16 08:00 | 2023-09-09 17:00 | 100% | SP-230158 |  | Wei Zhou, CATT | zhouwei@catt.cn | ; 8/6/23: 0%->90; 8/12/23: 90%->95; 15/3/24: 95%->100 | 33.503 | 99 | 50 |  |  | Thu 16/03/23 | Fri 15/03/24
1009 | 990108 | 5G-enabled fused location service capability exposure | 5GFLS | 1 | Rel-18 |  | 2021-06-11 08:00 | 2024-03-03 17:00 | 100% | SP-221234 |  | Liping Wu, CATT | wuliping@cictmobile.com |  | 23.434 | 99 | 50 |  |  | Fri 09/12/22 | NA
1010 | 920015 | Study on 5G-enabled fused location service capability exposure | FS_5GFLS | 2 | Rel-18 | S6 | 2021-06-11 08:00 | 2022-09-12 17:00 | 100% | SP-220097 |  | Zhang, Ling, CATT | zhangling@catt.cn | 2/7/21: 23.700-96 added;; 13/9/21: 0%->20; 13/12/21: 20%->40; 13/12/21: WID:SP-210477->SP-211512; 13/12/21: FCD:Fri 11/03/->06/22; 12/3/22: FCD:10/06/2022->9/22; 12/3/22: WID:SP-211512->SP-220097; 4/6/22: 40%->55; 12/9/22: 55%->75; 11/12/22: 75%->100 | 23.700-96 | 92 | 47 |  |  | Fri 11/06/21 | Sun 11/12/22
1011 | 980109 | Stage 2 of 5GFLS | 5GFLS | 2 | Rel-18 | S6 | 2022-12-09 08:00 | 2023-06-06 17:00 | 100% | SP-221234 |  | Liping Wu, CATT | wuliping@cictmobile.com | ; 17/3/23: 0%->60; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100 | 23.434 | 98 | 50 |  |  | Fri 09/12/22 | Thu 08/06/23
1012 | 990016 | CT1 aspects of 5GFLS | 5GFLS | 2 | Rel-18 | C1 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-230195 |  | Zhao, Xiaoxue, CATT | zhaoxiaoxue@cictmobile.com | 6/6/23: Compl:0%->60% | 24.545; 29.549 | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
1013 | 990069 | CT3 aspects of 5GFLS | 5GFLS | 2 | Rel-18 | C3 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-230195 |  | Zhao, Xiaoxue, CATT | zhaoxiaoxue@cictmobile.com | ; 9/6/23: 0%->70 | 24.545; 29.549 | 99 | 50 |  |  | Fri 09/12/22 | Fri 09/06/23
1014 | 0 | See also MCOver5GProSe under Mission Critical and LPHP under Verticals | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1015 | 0 | Rel-18 Verticals, Industries, Factories, Northbound API | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1016 | 930023 | Service exposure interfaces for industry | EXPOSE | 1 | Rel-18 | S1 | 2021-09-10 08:00 | 2021-09-20 17:00 | 100% | SP-211056 |  | Joachim W. Walewski | joachim.walewski@siemens.com | ; 13/12/21: 0%->100 | 22.261 | 93 | 47 |  |  | Fri 10/09/21 | Mon 13/12/21
1017 | 1010009 | Guidelines for CAPIF Usage | CAPIF_EXT | 1 | Rel-18 | S6 | 2023-09-07 08:00 | 2024-09-09 17:00 | 100% | SP-241692 |  | Junpei Uoshima, NTT DOCOMO | junpei.uoshima.mt@nttdocomo.com | 8/12/23: 0%->20; 4/1/24: 23.946 added;; 14/3/24: 20%->55; 13/6/24: 55%->80; 4/9/24: 80%->90; 5/12/24: 90%->100; 8/1/25: WID:SP-231161->SP-241692 (change Rel-19->Rel-18) | 23.946 | 101 | 51 |  |  | Thu 07/09/23 | Wed 08/01/25
1018 | 990109 | Generic group management, exposure and communication enhancements | GMEC | 1 | Rel-18 |  | 2021-12-20 08:00 | 2024-03-03 17:00 | 100% | SP-221339 |  | Qianghua Zhu, Huawei | zhuqianghua@huawei.com | ; 10/12/22: 0%->30; 9/1/23: WID:SP-220989->SP-221339 | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Fri 23/09/22 | Mon 09/01/23
1019 | 940061 | Study on generic group management, exposure and communication enhancements | FS_GMEC | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-211603 |  | Qianghua Zhu, Huawei | zhuqianghua@huawei.com | 21/1/22: 23.700-74 added;; 12/3/22: 0%->25; 4/6/22: 25%->70; 12/9/22: 70%->90; 10/12/22: 90%->95; 10/12/22: FCD:12/09/2022->12/22; 15/3/23: 95%->100 | 23.700-74 | 94 | 48 |  |  | Sun 19/12/21 | Wed 15/03/23
1020 | 970069 | Stage 2 of GMEC | GMEC | 2 | Rel-18 | S2 | 2022-09-23 08:00 | 2023-03-03 17:00 | 100% | SP-230101 |  | Qianghua Zhu, Huawei | zhuqianghua@huawei.com | ; 10/12/22: 0%->30; 9/1/23: WID:SP-220989->SP-221339; 15/3/23: WID:SP-221339->SP-230101; 15/3/23: 30%->70; 8/6/23: 70%->100 | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Fri 23/09/22 | Thu 08/06/23
1021 | 990009 | CT3 aspects of GMEC | GMEC | 2 | Rel-18 | C3 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240296 |  | El Moatamid, Abdessamad, Huawei | abdessamad.el.moatamid@huawei.com | 6/6/23: Compl:15%->40%6/6/23: WID: CP-230118->CP-231194 | 29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526 | 97 | 49 |  |  | Fri 23/09/22 | Tue 06/06/23
1022 | 990071 | CT4 aspects of GMEC | GMEC | 2 | Rel-18 | C4 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240296 |  | El Moatamid, Abdessamad, Huawei | abdessamad.el.moatamid@huawei.com | 6/6/23: Compl:5%->40%6/6/23: WID: CP-230118->CP-231194 | 29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526 | 97 | 49 |  |  | Fri 23/09/22 | Tue 06/06/23
1023 | 990072 | CT1 aspects of GMEC | GMEC | 2 | Rel-18 | C1 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240296 |  | El Moatamid, Abdessamad, Huawei | abdessamad.el.moatamid@huawei.com | 6/6/23: Compl:0%->75%6/6/23: WID: CP-230118->CP-231194 | 29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526 | 97 | 49 |  |  | Fri 23/09/22 | Tue 06/06/23
1024 | 930015 | Application layer support for Factories of the Future (FF) | FFAPP | 1 | Rel-18 | S6 | 2021-09-10 08:00 | 2023-03-03 17:00 | 100% | SP-230751 |  | Shao Weixiang, ZTE Corporation | shao.weixiang@zte.com.cn |  | 23.434 ; 23.545 | 93 | 47 |  |  | Fri 10/09/21 | Fri 30/06/23
1025 | 980131 | Service Enabler Architecture Layer for Verticals Phase 3 | SEAL_Ph3 | 1 | Rel-18 |  | 2021-12-10 08:00 | 2023-09-09 17:00 | 100% | SP-211518 |  | Basavaraj (Basu) Pattan, Samsung | basavarajjp@samsung.com |  | 23.434 | 94 | 48 |  |  | Fri 10/12/21 | Mon 12/09/22
1026 | 940024 | Stage 2 of SEAL_Ph3 | SEAL_Ph3 | 2 | Rel-18 | S6 | 2021-12-12 08:00 | 2023-06-06 17:00 | 100% | SP-230276 |  | Basavaraj (Basu) Pattan, Samsung | basavarajjp@samsung.com | ; 12/3/22: 0%->5; 4/6/22: 5%->20; 12/9/22: 20%->35; 11/12/22: 35%->60. Acronym: eSEAL_Ph2->SEAL_Ph3; 11/12/22: FCD:12/12/2022->/23; 17/3/23: WID:SP-211518->SP-230276; 17/3/23: FCD:03/03/2023->6/6//23; change rapport (was Basavaraj (Basu) Pattan, Samsu... | 23.434 | 94 | 48 |  |  | Sun 11/12/22 | Thu 08/06/23
1027 | 980064 | CT1 aspects of SEAL_Ph3 | SEAL_Ph3 | 2 | Rel-18 | C1 | 2021-12-12 08:00 | 2022-12-12 17:00 | 100% | CP-233219 |  | Vijay Sangameshwara (Samsung Electronics) | s.vijay@samsung.com | 6/6/23: Compl:10%->45% | 24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 29.549 | 94 | 48 |  |  | Fri 10/12/21 | Tue 06/06/23
1028 | 980065 | CT3 aspects of SEAL_Ph3 | SEAL_Ph3 | 2 | Rel-18 | C3 | 2021-12-10 08:00 | 2022-12-09 17:00 | 100% | CP-233219 |  | Vijay Sangameshwara (Samsung Electronics) | s.vijay@samsung.com | 9/6/23: 15%->45 | 24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 29.549 | 94 | 48 |  |  | Fri 10/12/21 | Fri 09/06/23
1029 | 990047 | Security aspects of SEAL_Ph3 | SEAL_Ph3 | 2 | Rel-18 | S3 | 2023-03-16 08:00 | 2023-09-09 17:00 | 100% | SP-230365 |  | Rajavelsamy Rajadurai, Samsung | rajvel@samsung.com | ; 8/6/23: 0%->80; 15/3/24: 80%->100 | 33.434 | 99 | 50 |  |  | Thu 16/03/23 | Fri 15/03/24
1030 | 980124 | SEAL data delivery enabler for vertical applications | SEALDD | 1 | Rel-18 |  | 2021-09-13 08:00 | 2024-03-03 17:00 | 100% | SP-220914 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | ; 23/9/22: 23.433 added; | 23.434 ; 23.433 | 97 | 49 |  |  | Sun 11/09/22 | Fri 23/09/22
1031 | 930013 | Study on SEAL data delivery enabler for vertical applications | FS_SEALDD | 2 | Rel-18 | S6 | 2021-09-13 08:00 | 2022-09-12 17:00 | 100% | SP-220467 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | 13/12/21: 0%->30; 12/3/22: 30%->45; 22/3/22: 23.700-34 added;; 4/6/22: 45%->60; 4/6/22: FCD:10/06/2022->09/22; 4/6/22: WID:SP-210955->SP-220467; 12/9/22: 60%->85; 11/12/22: 85%->100 | 23.700-34 | 93 | 47 |  |  | Mon 13/09/21 | Sun 11/12/22
1032 | 970037 | (Stage 2 of Seal DD) SEAL data delivery enabler for vertical applications | SEALDD | 2 | Rel-18 | S6 | 2022-09-09 08:00 | 2023-06-06 17:00 | 100% | SP-221232 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | ; 23/9/22: 23.433 added;; 11/12/22: 0%->60; 9/1/23: WID:SP-220914->SP-221232; 17/3/23: 60%->85; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 85%->100 | 23.434 ; 23.433; 23.558 | 97 | 49 |  |  | Sun 11/12/22 | Thu 08/06/23
1033 | 980066 | CT1 aspects of SEALDD | SEALDD | 2 | Rel-18 | C1 | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-240272 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 30/6/23: WID:CP-230338->CP-231284 | 24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 24.538; 29.549; 29.538; 29.558 | 97 | 49 |  |  | Sun 11/09/22 | Fri 30/06/23
1034 | 980067 | CT3 aspects of SEALDD | SEALDD | 2 | Rel-18 | C3 | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-240272 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 31/3/23: 29.548 added;; 9/6/23: 5%->25 | 24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 24.538; 29.549; 29.538; 29.558; 29.548 | 97 | 49 |  |  | Sun 11/09/22 | Fri 09/06/23
1035 | 1000006 | Security aspects of SEAL Data Delivery enabler | SEALDD | 2 | Rel-18 | S3 | 2023-06-08 08:00 | 2023-09-09 17:00 | 100% | SP-230560 |  | Ao Lei, Huawei, | leiao@huawei.com | ; 15/3/24: 0%->100 | 33.434 | 100 | 51 |  |  | Thu 08/06/23 | Fri 15/03/24
1036 | 910036 | Low Power High Accuracy Positioning for industrial IoT scenarios | LPHAP | 1 | Rel-18 | S1 | 2021-03-18 08:00 | 2021-06-11 17:00 | 100% | SP-210216 |  | Yuan Wang, Huawei | wangyuan5@huawei.com | ; 19/3/21: 0%->40; 11/6/21: 40%->100 | 22.104; 22.261 | 91 | 46 |  |  | Thu 18/03/21 | Fri 11/06/21
1037 | 890024 | Subscriber-aware Northbound API access | SNA | 1 | Rel-18 | S1 | 2020-09-01 08:00 | 2020-09-17 17:00 | 100% | SP-200797 |  | Minokuchi, Atsushi, NTT DOCOMO | minokuchi at nttdocomo dot com |  | 22.261 | 89 | 45 |  |  | Fri 11/09/20 | NA
1038 | 990117 | Application enablement aspects for subscriber-aware northbound API access | SNAAPP | 1 | Rel-18 |  | 2022-06-02 08:00 | 2023-09-09 17:00 | 100% | SP-220469 |  | Suzuki, Yuji, NTT DOCOMO | yuuji.suzuki.rm@nttdocomo.com | ; 11/12/22: 0%->55 | 23.222; 23.434 | 96 | 49 |  |  | Thu 02/06/22 | Sun 11/12/22
1039 | 960012 | Stage 2 of SNAAPP | SNAAPP | 2 | Rel-18 | S6 | 2022-06-02 08:00 | 2023-03-03 17:00 | 100% | SP-220469 |  | Suzuki, Yuji, NTT DOCOMO | yuuji.suzuki.rm@nttdocomo.com | ; 11/12/22: 0%->55; 17/3/23: 15%->90; 8/6/23: 90%->100 | 23.222; 23.434 | 96 | 49 |  |  | Thu 16/03/23 | Thu 08/06/23
1040 | 960028 | Study on SNAAPP securitY | FS_SNAAPPY | 2 | Rel-18 | S3 | 2022-06-02 08:00 | 2022-12-12 17:00 | 100% | SP-220526 |  | Zugenmaier, Alf, NTT DOCOMO, | zugenmai@hm.edu | 13/7/22: 33.884 added;; 12/9/22: 0%->10; 11/12/22: 10%->50; 17/3/23: 50%->60; 8/6/23: 60%->100 | 33.884 | 96 | 49 |  |  | Thu 02/06/22 | Thu 08/06/23
1041 | 990048 | Security aspects of SNAPP | SNAAPPY | 2 | Rel-18 | S3 | 2023-03-16 08:00 | 2023-09-09 17:00 | 100% | SP-230161 |  | Zugenmaier, Alf, NTT DOCOMO | zugenmai@hm.edu | ; 8/6/23: 0%->50; 8/12/23: 50%->85; 15/3/24: 85%->100 | 33.122 | 99 | 50 |  |  | Thu 16/03/23 | Fri 15/03/24
1042 | 1010002 | CT3 aspects of SNAAPP | SNAAPP | 2 | Rel-18 | C3 | 2023-03-16 08:00 | 2023-09-09 17:00 | 100% | CP-232128 |  | Eitoku, Haruka, NTT | haruka.eitoku@ntt.com |  | 29.222 | 99 | 50 |  |  | Thu 16/03/23 | Thu 08/06/23
1043 | 920039 | Smart Energy and Infrastructure | SEI | 1 | Rel-18 |  | 2020-06-25 08:00 | 2021-12-10 17:00 | 100% | SP-210523 |  | XIA Xu, China Telecom | xiaxu@chinatelecom.cn |  | 22.104;22.261 | 92 | 47 |  |  | Fri 11/06/21 | NA
1044 | 880038 | Study on 5G Smart Energy and Infrastructure | FS_5GSEI | 2 | Rel-18 | S1 | 2020-06-25 08:00 | 2021-06-11 17:00 | 100% | SP-200574 |  | XIA Xu, China Telecom | xiaxu@chinatelecom.cn | 28/7/20: 22.867 added;; 12/9/20: 0%->20; 5/12/20: 20%->60; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 60%->75; 11/6/21: 75%->90; 13/9/21: 90%->100 | 22.867 | 88 | 45 |  |  | Thu 25/06/20 | Mon 13/09/21
1045 | 920032 | Stage 1 of Smart Energy and Infrastructure | SEI | 2 | Rel-18 | S1 | 2021-06-11 08:00 | 2021-12-10 17:00 | 100% | SP-210523 |  | XIA Xu, China Telecom | xiaxu@chinatelecom.cn | ; 13/9/21: 0%->95; 10/12/21: 95%->100 | 22.104;22.261 | 92 | 47 |  |  | Fri 11/06/21 | Fri 10/12/21
1046 | 940040 | Study on Network and Service Operations for Energy Utilities | FS_NSOEU | 1 | Rel-18 | S5 | 2021-12-13 08:00 | 2023-06-06 17:00 | 100% | SP-211622 |  | Erik Guttman , Samsung | erik.guttman@samsung.com | 7/1/22: 28.902 added;; 4/6/22: 0%->25; 12/9/22: 25%->45; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 45%->55; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 55%->79; 8/6/23: 79%->100 | 28.902 | 94 | 48 |  |  | Mon 13/12/21 | Thu 08/06/23
1047 | 920014 | Study on application enablement aspects for subscriber-aware northbound API access | FS_SNAAPP | 1 | Rel-18 | S6 | 2021-06-11 08:00 | 2022-06-10 17:00 | 100% | SP-220094 |  | Suzuki, Yuji, NTT DOCOMO | yuuji.suzuki.rm@nttdocomo.com | 2/7/21: 23.700-95 added;; 13/9/21: 0%->20; 13/12/21: 20%->65; 12/3/22: 65%->75; 12/3/22: FCD:11/03/2022->6/22; 12/3/22: WID:SP-210476->SP-220094; 4/6/22: 75%->85; 12/9/22: 85%->90; 11/12/22: 90%->100 | 23.700-95 | 92 | 47 |  |  | Fri 11/06/21 | Sun 11/12/22
1048 | 960022 | Rel-18 Enhancements of 3GPP Northbound and Application Layer interfaces and APIs | NBI18 | 1 | Rel-18 |  | 2022-06-03 08:00 | 2024-03-03 17:00 | 100% | CP-231190 |  | Abdessamad El Moatamid, Huawei | abdessamad.el.moatamid@huawei.com | 30/6/23: WID:CP-221105->CP-231190 |  | 96 | 49 |  |  | Fri 03/06/22 | Fri 30/06/23
1049 | 960053 | CT1 aspects of NBI18 | NBI18 | 2 | Rel-18 | C1 | 2022-06-06 08:00 | 2024-03-03 17:00 | 100% | CP-231190 |  | Abdessamad El Moatamid, Huawei | abdessamad.el.moatamid@huawei.com | 6/6/23: Compl:25%->40%6/6/23: WID: CP-221105->CP-231190; 9/6/23: 40%->45; 9/6/23: 45%-> | 24.558 | 96 | 49 |  |  | Fri 03/06/22 | Fri 09/06/23
1050 | 960054 | CT3 aspects of NBI18 | NBI18 | 2 | Rel-18 | C3 | 2022-06-03 08:00 | 2024-03-03 17:00 | 100% | CP-231190 |  | Abdessamad El Moatamid, Huawei | abdessamad.el.moatamid@huawei.com | 6/6/23: Compl:30%->60%6/6/23: WID: CP-221105->CP-231190 | 29.116; 29.122; 29.222; 29.255; 29.257; 29.343; 29.486; 29.522; 29.538; 29.549; 29.558 | 96 | 49 |  |  | Fri 03/06/22 | Tue 06/06/23
1051 | 980027 | Study on Structure of Charging for Verticals | FS_SCV | 1 | Rel-18 | S5 | 2022-12-09 08:00 | 2023-12-12 17:00 | 100% | SP-230178 |  | CHEN SHAN, Huawei | chenshan@huawei.com | 16/3/23: WID:SP-221161->SP-230178; 17/3/23: 0%->8; 17/3/23: 28.843 added;; 8/6/23: 8%->80; 8/6/23: FCD:06/06/2023->12/23; 7/9/23: 80%->100 | 28.843 | 98 | 50 |  |  | Fri 09/12/22 | Thu 07/09/23
1052 | 1010015 | Charging Aspects of B2B | B2B_CH | 1 | Rel-18 | S5 | 2023-09-06 08:00 | 2024-03-03 17:00 | 100% | SP-231155 |  | Deng, Yimeng, Huawei | dengyimeng at huawei dot com | ; 8/12/23: 0%->80; 14/3/24: 80%->100 | 32.240; 32.290 | 101 | 51 |  |  | Wed 06/09/23 | Thu 14/03/24
1053 | 0 | Rel-18 Mission Critical and emergencies | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1054 | 940015 | Mission critical security enhancements phase 3 | MCXSec3 | 1 | Rel-18 | S3 | 2021-12-10 08:00 | 2023-03-03 17:00 | 100% | SP-211363 |  | Woodward, Tim, Motorola Solutions, Inc. | tim.woodward@motorolasolutions.com | ; 4/6/22: 0%->10; 12/9/22: 10%->15; 11/12/22: 15%->35; 17/3/23: 35%->75; 8/6/23: 75%->100 | 33.180 | 94 | 48 |  |  | Fri 10/12/21 | Thu 08/06/23
1055 | 1000042 | Enhanced Mission Critical Push-to-talk architecture phase 4 | enh4MCPTT | 1 | Rel-18 |  | 2021-12-10 08:00 | 2024-03-03 17:00 | 100% | SP-211519 |  | Harish Negalaguli (Motorola Solutions) | harish.negalaguli@motorolasolutions.com | ; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->55; 11/12/22: 55%->65; 17/3/23: 65%->80 | 23.379; 23.280; 23.281; 23.282; 23.283 | 94 | 48 |  |  | Fri 10/12/21 | Fri 17/03/23
1056 | 940025 | Stage 2 of enh4MCPTT | enh4MCPTT | 2 | Rel-18 | S6 | 2021-12-10 08:00 | 2023-03-03 17:00 | 100% | SP-211519 |  | Harish Negalaguli (Motorola Solutions) | harish.negalaguli@motorolasolutions.com | ; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->55; 11/12/22: 55%->65; 17/3/23: 65%->80; 8/6/23: 80%->100 | 23.379; 23.280; 23.281; 23.282; 23.283 | 94 | 48 |  |  | Fri 10/12/21 | Thu 08/06/23
1057 | 1000020 | CT aspects of enh4MCPTT | enh4MCPTT | 2 | Rel-18 | C1 | 2023-06-07 08:00 | 2024-03-03 17:00 | 100% | CP-240297 |  | Kiran Kapale, Samsung, | kiran.kapale@samsung.com | ; 30/6/23: 24.283 added; | 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582 ; 24.283 | 100 | 51 |  |  | Wed 07/06/23 | Fri 30/06/23
1058 | 930043 | Gateway UE function for Mission Critical Communication | MCGWUE | 1 | Rel-18 |  | 2020-06-25 08:00 | 2024-03-03 17:00 | 100% | SP-210959 |  | Oettl, Martin, Nokia | martin.oettl@nokia.com |  | 23.280; 23.289; 23.281; 23.282; 23.379 | 93 | 47 |  |  | Fri 10/09/21 | NA
1059 | 880033 | Study of Gateway UE function for Mission Critical Communication | FS_MCGWUE | 2 | Rel-18 | S6 | 2020-06-25 08:00 | 2021-09-20 17:00 | 100% | SP-200335 |  | Oettl, Martin, Nokia | martin.oettl@nokia.com | 13/9/20: 0%->10; 25/9/20: 23.700-79 added;; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->60; 13/9/21: 60%->100 | 23.700-79 | 88 | 45 |  |  | Fri 26/06/20 | Mon 13/09/21
1060 | 930017 | (Stage 2 of) Gateway UE function for Mission Critical Communication | MCGWUE | 2 | Rel-18 | S6 | 2021-09-10 08:00 | 2022-06-10 17:00 | 100% | SP-210959 |  | Oettl, Martin, Nokia | martin.oettl@nokia.com | ; 13/12/21: 0%->50; 12/3/22: 50%->75; 4/6/22: 75%->90; 12/9/22: 90%->100 | 23.280; 23.289; 23.281; 23.282; 23.379 | 93 | 47 |  |  | Fri 10/09/21 | Mon 12/09/22
1061 | 990011 | CT1 aspects of MCGWUE | MCGWUE | 2 | Rel-18 | C1 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-232164 |  | Magnus Tränk, Ericsson | magnus.trank@ericsson.com |  | 24.281.24.282.24.379.24.380.24.483.24.484.24.581.24.582 | 93 | 47 |  |  | Fri 10/09/21 | Mon 12/09/22
1062 | 970054 | Mission Critical Services over 5MBS | MCOver5MBS | 1 | Rel-18 |  | 2019-03-07 08:00 | 2023-12-12 17:00 | 100% | SP-210958 |  | Wendler, Ingo, UIC | ingo.wendler@sbb.ch | ; 13/12/21: 0%->30; 12/3/22: 30%->50; 12/3/22: FCD:11/03/2022->9/22; 4/6/22: 50%->85 | 23.289 | 93 | 47 |  |  | Fri 10/09/21 | Sat 04/06/22
1063 | 930016 | Stage 2 of Mission Critical Services over 5MBS | MCOver5MBS | 2 | Rel-18 | S6 | 2019-03-07 08:00 | 2022-03-11 17:00 | 100% | SP-210958 |  | Wendler, Ingo, UIC | ingo.wendler@sbb.ch | ; 13/12/21: 0%->30; 12/3/22: 30%->50; 12/3/22: FCD:11/03/2022->9/22; 4/6/22: 50%->85; 12/9/22: 0%->98; 12/9/22: FCD:10/06/2020->03/22; 11/12/22: 98%->100 | 23.289 | 93 | 47 |  |  | Fri 10/09/21 | Sun 11/12/22
1064 | 970033 | CT1 aspects of Mission Critical Services over 5MBS | MCOver5MBS | 2 | Rel-18 | C1 | 2022-09-13 08:00 | 2023-12-12 17:00 | 100% | CP-222175 |  | Chen, Ying, TD Tech Ltd. | chenying@td-tech.com | 6/6/23: Compl:20%->40% | 24.281; 24.282; 24.379; 24.380; 24.481; 24.483; 24.484; 42.581; 24.582 | 97 | 49 |  |  | Mon 05/09/22 | Tue 06/06/23
1065 | 970055 | Mission Critical Services over 5GProSe | MCOver5GProSe | 1 | Rel-18 |  | 2019-03-07 08:00 | 2023-12-12 17:00 | 100% | SP-211517 |  | Yanmei YANG, Huawei | yangyanmei@huawei.com | ; 12/3/22: 0%->50; 4/6/22: 50%->87 | 23.289 | 94 | 48 |  |  | Fri 10/12/21 | Sat 04/06/22
1066 | 940023 | Stage 2 of Mission Critical Services over 5GProSe | MCOver5GProSe | 2 | Rel-18 | S6 | 2019-03-07 08:00 | 2022-09-12 17:00 | 100% | SP-211517 |  | Yanmei YANG, Huawei | yangyanmei@huawei.com | ; 12/3/22: 0%->50; 4/6/22: 50%->87; 12/9/22: 0%->100; 12/9/22: FCD:10/06/2020->09/22 | 23.289 | 94 | 48 |  |  | Fri 10/12/21 | Mon 12/09/22
1067 | 970034 | CT1 aspects of Mission Critical Services over 5GProSe | MCOver5GProSe | 2 | Rel-18 | C1 | 2022-09-13 08:00 | 2023-12-12 17:00 | 100% | CP-233210 |  | Mengdi Ji, Huawei | jimengdi@huawei.com, | 3/24: rapporteur changed (was weihaitao@huawei.com) | 24.281; 24.282; 24.379; 24.380; 24.481; 24.483; 24.484; 24.581; 24.582 | 97 | 49 |  |  | Mon 05/09/22 | NA
1068 | 970027 | Stopped - ProSe Secondary Authentication | PROSESA | 1 | Rel-18 | S3 | 2022-09-12 08:00 | 2023-03-03 17:00 | 100% | SP-220874 |  | Samir Ferdi , Interdigital | samir. ferdi @ interdigital . com | ; 17/3/23: 0%->30; 8/6/23: 30%->90. 9/23: stopped at 90% | 33.503 | 97 | 49 | 101 |  | Sun 11/09/22 | Thu 08/06/23
1069 | 930026 | Sharing administrative configuration between interconnected MCX Service systems | SACI_MCS | 1 | Rel-18 | S1 | 2021-09-10 08:00 | 2021-12-10 17:00 | 100% | SP-211059 |  | Toobe, Jens, BDBOS | jens.toobe@bdbos.bmi.bund.de | ; 13/9/21: 0%->80; 10/12/21: 80%->100 | 22.280 | 93 | 47 |  |  | Fri 10/09/21 | Fri 10/12/21
1070 | 930025 | Ad hoc Group Communication support in Mission Critical Services | AHGC | 1 | Rel-18 | S1 | 2021-09-10 08:00 | 2021-09-20 17:00 | 100% | SP-211058 |  | Erik.Guttman, Samsung | Erik.Guttman@samsung.com | ; 10/12/21: 0%->100 | 22.280 | 93 | 47 |  |  | Fri 10/09/21 | Fri 10/12/21
1071 | 1010020 | Mission Critical ad hoc group Communications | MC_AHGC | 1 | Rel-18 | S6 | 2022-12-09 08:00 | 2024-03-03 17:00 | 100% | SP-221235 |  | Kiran Gurudev Kapale, Samsung | kiran.kapale@samsung.com | ; 11/12/22: 0%->35; 17/3/23: FCD:03/03/2023->/23; 17/3/23: 35%->85; 8/6/23: 85%->100 | 23.280; 23.379; 23.281; 23.282 | 98 | 50 |  |  | Fri 09/12/22 | Thu 08/06/23
1072 | 980051 | Stage 2 of Mission Critical ad hoc group Communications | MC_AHGC | 2 | Rel-18 | S6 | 2022-12-09 08:00 | 2023-06-06 17:00 | 100% | SP-221235 |  | Kiran Gurudev Kapale, Samsung | kiran.kapale@samsung.com | ; 11/12/22: 0%->35; 17/3/23: FCD:03/03/2023->/23; 17/3/23: 35%->85; 8/6/23: 85%->100 | 23.280; 23.379; 23.281; 23.282 | 98 | 50 |  |  | Fri 09/12/22 | Thu 08/06/23
1073 | 1010004 | CT1 aspects of Mission Critical ad hoc group Communications | MC_AHGC | 2 | Rel-18 | C1 | 2023-09-09 08:00 | 2024-03-03 17:00 | 100% | CP-232162 |  | Kiran Gurudev Kapale, Samsung | kiran.kapale@samsung.com |  | 24.379, 24.380, 24.281, 24.581, 24.282, 24.582, 24.481, 24.483, 24.484 | 98 | 50 |  |  | Fri 09/12/22 | Thu 08/06/23
1074 | 850043 | Study on sharing administrative configuration between interconnected MCX Service systems | FS_SACI_MCS | 1 | Rel-18 | S1 | 2019-09-19 08:00 | 2021-12-10 17:00 | 100% | SP-190837 |  | Toobe, Jens, BDBOS | jens.toobe at bdbos.bmi.bund.de | ; 8/10/19: 22.881 added;; 6/12/19: 0%->5; 12/9/20: 5%->20; 19/3/21: 20%->55; 19/3/21: FCD:12/06/2020->12/21; 11/6/21: 55%->90; 13/9/21: 90%->100 | New ; 22.881 | 85 | 43 |  |  | Fri 13/09/19 | Mon 13/09/21
1075 | 940020 | Study on sharing of administrative configuration between interconnected MC service systems | FS_MCShAC | 1 | Rel-18 | S6 | 2021-12-13 08:00 | 2023-03-03 17:00 | 100% | SP-211514 |  | Azem, Dania, BDBOS | dania.azem@bdbos.bmi.bund.de | 7/1/22: 23.700-38 added;; 12/3/22: 0%->5; 4/6/22: 5%->25; 12/9/22: 25%->25; 11/12/22: 25%->65; 17/3/23: 65%->80; 8/6/23: 80%->100 | 23.700-38 | 94 | 48 |  |  | Mon 13/12/21 | Thu 08/06/23
1076 | 940022 | Study on Mission Critical ad hoc group communications | FS_MCAHGC | 1 | Rel-18 | S6 | 2021-12-13 08:00 | 2022-12-12 17:00 | 100% | SP-211516 |  | Arunprasath Ramamoorthy, Samsung | arun.prasath@samsung.com | 7/1/22: 23.700-76 added;; 12/3/22: 0%->25; 4/6/22: 25%->75; 12/9/22: 75%->90; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 90%->95; 17/3/23: 95%->100 | 23.700-76 | 94 | 48 |  |  | Mon 13/12/21 | Fri 17/03/23
1077 | 800023 | Study on Mission Critical services support over 5G System | FS_MCOver5GS | 1 | Rel-18 | S6 | 2018-06-06 08:00 | 2022-06-10 17:00 | 100% | SP-200837 |  | Verweij, Kees, The Police of the Netherlands | kees.verweij@politie.nl | 6/8/18: 23.783 added;¦10/9/18: 0%->5¦7/12/18: 5%->35¦7/12/18: FCD:03/19->09/19¦14/12/18: WID:SP-180383->SP-181136. 03/19: Rel corrected (was shown as Rel-17); 31/5/19: 35%->40; 26/3/20: FCD:12/09/2019->09/20; 26/3/20: 40%->45; Rel-16->17; 03/22:Rel17-> | New; 23.783 | 80 | 41 |  |  | Wed 06/06/18 | Sat 04/06/22
1078 | 0 | Rel-18 Artificial Intelligence (AI)/Machine Learning (ML) | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1079 | 920037 | AI/ML model transfer in 5GS | AIML_MT | 1 | Rel-18 |  | 2019-12-06 08:00 | 2021-12-10 17:00 | 100% | SP-210520 |  | Jia SHEN, OPPO, sj@oppo.com |  |  | 22.261 | 92 | 47 |  |  | Fri 11/06/21 | Wed 13/07/22
1080 | 860009 | Study on traffic characteristics and performance requirements for AI/ML model transfer in 5GS | FS_AIML_MT | 2 | Rel-18 | S1 | 2019-12-06 08:00 | 2021-06-11 17:00 | 100% | SP-220441 |  | Jia SHEN, Oppo . | sj@oppo.com | 28/7/20: 33.852 added;; 12/9/20: 0%->40; 5/12/20: 40%->70; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 70%->75; 11/6/21: 75%->95; 13/9/21: 95%->100. 06/22: FS_AMMT->FS_AIML_MT; 21/6/22: WID:SP-191040->SP-220441 | 22.874 | 86 | 44 |  |  | Fri 06/12/19 | Tue 21/06/22
1081 | 920030 | Stage 1 of AMMT | AIML_MT | 2 | Rel-18 | S1 | 2021-06-11 08:00 | 2021-12-10 17:00 | 100% | SP-220440 |  | Jia SHEN, OPPO, sj@oppo.com |  | ; 13/9/21: 0%->80; 11/3/22: 80%->10006/22: AMMT->AIML_MT; 21/6/22: WID:SP-210587->SP-220440 | 22.261 | 92 | 47 |  |  | Fri 11/06/21 | Tue 21/06/22
1082 | 940084 | Study on Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface | FS_NR_AIML_air | 1 | Rel-18 | R1 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-251186 | RP-233132 | Juan Montojo (RAN1); Mattias Frenne (RAN2); Xiaofeng Liu (RAN4), Qualcomm; Ericsson; CAICT | juanm@qti.qualcomm.com; mattias.frenne@ericsson.com; liuxiaofeng1@caict.ac.cn | TR 38.8xx; compare REL-18 WI NR_AIML_NGRAN-Core; 21/1/22: 38.843 added;; 22/3/22: Stat Rep: ->RP-220534 ; 6/6/22: Compl:0%->5% 20/6/22: Acronym:FS_NR_AIML_air->FS_NR_AIML_Air; Rapporteur: Qualcomm->Juan Montojo, Qualcomm; Rap eMail: ->juanm@qti....;... | 38.843 | 94 | 48 |  |  | Thu 06/01/22 | Fri 18/07/25
1083 | 989997 | Artificial Intelligence (AI)/Machine Learning (ML) | AIMLsys | 1 | Rel-18 |  | 2021-12-20 08:00 | 2024-03-03 17:00 | 100% | SP-231278 |  | Alla Goldner, Oppo | v-alla.goldner@oppo.com | 10/12/22: 0%->5; 3/1/24: WID:SP-221329->SP-231278 | 23.501; 23.502; 23.503; 23.288 | 98 | 50 |  |  | Fri 09/12/22 | Wed 03/01/24
1084 | 960037 | Study on Security and Privacy of AI/ML-based Services and Applications in 5G | FS_AIML | 2 | Rel-18 | S3 | 2022-06-21 08:00 | 2023-03-03 17:00 | 100% | SP-220687 |  | Marcus Wong, OPPO | marcus.wong@oppo.com | 13/7/22: 33.898 added;; 12/9/22: 0%->5; 11/12/22: 5%->25; 17/3/23: 25%->35; 7/9/23: 35%->100 | 33.898 | 96 | 49 |  |  | Tue 21/06/22 | Thu 07/09/23
1085 | 940071 | Study on 5G System Support for AI/ML-based Services | FS_AIMLsys | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-220071 |  | Alla Goldner, Oppo | v-alla.goldner@oppo.com | 21/1/22: 23.700-80 added;; 12/3/22: 0%->10; 12/3/22: WID:SP-211648->SP-220071; 4/6/22: 10%->60; 12/9/22: 60%->70; 10/12/22: 70%->100; 10/12/22: FCD:12/09/2022->12/22 | 23.700-80 | 94 | 48 |  |  | Sun 19/12/21 | Sat 10/12/22
1086 | 980019 | (Stage 2 for AIML) System Support for AI/ML-based Services | AIMLsys | 2 | Rel-18 | S2 | 2022-12-09 08:00 | 2023-06-06 17:00 | 100% | SP-231278 |  | Alla Goldner, Oppo | v-alla.goldner@oppo.com | 10/12/22: 0%->5; 15/3/23: WID:SP-221329->SP-230095; 15/3/23: 5%->50; 8/6/23: 50%->100; 3/1/24: WID:SP-230095->SP-231278 | 23.501; 23.502; 23.503; 23.288 | 98 | 50 |  |  | Fri 09/12/22 | Wed 03/01/24
1087 | 990008 | CT3 aspects of AIML | AIMLsys | 2 | Rel-18 | C3 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-230329 |  | Tangudu, Narendranath Durga, Samsung | n.tangudu@samsung.com | 31/3/23: 29.543 added;6/6/23: Compl:10%->50% | 29.122.29.513.29.514.29.517.29.591.29.519.29.520.29.521.29.522.29.244.29.503.29.504.29.505.29.510; 29.543 | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
1088 | 990074 | CT4 aspects of AIML | AIMLsys | 2 | Rel-18 | C4 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-230329 |  | Tangudu, Narendranath Durga, Samsung | n.tangudu@samsung.com | 6/6/23: Compl:0%->60% | 29.122.29.513.29.514.29.517.29.591.29.519.29.520.29.521.29.522.29.244.29.503.29.504.29.505.29.510 | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
1089 | 941010 | Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN | NR_AIML_NGRAN | 1 | Rel-18 |  | 2021-12-13 08:00 | 2023-05-01 17:00 | 80% | RP-233441 |  | CMCC |  | no Perf. part; compare REL-18 SI FS_NR_AIML_air; 5/4/22: WID:RP-213602->RP-220635; 2/1/24: WID:RP-220635->RP-233441 |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 02/01/24
1090 | 941110 | Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN | NR_AIML_NGRAN-Core | 2 | Rel-18 | R3 | 2021-12-13 08:00 | 2023-05-01 17:00 | 80% | RP-233441 | RP-232673 | Fang Xie, Angelo Centonza, CMCC, Ericsson | xiefang@chinamobile.com, angelo.centonza@ericsson.com | no Perf. part; compare REL-18 SI FS_NR_AIML_air; 20/6/22: FCD:23/06/2023->23/06/2022; WID: RP-220635->RP-213602; Stat Rep: ->RP-221381; Rapporteur: CMCC->Fang Xie, Angelo Centonza, CMCC, Ericsson; Rap eMail: ->xiefang@chinamobile.com, angelo.centonza@e... |  | 94 | 48 |  |  | Thu 06/01/22 | Thu 21/09/23
1091 | 960031 | Study on the security aspects of Artificial Intelligence (AI)/Machine Learning (ML) for the NG-RAN | FS_NR_AIML_NGRAN_SEC | 1 | Rel-18 | S3 | 2022-06-02 08:00 | 2023-03-03 17:00 | 100% | SP-220529 |  | Tsiatsis, Vlasios, Ericsson | vlasios.tsiatsis@ericsson.com | 13/7/22: 33.877 added; 17/8/22: WID in SP-220529 marked as withdrawn in SA#96 tdoc list; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70. 030/6/23: "undeleted" as per Mirko+Vlasios email; 7/9/23: 70%->100 | 33.877 | 96 | 49 |  |  | Thu 02/06/22 | Thu 07/09/23
1092 | 940039 | Study on AI/ML management | FS_AIML_MGMT | 1 | Rel-18 | S5 | 2021-12-13 08:00 | 2023-06-06 17:00 | 100% | SP-211443 |  | Yao, Yizhi, Intel | yizhi<dot>yao<at>intel<dot>com | 7/1/22: 28.908 added;; 4/6/22: 0%->10; 12/9/22: 10%->55; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 55%->85; 11/12/22: FCD:10/03/2023->/23; 8/6/23: 85%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 85%->100 | 28.908 | 94 | 48 |  |  | Mon 13/12/21 | Thu 08/06/23
1093 | 990119 | AI/ML management | AIML_MGT | 1 | Rel-18 | S5 | 2023-03-17 08:00 | 2024-03-03 17:00 | 100% | SP-230335 |  | Yao, Yizhi, Intel | yizhi<dot>yao<at>intel<dot>com | ; 8/6/23: 0%->20; 7/9/23: 20%->35; 14/3/24: 35%->100; 14/3/24: FCD:12/12/2023->/24 | 28.105; 28.552; 32.425; 28.554; 28.541 | 99 | 50 |  |  | Fri 17/03/23 | Thu 14/03/24
1094 | 1020023 | NEF Charging enhancement to support AI/ML in 5GS | AIMLsysNEF_CH | 1 | Rel-18 | S5 | 2023-12-07 08:00 | 2023-12-12 17:00 | 100% | SP-231706 |  | Alla Goldner, OPPO | v-alla.goldner@oppo.com | ; 14/3/24: 0%->100; 14/3/24: 100%->100 | 32.254; 32.291 | 102 | 52 |  |  | Thu 07/12/23 | Thu 14/03/24
1095 | 0 | Rel-18 Multicast and Broadcast Services (MBS) | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1096 | 940099 | Enhancements of NR Multicast and Broadcast Services | NR_MBS_enh | 1 | Rel-18 |  | 2021-12-13 08:00 | 2025-12-12 17:00 | 68% | RP-232993 |  | CATT |  | no Perf. part; compare REL-17 WI NR_MBS-Core; 12/7/22: WID:RP-213568->RP-221458; 6/10/23: WID:RP-221458->RP-231829; 2/1/24: WID:RP-231829->RP-232993 |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 02/01/24
1097 | 940199 | Core part: Enhancements of NR Multicast and Broadcast Services | NR_MBS_enh-Core | 2 | Rel-18 | R2 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-232993 | RP-232992 | Rui Zhou, CATT | zhourui@catt.cn | no Perf. part; compare REL-17 WI NR_MBS-Core; 22/3/22: Stat Rep: ->RP-220734 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: Stat Rep: RP-220734->RP-221459; 20/6/22: Rapporteur: CATT->Erlin Zeng, CATT; Rap eMail: ->erlin.zeng@catt.cn13/7/22: FCD:23...;... |  | 94 | 48 |  |  | Thu 06/01/22 | Fri 08/12/23
1098 | 1060077 | UE Conformance - Enhancements of NR Multicast and Broadcast Services including CT aspects | NR_MBS_enh_5MBS_Ph2-UEConTest | 2 | Rel-18 | R5 | 2025-03-06 08:00 | 2025-12-12 17:00 | 10% | RP-243116 | RP-252723 | CATT |  | 6/3/25: Compl:0%->5%; Stat Rep: ->RP-250503; ; 3/4/25: WID:RP-243116->RP-250504; 6/6/25: FCD:Thu 13/11/25->Fri 12/12/25; WID: RP-250504->RP-243116; Stat Rep: RP-250503->RP-251630; ; 11/9/25: Compl:5%->10%; Stat Rep: RP-251630->RP-252723; |  | 106 | 54 |  |  | Fri 24/01/25 | Thu 11/09/25
1099 | 989999 | 5G multicast-broadcast services Phase 2 | 5MBS_Ph2 | 1 | Rel-18 |  | 2021-12-20 08:00 | 2024-03-03 17:00 | 100% | SP-221131 |  | Meng Li, Huawei, Huawei | raymond.limeng@huawei.com |  | 23.501; 23.502; 23.247 | 98 | 50 |  |  | Fri 09/12/22 | NA
1100 | 940067 | Study on architectural enhancements for 5G multicast-broadcast services Phase 2 | FS_5MBS_Ph2 | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-220072 |  | Meng Li, Huawei | raymond.limeng@huawei.com | 21/1/22: 23.700-47 added;; 12/3/22: 0%->15; 12/3/22: WID:SP-211645->SP-220072; 4/6/22: 15%->55; 12/9/22: 55%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100 | 23.700-47 | 94 | 48 |  |  | Sun 19/12/21 | Sat 10/12/22
1101 | 980013 | (Stage 2 of 5MBS_Ph2) Architectural enhancements for 5G multicast-broadcast services Phase 2 | 5MBS_Ph2 | 2 | Rel-18 | S2 | 2022-12-09 08:00 | 2023-06-06 17:00 | 100% | SP-230099 |  | Meng Li, Huawei, Huawei | raymond.limeng@huawei.com | ; 15/3/23: WID:SP-221131->SP-230099; 15/3/23: 0%->75; 8/6/23: 75%->100 | 23.501; 23.502; 23.247 | 98 | 50 |  |  | Fri 09/12/22 | Thu 08/06/23
1102 | 990001 | CT1 aspects for 5MBS_Ph2 | 5MBS_Ph2 | 2 | Rel-18 | C1 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-232031 |  | Rezagah, Roya, Huawei | roya.rezagah@huawei.com | 6/6/23: Compl:0%->65%; 30/6/23: WID:CP-230023->CP-231024. 03/24: rapporteur changed (was giorgi.gulbani@huawei.com) |  | 99 | 50 |  |  | Fri 09/12/22 | Fri 30/06/23
1103 | 990076 | CT3 aspects for 5MBS_Ph2 | 5MBS_Ph2 | 2 | Rel-18 | C3 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-232031 |  | Rezagah, Roya, Huawei | roya.rezagah@huawei.com | ; 9/6/23: 15%->40 |  | 99 | 50 |  |  | Fri 09/12/22 | Fri 09/06/23
1104 | 990077 | CT4 aspects for 5MBS_Ph2 | 5MBS_Ph2 | 2 | Rel-18 | C4 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-232031 |  | Rezagah, Roya, Huawei | roya.rezagah@huawei.com | ; 17/3/23: 5%->206/6/23: Compl:20%->70% |  | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
1105 | 1000005 | Security Enhancements for 5G Multicast-Broadcast Services Phase 2 | 5MBS_Ph2 | 2 | Rel-18 | S3 | 2023-06-08 08:00 | 2023-09-09 17:00 | 100% | SP-230559 |  | Longhua Guo, Huawei Technologies | guolonghua@huawei.com | ; 15/3/24: 0%->100 | 33.501 | 100 | 51 |  |  | Thu 08/06/23 | Fri 15/03/24
1106 | 960041 | Study on security enhancements for 5G multicast-broadcast services Phase 2 | FS_5MBS_SEC_Ph2 | 2 | Rel-18 | S3 | 2022-06-02 08:00 | 2023-03-03 17:00 | 100% | SP-220539 |  | Longhua Guo, Huawei Technologies | guolonghua@huawei.com | 13/7/22: 33.883 added;; 12/9/22: 0%->12; 11/12/22: 12%->50; 17/3/23: 50%->55; 8/6/23: 55%->100 | 33.883 | 96 | 49 |  |  | Thu 02/06/22 | Thu 08/06/23
1107 | 920071 | New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 | LTE_terr_bcast_bands_part2 | 1 | Rel-18 |  | 2021-06-15 08:00 | 2025-12-12 17:00 | 69% | RP-223378 |  | EBU |  | RAN4 part for WI LTE_terr_bcast_bands_part1-Core; REL--independent starting from REL-17; no Perf. part ; 5/4/22: WID:RP-211145->RP-220518; 23/9/22: WID:RP-220518->RP-222224; 9/1/23: WID:RP-222224->RP-223378 |  | 92 | 47 |  |  | Fri 02/07/21 | Mon 09/01/23
1108 | 920171 | Core part: New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 | LTE_terr_bcast_bands_part2-Core | 2 | Rel-18 | R4 | 2021-06-15 08:00 | 2023-09-08 17:00 | 100% | RP-232590 | RP-235288 | Gene Fong, Qualcomm Incorporated | gfong@qti.qualcomm.com | RAN4 part for WI LTE_terr_bcast_bands_part1-Core; REL--independent starting from REL-17; no Perf. part ; 13/9/21: CD:Wed 15/03/23->Wed 23/03/22 ; 22/3/22: CD:23/03/2022->12/06/2023; 22/3/22: Stat Rep: RP ; 6/6/22: CD:12/06/2023->23/0 ; 20/6/22: Rappor... | 36.792 | 92 | 47 |  |  | Fri 02/07/21 | Fri 06/10/23
1109 | 1050131 | UE Conformance - New bands and bandwidth allocation for LTE based 5G terrestrial broadcast | LTE_terr_bcast_bands_part2-UEConTest | 2 | Rel-18 | R5 | 2024-09-09 08:00 | 2025-12-12 17:00 | 30% | RP-242026 | RP-252051 | Qualcomm |  | 6/12/24: Compl:0%->5%; Stat Rep: ->RP-242900; ; 6/3/25: FCD:24/07/2025->12/12/2025; Compl:5%->15%; Stat Rep: RP-242900->RP-250398; ; 6/6/25: Stat Rep: RP-250398->RP-251233; ; 11/9/25: Compl:15%->30%; Stat Rep: RP-251233->RP-252051; |  | 105 | 53 |  |  | Thu 26/09/24 | Thu 11/09/25
1110 | 990078 | UE pre-configuration for 5MBS | UEConfig5MBS | 1 | Rel-18 |  | 2023-03-03 17:00 | 2024-03-03 17:00 | 100% | CP-230201 |  | Herrero-Veron, Christian(Huawei) | Christian.Herrero@huawei.com |  | 31.102 | 92 | 47 |  |  | Fri 02/07/21 | Mon 09/01/23
1111 | 990022 | CT1 aspects of UEConfig5MBS | UEConfig5MBS | 2 | Rel-18 | C1 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-230201 |  | Herrero-Veron, Christian(Huawei) | Christian.Herrero@huawei.com | 6/6/23: Compl:85%->95%6/6/23: CD:24/03/2023->03/03/2024 | 31.102 | 92 | 47 |  |  | Fri 02/07/21 | Tue 06/06/23
1112 | 990079 | CT6 aspects of UEConfig5MBS | UEConfig5MBS | 2 | Rel-18 | C6 | 2023-03-03 17:00 | 2023-03-03 17:00 | 100% | CP-230201 |  | Herrero-Veron, Christian(Huawei) | Christian.Herrero@huawei.com |  | 31.102 | 92 | 47 |  |  | Fri 02/07/21 | Mon 09/01/23
1113 | 0 | See also MCOver5MBS under Mission Critical | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1114 | 0 | See also TEI18_MBS4V2X under Autonomous Driving | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1115 | 0 | Rel-18 Slice | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1116 | 910095 | Study on 5G NR UE full stack testing for Network Slicing | FS_NR_Slice_Test | 1 | Rel-18 | R5 | 2021-03-12 08:00 | 2022-09-22 17:00 | 100% | RP-211976 | RP-221363 | Dan SONG, Yu SHI, CMCC, CU | songdan@chinamobile.com, shiyu19@chinaunicom.cn | TR 38.9XX; compare RAN2 REL-17 SI FS_NR_slice; related to REL-15 WI 5GS_Ph1 and REL-16 WI eNS) ; 2/7/21: 0%->10; 13/9/21: Compl:10%->28%; ; 29/9/21: WID:RP-210371->RP-211977; 04/22: Rel-17->Rel-18; 20/6/22: FCD:22/03/2022->22/09/2022; Compl:28%->82%; ... |  | 91 | 46 |  |  | Wed 07/04/21 | Fri 23/09/22
1117 | 910026 | Study on network slice management capability exposure | FS_NSCE | 1 | Rel-18 | S5 | 2021-03-18 08:00 | 2023-06-06 17:00 | 100% | SP-220350 |  | Xiaobo Yu, Alibaba Group | shibo.yxb@alibaba-inc.com | ; 11/6/21: 0%->5; 11/6/21: FCD:Fri 10/12/->12/21; 13/9/21: 5%->25; 13/12/21: 25%->65; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 22/3/22: WID:SP-210131->SP-220350; 4/6/22: 65%->80; 4/6/22: FCD:11/03/2022->03/23; 12/9/22: 80%->83; 12/9/2... | New | 91 | 46 |  |  | Thu 18/03/21 | Thu 08/06/23
1118 | 910038 | Enhanced Access to and Support of Network Slice | EASNS | 1 | Rel-18 |  | 2020-06-25 08:00 | 2024-03-03 17:00 | 100% | SP-210210 |  | Chun, SungDuck, LG Electronics Inc. | sungduck.chun@lge.com |  | 22.261 | 91 | 46 |  |  | Thu 18/03/21 | NA
1119 | 880035 | Study on EASNS | FS_EASNS | 2 | Rel-18 | S1 | 2020-06-25 08:00 | 2021-03-17 17:00 | 100% | SP-200571 |  | Chun, SungDuck, LG Electronics Inc | sungduck.chun@lge.com | 12/9/20: 0%->20; 25/9/20: 22.835 added;; 5/12/20: 20%->60; 19/3/21: 60%->85; 11/6/21: 85%->100 | 22.835 | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
1120 | 910032 | Stage 1 for EASNS | EASNS | 2 | Rel-18 | S1 | 2021-03-18 08:00 | 2021-09-10 17:00 | 100% | SP-210210 |  | Chun, SungDuck, LG Electronics Inc. | sungduck.chun@lge.com | ; 11/6/21: 0%->100 | 22.261 | 91 | 46 |  |  | Thu 18/03/21 | Fri 11/06/21
1121 | 1000023 | Stopped – CT1 aspects of Slice-based PLMN Selection | PLMNsel_NS | 2 | Rel-18 | C1 | 2023-06-07 08:00 | 2024-03-03 17:00 | 100% | CP-232165 |  | Shuang Liang, ZTE | liang.shuang3@zte.com.cn | 8/8/23: acronym changed SbPS to PLMNsel_NS | 23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 | 100 | 51 | CP-102 |  | Wed 07/06/23 | NA
1122 | 1000044 | Stopped – CT4 aspects of Slice-based PLMN Selection | PLMNsel_NS | 2 | Rel-18 | C4 | 2023-06-07 08:00 | 2024-03-03 17:00 | 100% | CP-232165 |  | Shuang Liang, ZTE | liang.shuang3@zte.com.cn | stopped | 23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 | 100 | 51 | CP-102 |  | Wed 07/06/23 | NA
1123 | 1000045 | Stopped – CT6 aspects of Slice-based PLMN Selection | PLMNsel_NS | 2 | Rel-18 | C6 | 2023-06-07 08:00 | 2024-03-03 17:00 | 100% | CP-232165 |  | Shuang Liang, ZTE | liang.shuang3@zte.com.cn | stopped | 23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 | 100 | 51 | CP-102 |  | Wed 07/06/23 | NA
1124 | 980127 | Network Slicing Phase 3 | eNS_Ph3 | 1 | Rel-18 |  | 2021-12-20 08:00 | 2024-03-03 17:00 | 100% | SP-221135 |  | ZHU Jinguo, ZTE | zhu.jinguo@zte.com.cn |  | 23.501; 23.502; 23.503 | 98 | 50 |  |  | Fri 09/12/22 | NA
1125 | 940063 | Study on Enhancement of Network Slicing Phase 3 | FS_eNS_Ph3 | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-220073 |  | ZHU Jinguo, ZTE | zhu.jinguo@zte.com.cn | 21/1/22: 23.700-41 added;; 21/1/22: 23.700-17 added;; 12/3/22: 0%->5; 12/3/22: WID:SP-211641->SP-220073; 4/6/22: 5%->50; 12/9/22: 50%->70; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 70%->100 | 23.700-41; 23.700-17 | 94 | 48 |  |  | Sun 19/12/21 | Sat 10/12/22
1126 | 960029 | Study on enhanced security for network slicing Phase 3 | FS_eNS_Ph3 | 2 | Rel-18 | S3 | 2022-06-02 08:00 | 2023-03-03 17:00 | 100% | SP-220527 |  | Zander Lei, Huawei | lei.zhongding@huawei.com | 13/7/22: 33.886 added;; 11/12/22: 0%->15; 17/3/23: 15%->50; 8/6/23: 50%->90; 15/3/24: 90%->100 | 33.886 | 96 | 49 |  |  | Thu 02/06/22 | Fri 15/03/24
1127 | 980017 | Stage 2 of Network Slicing Phase 3 | eNS_Ph3 | 2 | Rel-18 | S2 | 2022-12-09 08:00 | 2023-06-06 17:00 | 100% | SP-230104 |  | ZHU Jinguo, ZTE | zhu.jinguo@zte.com.cn | ; 15/3/23: WID:SP-221327->SP-230104; 15/3/23: 0%->50; 8/6/23: 50%->100 | 23.501; 23.502; 23.503 | 98 | 50 |  |  | Fri 09/12/22 | Thu 08/06/23
1128 | 990015 | CT1 aspects of Network Slicing Phase 3 | eNS_Ph3 | 2 | Rel-18 | C1 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-230194 |  | Hannah Wang, ZTE | wang.menghan@zte.com.cn | 6/6/23: Compl:0%->40% | 24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522 | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
1129 | 990081 | CT3 aspects of Network Slicing Phase 3 | eNS_Ph3 | 2 | Rel-18 | C3 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-230194 |  | Hannah Wang, ZTE | wang.menghan@zte.com.cn | ; 9/6/23: 0%->30 | 24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522 | 99 | 50 |  |  | Fri 09/12/22 | Fri 09/06/23
1130 | 990082 | CT4 aspects of Network Slicing Phase 3 | eNS_Ph3 | 2 | Rel-18 | C4 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-230194 |  | Hannah Wang, ZTE | wang.menghan@zte.com.cn | 6/6/23: Compl:5%->45% | 24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522 | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
1131 | 1030024 | Network Slice Replacement charging | eNS_Ph3_CH | 2 | Rel-18 | S5 | 2024-02-02 08:00 | 2024-03-03 17:00 | 100% | SP-240475 |  | Maryse Gardella, MATRIXX Software, | Maryse dot Gardella at Matrixx dot com) | ; 2/4/24: 0%->100 | 32.255; 32.256; 32.291; 32.298 | 103 | 52 |  |  | Thu 14/03/24 | Tue 02/04/24
1132 | 991037 | Network Slicing Phase 3: NR aspects | eNS_Ph3-NR | 1 | Rel-18 | R3 | 2023-03-03 08:00 | 2023-12-12 17:00 | 100% | RP-232793 |  | ZTE |  | 2/1/24: WID:RP-230787->RP-232793 |  | 99 | 50 |  |  | Wed 29/03/23 | Tue 02/01/24
1133 | 991137 | Core part: Network Slicing Phase 3: NR aspects | eNS_Ph3-NR-Core | 2 | Rel-18 | R3 | 2023-03-03 08:00 | 2023-12-12 17:00 | 100% | RP-232793 | RP-232866 | Dapeng Li, ZTE | Li.dapeng@zte.com.cn | ; 7/6/23: Compl:0%->30%; 6/9/23: Compl:30%->70%; WID: RP-230787->RP-231396; Stat Rep: ->RP-231889; Rapporteur: ZTE->Dapeng Li, ZTE; Rap eMail: ->Li.dapeng@zte.com.cn; ; 8/12/23: Compl:70%->100%; Stat Rep: RP-231889->RP-232866; |  | 99 | 50 |  |  | Wed 29/03/23 | Fri 08/12/23
1134 | 940045 | Network slicing provisioning rules | NSRULE | 1 | Rel-18 | S5 | 2021-12-10 08:00 | 2023-12-12 17:00 | 100% | SP-211449 |  | Robert Petersen, Ericsson | robert.petersen@ericsson.com | ; 4/6/22: 0%->35; 12/9/22: 35%->45; 12/9/22: FCD:12/09/2022->06/23; 11/12/22: 45%->55; 17/3/23: 55%->60; 8/6/23: 60%->60; 8/6/23: FCD:09/06/2023->12/24; 7/9/23: 60%->70; 7/9/23: FCD:12/12/2024->12/23; 8/12/23: 70%->100 | 28.531; 28.541 | 94 | 48 |  |  | Fri 10/12/21 | Fri 08/12/23
1135 | 950039 | Study on intent-driven management for network slicing | FS_NETSLICE_IDMS | 1 | Rel-18 | S5 | 2022-03-10 08:00 | 2023-12-12 17:00 | 100% | SP-220278 |  | Jan Groenendijk , Ericsson | Jan.Groenendijk@ericsson.com | 5/4/22: 28.836 added;; 11/9/22: FCD:12/09/2022->06/23; 12/9/22: 0%->40; 12/9/22: FCD:12/06/2023->12/22; 11/12/22: 40%->50; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 50%->85; 8/6/23: FCD:06/06/2023->/23; 7/9/23: 85%->85; 7/9/23: FCD:09/09/2023->12/23; 8/12/23 | 28.836 | 95 | 48 |  |  | Thu 10/03/22 | Fri 08/12/23
1136 | 990030 | Intent driven Management Service for Mobile Network phase 2 | IDMS_MN_ph2 | 1 | Rel-18 | S5 | 2023-03-16 08:00 | 2023-12-12 17:00 | 100% | SP-230180 |  | Xu Ruiyue, Huawei | Xuruiyue@huawei.com | ; 8/6/23: 0%->40; 8/6/23: 40%->; 7/9/23: 40%->75; 8/12/23: 75%->100; 4/1/24: 28.914 added; | 28.312 ; 28.914 | 99 | 50 |  |  | Thu 16/03/23 | Thu 04/01/24
1137 | 910023 | Study on enhanced security for network slicing Phase 2 | FS_eNS2_SEC | 1 | Rel-18 | S3 | 2021-03-18 08:00 | 2021-12-10 17:00 | 100% | SP-210106 |  | Zander Lei, Huawei | lei.zhongding@huawei.com | ; 19/3/21: 0%->10; 9/4/21: FCD:11/06/2021->09/21; 11/6/21: 10%->15; 11/6/21: FCD:Wed 08/09/->12/21; 2/7/21: 33.874 added;; 13/9/21: 15%->30; 13/3/22: Rel-17->Rel-18; 4/6/22: 30%->100 | New ; 33.874 | 91 | 46 |  |  | Thu 18/03/21 | Sat 04/06/22
1138 | 960048 | Study on Media Streaming aspects of Network Slicing Phase 2 | FS_MS_NS_Ph2 | 1 | Rel-18 | S4 | 2022-06-15 08:00 | 2023-12-12 17:00 | 100% | SP-220675 |  | Prakash Kolan, samsung | p.kolan@samsung.com | 3/8/22: 26.941 added; 17/8/22: FS_eNS_Ph3->FS_MS_NS_Ph2; WID:SP-220615->SP-220675; 12/9/22: 0%->15; 11/12/22: 15%->20; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 20%->25; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 25%->40; 7/9/23: 40%->65; 8/12/23: 65%->100 | 26.941 | 96 | 49 |  |  | Fri 03/06/22 | Fri 08/12/23
1139 | 940013 | Enhanced security for Phase 2 network slicing | eNS2_SEC | 1 | Rel-18 | S3 | 2021-12-10 08:00 | 2022-03-11 17:00 | 100% | SP-211361 |  | Lei, Zander, Huawei | lei.zhongding@huawei.com | 12/3/22: 0%->70; 13/3/22: Rel-17->Rel-18; 4/6/22: 70%->100 | 33.501; | 94 | 48 |  |  | Fri 10/12/21 | Sat 04/06/22
1140 | 910022 | Study on Network Slice Capability Exposure for Application Layer Enablement | FS_NSCALE | 1 | Rel-18 | S6 | 2021-03-18 08:00 | 2022-09-12 17:00 | 100% | SP-211509 |  | Zheng, Shaowen, CMCC | zhengshaowen@chinamobile.com | 2/7/21: 23.700-99 added;; 13/9/21: 0%->25; 13/12/21: 25%->55; 13/12/21: FCD:Fri 11/03/->06/22; 13/12/21: WID:SP-210177->SP-211509; 12/3/22: 55%->70; 4/6/22: 70%->85; 12/9/22: 85%->95; 12/9/22: FCD:10/06/2022->09/22; 11/12/22: 95%->100 | 23.700-99 | 91 | 46 |  |  | Thu 18/03/21 | Sun 11/12/22
1141 | 1020049 | Network Slice Capability Exposure for Application Layer Enablement | NSCALE | 1 | Rel-18 |  | 2022-06-02 08:00 | 2024-03-15 17:00 | 100% | SP-220470 |  | Zheng, Shaowen, CMCC | zhengshaowen@chinamobile.com | ; 13/7/22: 23.435 added;; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70; 8/6/23: 70%->100 | 23.434 ; 23.435 | 96 | 49 |  |  | Thu 02/06/22 | Thu 08/06/23
1142 | 960013 | (Stage 2 of NSCALE) Network Slice Capability Exposure for Application Layer Enablement | NSCALE | 2 | Rel-18 | S6 | 2022-06-02 08:00 | 2023-03-03 17:00 | 100% | SP-220470 |  | Zheng, Shaowen, CMCC | zhengshaowen@chinamobile.com | ; 13/7/22: 23.435 added;; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70; 8/6/23: 70%->100 | 23.434 ; 23.435 | 96 | 49 |  |  | Thu 02/06/22 | Thu 08/06/23
1143 | 1020050 | CT1 aspects of NSCALE | NSCALE | 2 | Rel-18 | C1 | 2022-06-02 08:00 | 2024-03-03 17:00 | 100% | CP-233310 |  | Huang Zhenning, China Mobile | huangzhenning@chinamobile.com |  | 24.549 | 96 | 49 |  |  | Thu 02/06/22 | Thu 08/06/23
1144 | 1020006 | CT3 aspects of NSCALE | NSCALE | 2 | Rel-18 | C3 | 2022-06-02 08:00 | 2024-03-03 17:00 | 100% | CP-233310 |  | Huang Zhenning, China Mobile | huangzhenning@chinamobile.com |  | 29.222, 29.520, 29.522, 29.549 | 96 | 49 |  |  | Thu 02/06/22 | Thu 08/06/23
1145 | 1020046 | CT4 aspects of NSCALE | NSCALE | 2 | Rel-18 | C4 | 2022-06-02 08:00 | 2024-03-15 17:00 | 100% | CP-233310 |  | Huang Zhenning, China Mobile | huangzhenning@chinamobile.com |  | 29.536 | 96 | 49 |  |  | Thu 02/06/22 | Thu 08/06/23
1146 | 960005 | Study on new UICC application for network slice-specific authentication and authorization (NSSAA) | FS_NS_Slice-USIM | 1 | Rel-18 | C6 | 2022-06-03 08:00 | 2023-09-09 17:00 | 100% | CP-221186 |  | COLLET, Hervé, Thales | herve.collet@thalesgroup.com | 13/7/22: 31.826 added; | 31.826 | 96 | 49 |  |  | Fri 03/06/22 | Wed 13/07/22
1147 | 900023 | Study on Charging Aspects for Network Slicing Phase 2 | FS_NETSLICE_CH_Ph2 | 1 | Rel-18 | S5 | 2021-01-12 08:00 | 2023-03-03 17:00 | 100% | SP-201082 |  | Matrixx, Gerald Görmer | Gerald dot Goermer at Matrixx dot com | 21/3/21: 0%->15; 13/9/21: 15%->50; 13/9/21: FCD:Fri 10/09/->12/21; 12/3/22: 50%->70; 4/6/22: 70%->75; 4/6/22: FCD:10/12/2021->03/23; 21/6/22: 75%->100. 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->85; 11/12/22: 85... |  | 90 | 46 |  |  | Tue 12/01/21 | Fri 17/03/23
1148 | 980025 | Charging Aspects of Network Slicing Phase 2 | NETSLICE_CH_Ph2 | 1 | Rel-18 | S5 | 2022-12-12 08:00 | 2024-03-03 17:00 | 100% | SP-231448 |  | Gerald Görmer, MATRIXX Software | Gerald dot Goermer at Matrixx dot com | ; 16/3/23: FCD:09/09/2023->12/20; 16/3/23: WID:SP-221159->SP-230176; 17/3/23: 0%->5; 17/3/23: 28.203 added;; 8/6/23: 5%->40; 7/9/23: 40%->50; 8/12/23: 50%->75; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-230176->SP-231448; 14/3/24: 75%->100 | 32.240; 32.290; 32.291; 32.298; 32.297 ; 28.203 | 98 | 50 |  |  | Fri 09/12/22 | Thu 14/03/24
1149 | 1000002 | Enhancement of Network Slicing UICC application for network slice-specific authentication and authorization | eNS_UICC | 1 | Rel-18 | C6 | 2023-06-30 08:00 | 2024-03-03 17:00 | 100% | CP-231351 |  | COLLET, Hervé, Thales | herve.collet@thalesgroup.com | 21/9/23: 31.105 added; | 31.105 | 100 | 51 |  |  | Fri 30/06/23 | Thu 21/09/23
1150 | 0 | Rel-18 eXtended, Augmented and Virtual Reality (XR, AR, VR), immersive | - | 1 | Rel-18 |  | 2019-03-07 07:00 | 2019-03-07 07:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1151 | 981039 | XR (eXtended Reality) enhancements for NR | NR_XR_enh | 1 | Rel-18 |  | 2021-12-13 08:00 | 2024-12-12 17:00 | 91% | RP-232778 |  | Nokia |  | 29/3/23: WID:RP-223502->RP-230786; 2/1/24: WID:RP-230786->RP-232778 |  | 98 | 50 |  |  | Mon 09/01/23 | Tue 02/01/24
1152 | 981139 | Core part: XR (eXtended Reality) enhancements for NR | NR_XR_enh-Core | 2 | Rel-18 | R2 | 2022-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-223502 | RP-232779 | Benoist S bire, Nokia | benoist.sebire@nokia.com | 17/3/23: Compl:0%->10%; Stat Rep: ->RP-230277; Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com; 31/3/23: WID: RP-230786->RP-223502; Stat Rep: RP-230277->RP-230785; ;...; 6/9/23: Compl:45%->68%; Stat Rep: RP-230785->RP-2... |  | 98 | 50 |  |  | Mon 09/01/23 | Fri 08/12/23
1153 | 940087 | Study on XR (eXtended Reality) enhancements for NR | FS_NR_XR_enh | 2 | Rel-18 | R2 | 2021-12-13 08:00 | 2023-03-03 17:00 | 100% | RP-220285 | RP-230276 | Benoist S bire, Nokia | benoist.sebire@nokia.com | TR 38.8xx; basic XR functionality introduced in REL-15 WI NR_newRAT; 22/3/22: Stat Rep: ->RP-220511; 5/4/22: WID:RP-213587->RP-220285 6/6 ; 20/6/22: Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com13/7/22: 38.835 add...;... | 38.835 | 94 | 48 |  |  | Thu 06/01/22 | Fri 17/03/23
1154 | 1030063 | UE Conformance - XR (eXtended Reality) enhancements for NR plus CT1 aspects | NR_XR_enh_plus_CT1-UEConTest | 2 | Rel-18 | R5 | 2024-03-03 08:00 | 2025-12-12 17:00 | 84% | RP-241588 | RP-252018 | Nokia |  | 13/6/24: Compl:0%->5%; Stat Rep: ->RP-240936; ; 23/7/24: WID:RP-240088->RP-241588; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->40%; Stat Rep: RP-240936->RP-241790; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:40%->60%; Stat Rep: RP-241790->RP-242607; ; |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
1155 | 990110 | Architecture Enhancements for XR (Extended Reality) and media service | XRM | 1 | Rel-18 |  | 2021-12-20 08:00 | 2024-03-03 17:00 | 100% | SP-221326 |  | Dan WANG, China Mobile | wangdanyjy@chinamobile.com |  | 23.501; 23.502; 23.503 | 99 | 50 |  |  | Fri 09/12/22 | NA
1156 | 940068 | Study on architecture enhancement for XR and media services | FS_XRM | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-220705 |  | Dan Wang, China Mobile | wangdanyjy@chinamobile.com | 21/1/22: 23.700-60 added;; 12/3/22: 0%->15; 4/6/22: 15%->40; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211646->SP-220705; 12/9/22: 40%->75; 10/12/22: 75%->100 | 23.700-60 | 94 | 48 |  |  | Sun 19/12/21 | Sat 10/12/22
1157 | 980016 | (Stage 2 for XRM) Architecture Enhancements for XR (Extended Reality) and media service | XRM | 2 | Rel-18 | S2 | 2022-12-09 08:00 | 2023-06-06 17:00 | 100% | SP-230092 |  | Dan WANG, China Mobile | wangdanyjy@chinamobile.com | 15/3/23: WID:SP-221326->SP-230092; 15/3/23: 0%->55; 8/6/23: 55%->98; 7/9/23: 98%->100 | 23.501; 23.502; 23.503 | 98 | 50 |  |  | Fri 09/12/22 | Thu 07/09/23
1158 | 1030048 | CT1 aspects of XRM | XRM | 2 | Rel-18 | C1 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240081 |  | Zhennning Huang, China Mobile | huangzhenning@chinamobile.com | 6/6/23: Compl:20%->65%6/6/23: WID: CP-230115->CP-231196; 2/4/24: 0%->98 | 29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564 | 99 | 50 |  |  | Fri 09/12/22 | Tue 02/04/24
1159 | 990006 | CT3 aspects of XRM | XRM | 2 | Rel-18 | C3 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240081 |  | Zhennning Huang, China Mobile | huangzhenning@chinamobile.com | 6/6/23: Compl:20%->65%6/6/23: WID: CP-230115->CP-231196 | 29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564 | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
1160 | 990084 | CT4 aspects of XRM | XRM | 2 | Rel-18 | C4 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240081 |  | Zhennning Huang, China Mobile | huangzhenning@chinamobile.com | 6/6/23: Compl:0%->65%6/6/23: WID: CP-230115->CP-231196 | 29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564 | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
1161 | 950012 | Study on immersive Real-time Communication for WebRTC Phase 2 | FS_eiRTCW | 1 | Rel-18 | S4 | 2022-03-10 08:00 | 2024-03-03 17:00 | 100% | SP-230166 |  | Yoshihiro INOUE, NTT | Yoshihiro.inoue@ntt-at.co.jp | 4/6/22: 0%->10; 17/8/22: FS_iRTCW_Ph2->FS_eiRTCW ; 12/9/22: 10%->30; 16/3/23: WID:SP-220239->SP-230166; 16/3/23: FCD:06/06/2023->3/3/24. Rapporteur changed from Naotaka MORITA, NTT .; 17/3/23: 30%->35; 17/3/23: FCD:03/03/2024->/24; 8/6/23: 35%->45; 7/9... | 26.930 | 95 | 48 |  |  | Thu 10/03/22 | Thu 14/03/24
1162 | 950014 | Immersive Real-time Communication for WebRTC | iRTCW | 1 | Rel-18 | S4 | 2022-03-15 08:00 | 2024-06-06 17:00 | 100% | SP-230977 |  | Kyunghun Jung, Facebook | kyunghun@fb.com | 5/4/22: 26.113 added;; 4/6/22: 0%->5; 12/9/22: 5%->10; 11/12/22: 10%->20; 11/12/22: WID:SP-220241->SP-221032; 17/3/23: 20%->30; 8/6/23: 30%->55; 7/9/23: WID:SP-221032->SP-230977; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 55%->60; 14/3/24: FCD:03/03/2024->/... | 26.113 | 95 | 48 |  |  | Thu 10/03/22 | Thu 13/06/24
1163 | 950013 | Study on Smartly Tethering AR Glasses | FS_SmarTAR | 1 | Rel-18 | S4 | 2022-03-10 08:00 | 2023-06-06 17:00 | 100% | SP-220240 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | ; 5/4/22: 26.806 added;; 4/6/22: 0%->30; 12/9/22: 30%->40; 12/9/22: FCD:10/03/2023->03/23; 11/12/22: 40%->60; 17/3/23: 60%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100 | 26.998 ; 26.806 | 95 | 48 |  |  | Thu 10/03/22 | Thu 08/06/23
1164 | 950015 | Media Capabilities for Augmented Reality | MeCAR | 1 | Rel-18 | S4 | 2022-03-10 08:00 | 2024-03-03 17:00 | 100% | SP-220242 |  | Emmanuel Thomas, Xiaomi | thomase@xiaomi.com | ; 5/4/22: 26.119 added;; 4/6/22: 0%->8; 12/9/22: 8%->15; 11/12/22: 15%->30; 11/12/22: FCD:10/03/2023->12/23; 17/3/23: 30%->40; 8/6/23: 40%->60; 7/9/23: 60%->65; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 65%->80; 8/12/23: FCD:03/03/2024->/2024; 14/3/24: 80%-> | 26.511; 26.117; 26.925; 26.XXX ; 26.119 | 95 | 48 |  |  | Thu 10/03/22 | Thu 14/03/24
1165 | 960042 | IMS-based AR Conversational Services | IBACS | 1 | Rel-18 | S4 | 2022-06-03 08:00 | 2024-06-06 17:00 | 100% | SP-230165 |  | Gunkel, Simon, KPN N.V. | Simon.Gunkel@tno.nl | 3/8/22: 26.264 added; 17/8/22: IMS4AR->IBACS; 17/8/22: WID:SP-220609->SP-220668; 12/9/22: 0%->5; 11/12/22: 5%->15; 11/12/22: FCD:08/12/2023->12/23; 16/3/23: WID:SP-220668->SP-230165; 17/3/23: 15%->20; 8/6/23: 20%->30; 8/6/23: FCD:12/12/2023->03/20; 8/1... | 26.264 | 96 | 49 |  |  | Fri 03/06/22 | Thu 13/06/24
1166 | 960044 | Generic architecture for RT and AR/MR | GA4RTAR | 1 | Rel-18 | S4 | 2022-06-03 08:00 | 2023-06-06 17:00 | 100% | SP-220672 |  | Hakju Ryan Lee, Samsung | hakju00.lee@samsung.com | 17/8/22: GA4RTARMR-> GA4RTAR; 17/8/22: WID:SP-220611->SP-220672; 12/9/22: 0%->25; 11/12/22: 25%->60; 11/12/22: FCD:08/12/2023->03/23; 17/3/23: 60%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100 |  | 96 | 49 |  |  | Fri 03/06/22 | Thu 08/06/23
1167 | 960046 | Real-time Transport Protocol Configurations | 5G_RTP | 1 | Rel-18 | S4 | 2022-06-03 08:00 | 2024-03-03 17:00 | 100% | SP-230541 |  | Igor Curcio, Nokia Corporation | igor.curcio@nokia.com | 3/8/22: 26.522 added; 17/8/22: RTPconfig->5G_RTP; 12/9/22: 0%->3; 11/12/22: 3%->7; 11/12/22: FCD:08/06/2023->/23; 17/3/23: 7%->15; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 15%->35; 8/6/23: FCD:12/12/2023->03/20; 8/6/23: WID:SP-220613->SP-230541; 7/9/23:... | 26.522 | 96 | 49 |  |  | Fri 03/06/22 | Thu 14/03/24
1168 | 830005 | Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 1 | Rel-18 | S4 | 2019-03-07 08:00 | 2024-06-06 17:00 | 100% | SP-190040 |  | Stéphane Ragot, Orange | stephane.ragot@orange.com | 31/5/19: 0%->10; 25/3/20: 10%->15; 5/12/20: 15%->20; 5/12/20: FCD:04/12/2020->12/20. 12/21: Rel-17->Rel-18; 4/6/22: 20%->; 11/12/22: 20%->25; 11/12/22: FCD:02/12/2022->12/23; 17/3/23: 25%->30; 8/6/23: 30%->40; 7/9/23: 40%->50; 7/9/23: FCD:12/12/2023->/... | 26.260; new | 83 | 42 |  |  | Thu 14/03/19 | Thu 13/06/24
1169 | 1030047 | EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 1 | Rel-18 |  | 2017-09-08 08:00 | 2024-06-06 17:00 | 100% | SP-220608 |  | Bin Wang, Huawei Technologies Co Ltd | binbin.wang@huawei.com | 15/12/17: 0%->5¦16/3/18: 5%->10¦7/6/18: 10%->15¦10/9/18: 15%->20¦7/3/19: 20%->25; 31/5/19: 25%->30; 13/9/19: FCD:11/12/2020->06/20; 13/9/19: 30%->26; 6/12/19: 26%->27; 5/12…; 12/21: Rel-17->Rel-18; 4/6/22: 30%->35; 12/9/22: 35%->40; 11/12/22: 40%->45; ... | 26.114; new; 26.258; 26.256; 26.255; 26.254; 26.253; 26.251; 26.252; 26.250; 26.997 | 77 | 39 |  |  | Fri 08/09/17 | Fri 08/12/23
1170 | 770024 | EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 2 | Rel-18 | S4 | 2017-09-08 08:00 | 2024-06-06 17:00 | 100% | SP-220608 |  | Bin Wang, Huawei Technologies Co Ltd | binbin.wang@huawei.com | 15/12/17: 0%->5¦16/3/18: 5%->10¦7/6/18: 10%->15¦10/9/18: 15%->20¦7/3/19: 20%->25; 31/5/19: 25%->30; 13/9/19: FCD:11/12/2020->06/20; 13/9/19: 30%->26; 6/12/19: 26%->27; 5/12…; 12/21: Rel-17->Rel-18; 4/6/22: 30%->35; 12/9/22: 35%->40; 11/12/22: 40%->45; ... | 26.114; new; 26.258; 26.256; 26.255; 26.254; 26.253; 26.251; 26.252; 26.250; 26.997 | 77 | 39 |  |  | Fri 08/09/17 | Thu 13/06/24
1171 | 1030025 | CT3 aspects of IVAS_Codec | IVAS_Codec | 2 | Rel-18 | C3 | 2024-03-03 08:00 | 2024-06-06 17:00 | 100% | CP-240021 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com |  | 23.333, 29.333, 23.334, 29.334, 29.162, 29.238, 29.163, 29.332, 29.292, 29.232, 24.229 | 77 | 39 |  |  | Fri 08/09/17 | Fri 08/12/23
1172 | 1030001 | CT4 aspects of IVAS_Codec | IVAS_Codec | 2 | Rel-18 | C4 | 2024-03-03 08:00 | 2024-06-06 17:00 | 100% | CP-240021 |  | Landais, Bruno, Nokia | bruno.landais@nokia.com |  | 23.333, 29.333, 23.334, 29.334, 29.162, 29.238, 29.163, 29.332, 29.292, 29.232, 24.229 | 77 | 39 |  |  | Fri 08/09/17 | Fri 08/12/23
1173 | 990025 | Immersive Audio for Split Rendering Scenarios | ISAR | 1 | Rel-18 | S4 | 2023-03-16 08:00 | 2024-06-06 17:00 | 100% | SP-231291 |  | Stefan Bruhn, Dolby Laboratories Inc | stefan.bruhn@dolby.com | ; 8/6/23: 0%->10; 8/6/23: 26.566 added;; 8/6/23: 26.866 added;; 8/6/23: 26.865 added;; 7/9/23: 10%->15; 8/12/23: 15%->25; 8/12/23: WID:SP-230167->SP-231291; 14/3/24: 25%->35; 14/3/24: FCD:03/03/2024->/24; 3/4/24: 26.249 added; 26.996 added;; 13/6/24: 35% | 26.119 ; 26.566; 26.866; 26.865; 26.249; 26.996 | 99 | 50 |  |  | Thu 16/03/23 | Thu 13/06/24
1174 | 960045 | Split Rendering Media Service Enabler | SR_MSE | 1 | Rel-18 | S4 | 2022-06-03 08:00 | 2024-06-06 17:00 | 100% | SP-231291 |  | Bouazizi, Imed, Qualcomm Incorporated | bouazizi@qti.qualcomm.com | 3/8/22: 26.565 added;; 17/8/22: WID:SP-220612->SP-220685; 12/9/22: 0%->5; 11/12/22: 5%->15; 11/12/22: FCD:08/12/2023->09/23; 17/3/23: 15%->25; 17/3/23: FCD:09/09/2023->12/23; 8/6/23: 25%->40; 8/6/23: FCD:12/12/2023->03/20; 7/9/23: 40%->50; 8/12/23: 50%... | 26.565 | 96 | 49 |  |  | Fri 03/06/22 | Thu 13/06/24
1175 | 960049 | Study on AR and MR QoE Metrics | FS_ARMRQoE | 1 | Rel-18 | S4 | 2022-06-03 08:00 | 2024-03-03 17:00 | 100% | SP-220708 |  | Shuai Gao, chinaunicom | gaos30@chinaunicom.cn | 13/7/22: 26.812 added;; 17/8/22: WID:SP-220616->SP-220708; 12/9/22: 0%->5; 11/12/22: 5%->10; 17/3/23: 10%->15; 8/6/23: 15%->27; 7/9/23: 27%->50; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 50%->65; 14/3/24: 65%->100 | 26.812 | 96 | 49 |  |  | Fri 03/06/22 | Thu 14/03/24
1176 | 960050 | Study on Audio Aspects for Glasses-type AR/MR Devices | FS_Audio_5GSTAR | 1 | Rel-18 | S4 | 2022-06-03 08:00 | 2022-12-08 17:00 | 100% | SP-220617 |  | Stéphane Ragot, Orange | stephane.ragot@orange.com | 17/8/22: FS_ARMRglass->FS_Audio_5GSTAR; 12/9/22: 0%->5; 11/12/22: 5%->100 | 26.998; | 96 | 49 |  |  | Fri 03/06/22 | Sun 11/12/22
1177 | 0 | Rel-18 Transportations (Railways, V2X) | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1178 | 880036 | Study on Off-Network for Rail | FS_OffNetRail | 1 | Rel-18 | S1 | 2020-06-25 08:00 | 2021-12-10 17:00 | 100% | SP-200572 |  | Guillaume Gach | Ext.gach <at> uic.org | 28/7/20: 22.990 added;; 12/9/20: 0%->10; 5/12/20: 10%->30; 19/3/21: FCD:17/03/2021->12/21; 19/3/21: 30%->50; 13/9/21: 50%->90; 10/12/21: 90%->100 | 22.990 | 88 | 45 |  |  | Thu 25/06/20 | Fri 10/12/21
1179 | 880034 | Study of Interconnection and Migration Aspects for Railways | FS_IRail | 1 | Rel-18 | S6 | 2020-06-25 08:00 | 2021-09-16 17:00 | 100% | SP-200336 |  | Oettl, Martin, Nokia | martin.oettl@nokia.com | 13/9/20: 0%->10; 25/9/20: 23.700-90 added;; 21/3/21: 10%->15; 11/6/21: 15%->30; 13/9/21: 30%->60; 13/12/21: 60%->85; 12/3/22: 85%->100 | 23.700-90 | 88 | 45 |  |  | Fri 26/06/20 | Sat 12/03/22
1180 | 980122 | Interconnection and Migration Aspects for Railways | IRail | 1 | Rel-18 |  | 2022-03-03 08:00 | 2023-12-12 17:00 | 100% | SP-220098 |  | Oettl, Martin, Nokia | martin.oettl@nokia.com |  | 23.280; 23.281; 23.282; 23.379 | 95 | 48 |  |  | Thu 10/03/22 | Mon 12/09/22
1181 | 950025 | Stage 2 of Irail | IRail | 2 | Rel-18 | S6 | 2022-03-03 08:00 | 2022-12-12 17:00 | 100% | SP-220098 |  | Oettl, Martin, Nokia | martin.oettl@nokia.com | ; 4/6/22: 0%->40; 12/9/22: 40%->60; 11/12/22: 60%->75; 17/3/23: 75%->85; 8/6/23: 85%->100 | 23.280; 23.281; 23.282; 23.379 | 95 | 48 |  |  | Sun 11/12/22 | Thu 08/06/23
1182 | 980070 | CT1 aspects of eMCSMI_IRail | eMCSMI_IRail | 2 | Rel-18 | C1 | 2022-12-16 08:00 | 2023-12-12 17:00 | 100% | CP-240270 |  | Won, Sung Hwan, Nokia | sung.won@nokia.com | 6/6/23: Compl:10%->15% | 24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482; 24.281; 24.581; 24.582; 29.283 | 95 | 48 |  |  | Thu 10/03/22 | Tue 06/06/23
1183 | 980071 | deleted - CT4 aspects of eMCSMI_IRail | eMCSMI_IRail | 2 | Rel-18 | C4 | 2022-12-16 08:00 | 2023-12-12 17:00 | 100% | CP-240270 |  | Won, Sung Hwan, Nokia | sung.won@nokia.com | 2/4/24: deleted at 100% | 24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482; 24.281; 24.581; 24.582; 29.283 | 95 | 48 |  |  | Thu 10/03/22 | Tue 02/04/24
1184 | 900026 | Study on FRMCS Phase 4 | FS_FRMCS_Ph4 | 1 | Rel-18 | S1 | 2020-12-04 08:00 | 2021-12-10 17:00 | 100% | SP-220436 |  | Guillaume Gach; UIC | Guillaume Gach; gach <at> uic.org | 22.989 ; 19/3/21: FCD:12/09/2021->12/21; 19/3/21: 0%->20; 13/9/21: 20%->80; 10/12/21: 80%->100; 21/6/22: WID:SP-201038->SP-220436. FS_eFRMCS -> FS_FRMCS_Ph4 |  | 90 | 46 |  |  | Fri 04/12/20 | Tue 21/06/22
1185 | 930014 | Study on enhancements to application layer support for V2X services; Phase 2 | FS_eV2XAPP2 | 1 | Rel-18 | S6 | 2021-09-13 08:00 | 2022-09-12 17:00 | 100% | SP-220466 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | 13/12/21: 0%->30; 22/3/22: 23.700-64 added;; 4/6/22: 30%->65; 4/6/22: FCD:10/06/2022->09/22; 4/6/22: WID:SP-210956->SP-220466; 12/9/22: 65%->85; 11/12/22: 85%->100 | 23.700-64 | 93 | 47 |  |  | Mon 13/09/21 | Sun 11/12/22
1186 | 980125 | Application layer support for V2X services; Phase 3 | V2XAPP_Ph3 | 1 | Rel-18 |  | 2022-09-09 08:00 | 2024-03-03 17:00 | 100% | SP-220916 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com |  | 23.286; 23.434 | 97 | 49 |  |  | Sun 11/09/22 | NA
1187 | 970039 | Stage 2 of V2XAPP_Ph3 | V2XAPP_Ph3 | 2 | Rel-18 | S6 | 2022-09-09 08:00 | 2023-06-06 17:00 | 100% | SP-221229 |  | Niranth Amogh, Huawei Telecommunications India | namogh@huawei.com | ; 11/12/22: 0%->45; 9/1/23: WID:SP-220916->SP-221229; 17/3/23: 45%->75; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 75%->100 | 23.286; 23.434 | 97 | 49 |  |  | Sun 11/12/22 | Thu 08/06/23
1188 | 980072 | CT1 aspects of V2XAPP_Ph3 | V2XAPP_Ph3 | 2 | Rel-18 | C1 | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-233214 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com | 6/6/23: Compl:0%->20%; 30/6/23: WID:CP-223107->CP-231285 | 24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549; 29.486; 24.549; 29.558 | 97 | 49 |  |  | Sun 11/09/22 | Fri 30/06/23
1189 | 980073 | CT3 aspects of V2XAPP_Ph3 | V2XAPP_Ph3 | 2 | Rel-18 | C3 | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-233214 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  | 24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549; 29.486; 24.549; 29.558 | 97 | 49 |  |  | Sun 11/09/22 | NA
1190 | 1000043 | MBS support for V2X services | TEI18_MBS4V2X | 1 | Rel-18 |  | 2022-09-12 08:00 | 2024-03-03 17:00 | 100% | SP-220793 |  | LaeYoung Kim (LG Electronics), | laeyoung.kim@lge.com | ; 22/3/23: 0%->100 | 23.287; 23.501 | 97 | 49 |  |  | Sun 11/09/22 | Wed 22/03/23
1191 | 970003 | (Stage 2 of) MBS support for V2X services | TEI18_MBS4V2X | 2 | Rel-18 | S2 | 2022-09-12 08:00 | 2023-03-03 17:00 | 100% | SP-220793 |  | LaeYoung Kim (LG Electronics), | laeyoung.kim@lge.com | ; 22/3/23: 0%->100 | 23.287; 23.501 | 97 | 49 |  |  | Sun 11/09/22 | Wed 22/03/23
1192 | 1000022 | CT1 aspects of MBS support for V2X services | TEI18_MBS4V2X | 2 | Rel-18 | C1 | 2023-06-07 08:00 | 2024-03-03 17:00 | 100% | CP-231357 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  | 24.587; 24.588; 31.102 | 100 | 51 |  |  | Wed 07/06/23 | NA
1193 | 1010021 | CT6 aspects of MBS support for V2X services | TEI18_MBS4V2X | 2 | Rel-18 | C6 | 2023-06-07 08:00 | 2024-03-03 17:00 | 100% | CP-231357 |  | Herrero Veron, Christian (Huawei) | Christian.Herrero at huawei.com |  | 24.587; 24.588; 31.102 | 101 | 51 |  |  | Wed 07/06/23 | NA
1194 | 950079 | Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | NR_HST_FR2_enh | 1 | Rel-18 |  | 2022-03-15 08:00 | 2024-12-12 17:00 | 75% | RP-222272 |  | Samsung |  | compare REL-17 WI NR_HST_FR2 ; 23/9/22: WID:RP-220985->RP-222272 |  | 95 | 48 |  |  | Tue 05/04/22 | Fri 23/09/22
1195 | 950179 | Core part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | NR_HST_FR2_enh-Core | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2023-09-08 17:00 | 100% | RP-222272 | RP- 241272 | WANG, He (Jackson), Samsung | h0809.wang@samsung.com | compare REL-17 WI NR_HST_FR2 ; 6/6/22: CD:15/09/2023->23/09/2022 ; 6/6/22: Stat Rep: ->RP-221405; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/202... |  | 95 | 48 |  |  | Tue 05/04/22 | Thu 13/06/24
1196 | 950279 | Perf. part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | NR_HST_FR2_enh-Perf | 2 | Rel-18 | R4 | 2022-03-16 08:00 | 2024-06-06 17:00 | 100% | RP-222272 | RP- 241272 | WANG, He (Jackson), Samsung | h0809.wang@samsung.com | 6/6/22: CD:15/03/2024->24/03/2023 6/6/22: Stat Rep: ->RP-221405; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com13/7/22: FCD:24/03/2023->03/20 ; ...; 9/12/22: FCD:24/03/2023->01/03/2024; Stat Rep: RP-... |  | 95 | 48 |  |  | Tue 05/04/22 | Thu 13/06/24
1197 | 1030071 | UE Conformance - Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | NR_HST_FR2_enh-UEConTest | 2 | Rel-18 | R5 | 2024-03-03 08:00 | 2025-12-12 17:00 | 38% | RP-240371 | RP-252078 | Samsung |  | 13/6/24: Compl:0%->5%; Stat Rep: ->RP-241278; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->36%; Stat Rep: RP-241278->RP-241981; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:36%->38%; Stat Rep: RP-241981->RP-242595; ; 6/3/25: FCD:28/05/2025->12/12/2025; |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
1198 | 0 | Rel-18 User Plane traffic and services | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1199 | 920036 | Evolution of IMS Multimedia Telephony Service | eMMTEL | 1 | Rel-18 |  | 2019-09-19 08:00 | 2025-12-12 17:00 | 99% | SP-210519 |  | Hu Yue, China Mobile | huyueyjy@chinamobile.com |  | 22.261;22.173 | 92 | 47 |  |  | Fri 11/06/21 | NA
1200 | 850042 | Study on evolution of IMS multimedia telephony service | FS_MMTELin5G | 2 | Rel-18 | S1 | 2019-09-19 08:00 | 2021-09-08 17:00 | 100% | SP-190836 |  | Yan Di, China Mobile | yandi@chinamobile.com | ; 8/10/19: 22.873 added;; 6/12/19: 0%->10; 12/9/20: 10%->15; 5/12/20: 15%->40; 19/3/21: 40%->75; 19/3/21: FCD:11/12/2020->09/21; 11/6/21: 75%->95; 13/9/21: 95%->100 | New ; 22.873 | 85 | 43 |  |  | Fri 13/09/19 | Mon 13/09/21
1201 | 920029 | Stage 1 of Evolution of IMS Multimedia Telephony Service | eMMTEL | 2 | Rel-18 | S1 | 2021-06-11 08:00 | 2021-12-10 17:00 | 100% | SP-210519 |  | Hu Yue, China Mobile | huyueyjy@chinamobile.com | ; 13/9/21: 0%->100 | 22.261;22.173 | 92 | 47 |  |  | Fri 11/06/21 | Mon 13/09/21
1202 | 940066 | Study on system architecture for next generation real time communication services | FS_NG_RTC | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2023-03-03 17:00 | 100% | SP-220288 |  | Yi Jiang | jiangyi at chinamobile dot com | 21/1/22: 23.700-87 added;; 12/3/22: 0%->20; 5/4/22: WID:SP-211644->SP-220288; 4/6/22: 20%->55; 12/9/22: 55%->79; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 79%->85; 15/3/23: 85%->100; 16/3/23: FCD:12/12/2022->/23 | 23.700-87 | 94 | 48 |  |  | Sun 19/12/21 | Thu 16/03/23
1203 | 970014 | System architecture for Next Generation Real time Communication services | NG_RTC | 2 | Rel-18 | S2 | 2022-09-12 08:00 | 2023-06-06 17:00 | 100% | SP-230098 |  | Yi Jiang, China Mobile | jiangyi at chinamobile dot com | ; 15/3/23: WID:SP-220804->SP-230098; 15/3/23: 0%->60; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100 | 23.228; 23.502 | 97 | 49 |  |  | Sun 11/09/22 | Thu 08/06/23
1204 | 990023 | CT1 aspects of NG_RTC | NG_RTC | 2 | Rel-18 | C1 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240271 |  | Chen Xu, China Mobile | chenxu@chinamobile.com | ; 31/3/23: 24.186 added;6/6/23: Compl:0%->15% | 24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 24.186 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1205 | 990086 | CT3 aspects of NG_RTC | NG_RTC | 2 | Rel-18 | C3 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240271 |  | Chen Xu, China Mobile | chenxu@chinamobile.com |  | 24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333 | 97 | 49 |  |  | Sun 11/09/22 | NA
1206 | 990087 | CT4 aspects of NG_RTC | NG_RTC | 2 | Rel-18 | C4 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240271 |  | Chen Xu, China Mobile | chenxu@chinamobile.com | ; 31/3/23: 29.176 added;; 31/3/23: 29.175 added;6/6/23: Compl:0%->25%; 4/1/24: 29.330 added; | 24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 29.176; 29.175; 29.330 | 97 | 49 |  |  | Sun 11/09/22 | Thu 04/01/24
1207 | 1030027 | CT6 aspects of NG_RTC | NG_RTC | 2 | Rel-18 | C6 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240271 |  | Chen Xu, China Mobile | chenxu@chinamobile.com | ; 31/3/23: 29.176 added;; 31/3/23: 29.175 added;6/6/23: Compl:0%->25%; 4/1/24: 29.330 added; | 24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 29.176; 29.175; 29.330 | 97 | 49 |  |  | Sun 11/09/22 | Thu 04/01/24
1208 | 960032 | Study on security support for Next Generation Real Time Communication services | FS_NG_RTC_SEC | 2 | Rel-18 | S3 | 2022-06-02 08:00 | 2023-06-06 17:00 | 100% | SP-220530 |  | Fei, Li, Huawei | Austin.lifei@huawei.com | 13/7/22: 33.890 added;; 12/9/22: 0%->40; 11/12/22: 40%->70; 17/3/23: 70%->90; 8/6/23: 90%->100 | 33.890 | 96 | 49 |  |  | Thu 02/06/22 | Thu 08/06/23
1209 | 990038 | Security support for Next Generation Real Time Communication services | NG_RTC_SEC | 2 | Rel-18 | S3 | 2023-03-16 08:00 | 2023-09-09 17:00 | 100% | SP-230151 |  | Fei, Li, Huawei | Austin.lifei@huawei.com | ; 15/3/24: 0%->100 | 33.328 | 99 | 50 |  |  | Thu 16/03/23 | Fri 15/03/24
1210 | 1050133 | UE Conformance - IMS Data Channel for NG RTC (Real Time Communication) | NG_RTC_IMS_dataCH-UEConTest | 2 | Rel-18 | R5 | 2024-09-09 08:00 | 2025-12-12 17:00 | 99% | RP-242078 | RP-252648 | Huawei |  | 6/12/24: Compl:0%->5%; Stat Rep: ->RP-243093; ; 6/3/25: FCD:24/07/2025->12/12/2025; Compl:5%->21%; Stat Rep: RP-243093->RP-250451; ; 6/6/25: Compl:21%->71%; Stat Rep: RP-250451->RP-251491; ; 11/9/25: Compl:71%->99%; Stat Rep: RP-251491->RP-252648; |  | 105 | 53 |  |  | Thu 26/09/24 | Thu 11/09/25
1211 | 1000008 | Charging Aspects of IMS Data Channel | IDC_CH | 1 | Rel-18 | S5 | 2023-06-08 08:00 | 2024-03-03 17:00 | 100% | SP-230621 |  | Chen, Ai, China Mobile, | chenai at chinamobile dot com | ; 8/12/23: 0%->40; 14/3/24: 40%->100 | 32.260; 32.255; 32.291; 32.298 | 100 | 51 |  |  | Thu 08/06/23 | Thu 14/03/24
1212 | 990111 | Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 3 | ATSSS_Ph3 | 1 | Rel-18 |  | 2021-12-20 08:00 | 2026-03-03 17:00 | 90% | SP-221334 |  | Apostolis Salkintzis, Lenovo | y1026c@lenovo.com | ; 9/1/23: WID:SP-220813->SP-221334 | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Sun 11/09/22 | Mon 09/01/23
1213 | 940070 | Study on Access Traffic Steering, Switching and Splitting support in the 5G system architecture; Phase 3 | FS_ATSSS_Ph3 | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-211612 |  | Salkintzis, Apostolis, Lenovo, | y1026c@lenovo.com | 21/1/22: 23.700-53 added;; 12/3/22: 0%->20; 4/6/22: 20%->70; 12/9/22: 70%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100 | 23.700-53 | 94 | 48 |  |  | Sun 19/12/21 | Sat 10/12/22
1214 | 970023 | Stage 2 of ATSSS_Ph3 | ATSSS_Ph3 | 2 | Rel-18 | S2 | 2022-09-12 08:00 | 2023-06-06 17:00 | 100% | SP-221334 |  | Apostolis Salkintzis, Lenovo | y1026c@lenovo.com | ; 9/1/23: WID:SP-220813->SP-221334; 15/3/23: 0%->85; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 85%->100 | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Sun 11/09/22 | Thu 08/06/23
1215 | 990021 | CT1 aspects of ATSSS_Ph3 | ATSSS_Ph3 | 2 | Rel-18 | C1 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-230334 |  | Atarius, Roozbeh, Lenovo | ratarius@motorola.com | 6/6/23: Compl:0%->50% | 24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1216 | 990089 | CT3 aspects of ATSSS_Ph3 | ATSSS_Ph3 | 2 | Rel-18 | C3 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-230334 |  | Atarius, Roozbeh, Lenovo | ratarius@motorola.com | 9/6/23: 0%->60 | 24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510 | 97 | 49 |  |  | Sun 11/09/22 | Fri 09/06/23
1217 | 990090 | CT4 aspects of ATSSS_Ph3 | ATSSS_Ph3 | 2 | Rel-18 | C4 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-230334 |  | Atarius, Roozbeh, Lenovo | ratarius@motorola.com | 6/6/23: Compl:5%->50% | 24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1218 | 1070061 | UE Conformance - Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 3 | ATSSS_Ph3-UEConTest | 2 | Rel-18 | R5 | 2025-03-03 08:00 | 2026-03-03 17:00 | 59% | RP-250067 | RP-251997 | China Telecom |  | 6/6/25: Compl:0%->5%; Stat Rep: ->RP-250896; ; 11/9/25: Compl:5%->59%; Stat Rep: RP-250896->RP-251997; |  | 107 | 54 |  |  | Wed 26/03/25 | Thu 11/09/25
1219 | 940076 | Study on UPF enhancement for Exposure And SBA | FS_UPEAS | 1 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-220417 |  | Yan Han, China Mobile | hanyan@chinamobile.com | 21/1/22: 23.700-62 added;; 12/3/22: 0%->20; 4/6/22: 20%->60; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211652->SP-220417; 12/9/22: 60%->80; 10/12/22: 80%->98; 15/3/23: 98%->100 | 23.700-62 | 94 | 48 |  |  | Sun 19/12/21 | Wed 15/03/23
1220 | 990112 | UPF enhancement for Exposure and SBA | UPEAS | 1 | Rel-18 |  | 2022-09-12 08:00 | 2024-03-03 17:00 | 100% | SP-220809 |  | Yan Han, China Mobile | hanyan@chinamobile.com | ; 10/12/22: 0%->20 | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Sun 11/09/22 | Sat 10/12/22
1221 | 970019 | Stage 2 of UPEAS | UPEAS | 2 | Rel-18 | S2 | 2022-09-12 08:00 | 2023-06-06 17:00 | 100% | SP-230103 |  | Yan Han, China Mobile | hanyan@chinamobile.com | ; 10/12/22: 0%->20; 15/3/23: WID:SP-220809->SP-230103; 15/3/23: 20%->75; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 75%->100 | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Sun 11/09/22 | Thu 08/06/23
1222 | 990002 | CT4 aspects of UPF enhancement for exposure and SBA | UPEAS | 2 | Rel-18 | C4 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240022 |  | Rong Wang, China Mobile | wangrongyjy@chinamobile.com | 17/3/23: 10%->406/6/23: Compl:40%->70% | 29.510.29.564.29.244.29.571.29.508.29.522.29.512.29.513.29.514.29.565.29.574.29.575.29.552 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1223 | 990092 | CT3 aspects of UPF enhancement for exposure and SBA | UPEAS | 2 | Rel-18 | C3 | 2023-04-18 08:00 | 2024-03-03 17:00 | 100% | CP-240022 |  | Rong Wang, China Mobile | wangrongyjy@chinamobile.com | 9/6/23: 0%->90 | 29.510.29.564.29.244.29.571.29.508.29.522.29.512.29.513.29.514.29.565.29.574.29.575.29.552 | 97 | 49 |  |  | Sun 11/09/22 | Fri 09/06/23
1224 | 930027 | Tactile and multi-modality communication services | TACMM | 1 | Rel-18 |  | 2020-12-04 08:00 | 2021-12-10 17:00 | 100% | SP-211053 |  | Xiaonan Shi, CMCC | shixiaonan@chinamobile.com |  | 22.261 | 93 | 47 |  |  | Fri 10/09/21 | NA
1225 | 900027 | Study on TACMM | FS_TACMM | 2 | Rel-18 | S1 | 2020-12-04 08:00 | 2021-06-11 17:00 | 100% | SP-210209 |  | Shi, Xiaonan, China Mobile | shixiaonan@chinamobile.com | 10/2/21: 22.847 added;; 19/3/21: 0%->30; 11/6/21: 30%->40; 13/9/21: 40%->85; 14/9/21: WID:SP-201039->SP-210209; 10/12/21: 85%->100 | 22.847 | 90 | 46 |  |  | Fri 04/12/20 | Fri 10/12/21
1226 | 930020 | Stage 1 of TACMM | TACMM | 2 | Rel-18 | S1 | 2021-09-10 08:00 | 2021-12-10 17:00 | 100% | SP-211053 |  | Xiaonan Shi, CMCC | shixiaonan@chinamobile.com | ; 10/12/21: 0%->100 | 22.261 | 93 | 47 |  |  | Fri 10/09/21 | Fri 10/12/21
1227 | 0 | Rel-18 Edge computing | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1228 | 980132 | Architecture for enabling Edge Applications Phase 2 | EDGEAPP_Ph2 | 1 | Rel-18 |  | 2022-09-09 08:00 | 2023-12-12 17:00 | 100% | SP-221231 |  | Sapan Shah, Samsung | sapan.shah@samsung.com |  |  | 97 | 49 |  |  | Sun 11/09/22 | Mon 12/09/22
1229 | 970040 | (Stage 2 of EDGEAPP_Ph2) Architecture for enabling Edge Applications Phase 2 | EDGEAPP_Ph2 | 2 | Rel-18 | S6 | 2022-09-09 08:00 | 2023-03-03 17:00 | 100% | SP-221231 |  | Sapan Shah, Samsung | sapan.shah@samsung.com | ; 12/9/22: 0%->5; 11/12/22: 0%->30; 9/1/23: WID:SP-220917->SP-221231; 17/3/23: 30%->70; 8/6/23: 70%->100 | 23.558; 23.958 | 97 | 49 |  |  | Sun 11/12/22 | Thu 08/06/23
1230 | 980074 | CT1 aspects of EDGEAPP_Ph2 | EDGEAPP_Ph2 | 2 | Rel-18 | C1 | 2022-12-15 08:00 | 2023-12-12 17:00 | 100% | CP-233114 |  | Narendranath Durga Tangudu | n.tangudu@samsung.com | ; 6/6/23: Compl:5%->40%; 6/6/23: WID: CP-223207->CP-231197 | 24.558; 29.558; 29.222 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1231 | 980075 | CT3 aspects of EDGEAPP_Ph2 | EDGEAPP_Ph2 | 2 | Rel-18 | C3 | 2022-12-15 08:00 | 2023-12-12 17:00 | 100% | CP-233114 |  | Narendranath Durga Tangudu | n.tangudu@samsung.com | ; 6/6/23: Compl:10%->40%; 6/6/23: WID: CP-223207->CP-231197 | 24.558; 29.558; 29.222 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1232 | 960011 | Edge Application Standards in 3GPP and alignment with External Organizations | EDGEAPP_EXT | 1 | Rel-18 | S6 | 2022-06-02 08:00 | 2023-12-12 17:00 | 100% | SP-220990 |  | Meghashree Dattatri Kedalagudde, Intel | meghashree.dattatri.kedalagudde@intel.com | 13/7/22: 23.958 added;; 12/9/22: 0%->5; 12/9/22: WID:SP-220468->SP-220912; 17/3/23: 5%->10; 8/6/23: 10%->50; 7/9/23: 50%->65; 13/9/23: FCD:06/06/2023->12/20; 13/9/23: WID:SP-220990->SP-231156; 15/3/24: 65%->98; 13/6/24: 98%->100; 13/6/24: WID:SP-231156->S | 23.958 | 96 | 49 |  |  | Thu 02/06/22 | Thu 13/06/24
1233 | 920017 | Study on enhanced architecture for enabling Edge Applications | FS_eEDGEAPP | 1 | Rel-18 | S6 | 2021-06-11 08:00 | 2022-06-10 17:00 | 100% | SP-211510 |  | Gupta, Nishant, Samsung | nishant.gup@samsung.com | 2/7/21: 23.700-98 added;; 13/9/21: 0%->10; 13/12/21: 10%->45; 13/12/21: WID:SP-210479->SP-211510; 13/12/21: FCD:Fri 11/03/->06/22; 12/3/22: 45%->55; 4/6/22: 55%->75; 12/9/22: 75%->90; 11/12/22: 90%->100 | 23.700-98 | 92 | 47 |  |  | Fri 11/06/21 | Sun 11/12/22
1234 | 980123 | Edge Computing Phase 2 | FS_EDGE_Ph2 | 1 | Rel-18 |  | 2021-12-20 08:00 | 2024-06-06 17:00 | 100% |  |  | Patrice Hédé, Huawei Technologies | patrice dot hede at huawei dot com | 21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070 | 23.700-48 | 95 | 48 |  |  | Sun 11/12/22 | NA
1235 | 950049 | Study on Edge Computing phase 2 | FS_EDGE_Ph2 | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-220070 |  | Patrice Hédé, Huawei Technologies | patrice dot hede at huawei dot com | 21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070 | 23.700-48 | 95 | 48 |  |  | Sun 19/12/21 | Sat 12/03/22
1236 | 940059 | Study on Stage 2 of Edge Computing phase 2 | FS_EDGE_Ph2 | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-220352 |  | Patrice Hédé, Huawei Technologies | patrice dot hede at huawei dot com | 21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070; 4/6/22: 13%->55; 12/9/22: 55%->83; 10/12/22: 83%->100 | 23.700-48 | 94 | 48 |  |  | Sun 19/12/21 | Sat 10/12/22
1237 | 950023 | Study on Security of Edge Computing phase 2 | FS_EDGE_Ph2 | 2 | Rel-18 | S3 | 2022-03-10 08:00 | 2022-12-12 17:00 | 100% | SP-220201 |  | Bo Zhang, Huawei | zhangbo6@huawei.com | 4/6/22: 0%->30; 13/7/22: 33.739 added;; 12/9/22: 30%->40; 11/12/22: 40%->70; 17/3/23: 70%->80; 8/6/23: 80%->90; 15/3/24: 90%->100 | 33.739 | 95 | 48 |  |  | Thu 10/03/22 | Fri 15/03/24
1238 | 970026 | (stage 2 of) Edge Computing Phase 2 | EDGE_Ph2 | 2 | Rel-18 | S2 | 2022-09-23 08:00 | 2023-06-06 17:00 | 100% | SP-230112 |  | Patrice Hédé, Huawei Technologies | patrice dot hede at huawei dot com | ; 10/12/22: 0%->15; 9/1/23: WID:SP-220987->SP-221337; 15/3/23: WID:SP-221337->SP-230112; 15/3/23: 15%->80; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 80%->100 | 23.548; 23.501; 23.502; 23.503 | 97 | 49 |  |  | Sun 11/09/22 | Thu 08/06/23
1239 | 1040038 | CT1 aspects of EDGE_Ph2 | EDGE_Ph2 | 2 | Rel-18 | C1 | 2022-12-16 08:00 | 2024-06-06 17:00 | 100% | CP-241027 |  | Qi Caixia, Huawei | caixia.qi@huawei.com | 9/6/23: 30%->35 | 29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519 | 97 | 49 |  |  | Sun 11/09/22 | Fri 09/06/23
1240 | 980076 | CT3 aspects of EDGE_Ph2 | EDGE_Ph2 | 2 | Rel-18 | C3 | 2022-12-16 08:00 | 2024-06-06 17:00 | 100% | CP-241027 |  | Qi Caixia, Huawei | caixia.qi@huawei.com | 9/6/23: 30%->35 | 29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519 | 97 | 49 |  |  | Sun 11/09/22 | Fri 09/06/23
1241 | 980077 | CT4 aspects of EDGE_Ph2 | EDGE_Ph2 | 2 | Rel-18 | C4 | 2022-12-16 08:00 | 2024-06-06 17:00 | 100% | CP-241027 |  | Qi Caixia, Huawei | caixia.qi@huawei.com | ; 6/6/23: Compl:20%->45%; 16/7/24: WID:CP-233026->CP-241027 | 29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519 | 97 | 49 |  |  | Sun 11/09/22 | Tue 16/07/24
1242 | 990039 | Security Aspects of Support for Edge Computing in 5GC phase 2 | EDGE_Ph2 | 2 | Rel-18 | S3 | 2023-03-16 08:00 | 2023-09-09 17:00 | 100% | SP-230366 |  | Bo Zhang, Huawei Technologies | zhangbo6@huawei.com | 31/3/23: WID:SP-230152->SP-230366; 7/9/23: 0%->95; 15/3/24: 95%->100 | 33.558; 33.501 | 99 | 50 |  |  | Thu 16/03/23 | Fri 15/03/24
1243 | 0 | Rel-18 Non-Public Networks | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1244 | 920038 | 5G Networks Providing Access to Localized Services | PALS | 1 | Rel-18 |  | 2020-09-16 08:00 | 2021-09-08 17:00 | 100% | SP-210522 |  | Lola Awoniyi-Oteri, qualcomm | oawoniyi@qti.qualcomm.com |  | 22.261 | 92 | 47 |  |  | Fri 11/06/21 | NA
1245 | 890023 | Study on PALS | FS_PALS | 2 | Rel-18 | S1 | 2020-09-16 08:00 | 2021-06-11 17:00 | 100% | SP-200799 |  | Jack Nasielski | jackn <at> qti.qualcomm.com | 5/12/20: 0%->35; 19/3/21: 35%->77; 11/6/21: 77%->95; 13/9/21: 95%->100 | 22.844 | 89 | 45 |  |  | Thu 10/09/20 | Mon 13/09/21
1246 | 920031 | Stage 1 of PALS | PALS | 2 | Rel-18 | S1 | 2021-06-11 08:00 | 2021-09-08 17:00 | 100% | SP-210588 |  | Lola Awoniyi-Oteri, qualcomm | oawoniyi@qti.qualcomm.com | ; 10/12/21: 0%->100 | 22.261 | 92 | 47 |  |  | Fri 11/06/21 | Fri 10/12/21
1247 | 980128 | Non-Public Networks Phase 2 | eNPN_Ph2 | 1 | Rel-18 |  | 2021-12-13 08:00 | 2025-12-12 17:00 | 91% | SP-220805 |  | Hedman, Peter, Ericsson | peter . hedman @ ericsson . com | ; 10/12/22: 0%->50 | 23.501; 23.502; 23.402 | 97 | 49 |  |  | Sun 11/09/22 | Sat 10/12/22
1248 | 940075 | Study on enhanced support of Non-Public Networks phase 2 | FS_eNPN_Ph2 | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-220418 |  | Hedman, Peter, Ericsson | peter . hedman @ ericsson . com | 21/1/22: 23.700-08 added;; 12/3/22: 0%->10; 4/6/22: 10%->50; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211656->SP-220418; 12/9/22: 50%->75; 12/9/22: FCD:12/12/2022->12/22; 10/12/22: 75%->98; 15/3/23: 98%->100 | 23.700-08 | 94 | 48 |  |  | Sun 19/12/21 | Wed 15/03/23
1249 | 970015 | Stage 2 of Non-Public Networks Phase 2 | eNPN_Ph2 | 2 | Rel-18 | S2 | 2022-09-12 08:00 | 2023-06-06 17:00 | 100% | SP-230096 |  | Hedman, Peter, Ericsson | peter . hedman @ ericsson . com | ; 10/12/22: 0%->50; 9/1/23: WID:SP-220805->SP-221340; 15/3/23: 50%->90; 15/3/23: WID:SP-221340->SP-230096; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 90%->100 | 23.501; 23.502; 23.402 | 97 | 49 |  |  | Sun 11/09/22 | Thu 08/06/23
1250 | 960033 | Study on security aspects of enhanced support of Non-Public Networks phase 2 | FS_eNPN_Ph2_SEC | 2 | Rel-18 | S3 | 2022-06-02 08:00 | 2023-03-03 17:00 | 100% | SP-220531 |  | Jost, Christine, Ericsson, | (christine.jost@ericsson.com) | 13/7/22: 33.858 added;; 12/9/22: 0%->10; 11/12/22: 10%->60; 17/3/23: 60%->78; 8/6/23: 78%->99; 15/3/24: 99%->100 | 33.858 | 96 | 49 |  |  | Thu 02/06/22 | Fri 15/03/24
1251 | 990043 | Security aspects of support of Non-Public Networks phase 2 | eNPN_Ph2 | 2 | Rel-18 | S3 | 2023-03-16 08:00 | 2023-09-09 17:00 | 100% | SP-230156 |  | Jost, Christine, Ericsson | christine.jost@ericsson.com | ; 8/6/23: 0%->65; 7/9/23: 65%->90; 14/3/24: 90%->100 | 33.501 | 99 | 50 |  |  | Thu 16/03/23 | Thu 14/03/24
1252 | 980078 | CT1 aspects of eNPN_Ph2 | eNPN_Ph2 | 2 | Rel-18 | C1 | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-231286 |  | Sedlacek, Ivo, Ericsson | ivo <dot> sedlacek <at> ericsson <dot> com | ; 6/6/23: Compl:33%->60%; 30/6/23: WID:CP-223104->CP-231286 | 23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550 | 97 | 49 |  |  | Sun 11/09/22 | Fri 30/06/23
1253 | 980079 | CT3 aspects of eNPN_Ph2 | eNPN_Ph2 | 2 | Rel-18 | C3 | 2022-12-15 08:00 | 2024-03-03 17:00 | 100% | CP-231286 |  | Sedlacek, Ivo, Ericsson | ivo <dot> sedlacek <at> ericsson <dot> com | ; 9/6/23: 30%->60 | 23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550 | 97 | 49 |  |  | Sun 11/09/22 | Fri 09/06/23
1254 | 980080 | CT4 aspects of eNPN_Ph2 | eNPN_Ph2 | 2 | Rel-18 | C4 | 2022-12-15 08:00 | 2024-03-03 17:00 | 100% | CP-231286 |  | Sedlacek, Ivo, Ericsson | ivo <dot> sedlacek <at> ericsson <dot> com | ; 6/6/23: Compl:50%->65% | 23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1255 | 940043 | Study on Charging Aspects for Enhanced Support of Non-Public Networks | FS_eNPN_CH | 2 | Rel-18 | S5 | 2021-12-13 08:00 | 2023-03-03 17:00 | 100% | SP-211447 |  | Chen, Ai, China Mobile | chenai@chinamobile.com | 7/1/22: 28.828 added;; 12/9/22: 0%->60; 11/12/22: 60%->75; 17/3/23: 75%->100 | 28.828 | 94 | 48 |  |  | Mon 13/12/21 | Fri 17/03/23
1256 | 990028 | Charging Aspects for Enhanced Support of Non-Public Networks | eNPN_CH | 2 | Rel-18 | S5 | 2023-03-16 08:00 | 2024-03-03 17:00 | 100% | SP-230177 |  | Chen, Ai, China Mobile | chenai at chinamobile dot com | ; 8/6/23: 0%->10; 7/9/23: 10%->30; 8/12/23: 30%->65; 14/3/24: 65%->100 | 32.255; 32.256; 28.203; 32.291; 32.298 | 99 | 50 |  |  | Thu 16/03/23 | Thu 14/03/24
1257 | 991138 | Core part: Non-Public Networks Phase 2: NG-RAN aspects | eNPN_Ph2-NGRAN-Core | 2 | Rel-18 | R3 | 2023-03-06 08:00 | 2023-12-12 17:00 | 100% | RP-233569 | RP-233567 | Shengnan Liu, China Telecom | liushn@chinatelecom.cn | ; 7/6/23: Compl:0%->97%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:97%->100%; WID: RP-230788->RP-231185; Stat Rep: ->RP-232261; Rapporteur: China Telecom->Shengnan Liu, China Telecom; Rap eMail: ->liushn@chinatelecom.cn; ; 21/9/23: FCD:22/09/2023->12/1... |  | 99 | 50 |  |  | Fri 07/04/23 | Tue 02/01/24
1258 | 1040106 | UE Conformance - Non-Public Networks Phase 2: NG-RAN aspects plus CT1 aspects | eNPN_Ph2-NGRAN_plus_CT1-UEConTest | 2 | Rel-18 | R5 | 2024-06-06 08:00 | 2025-12-12 17:00 | 50% | RP-241307 | RP-252549 | China Telecom |  | 6/12/24: Compl:0%->5%; Stat Rep: ->RP-242870; ; 6/3/25: FCD:24/06/2025->12/12/2025; Compl:5%->17%; Stat Rep: RP-242870->RP-250379; ; 6/6/25: Compl:17%->32%; Stat Rep: RP-250379->RP-251463; ; 11/9/25: Compl:32%->50%; Stat Rep: RP-251463->RP-252549; |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 11/09/25
1259 | 0 | Rel-18 AM and UE Policy | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1260 | 840020 | Study on enhancement of 5G UE Policy | FS_eUEPO | 1 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-211649 |  | Changhong Shan, Intel | chang.hong.shan@intel.com | 26/6/19: 23.760 added; 21/01/22: moved Rel-17 to Rel-18 at SA#94e. Deletion of 940072, temporarily mistakenly added as FS_eUEPO_Ph2; WID:SP-190449->SP-211649; 12/3/22: 0%->25; 4/6/22: 25%->70; 4/6/22: FCD:12/09/2022->12/22; 12/9/22: 70%->80; 10/12/22: ... | New ; 23.760 | 84 | 43 |  |  | Fri 31/05/19 | Wed 15/03/23
1261 | 980114 | Enhancement of 5G UE Policy | eUEPO | 1 | Rel-18 |  | 2022-09-09 08:00 | 2024-06-06 17:00 | 100% | SP-220980 |  | Changhong Shan, Intel | chang.hong.shan@intel.com |  | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Fri 23/09/22 | NA
1262 | 970025 | (Stage 2 of) Enhancement of 5G UE Policy | eUEPO | 2 | Rel-18 | S2 | 2022-09-09 08:00 | 2023-06-06 17:00 | 100% | SP-230094 |  | Changhong Shan, Intel | chang.hong.shan@intel.com | ; 9/1/23: WID:SP-220980->SP-221342; 15/3/23: 0%->65; 15/3/23: WID:SP-221342->SP-230094; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 65%->100 | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Sat 10/12/22 | Thu 08/06/23
1263 | 980081 | CT1 aspects of eUEPO | eUEPO | 2 | Rel-18 | C1 | 2022-12-16 08:00 | 2024-06-06 17:00 | 100% | CP-241076 |  | Thomas Luetzenkirchen, Intel | thomas.luetzenkirchen@intel.com | ; 6/6/23: Compl:10%->30%; 6/6/23: WID: CP-230276->CP-231192; 23/7/24: WID:CP-240080->CP-241076 | 24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564 | 97 | 49 |  |  | Fri 23/09/22 | Tue 23/07/24
1264 | 980082 | CT3 aspects of eUEPO | eUEPO | 2 | Rel-18 | C3 | 2022-12-16 08:00 | 2024-06-06 17:00 | 100% | CP-241076 |  | Thomas Luetzenkirchen, Intel | thomas.luetzenkirchen@intel.com | ; 6/6/23: Compl:10%->40%; 6/6/23: WID: CP-230276->CP-231192 | 24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564 | 97 | 49 |  |  | Fri 23/09/22 | Tue 06/06/23
1265 | 990093 | CT4 aspects of eUEPO | eUEPO | 2 | Rel-18 | C4 | 2022-12-16 08:00 | 2024-06-06 17:00 | 100% | CP-241076 |  | Thomas Luetzenkirchen, Intel | thomas.luetzenkirchen@intel.com | ; 6/6/23: Compl:10%->30%; 6/6/23: WID: CP-230276->CP-231192 | 24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564 | 97 | 49 |  |  | Fri 23/09/22 | Tue 06/06/23
1266 | 1000041 | Spending Limits for AM and UE Policies in the 5GC | TEI18_SLAMUP | 1 | Rel-18 |  | 2022-09-12 08:00 | 2023-12-12 17:00 | 100% | SP-220794 |  | Baniel, Uriuri dot baniel at oracle dot com | uri dot baniel at oracle dot com | ; 22/3/23: 0%->80; 22/3/23: FCD:12/12/2022->06/20 | 23.503; 23.501; 23.502 | 97 | 49 |  |  | Sun 11/09/22 | Wed 22/03/23
1267 | 970004 | Stage 2 of TEI18_SLAMUP | TEI18_SLAMUP | 2 | Rel-18 | S2 | 2022-09-12 08:00 | 2023-06-06 17:00 | 100% | SP-220794 |  | Baniel, Uriuri dot baniel at oracle dot com | uri dot baniel at oracle dot com | ; 22/3/23: 0%->80; 22/3/23: FCD:12/12/2022->06/20; 8/6/23: 80%->100 | 23.503; 23.501; 23.502 | 97 | 49 |  |  | Sun 11/09/22 | Thu 08/06/23
1268 | 1000040 | CT3 aspects on TEI18_SLAMUP | TEI18_SLAMUP | 2 | Rel-18 | C3 | 2023-06-07 08:00 | 2023-12-12 17:00 | 100% | CP-233125 |  | SUN, Yue, China Telecom | suny20@chinatelecom.cn |  | 29.513; 29.519; 29.594 | 100 | 51 |  |  | Wed 07/06/23 | NA
1269 | 1020048 | CT4 aspects on TEI18_SLAMUP | TEI18_SLAMUP | 2 | Rel-18 | C4 | 2023-06-07 08:00 | 2023-12-12 17:00 | 100% | CP-233125 |  | SUN, Yue, China Telecom | suny20@chinatelecom.cn |  | 29.513; 29.519; 29.594 | 102 | 52 |  |  | Wed 07/06/23 | NA
1270 | 970001 | Rel-18 Enhancements of UE Policy | UEP18 | 1 | Rel-18 |  | 2019-03-07 08:00 | 2023-12-13 17:00 | 100% | CP_233115 |  | Fuencisla García, Ericsson | fuencisla.garcia@ericsson.com |  | 29.525; 29.507; 29.513; 29.518 | 97 | 49 |  |  | Thu 10/03/22 | NA
1271 | 970045 | CT3 aspects of UEP18 | UEP18 | 2 | Rel-18 | C3 | 2019-03-07 08:00 | 2023-12-12 17:00 | 100% | CP-233115 |  | Fuencisla García, Ericsson | fuencisla.garcia@ericsson.com | ; 6/6/23: Compl:20%->50% | 29.525; 29.507; 29.513 | 97 | 49 |  |  | Wed 07/09/22 | Tue 06/06/23
1272 | 970046 | CT4 aspects of UEP18 | UEP18 | 2 | Rel-18 | C4 | 2019-03-11 08:00 | 2023-12-12 17:00 | 100% | CP-233115 |  | Fuencisla García, Ericsson | fuencisla.garcia@ericsson.com |  | 29.518 | 97 | 49 |  |  | Wed 07/09/22 | NA
1273 | 990113 | 5G AM Policy | AMP | 1 | Rel-18 |  | 2019-03-07 17:00 | 2024-03-03 17:00 | 100% | SP-221335 |  | Chen, Zhuoyi, China Telecom | chenzy34@chinatelecom.cn | ; 10/12/22: 0%->80; 9/1/23: WID:SP-220807->SP-221335 | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Sun 11/09/22 | Mon 09/01/23
1274 | 940064 | Study on 5G AM Policy | FS_AMP | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-09-12 17:00 | 100% | SP-220647 |  | Chen, Zhuoyi, China Telecom | chenzy34@chinatelecom.cn | 21/1/22: 23.700-89 added;; 4/6/22: 0%->80; 21/6/22: WID:SP-211642->SP-220647; 12/9/22: 80%->100 | 23.700-89 | 94 | 48 |  |  | Sun 19/12/21 | Mon 12/09/22
1275 | 970017 | Stage 2 of 5G AM Policy | AMP | 2 | Rel-18 | S2 | 2019-03-07 17:00 | 2019-03-07 17:00 | 100% | SP-221335 |  | Chen, Zhuoyi, China Telecom | chenzy34@chinatelecom.cn | ; 10/12/22: 0%->80; 9/1/23: WID:SP-220807->SP-221335; 15/3/23: 80%->100; | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Sun 11/09/22 | Wed 15/03/23
1276 | 990007 | CT3 aspects of 5G AM Policy | AMP | 2 | Rel-18 | C3 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-232130 |  | SUN, Yue, China Telecom | suny20@chinatelecom.cn | ; 6/6/23: Compl:0%->85%; 6/6/23: CD:16/06/2023->09/09/2023; 6/6/23: WID: CP-230116->CP-231302 | 29.507; 29.513; 29.274 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1277 | 990095 | CT4 aspects of 5G AM Policy | AMP | 2 | Rel-18 | C4 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-232130 |  | SUN, Yue, China Telecom | suny20@chinatelecom.cn | ; 6/6/23: Compl:0%->90%; 6/6/23: WID: CP-230116->CP-231302 | 29.507; 29.513; 29.274 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1278 | 990114 | Dynamically Changing AM Policies in the 5GC Phase 2 | TEI18_DCAMP_Ph2 | 1 | Rel-18 |  | 2021-12-20 08:00 | 2023-09-09 17:00 | 100% | SP-220799 |  | Yubing Liu | liuyb9@chinatelecom.cn |  | 23.502 | 97 | 49 |  |  | Sun 11/09/22 | NA
1279 | 970009 | Stage 2 of TEI18_DCAMP_Ph2 | TEI18_DCAMP_Ph2 | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2023-06-06 17:00 | 100% | SP-230102 |  | Yubing Liu | liuyb9@chinatelecom.cn | ; 16/3/23: FCD:12/09/2022->/23; 16/3/23: WID:SP-220799->SP-230102 | 23.502 | 97 | 49 |  |  | Sun 11/09/22 | Thu 16/03/23
1280 | 990005 | CT3 aspects on Dynamically Changing AM Policies in the 5GC Phase 2 | TEI18_DCAMP_Ph2 | 2 | Rel-18 | C3 | 2021-12-20 08:00 | 2023-09-09 17:00 | 100% | CP-233124 |  | SUN, Yue, China Telecom | suny20@chinatelecom.cn | ; 6/6/23: Compl:0%->80%; 6/6/23: CD:12/09/2022->09/09/2023 | 29.513; 29.519; 29.522; 29.534 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1281 | 1020047 | CT4 aspects on Dynamically Changing AM Policies in the 5GC Phase 2 | TEI18_DCAMP_Ph2 | 2 | Rel-18 | C4 | 2021-12-20 08:00 | 2023-09-09 17:00 | 100% | CP-233124 |  | SUN, Yue, China Telecom | suny20@chinatelecom.cn | ; 6/6/23: Compl:0%->80%; 6/6/23: CD:12/09/2022->09/09/2023 | 29.513; 29.519; 29.522; 29.534 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1282 | 0 | Rel-18 User plane improvements | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1283 | 1000017 | Study on new HEVC profiles and operating points | FS_HEVC_Profiles | 1 | Rel-18 | S4 | 2023-06-08 08:00 | 2024-03-03 17:00 | 100% | SP-230540 |  | Waqar Zia | waqar_zia (at) apple.com | ; 7/9/23: 0%->30; 21/9/23: 26.966 added;; 8/12/23: 30%->65; 14/3/24: 65%->100 | 26.955 ; 26.966 | 100 | 51 |  |  | Thu 08/06/23 | Thu 14/03/24
1284 | 940010 | Study on 5G Media Service Enablers | FS_5G_MSE | 1 | Rel-18 | S4 | 2021-12-13 08:00 | 2022-12-12 17:00 | 100% | SP-211338 |  | Thomas Stockhammer, Qualcomm Incorporated | tsto@qti.qualcomm.com | 12/3/22: 0%->20; 4/6/22: 20%->30; 12/9/22: 30%->60; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 60%->100 |  | 94 | 48 |  |  | Mon 13/12/21 | Sun 11/12/22
1285 | 960043 | UE Testing Phase 2 | eUET | 1 | Rel-18 | S4 | 2022-06-02 08:00 | 2024-03-03 17:00 | 100% | SP-220610 |  | Stéphane Ragot, Orange | stephane.ragot@orange.com | ; 3/8/22: 26.130 added; 17/8/22: UETest_Ph2-> eUET; 12/9/22: 0%->10; 11/12/22: 10%->15; 17/3/23: 15%->20; 8/6/23: 20%->30; 7/9/23: 30%->35; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 35%->65; 14/3/24: 65%->100 | 26.131; 26.132; 26.801 ; 26.130 | 96 | 49 |  |  | Fri 03/06/22 | Thu 14/03/24
1286 | 980009 | 5G Media Streaming Audio codec phase 2 for 5G-Advanced | 5GMS_Audio_Ph2 | 1 | Rel-18 | S4 | 2022-12-09 08:00 | 2023-03-03 17:00 | 100% | SP-221033 |  | Frédéric Gabin (Dolby Laboratories Inc.) | frederic.gabin@dolby.com | 17/3/23: 0%->100 | 26.117; 26.511 | 98 | 50 |  |  | Fri 09/12/22 | Fri 17/03/23
1287 | 960047 | 5G Media Streaming Architecture Phase 2 | 5GMS_Ph2 | 1 | Rel-18 | S4 | 2022-06-02 08:00 | 2023-06-06 17:00 | 100% | SP-230164 |  | Iraj Sodagar, Tencent | <irajs@live.com> | 17/8/22: 5GMSA_Ph2-> 5GMS_Ph2; 17/8/22: WID:SP-220614->SP-220667; 12/9/22: 0%->15; 11/12/22: 15%->25; 16/3/23: WID:SP-220667->SP-230164; 16/3/23: FCD:03/03/2023->/23; 17/3/23: 25%->50; 8/6/23: 50%->100 | 26.501 | 96 | 49 |  |  | Fri 03/06/22 | Thu 08/06/23
1288 | 980007 | Enhanced Multiparty RTT | MP_RTT | 1 | Rel-18 | S4 | 2022-12-12 08:00 | 2024-03-03 17:00 | 100% | SP-231709 |  | Huan-yu Su, Huawei | su.huanyu@huawei.com | ; 17/3/23: 0%->5; 8/6/23: 5%->30; 7/9/23: 30%->50; 8/12/23: 50%->75; 8/12/23: FCD:12/12/2023->/2024; 8/12/23: WID:SP-221346->SP-231290; 3/1/24: WID:SP-231290->SP-231709; 14/3/24: 75%->100; 3/4/24: 26.982 added; | 26.114 ; 26.982 | 98 | 50 |  |  | Fri 09/12/22 | Wed 03/04/24
1289 | 870013 | Traffic Models and Quality Evaluation Methods for Media and XR Services in 5G Systems | FS_XRTraffic | 1 | Rel-18 | S4 | 2020-03-25 08:00 | 2023-09-09 17:00 | 100% | SP-210043 |  | Thomas Stockhammer | tsto@qti.qualcomm.com | 10/6/20: 0%->15; 28/06/20: Rel-16->Rel-17; 5/12/20: 15%->40; 21/3/21: 40%->50; 21/3/21: FCD:18/06/2020->09/21; 11/6/21: 50%->65. 2/7/21: name change from "Study on Typical Traffic Characteristics for XR Services and other Media"; 13/9/21: 65%->70; 13/1... | 26.925 | 87 | 44 |  |  | Fri 06/12/19 | Thu 07/09/23
1290 | 1000015 | 5G-Advanced media profiles for messaging services | PROMISE | 1 | Rel-18 | S4 | 2023-06-08 08:00 | 2024-03-03 17:00 | 100% | SP-230542 |  | Frédéric Gabin (Dolby Laboratories Inc.) – | frederic.gabin@dolby.com | 30/6/23: 26.143 added;; 7/9/23: 0%->15; 8/12/23: 15%->40; 14/3/24: 40%->100 | 26.140; 26.141 ; 26.143 | 100 | 51 |  |  | Thu 08/06/23 | Thu 14/03/24
1291 | 1000018 | 5G Media Streaming Protocols Phase 2 | 5GMS_Pro_Ph2 | 1 | Rel-18 | S4 | 2023-06-08 08:00 | 2024-06-06 17:00 | 100% | SP-230976 |  | Thomas Stockhammer, Qualcomm Incorporated, | tsto@qti.qualcomm.com | ; 7/9/23: WID:SP-230543->SP-230976; 7/9/23: 0%->25; ; 21/9/23: 26.510 added;; 8/12/23: 25%->55; 14/3/24: 55%->75; 14/3/24: FCD:03/03/2024->/24; 13/6/24: 75%->100 | 26.512; 26.247; 26.517; 26.532 ; 26.510 | 100 | 51 |  |  | Thu 08/06/23 | Thu 13/06/24
1292 | 0 | Rel-18 Other topics | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1293 | 1030040 | AKMA service disabling in roaming | AKMA_Disable | 1 | Rel-18 | S3 | 2024-02-02 08:00 | 2024-03-03 17:00 | 100% | SP-240246 |  | Khare, Saurabh | saurabh.khare@nokia.com | 15/3/24: 0%->100 |  | 103 | 52 |  |  | Thu 14/03/24 | Fri 15/03/24
1294 | 980110 | Support for Wireless and Wireline Convergence Phase 2 | 5WWC_Ph2 | 1 | Rel-18 |  | 2021-12-20 08:00 | 2024-03-03 17:00 | 100% | SP-220904 |  | Laurent Thiebaut, Nokia | Laurent.thiebaut@nokia.com |  | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Sun 11/09/22 | NA
1295 | 840085 | Study on the support for 5WWC Phase 2 | FS_5WWC_Ph2 | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-220419 |  | Laurent Thiebaut, Nokia | laurent.thiebaut@nokia.com | 26/6/19: 23.700-16 added; 21/01/22: moved Rel-17 to Rel-18 at SA#94e. Deletion of 940062, temporarily mistakenly added as FS_5WWV_Ph3; WID:SP-190562->SP-211640; 12/3/22: 0%->30. 4/6/22: 30%->60; 21/6/22: WID:SP-211640...; 12/9/22: FCD:12/09/2022->12/20... | 23.700-17 | 84 | 43 |  |  | Sat 03/06/17 | Wed 15/03/23
1296 | 960030 | Study on Security aspects for 5WWC Phase 2 | FS_5WWC_Ph2_Sec | 2 | Rel-18 | S3 | 2022-06-02 08:00 | 2023-03-03 17:00 | 100% | SP-221144 |  | Saurabh Khare, Nokia | Saurabh.khare@nokia.com | 13/7/22: 33.887 added;; 12/9/22: 0%->30; 11/12/22: 30%->60; 9/1/23: WID:SP-220528->SP-221144; 17/3/23: 60%->80; 8/6/23: 80%->100 | 33.887 | 96 | 49 |  |  | Thu 02/06/22 | Thu 08/06/23
1297 | 970010 | Stage 2 of 5WWC_Ph2 | 5WWC_Ph2 | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2023-06-06 17:00 | 100% | SP-230367 |  | Laurent Thiebaut, Nokia | Laurent.thiebaut@nokia.com | ; 15/3/23: 30%->45; 15/3/23: WID:SP-220904->SP-230100; 15/3/23: FCD:12/12/2022->/23; 31/3/23: WID:SP-230100->SP-230367; 8/6/23: 45%->100 | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Fri 09/12/22 | Thu 08/06/23
1298 | 980083 | CT1 aspects of 5WWC_Ph2 | 5WWC_Ph2 | 2 | Rel-18 | C1 | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-233221 |  | Nassar, Mohamed A.(Nokia) | mohamed.a.nassar@nokia.com | ; 6/6/23: Compl:50%->60%; 30/6/23: WID:CP-223114->CP-231302; 30/6/23: WID:CP-231302->CP-231287 | 24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522 | 97 | 49 |  |  | Sun 11/09/22 | Fri 30/06/23
1299 | 980084 | CT3 aspects of 5WWC_Ph2 | 5WWC_Ph2 | 2 | Rel-18 | C3 | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-233221 |  | Nassar, Mohamed A.(Nokia) | mohamed.a.nassar@nokia.com | ; 9/6/23: 15%->40 | 24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522 | 97 | 49 |  |  | Sun 11/09/22 | Fri 09/06/23
1300 | 980085 | CT4 aspects of 5WWC_Ph2 | 5WWC_Ph2 | 2 | Rel-18 | C4 | 2022-12-15 08:00 | 2024-03-03 17:00 | 100% | CP-233221 |  | Nassar, Mohamed A.(Nokia) | mohamed.a.nassar@nokia.com | ; 6/6/23: Compl:40%->65% | 24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1301 | 990035 | Security aspects for 5WWC Phase 2 | 5WWC_Ph2_Sec | 2 | Rel-18 | S3 | 2023-03-16 08:00 | 2023-09-09 17:00 | 100% | SP-230148 |  | Khare, Saurabh, Nokia | saurabh.khare@nokia.com | ; 8/6/23: 0%->80; 15/3/24: 80%->100 | 33.501 | 99 | 50 |  |  | Thu 16/03/23 | Fri 15/03/24
1302 | 1010016 | Charging Aspects of 5WWC phase 2 | 5WWC_Ph2 | 2 | Rel-18 | S5 | 2023-09-06 08:00 | 2024-03-03 17:00 | 100% | SP-231154 |  | Sun Mingrui, China Unicom | sunmr19@chinaunicom.cn | ; 8/12/23: 0%->40; 14/3/24: 40%->100 | 32.255; 32.291; 32.298 | 101 | 51 |  |  | Wed 06/09/23 | Thu 14/03/24
1303 | 980129 | Enhancement of NSAC for maximum number of UEs with at least one PDU session/PDN connection | eNSAC | 1 | Rel-18 |  | 2022-09-09 08:00 | 2023-12-12 17:00 | 100% | SP-220988 |  | ZHU Jinguo, ZTE | zhu.jinguo@zte.com.cn |  | 23.501; 23.502 | 97 | 49 |  |  | Fri 23/09/22 | NA
1304 | 970058 | Stage 2 of eNSAC | eNSAC | 2 | Rel-18 | S2 | 2022-09-09 08:00 | 2023-06-06 17:00 | 100% | SP-230113 |  | ZHU Jinguo, ZTE | zhu.jinguo@zte.com.cn | ; 16/3/23: FCD:03/03/2023->/23; 16/3/23: WID:SP-220988->SP-230113; 8/6/23: 0%->100 | 23.501; 23.502 | 97 | 49 |  |  | Mon 12/12/22 | Thu 08/06/23
1305 | 980086 | CT3 aspects of eNSAC | eNSAC | 2 | Rel-18 | C3 | 2022-12-15 08:00 | 2023-06-06 17:00 | 100% | CP-232025 |  | Li, Zhijun, ZTE | li.zhijun3@zte.com.cn |  | 29.510; 29.536; 29.571; 29.122; 29.522 | 97 | 49 |  |  | Fri 23/09/22 | NA
1306 | 980087 | CT4 aspects of eNSAC | eNSAC | 2 | Rel-18 | C4 | 2022-12-15 08:00 | 2023-12-12 17:00 | 100% | CP-232025 |  | Li, Zhijun, ZTE | li.zhijun3@zte.com.cn | ; 6/6/23: Compl:0%->25% | 29.510; 29.536; 29.571; 29.122; 29.522 | 97 | 49 |  |  | Fri 23/09/22 | Tue 06/06/23
1307 | 970031 | Management Data Analytics phase 2 | eMDAS_Ph2 | 1 | Rel-18 | S5 | 2022-09-23 08:00 | 2024-03-03 17:00 | 100% | SP-240267 |  | Yao, Yizhi, Intel | yizhi<dot>yao<at>intel<dot>com | ; 11/12/22: 0%->5; 17/3/23: 5%->15; 8/6/23: 15%->25; 8/6/23: 25%->25; 7/9/23: 25%->50; 8/12/23: 50%->87; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 87%->100; 2/4/24: WID:SP-220981->SP-240267 | 28.104; 28.552; 32.425; 28.554; 28.541; 28.622; 28.623; 28.533 | 97 | 49 |  |  | Sun 11/09/22 | Tue 02/04/24
1308 | 990115 | Application Data Analytics Enablement Service | ADAES | 1 | Rel-18 |  | 2021-12-13 08:00 | 2024-03-03 17:00 | 100% | SP-220913 |  | Pateromichelakis, Emmanouil (Manos) | epateromiche@lenovo.com | ; 23/9/22: 23.436 added;; 11/12/22: 0%->45; 11/12/22: 45%-> | 23.434 ; 23.436 | 97 | 49 |  |  | Sun 11/09/22 | Sun 11/12/22
1309 | 940019 | Study on Application Data Analytics Enablement Service | FS_ADAES | 2 | Rel-18 | S6 | 2021-12-13 08:00 | 2022-09-12 17:00 | 100% | SP-211513 |  | Pateromichelakis, Emmanouil (Manos) | epateromiche@lenovo.com | 7/1/22: 23.700-36 added;; 12/3/22: 0%->15; 4/6/22: 15%->55; 12/9/22: 55%->95; 11/12/22: 95%->100 | 23.700-36 | 94 | 48 |  |  | Mon 13/12/21 | Sun 11/12/22
1310 | 970036 | Stage 2 of ADAES | ADAES | 2 | Rel-18 | S6 | 2022-09-12 08:00 | 2023-06-06 17:00 | 100% | SP-230275 |  | Pateromichelakis, Emmanouil (Manos) | epateromiche@lenovo.com | ; 23/9/22: 23.436 added;; 11/12/22: 0%->45; 11/12/22: 45%->; 17/3/23: FCD:03/03/2023->/23; 17/3/23: WID:SP-220913->SP-230275; 17/3/23: 45%->80; 8/6/23: 80%->100 | 23.434 ; 23.436 | 97 | 49 |  |  | Sun 11/09/22 | Thu 08/06/23
1311 | 990020 | CT1 aspects of ADAES | ADAES | 2 | Rel-18 | C1 | 2022-09-12 08:00 | 2024-03-03 17:00 | 100% | CP-240268 |  | Atarius, Roozbeh, Lenovo | ratarius@motorola.com | 31/3/23: 24.559 added;; 6/6/23: Compl:0%->5% | 29.549; 24.559 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1312 | 990097 | CT3 aspects of ADAES | ADAES | 2 | Rel-18 | C3 | 2022-09-12 08:00 | 2024-03-03 17:00 | 100% | CP-240268 |  | Atarius, Roozbeh, Lenovo | ratarius@motorola.com | 9/6/23: 0%->5 | 29.549 | 97 | 49 |  |  | Sun 11/09/22 | Fri 09/06/23
1313 | 940079 | Study on Seamless UE context recovery | FS_SUECR | 1 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-09-12 17:00 | 100% | SP-211654 |  | Lalith Kumar | lalith.kumar@samsung.com | 21/1/22: 23.700-61 added;; 12/3/22: 0%->25; 4/6/22: 25%->100 | 23.700-61 | 94 | 48 |  |  | Sun 19/12/21 | Sat 04/06/22
1314 | 980116 | Seamless UE context recovery | SUECR | 1 | Rel-18 |  | 2022-09-08 08:00 | 2023-09-09 17:00 | 100% | SP-220810 |  | Lalith kumar, Samsung | lalith.kumar@samsung.com |  | 23.501; 23.502 | 97 | 49 |  |  | Sun 11/09/22 | NA
1315 | 970020 | Stage 2 of Seamless UE context recovery | SUECR | 2 | Rel-18 | S2 | 2022-09-08 08:00 | 2022-12-12 17:00 | 100% | SP-220810 |  | Lalith kumar, Samsung | lalith.kumar@samsung.com | ; 10/12/22: 0%->100 | 23.501; 23.502 | 97 | 49 |  |  | Sat 10/12/22 | Sat 10/12/22
1316 | 980088 | CT1 aspects of Seamless UE context recovery | SUECR | 2 | Rel-18 | C1 | 2022-12-16 08:00 | 2023-09-09 17:00 | 100% | CP-223113 |  | Hashmi, Danish Ehsan, Samsung | danis.hashmi@samsung.com | ; 6/6/23: Compl:90%->95% | 24.501; 27.007; 29.122; 29.522; 29.518 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1317 | 980089 | CT3 aspects of Seamless UE context recovery | SUECR | 2 | Rel-18 | C3 | 2022-12-16 08:00 | 2023-09-09 17:00 | 100% | CP-223113 |  | Hashmi, Danish Ehsan, Samsung | danis.hashmi@samsung.com | ; 9/6/23: 60%->80 | 24.501; 27.007; 29.122; 29.522; 29.518 | 97 | 49 |  |  | Sun 11/09/22 | Fri 09/06/23
1318 | 980090 | CT4 aspects of Seamless UE context recovery | SUECR | 2 | Rel-18 | C4 | 2022-12-16 08:00 | 2023-09-09 17:00 | 100% | CP-223113 |  | Hashmi, Danish Ehsan, Samsung | danis.hashmi@samsung.com |  | 24.501; 27.007; 29.122; 29.522; 29.518 | 97 | 49 |  |  | Sun 11/09/22 | NA
1319 | 980115 | 5G System Enabler for Service Function Chaining | SFC | 1 | Rel-18 |  | 2021-12-20 08:00 | 2024-03-03 17:00 | 100% | SP-220802 |  | Meghashree Dattatri Kedalagudde, Intel | meghashree.dattatri.kedalagudde@intel.com |  | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Sun 11/09/22 | NA
1320 | 970012 | Stage 2 of 5G System Enabler for Service Function Chaining | SFC | 2 | Rel-18 | S2 | 2022-09-09 08:00 | 2023-06-06 17:00 | 100% | SP-230120 |  | Meghashree Dattatri Kedalagudde, Intel | meghashree.dattatri.kedalagudde@intel.com | ; 9/1/23: WID:SP-220802->SP-221336; 15/3/23: 0%->60; 15/3/23: WID:SP-221336->SP-230120; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100 | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Sat 10/12/22 | Thu 08/06/23
1321 | 980091 | CT3 aspects of SFC | SFC | 2 | Rel-18 | C3 | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-231193 |  | Yue Sun, China Telecom | suny20@chinatelecom.cn | ; 6/6/23: Compl:10%->90%; 6/6/23: CD:12/12/2023->03/03/2024; 6/6/23: WID: CP-223210->CP-231193. 2/4/23: rapporteur: Thomas Luetzenkirchen, Intel-> Yue Sun, China Telecom | 29.244; 29.512; 29.513; 29.514; 29.519; 29.522 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1322 | 980092 | CT4 aspects of SFC | SFC | 2 | Rel-18 | C4 | 2021-12-20 08:00 | 2023-12-12 17:00 | 100% | CP-231193 |  | Yue Sun, China Telecom | suny20@chinatelecom.cn | ; 6/6/23: Compl:100%->80%; 6/6/23: CD:12/12/2022->12/12/2023; 6/6/23: WID: CP-223210->CP-231193. 2/4/23: rapporteur: Thomas Luetzenkirchen, Intel-> Yue Sun, China Telecom | 29.244; 29.512; 29.513; 29.514; 29.519; 29.522 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1323 | 940052 | Study on System Enabler for Service Function Chaining | FS_SFC | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-220415 |  | Meghashree D Kedalagudde, Intel | meghashree.dattatri.kedalagudde@intel.com | 21/1/22: 23.700-18 added;; 12/3/22: 0%->25; 4/6/22: 25%->60; 21/6/22: WID:SP-211594->SP-220415: rap change; 12/9/22: 60%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100 | 23.700-18 | 94 | 48 |  |  | Sun 19/12/21 | Sat 10/12/22
1324 | 940054 | Study on Extensions to the TSC Framework to support Deterministic Networking (DetNet) | FS_DetNet | 1 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-211633 |  | Miklós, György, Ericsson | gyorgy.miklos@ericsson.com | 21/1/22: 23.700-46 added;; 12/3/22: 0%->10; 4/6/22: 10%->70; 12/9/22: 70%->90; 12/9/22: FCD:12/09/2022->12/22; 15/3/23: 90%->100 | 23.700-46 | 94 | 48 |  |  | Sun 19/12/21 | Wed 15/03/23
1325 | 980119 | Extensions to the TSC Framework to support DetNet | DetNet | 1 | Rel-18 |  | 2022-09-08 08:00 | 2024-03-03 17:00 | 100% | SP-220801 |  | Miklós, György, Ericsson | gyorgy.miklos@ericsson.com |  | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Sun 11/09/22 | NA
1326 | 970011 | Stage 2 of Extensions to the TSC Framework to support DetNet | DetNet | 2 | Rel-18 | S2 | 2022-09-08 08:00 | 2023-06-06 17:00 | 100% | SP-230172 |  | Miklós, György, Ericsson | gyorgy.miklos@ericsson.com | ; 15/3/23: WID:SP-220801->SP-230172; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100 | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Sat 10/12/22 | Thu 08/06/23
1327 | 980093 | CT1 aspects of Detnet | DetNet | 2 | Rel-18 | C1 | 2022-12-16 08:00 | 2023-12-12 17:00 | 100% | CP-231195 |  | Fuencisla García, Ericsson | fuencisla.garcia@ericsson.com | ; 6/6/23: Compl:90%->100%; 6/6/23: WID: CP-223206->CP-231195 | 24.539; 29.244; 29.513; 29.512; 29.514 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1328 | 980094 | CT3 aspects of Detnet | DetNet | 2 | Rel-18 | C3 | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-231195 |  | Fuencisla García, Ericsson | fuencisla.garcia@ericsson.com | ; 6/6/23: Compl:50%->80%; 6/6/23: CD:12/12/2023->03/03/2024; 6/6/23: WID: CP-223206->CP-231195 | 24.539; 29.244; 29.513; 29.512; 29.514 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1329 | 1020064 | (IETF) CT3 part of DetNet (draft-ietf-detnet-yang) | DetNet | 3 | Rel-18 | C3-IETF | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-231195 |  | Fuencisla García, Ericsson | fuencisla.garcia@ericsson.com | CT3 part complete. SA2 reference cleanup pending | 29.513, 29.565 | 97 | 49 |  |  | Sun 11/09/22 | Tue 02/04/24
1330 | 980095 | CT4 aspects of Detnet | DetNet | 2 | Rel-18 | C4 | 2022-12-16 08:00 | 2023-12-12 17:00 | 100% | CP-231195 |  | Fuencisla García, Ericsson | fuencisla.garcia@ericsson.com | ; 6/6/23: Compl:10%->80%; 6/6/23: WID: CP-223206->CP-231195 | 24.539; 29.244; 29.513; 29.512; 29.514 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1331 | 980117 | Multiple location report for MT-LR Immediate Location Request for regulatory services | TEI18_MLR | 1 | Rel-18 |  | 2022-09-08 08:00 | 2023-06-06 17:00 | 100% | SP-220795 |  | Joul, Christopher, T-Mobile USA | chris.joul@t-mobile.com |  | 23.273 | 97 | 49 |  |  | Sun 11/09/22 | NA
1332 | 970005 | Stage 2 of TEI18_MLR | TEI18_MLR | 2 | Rel-18 | S2 | 2022-09-08 08:00 | 2022-12-12 17:00 | 100% | SP-220795 |  | Joul, Christopher, T-Mobile USA | chris.joul@t-mobile.com | ; 10/12/22: 0%->100 | 23.273 | 97 | 49 |  |  | Sat 10/12/22 | Sat 10/12/22
1333 | 980002 | CT4 aspects on TEI18_MLR | TEI18_MLR | 2 | Rel-18 | C4 | 2022-12-16 08:00 | 2023-06-06 17:00 | 100% | CP-223022 |  | Jones Yunjie, Lu, Ericsson | jones.lu@ericsson.com | ; 6/6/23: Compl:80%->100%; 6/6/23: CD:12/12/2023->06/06/2023 | 29.571; 29.518 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1334 | 980120 | TEI18 on Enhancement of Application Detection Event Exposure | TEI18_ADEE | 1 | Rel-18 |  | 2022-09-08 08:00 | 2023-06-06 17:00 | 100% | SP-220796 |  | Aihua Li, China Mobile | liaihua@chinamobile.com |  | 23.503; 23.502 | 97 | 49 |  |  | Sun 11/09/22 | NA
1335 | 970006 | Stage 2 of TEI18_ADEE | TEI18_ADEE | 2 | Rel-18 | S2 | 2022-09-08 08:00 | 2023-03-03 17:00 | 100% | SP-220796 |  | Aihua Li, China Mobile | liaihua@chinamobile.com | ; 22/3/23: 0%->100 | 23.503; 23.502 | 97 | 49 |  |  | Sat 10/12/22 | Wed 22/03/23
1336 | 980030 | CT3 aspects of TEI18_ADEE | TEI18_ADEE | 2 | Rel-18 | C3 | 2022-12-15 08:00 | 2023-06-06 17:00 | 100% | CP-223202 |  | Zhenning Huang, China Mobile | huangzhenning@chinamobile.com | ; 6/6/23: Compl:0%->100% | 29.522; 29.514; 29.512 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1337 | 980121 | General Support of IPv6 Prefix Delegation in 5GS | TEI18_IPv6PD | 1 | Rel-18 |  | 2022-09-08 08:00 | 2023-12-12 17:00 | 100% | SP-220797 |  | Gan, Judy, Ericsson | Judy.Gan.Juying@ericsson.com |  | 23.501; 23.502; 23.503; 23.304; 23.316 | 97 | 49 |  |  | Sun 11/09/22 | NA
1338 | 970007 | Stage 2 of TEI18_IPv6PD | TEI18_IPv6PD | 2 | Rel-18 | S2 | 2022-09-08 08:00 | 2023-03-03 17:00 | 100% | SP-220797 |  | Gan, Judy, Ericsson | Judy.Gan.Juying@ericsson.com | ; 22/3/23: 0%->100 | 23.501; 23.502; 23.503; 23.304; 23.316 | 97 | 49 |  |  | Sat 10/12/22 | Wed 22/03/23
1339 | 980096 | CT1 aspects of TEI18_IPv6PD | TEI18_IPv6PD | 2 | Rel-18 | C1 | 2022-12-16 08:00 | 2023-12-12 17:00 | 100% | CP-230121 |  | Maria Tianmei, Liang, Ericsson | Maria.liang@ericsson.com | ; 6/6/23: Compl:95%->100%; 6/6/23: WID: CP-223203->CP-230121 | 24.501; 29.561; 29.512; 29.521; 29.244; 29.513 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1340 | 980097 | CT3 aspects of TEI18_IPv6PD | TEI18_IPv6PD | 2 | Rel-18 | C3 | 2022-12-16 08:00 | 2023-12-12 17:00 | 100% | CP-230121 |  | Maria Tianmei, Liang, Ericsson | Maria.liang@ericsson.com |  | 24.501; 29.561; 29.512; 29.521; 29.244; 29.513 | 97 | 49 |  |  | Sun 11/09/22 | NA
1341 | 980098 | CT4 aspects of TEI18_IPv6PD | TEI18_IPv6PD | 2 | Rel-18 | C4 | 2022-12-16 08:00 | 2023-12-12 17:00 | 100% | CP-230121 |  | Maria Tianmei, Liang, Ericsson | Maria.liang@ericsson.com |  | 24.501; 29.561; 29.512; 29.521; 29.244; 29.513 | 97 | 49 |  |  | Sun 11/09/22 | NA
1342 | 980118 | Secondary DN Authentication and authorization in EPC IWK cases | TEI18_SDNAEPC | 1 | Rel-18 |  | 2022-09-08 08:00 | 2024-03-03 17:00 | 100% | SP-220798 |  | Laurent Thiebaut, Nokia | Laurent.thiebaut@nokia.com |  | 23.501; 23.502 | 97 | 49 |  |  | Sun 11/09/22 | NA
1343 | 970008 | Stage 2 of Secondary DN Authentication and authorization in EPC IWK cases | TEI18_SDNAEPC | 2 | Rel-18 | S2 | 2022-09-08 08:00 | 2022-12-12 17:00 | 100% | SP-220798 |  | Laurent Thiebaut, Nokia | Laurent.thiebaut@nokia.com | ; 10/12/22: 0%->100 | 23.501; 23.502 | 97 | 49 |  |  | Sat 10/12/22 | Sat 10/12/22
1344 | 980099 | CT1 aspects of TEI18_SDNAEPC | TEI18_SDNAEPC | 2 | Rel-18 | C1 | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-230188 |  | Nassar, Mohamed A.(Nokia) | mohamed.a.nassar@nokia.com | ; 6/6/23: Compl:80%->90% | 24.501; 24.301; 24.008; 29.561; 29.274 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1345 | 980100 | CT3 aspects of TEI18_SDNAEPC | TEI18_SDNAEPC | 2 | Rel-18 | C3 | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-230188 |  | Nassar, Mohamed A.(Nokia) | mohamed.a.nassar@nokia.com | ; 9/6/23: 96%-> | 24.501; 24.301; 24.008; 29.561; 29.274 | 97 | 49 |  |  | Sun 11/09/22 | Fri 09/06/23
1346 | 980101 | CT4 aspects of TEI18_SDNAEPC | TEI18_SDNAEPC | 2 | Rel-18 | C4 | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-230188 |  | Nassar, Mohamed A.(Nokia) | mohamed.a.nassar@nokia.com |  | 24.501; 24.301; 24.008; 29.561; 29.274 | 97 | 49 |  |  | Sun 11/09/22 | NA
1347 | 990116 | Message Service within the 5G system (MSGin5G) Phase 2 | 5GMARCH_Ph2 | 1 | Rel-18 |  | 2022-03-10 08:00 | 2023-12-12 17:00 | 100% | SP-220330 |  | Liu, Yue, China Mobile | liuyueyjy@chinamobile.com | ; 4/6/22: 0%->30; 12/9/22: 30%->55; 11/12/22: 55%->70 | 23.554 | 95 | 48 |  |  | Thu 10/03/22 | Sun 11/12/22
1348 | 950026 | Stage 2 of 5GMARCH_Ph2 | 5GMARCH_Ph2 | 2 | Rel-18 | S6 | 2022-03-10 08:00 | 2023-03-03 17:00 | 100% | SP-220330 |  | Liu, Yue, China Mobile | liuyueyjy@chinamobile.com | ; 4/6/22: 0%->30; 12/9/22: 30%->55; 11/12/22: 55%->70; 17/3/23: 70%->80; 8/6/23: 80%->100 | 23.554 | 95 | 48 |  |  | Thu 10/03/22 | Thu 08/06/23
1349 | 990019 | CT1 aspects of 5GMARCH_Ph2 | 5GMARCH_Ph2 | 2 | Rel-18 | C1 | 2023-03-13 08:00 | 2023-12-12 17:00 | 100% | CP-230198 |  | Liu, Yue, China Mobile | liuyueyjy@chinamobile.com | ; 6/6/23: Compl:0%->15% | 24.538; 24.544; 24.546; 29.538; 29.222 | 95 | 48 |  |  | Thu 10/03/22 | Tue 06/06/23
1350 | 990099 | CT3 aspects of 5GMARCH_Ph2 | 5GMARCH_Ph2 | 2 | Rel-18 | C3 | 2023-03-13 08:00 | 2023-12-12 17:00 | 100% | CP-230198 |  | Liu, Yue, China Mobile | liuyueyjy@chinamobile.com | 9/6/23: 0%->80 | 24.538; 24.544; 24.546; 29.538; 29.222 | 95 | 48 |  |  | Thu 10/03/22 | Fri 09/06/23
1351 | 990041 | Security aspects of MSGin5G Ph2 | 5GMARCH_Ph2_SEC | 2 | Rel-18 | S3 | 2023-02-02 08:00 | 2023-03-03 17:00 | 100% | SP-230154 |  | Huang Xiaoting, China Mobile | huangxiaoting@chinamobile.com | ; 8/6/23: 0%->100 | 33.501 | 99 | 50 |  |  | Thu 16/03/23 | Thu 08/06/23
1352 | 910039 | 5G Timing Resiliency System | 5TRS | 1 | Rel-18 |  | 2020-06-25 08:00 | 2024-03-03 17:00 | 100% | SP-210211 |  | Betsy Covell, Nokia | betsy.covell@nokia.com |  | 22.261; 22.104 | 91 | 46 |  |  | Thu 18/03/21 | NA
1353 | 880037 | Study on 5TRS | FS_5TRS | 2 | Rel-18 | S1 | 2020-06-25 08:00 | 2021-03-12 17:00 | 100% | SP-200573 |  | Betsy Covell, Nokia | betsy.covell@nokia.com | 28/7/20: 22.878 added;; 12/9/20: 0%->10; 5/12/20: 10%->75; 19/3/21: FCD:16/12/2020->03/21; 19/3/21: 75%->97; 11/6/21: 97%->100 | 22.878 | 88 | 45 |  |  | Thu 25/06/20 | Fri 11/06/21
1354 | 940055 | Study on 5G Timing Resiliency and TSC&URLLC enhancements | FS_5TRS_URLLC | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-211634 |  | Devaki Chandramouli | Devaki.chandramouli@nokia.com | 21/1/22: 23.700-25 added;; 12/3/22: 0%->25; 4/6/22: 25%->65; 12/9/22: 65%->83; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 83%->98; 15/3/23: 98%->100 | 23.700-25 | 94 | 48 |  |  | Sun 19/12/21 | Wed 15/03/23
1355 | 910033 | Stage 1 for 5TRS | 5TRS | 2 | Rel-18 | S1 | 2021-03-18 08:00 | 2021-09-10 17:00 | 100% | SP-210211 |  | Betsy Covell, Nokia | betsy.covell@nokia.com | ; 11/6/21: 0%->100 | 22.261; 22.104 | 91 | 46 |  |  | Thu 18/03/21 | Fri 11/06/21
1356 | 970024 | Stage 2 of Timing Resiliency and URLLC enhancements | TRS_URLLC | 2 | Rel-18 | S2 | 2022-09-12 08:00 | 2023-03-03 17:00 | 100% | SP-230107 |  | Devaki Chandramouli | Devaki.chandramouli@nokia.com | ; 10/12/22: 0%->50; 9/1/23: WID:SP-220814->SP-221341; 15/3/23: 50%->80; 15/3/23: WID:SP-221341->SP-230107; 8/6/23: 80%->100 | 23.501; 23.502; 23.503 | 97 | 49 |  |  | Sun 11/09/22 | Thu 08/06/23
1357 | 980102 | CT1 aspects of TRS_URLLC | TRS_URLLC | 2 | Rel-18 | C1 | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-231360 |  | Apostolos Papageorgiou (Nokia) | apostolos.papageorgiou@nokia.com | ; 6/6/23: Compl:70%->95%; 6/6/23: WID: CP-223205->CP-231198; 30/6/23: WID:CP-231198->CP-231360 | 24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244.24.539 | 97 | 49 |  |  | Sun 11/09/22 | Fri 30/06/23
1358 | 980103 | CT3 aspects of TRS_URLLC | TRS_URLLC | 2 | Rel-18 | C3 | 2022-12-16 08:00 | 2024-03-03 17:00 | 100% | CP-231360 |  | Apostolos Papageorgiou (Nokia) | apostolos.papageorgiou@nokia.com | ; 6/6/23: Compl:25%->75%; 6/6/23: WID: CP-223205->CP-231198 | 24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244.24.539 | 97 | 49 |  |  | Sun 11/09/22 | Tue 06/06/23
1359 | 980104 | CT4 aspects of TRS_URLLC | TRS_URLLC | 2 | Rel-18 | C4 | 2022-12-16 08:00 | 2023-12-12 17:00 | 100% | CP-231360 |  | Apostolos Papageorgiou (Nokia) | apostolos.papageorgiou@nokia.com | ; 6/6/23: Compl:40%->55%; 6/6/23: WID: CP-223205->CP-231198; 30/6/23: 29.585 added; | 24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244; 29.585 | 97 | 49 |  |  | Sun 11/09/22 | Fri 30/06/23
1360 | 950028 | Study on Management Aspects of URLLC | FS_URLLC_Mgt | 1 | Rel-18 | S5 | 2022-03-10 08:00 | 2023-06-06 17:00 | 100% | SP-230772 |  | Wang,Zhaoning,China Unicom | wangzn18@chinaunicom.cn | 5/4/22: 28.832 added;; 4/6/22: 0%->15; 12/9/22: 15%->40; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 40%->60; 17/3/23: 60%->62; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 62%->100; 30/6/23: WID:SP-220146->SP-230772 | 28.832 | 95 | 48 |  |  | Thu 10/03/22 | Fri 30/06/23
1361 | 940088 | Study on enhancement for resiliency of gNB-CU (Central Unit)-CP (Control Plane) | FS_gNB_CU_CP_resiliency | 1 | Rel-18 | R3 | 2021-12-13 08:00 | 2022-09-22 17:00 | 100% | RP-222249 | RP-221439 | Masato Taniguchi, NTT DOCOMO, INC. | masato.taniguchi.mf@nttdocomo.com | ; 22/3/22: CD:12/09/2022->12/09/2023; 22/3/22: Stat Rep: ->RP-2205556/6/22: CD:12/09/2023->22/09/20226/6/22: Stat Rep: RP-220555->RP-221439; 20/6/22: Rapporteur: NTT DOCOMO->Masato Taniguchi, NTT DOCOMO, INC.; Rap eMail: ->masato.taniguchi.mf@nttdocomo... | 38.879 | 94 | 48 |  |  | Thu 06/01/22 | Fri 23/09/22
1362 | 991036 | NR Timing Resiliency and URLLC enhancements | TRS_URLLC-NR | 1 | Rel-18 | R3 | 2023-03-03 08:00 | 2023-12-12 17:00 | 100% | RP-232863 |  | Nokia |  | 2/1/24: WID:RP-230754->RP-232863 |  | 99 | 50 |  |  | Wed 29/03/23 | Tue 02/01/24
1363 | 991136 | Core part: NR Timing Resiliency and URLLC enhancements | TRS_URLLC-NR-Core | 2 | Rel-18 | R3 | 2023-03-03 08:00 | 2023-12-12 17:00 | 100% | RP-232863 | RP-232864 | Sean Kelley, Nokia | sean.kelley@nokia.com | ; ...; 6/9/23: Compl:25%->60%; WID: RP-230754->RP-231106; Stat Rep: ->RP-231581; Rapporteur: Nokia->Sean Kelley, Nokia; Rap eMail: ->sean.kelley@nokia.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-231581->RP-232864; |  | 99 | 50 |  |  | Wed 29/03/23 | Fri 08/12/23
1364 | 930028 | Vehicle-Mounted Relays | VMR | 1 | Rel-18 |  | 2020-09-16 08:00 | 2024-03-03 17:00 | 100% | SP-211054 |  | Francesco Pica, Qualcomm | fpica@qti.qualcomm.com |  | 22.261 | 93 | 47 |  |  | Fri 10/09/21 | NA
1365 | 890022 | Study on VMR | FS_VMR | 2 | Rel-18 | S1 | 2020-09-16 08:00 | 2021-09-08 17:00 | 100% | SP-200798 |  | Francesco Pica | fpica@qti.qualcomm.com | 5/12/20: 0%->35; 19/3/21: FCD:11/06/2021->09/21; 19/3/21: 35%->60; 11/6/21: 60%->85; 13/9/21: 85%->100 | 22.839 | 89 | 45 |  |  | Thu 10/09/20 | Mon 13/09/21
1366 | 930021 | Stage 1 of VMR | VMR | 2 | Rel-18 | S1 | 2021-09-10 08:00 | 2021-12-10 17:00 | 100% | SP-211054 |  | Francesco Pica, Qualcomm | fpica@qti.qualcomm.com | ; 13/9/21: 0%->95; 14/12/21: 95%->100 | 22.261 | 93 | 47 |  |  | Fri 10/09/21 | Tue 14/12/21
1367 | 980018 | (Stage 2 for VMR) Architecture Enhancements for Vehicle Mounted Relays | VMR | 2 | Rel-18 | S2 | 2022-12-09 08:00 | 2023-06-06 17:00 | 100% | SP-230105 |  | Cheng, Hong, Qualcomm Incorporated, | hongc@qti.qualcomm.com | ; 10/12/22: 0%->20; 15/3/23: WID:SP-221328->SP-230105; 15/3/23: 20%->40; 8/6/23: 40%->100; 4/1/24: 28.875 added; | 23.501; 23.502; 23.503; 23.273 ; 28.875 | 98 | 50 |  |  | Fri 09/12/22 | Thu 04/01/24
1368 | 990013 | CT1 aspects of VMR | VMR | 2 | Rel-18 | C1 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-232168 |  | Kim, Sunghoon, Qualcomm Incorporated | sunghoon@qti.qualcomm.com | ; 6/6/23: Compl:0%->20% | 23.122.23.041.24.501.24.526.27.007.29.513.29.519.29.522.29.525.23.008.29.503.29.505.29.510.29.515.29.518.29.571.29.572 | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
1369 | 990102 | CT4 aspects of VMR | VMR | 2 | Rel-18 | C4 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-232168 |  | Kim, Sunghoon, Qualcomm Incorporated | sunghoon@qti.qualcomm.com | ; 6/6/23: Compl:0%->25% | 23.122.23.041.24.501.24.526.27.007.29.513.29.519.29.522.29.525.23.008.29.503.29.505.29.510.29.515.29.518.29.571.29.572 | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
1370 | 940057 | Study on Architecture Enhancements for Vehicle Mounted Relays | FS_VMR | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-211636 |  | Cheng, Hong, Qualcomm Incorporated, | hongc@qti.qualcomm.com | 21/1/22: 23.700-05 added;; 12/3/22: 0%->20; 4/6/22: 20%->55; 12/9/22: 55%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100 | 23.700-05 | 94 | 48 |  |  | Sun 19/12/21 | Sat 10/12/22
1371 | 941009 | Mobile IAB (Integrated Access and Backhaul) for NR | NR_mobile_IAB | 1 | Rel-18 |  | 2021-12-13 08:00 | 2024-06-06 17:00 | 100% | RP-240104 |  | Qualcomm |  | compare REL-16 WI NR_IAB and REL-17 WI NR_IAB_enh; no Perf. part; 5/4/22: WID:RP-213601->RP-220843; 12/7/22: WID:RP-220843->RP-221815; 23/9/22: WID:RP-221815->RP-222671; 6/10/23: WID:RP-222671->RP-232643; 2/1/24: WID:RP-232643->RP-233320; 2/4/24: WID:RP-2 |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 02/04/24
1372 | 941109 | Core part: Mobile IAB (Integrated Access and Backhaul) for NR | NR_mobile_IAB-Core | 2 | Rel-18 | R3 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-240319 | RP-241123 | Georg Hampel, Qualcomm Incorporated | ghampel@qti.qualcomm.com | compare REL-16 WI NR_IAB and REL-17 WI NR_IAB_enh;; 22/3/22: Stat Rep: ->RP-220430 6/6/22: CD:12/12/2023->23/12/2022 6/6/22: Stat Rep: RP- ; 20/6/22: Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com13...;... |  | 94 | 48 |  |  | Thu 06/01/22 | Thu 13/06/24
1373 | 941209 | Perf. part: Mobile IAB (Integrated Access and Backhaul) for NR | NR_mobile_IAB-Perf | 2 | Rel-18 | R3 | 2021-12-15 08:00 | 2024-06-06 17:00 | 100% | RP-240319 | RP-241123 | Georg Hampel, Qualcomm Incorporated | ghampel@qti.qualcomm.com | ; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220430 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220430->RP ; 20/6/22: WG: R4->R3; Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualco... |  | 94 | 48 |  |  | Thu 06/01/22 | Thu 13/06/24
1374 | 941008 | Enhancement on NR QoE management and optimizations for diverse services | NR_QoE_enh | 1 | Rel-18 |  | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-223488 |  | China Unicom |  | compare REL-17 WI NR_QoE-Core; QoE = Quality of Experience; no Perf. part; 12/7/22: WID:RP-213594->RP-221803; 9/1/23: WID:RP-221803->RP-223488 |  | 94 | 48 |  |  | Thu 06/01/22 | Mon 09/01/23
1375 | 941108 | Core part: Enhancement on NR QoE management and optimizations for diverse services | NR_QoE_enh-Core | 2 | Rel-18 | R3 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-223488 | RP-233603 | Pei Li, China Unicom | lip104@chinaunicom.cn | compare REL-17 WI NR_QoE-Core; QoE = Quality of Experience; no Perf. part; 20/6/22: FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221244; Rapporteur: China Unicom->Pei Li, China Unicom; Rap eMail: ->lip104@chinaunicom.cn13/7/22: FCD:23/12/2022->12/20;...;... |  | 94 | 48 |  |  | Thu 06/01/22 | Fri 08/12/23
1376 | 940032 | Study on Key Quality Indicators (KQIs) for 5G service experience | FS_KQI_5G | 1 | Rel-18 | S5 | 2021-12-13 08:00 | 2024-03-03 17:00 | 100% | SP-231432 |  | Man WANG, Huawei | wangman1@huawei.com | 7/1/22: 28.863 added;; 4/6/22: 0%->10; 12/9/22: 10%->20; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 20%->35; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 35%->; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 35%->65; 8/12/23: 65%->100; 3/1/24: WID:SP-211433->SP-231432 | 28.863 | 94 | 48 |  |  | Mon 13/12/21 | Wed 03/01/24
1377 | 950031 | Additional NRM features phase 2 | AdNRM_ph2 | 1 | Rel-18 | S5 | 2022-03-10 08:00 | 2024-03-03 17:00 | 100% | SP-231440 |  | Sean Sun, Nokia | sean.sun@nokia-sbell.com | 4/6/22: 0%->7; 12/9/22: 7%->30; 12/9/22: FCD:11/03/2022->03/23; 11/12/22: 30%->55; 17/3/23: 55%->65; 8/6/23: 65%->80; 8/6/23: FCD:03/03/2023->/24; 8/6/23: 80%->; 7/9/23: 80%->88; 8/12/23: 88%->99; 3/1/24: WID:SP-220351->SP-231440; 14/3/24: 99%->100 |  | 95 | 48 |  |  | Thu 10/03/22 | Thu 14/03/24
1378 | 940031 | MPS when access to EPC/5GC is WLAN | MPS_WLAN | 1 | Rel-18 |  | 2021-09-10 08:00 | 2026-03-03 17:00 | 80% | SP-211057 |  | Singh, Ray; Peraton Labs | rsingh@peratonlabs.com |  |  | 94 | 48 |  |  | Fri 10/09/21 | Fri 07/01/22
1379 | 930024 | Stage 1 of MPS_WLAN | MPS_WLAN | 2 | Rel-18 | S1 | 2021-09-10 08:00 | 2021-12-10 17:00 | 100% | SP-211057 |  | Singh, Ray; Peraton Labs | rsingh@peratonlabs.com | 10/12/21: 0%->100 | 22.153 | 93 | 47 |  |  | Fri 10/09/21 | Fri 10/12/21
1380 | 940053 | Stage 2 of MPS_WLAN | MPS_WLAN | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2023-06-06 17:00 | 100% | SP-230108 |  | Robert C Streijl; Peraton Labs | rstreijl@peratonlabs.com | ; 10/12/22: 0%->0; 10/12/22: FCD:12/09/2022->03/23; 15/3/23: 0%->50; 15/3/23: WID:SP-211595->SP-230108; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 50%->100 | 23.401; 23.402; 23.501; 23.502 | 94 | 48 |  |  | Sun 19/12/21 | Thu 08/06/23
1381 | 1000021 | CT1 aspects of MPS_WLAN | MPS_WLAN | 2 | Rel-18 | C1 | 2023-06-07 08:00 | 2024-03-03 17:00 | 100% | CP-240299 |  | Monnes, Peter, Peraton Labs | pmonnes@peratonlabs.com |  | 23.003; 24.302; 24.502; 29.273 | 100 | 51 |  |  | Wed 07/06/23 | NA
1382 | 1000046 | CT4 aspects of MPS_WLAN | MPS_WLAN | 2 | Rel-18 | C4 | 2023-06-07 08:00 | 2024-03-03 17:00 | 100% | CP-240299 |  | Monnes, Peter, Peraton Labs | pmonnes@peratonlabs.com |  | 23.003; 24.302; 24.502; 29.273 | 100 | 51 |  |  | Wed 07/06/23 | NA
1383 | 1030049 | CT6 aspects of MPS_WLAN | MPS_WLAN | 2 | Rel-18 | C6 | 2023-06-07 08:00 | 2024-03-03 17:00 | 100% | CP-240299 |  | Monnes, Peter, Peraton Labs | pmonnes@peratonlabs.com |  | 23.003; 24.302; 24.502; 29.273 | 100 | 51 |  |  | Wed 07/06/23 | NA
1384 | 1080075 | UE Conformance - MPS when access to EPC/5GC is WLAN | MPS_WLAN-UEConTest | 2 | Rel-18 | R5 | 2025-06-06 08:00 | 2026-03-03 17:00 | 5% | RP-250893 | RP-252013 | China Telecom |  | MPS = Multimedia Priority Service; tested: CT1 REL-18 WI MPS_WLAN ; 11/9/25: Compl:0%->5%; Stat Rep: ->RP-252013; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
1385 | 941007 | Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | NR_ENDC_SON_MDT_enh2 | 1 | Rel-18 |  | 2021-01-01 08:00 | 2023-12-12 17:00 | 100% | RP-233438 |  | CMCC |  | compare REL-16 WI NR_SON_MDT-Core and REL-17 WI NR_ENDC_SON_MDT_enh-Core; no Perf. part; 5/4/22: WID:RP-213553->RP-221000; 12/7/22: WID:RP-221000->RP-221825; 2/1/24: WID:RP-221825->RP-233438 |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 02/01/24
1386 | 941107 | Core part: Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | NR_ENDC_SON_MDT_enh2-Core | 2 | Rel-18 | R3 | 2021-01-01 08:00 | 2023-12-12 17:00 | 100% | RP-233438 | RP-233437 | Liang LIU, CMCC | liuliang@chinamobile.com | compare REL-16 WI NR_SON_MDT-Core and REL-17 WI NR_ENDC_SON_MDT_enh-Core; no Perf. part; 20/6/22: FCD:31/12/2021->23/12/2022; Stat Rep: ->RP-221372; Rapporteur: CMCC->Liang LIU, CMCC; Rap eMail: ->liuliang@chinamobile.com13/7/22: FCD:23/12/2022->12...;... |  | 94 | 48 |  |  | Thu 06/01/22 | Fri 08/12/23
1387 | 950064 | UE Conformance - Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) | NR_ENDC_SON_MDT_enh-UEConTest | 2 | Rel-17 | R5 | 2022-03-15 08:00 | 2023-09-22 17:00 | 100% | RP-233438 | RP-232241 | Danni Song, CMCC | songdan@chinamobile.com | tested: REL-17 WI NR_ENDC_SON_MDT_enh 6/6/22: Compl:0%->5% 6/6/22: CD:15/06/2 ; 20/6/22: Rapporteur: CMCC->Luting Kong, CMCC; Rap eMail: ->kongluting@chinamobile.com12/7/22: WID:RP-220620->RP-221365 ...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:7%-... |  | 95 | 48 |  |  | Tue 05/04/22 | Fri 06/10/23
1388 | 940030 | Self-Configuration of RAN Network Entities | RANSC | 1 | Rel-18 | S5 | 2021-12-10 08:00 | 2024-03-03 17:00 | 100% | SP-211431 |  | Hu, Yaxi, China Mobile | huyaxi@cmdi.chinamobile.com | ; 7/1/22: 28.317 added;; 4/6/22: 0%->5; 11/12/22: 5%->45; 17/3/23: 45%->50; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 50%->55; 8/6/23: 55%->55; 7/9/23: 55%->65; 8/12/23: 65%->90; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 90%->100 | 28.313; ; 28.317 | 94 | 48 |  |  | Fri 10/12/21 | Thu 14/03/24
1389 | 900028 | Support for Service Function Chaining | SFChain | 1 | Rel-18 | S1 | 2020-12-04 08:00 | 2021-03-12 17:00 | 100% | SP-201040 |  | Ellen Liao; Intel | ellen.c.liao at intel.com | 22.261; 22.101; 22.115 ; 5/12/20: 0%->100 |  | 90 | 46 |  |  | Fri 04/12/20 | Sat 05/12/20
1390 | 910035 | Data Integrity in 5GS | DI_5G | 1 | Rel-18 | S1 | 2021-03-18 08:00 | 2021-03-25 17:00 | 100% | SP-210213 |  | Qun wei, China Unicom | Weiqun5 <at> chinaunicom.cn | ; 19/3/21: 0%->100 | 22.261 | 91 | 46 |  |  | Thu 18/03/21 | Fri 19/03/21
1391 | 920033 | Signal level Enhanced Network Selection | SENSE | 1 | Rel-18 | S1 | 2022-09-16 08:00 | 2024-03-01 17:00 | 100% | SP-210525 |  | Bischinger, Kurt; Deutsche Telekom | kurt.bischinger@magenta.at | ; 11/6/21: 0%->40; 10/12/21: 40%->100 | 22.011 | 92 | 47 |  |  | Fri 11/06/21 | Fri 10/12/21
1392 | 970059 | CT1 aspects of SENSE | SENSE | 2 | Rel-18 | C1 | 2022-12-16 08:00 | 2023-06-06 17:00 | 100% | CP-222237 |  | Reinhard Lauster, Deutsche Telekom | reinhard.lauster@magenta.at | ; 6/6/23: Compl:65%->95%; 6/6/23: CD:16/12/2022->06/06/2023 | 23.122; 24.501; 27.007 | 97 | 49 |  |  | Mon 19/09/22 | Tue 06/06/23
1393 | 970060 | CT6 aspects of SENSE | SENSE | 2 | Rel-18 | C6 | 2022-09-16 08:00 | 2022-09-16 17:00 | 100% | CP-222237 |  | Reinhard Lauster, Deutsche Telekom | reinhard.lauster@magenta.at |  | 31.102 | 97 | 49 |  |  | Mon 19/09/22 | NA
1394 | 1010052 | UE Conformance - Signal level Enhanced Network Selection | SENSE-UEContest | 2 | Rel-18 | R5 | 2023-09-09 08:00 | 2024-03-01 17:00 | 100% | RP-233770 | RP-240288 | Ya Zhao, Huawei Technologies. Co., Ltd | zhaoya@hisilicon.com | 8/12/23: Compl:0%->5%; Stat Rep: ->RP-233769; Rapporteur: Huawei->Ya Zhao, Huawei Technologies. Co., Ltd; Rap eMail: ->zhaoya@hisilicon.com; ; 2/1/24: WID:RP-232362->RP-233770; 14/3/24: FCD:05/06/2024->01/03/2024; Compl:5%->100%; Stat Rep: RP-233769->RP- |  | 101 | 51 |  |  | Fri 06/10/23 | Thu 14/03/24
1395 | 940017 | SECAM and SCAS for 3GPP virtualized network products | VNP_SECAM_SCAS | 1 | Rel-18 | S3 | 2021-12-10 08:00 | 2023-03-03 17:00 | 100% | SP-211365 |  | Qi Minpeng, China Mobile | qiminpeng@chinamobile.com | 7/1/22: 33.527 added;; 12/9/22: 0%->40; 11/12/22: 40%->65; 17/3/23: 65%->75; 15/3/24: 75%->100 | 33.527; 33.927; 33.936 | 94 | 48 |  |  | Fri 10/12/21 | Fri 15/03/24
1396 | 950016 | Security Assurance Specification (SCAS) for 5G Rel-17 Features | SCAS_5G_Ph2 | 1 | Rel-18 | S3 | 2022-03-10 08:00 | 2022-12-12 17:00 | 100% | SP-220192 |  | Rong Wu, Huawei Technologies Co., Ltd. | Raina.wu@huawei.com | ; 4/6/22: 0%->10; 17/3/23: 10%->30; 15/3/24: 30%->100 | 33.926; 33.117; 33.511; 33.512; 33.513; 33.514; 33.515; 33.516; 33.517; 33.518; 33.519; 33.520; 33.521; 33.522; 33.326 | 95 | 48 |  |  | Thu 10/03/22 | Fri 15/03/24
1397 | 960035 | Study on URSP rules to securely identify applications | FS_USIA | 1 | Rel-18 | S3 | 2022-06-02 08:00 | 2023-03-03 17:00 | 100% | SP-220533 |  | Andreas Kunz, Lenovo | akunz@lenovo.com | 13/7/22: 33.892 added;; 12/9/22: 0%->30; 11/12/22: 30%->50; 17/3/23: 50%->80; 7/9/23: 80%->100 | 33.892 | 96 | 49 |  |  | Thu 02/06/22 | Thu 07/09/23
1398 | 810032 | Study on 5G security enhancement against false base stations | FS_5GFBS | 1 | Rel-18 | S3 | 2018-09-06 08:00 | 2022-12-09 17:00 | 100% | SP-180690 |  | Ivy Guo, Apple | ivy_guo@apple.com | 7/12/18: 0%->10¦20/3/19: FCD:019->09/19¦20/3/19: 10%->50; 31/5/19: 50%->65; 13/9/19: 65%->66; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 66%->75; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: 75%->80; 26/6/20: FCD:12/03/2020->12/20; ; | New | 81 | 41 |  |  | Thu 06/09/18 | Thu 08/06/23
1399 | 960040 | Security Enhancement on RRCResumeRequest Message Protection | SERP | 1 | Rel-18 | S3 | 2022-06-02 08:00 | 2022-12-12 17:00 | 100% | SP-220538 |  | Ivy Guo, Apple | <ivy_guo@apple.com> | 7/9/23: 0%->100 |  | 96 | 49 |  |  | Thu 02/06/22 | Thu 07/09/23
1400 | 960055 | Stage-3 5GS NAS protocol development 18 | 5GProtoc18 | 1 | Rel-18 |  | 2022-06-03 08:00 | 2023-12-12 17:00 | 100% | CP-221268 |  | Sedlacek, Ivo, Ericsson, | ivo <dot> sedlacek <at> ericsson <dot> com | ; 6/6/23: Compl:30%->40% | 23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 | 96 | 49 |  |  | Fri 03/06/22 | Tue 06/06/23
1401 | 960007 | Stage-3 5GS NAS protocol development 18 general aspects | 5GProtoc18 | 2 | Rel-18 | C1 | 2022-06-03 08:00 | 2023-12-12 17:00 | 100% | CP-221268 |  | Sedlacek, Ivo, Ericsson, | ivo <dot> sedlacek <at> ericsson <dot> com |  | 23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 | 96 | 49 |  |  | Fri 03/06/22 | NA
1402 | 960056 | Stage-3 5GS NAS protocol development 18 non 3GPP aspects | 5GProtoc18-non3GPP | 2 | Rel-18 | C1 | 2022-06-03 08:00 | 2023-12-12 17:00 | 100% | CP-221268 |  | Sedlacek, Ivo, Ericsson, | ivo <dot> sedlacek <at> ericsson <dot> com |  | 23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 | 96 | 49 |  |  | Fri 03/06/22 | NA
1403 | 960057 | Stage-3 SAE Protocol Development | SAES18 | 1 | Rel-18 |  | 2022-06-03 08:00 | 2023-12-12 17:00 | 100% | CP-221269 |  | Sethi, Anuj, InterDigital |  | ; 6/6/23: Compl:30%->40% | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 96 | 49 |  |  | Fri 03/06/22 | Tue 06/06/23
1404 | 960008 | Stage-3 SAE Protocol Development general | SAES18 | 2 | Rel-18 | C1 | 2022-06-03 08:00 | 2023-12-12 17:00 | 100% | CP-221269 |  | Sethi, Anuj, InterDigital |  |  | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 96 | 49 |  |  | Fri 03/06/22 | NA
1405 | 960058 | Stage-3 SAE Protocol Development CSFB | SAES18-CSFB | 2 | Rel-18 | C1 | 2022-06-03 08:00 | 2023-12-12 17:00 | 100% | CP-221269 |  | Sethi, Anuj, InterDigital |  |  | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 96 | 49 |  |  | Fri 03/06/22 | NA
1406 | 960059 | Stage-3 SAE Protocol Development non 3GPP | SAES18-non3GPP | 2 | Rel-18 | C1 | 2022-06-03 08:00 | 2023-12-12 17:00 | 100% | CP-221269 |  | Sethi, Anuj, InterDigital |  |  | 23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 | 96 | 49 |  |  | Fri 03/06/22 | NA
1407 | 960009 | Protocol enhancements for Mission Critical Services | MCProtoc18 | 1 | Rel-18 |  | 2022-06-03 08:00 | 2024-03-03 17:00 | 100% | CP-232163 |  | AXELL, Jörgen, Ericsson | jorgen.axell@ericsson.com | ; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated | 24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283 | 96 | 49 |  |  | Fri 03/06/22 | Mon 20/06/22
1408 | 980105 | CT1 aspects of MCProtoc18 | MCProtoc18 | 2 | Rel-18 | C1 | 2022-06-03 08:00 | 2024-03-03 17:00 | 100% | CP-233212 |  | Magnus Tränk, Ericsson | magnus.trank@ericsson.com | ; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 9/6/23: 30%->40 | 24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283 | 96 | 49 |  |  | Fri 03/06/22 | Fri 09/06/23
1409 | 980106 | CT3 aspects of MCProtoc18 | MCProtoc18 | 2 | Rel-18 | C3 | 2022-06-06 08:00 | 2024-03-03 17:00 | 100% | CP-233212 |  | Magnus Tränk, Ericsson | magnus.trank@ericsson.com | ; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 9/6/23: 10%->30 | 24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283 | 96 | 49 |  |  | Fri 03/06/22 | Fri 09/06/23
1410 | 980107 | CT4 aspects of MCProtoc18 | MCProtoc18 | 2 | Rel-18 | C4 | 2022-06-03 08:00 | 2024-03-03 17:00 | 100% | CP-233212 |  | Magnus Tränk, Ericsson | magnus.trank@ericsson.com | ; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 6/6/23: Compl:... | 24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283 | 96 | 49 |  |  | Fri 03/06/22 | Tue 06/06/23
1411 | 960010 | MPS for Supplementary Services | MPSSupServ | 1 | Rel-18 | C1 | 2022-06-03 08:00 | 2022-12-08 17:00 | 100% | CP-221271 |  | Peter Monnes, Peraton Labs | pmonnes@peratonlabs.com | 20/6/22: FCD:12/12/2022->08/12/2022WID: C1-221271->CP-221271Rapporteur: Peter Monnes, Peraton Labs ->Peter Monnes, Peraton LabsRap eMail: pmonnes@peratonlabs.com ->pmonnes@peratonlabs.comList of Impacted TS & TR updated | 24.229; 24.173; 24.629; 24.605; 24.239; 24.604; 24.642 | 96 | 49 |  |  | Fri 03/06/22 | Mon 20/06/22
1412 | 970035 | IMS Stage-3 IETF Protocol Alignment | IMSProtoc18 | 1 | Rel-18 |  | 2022-06-03 08:00 | 2023-12-12 17:00 | 100% | CP-223102 |  | Won, Sung Hwan, Nokia | sung(dot)won(at)nokia(dot)com |  | 23.218; 24.229; 24.930; 29.163; 29.165; 29.292 | 96 | 49 |  |  | Fri 03/06/22 | Mon 20/06/22
1413 | 970047 | CT1 aspects of IMSProtoc18 | IMSProtoc18 | 2 | Rel-18 | C1 | 2022-06-03 08:00 | 2023-12-12 17:00 | 100% | CP-223102 |  | Won, Sung Hwan, Nokia | sung(dot)won(at)nokia(dot)com | ; 6/6/23: Compl:30%->40% | 23.218; 24.229; 24.930; 29.163; 29.165; 29.292 | 97 | 49 |  |  | Wed 07/09/22 | Tue 06/06/23
1414 | 970048 | CT3 aspects of IMSProtoc18 | IMSProtoc18 | 2 | Rel-18 | C3 | 2022-06-03 08:00 | 2023-12-12 17:00 | 100% | CP-223102 |  | Won, Sung Hwan, Nokia | sung(dot)won(at)nokia(dot)com | 9/6/23: 30%->60 | 23.218; 24.229; 24.930; 29.163; 29.165; 29.292 | 97 | 49 |  |  | Wed 07/09/22 | Fri 09/06/23
1415 | 980004 | Enhancement of Shared Data ID and Handling | ShDatID_H | 1 | Rel-18 | C4 | 2022-03-07 08:00 | 2024-03-03 17:00 | 100% | CP-232030 |  | Jing, Hao, Huawei | hao.jing@huawei.com | ; 6/6/23: Compl:0%->40% | 29.503; 29.504; 29.505 | 96 | 49 |  |  | Fri 03/06/22 | Tue 06/06/23
1416 | 1050016 | UE conformance test for NB-IoT/eMTC Non-Terrestrial Networks in EPS | IoT_SAT_UEConTest | 1 | Rel-18 | C6 | 2024-09-09 08:00 | 2025-09-09 17:00 | 100% | CP-242075 |  | Daiwei Zhou, MediaTek Inc | daiwei.zhou@mediatek.com |  |  | 96 | 49 |  |  | Fri 03/06/22 | Tue 06/06/23
1417 | 1050008 | Test method of GBA_U Based APIs | TEST_GBA_U_APIs | 1 | Rel-18 | C6 | 2024-09-09 08:00 | 2025-06-06 17:00 | 80% | CP-242028 |  | Huo Weijing(China Mobile) | huoweijing@chinamobile.com |  |  | 96 | 49 |  |  | Fri 03/06/22 | Tue 06/06/23
1418 | 980036 | Rel-18 enhancements of session management policy control | SMPC18 | 1 | Rel-18 | C3 | 2022-12-15 08:00 | 2023-12-12 17:00 | 100% | CP-223208 |  | Xiaoyun Zhou, Huawei | zhouxiaoyun8@huawei.com | ; 6/6/23: Compl:25%->60% | 29.512; 29.513; 29.514 | 96 | 49 |  |  | Fri 03/06/22 | Tue 06/06/23
1419 | 960014 | Deleted - SMS over IMS to emergency centre | SMS2ECdeleted | 1 | Rel-18 | S1 | 2022-06-02 08:00 | 2022-06-08 15:00 | 100% | SP-220438 |  | Bruno Tossou, Orange | bruno.tossou@orange.com | ; 4/6/22: 0%->45; 12/9/22: 45%->100 | 22.101 | 96 | 49 |  |  | Thu 02/06/22 | Mon 12/09/22
1420 | 990003 | Enhancements on Service-based support for SMS in 5GC | eSMS_SBI | 1 | Rel-18 | C4 | 2023-03-13 08:00 | 2023-12-15 17:00 | 100% | CP-230025 |  | Liu, Liu, China Telecom | liuliu66@chinatelecom.cn | ; 6/6/23: Compl:0%->50% | 23.540; 29.338; 29.329; 29.230 | 96 | 49 |  |  | Fri 03/06/22 | Tue 06/06/23
1421 | 1010026 | Modified PRINS for roaming service providers in 5G | Roaming5G | 1 | Rel-18 | S1 | 2023-08-08 08:00 | 2023-09-09 17:00 | 100% | SP-231190 |  | Targali, Yousif, Verizon | yousif.targali@verizon.com | 9/23: company-submitted WID, to be corrected | 22.261; 33.501 | 101 | 51 |  |  | Wed 20/09/23 | NA
1422 | 1010027 | Stage 1 of Roaming5G | Roaming5G | 2 | Rel-18 | S1 | 2023-08-08 08:00 | 2023-09-09 17:00 | 100% | SP-231190 |  | Targali, Yousif, Verizon | yousif.targali@verizon.com | 9/23: company-submitted WID, to be corrected | 22.261 | 101 | 51 |  |  | Wed 20/09/23 | NA
1423 | 1010028 | Stage 3 of Roaming5G | Roaming5G | 2 | Rel-18 | S3 | 2023-08-08 08:00 | 2023-09-09 17:00 | 100% | SP-231190 |  | Targali, Yousif, Verizon | yousif.targali@verizon.com | 9/23: company-submitted WID, to be corrected; 8/12/23: 100%->100 | 33.501 | 101 | 51 |  |  | Wed 20/09/23 | Fri 08/12/23
1424 | 1020001 | NRF API enhancements to avoid signalling and storing of redundant data | NRFe | 1 | Rel-18 | C4 | 2023-12-12 08:00 | 2024-03-15 17:00 | 100% | CP-233025 |  | Wiehe, Ulrich, Nokia | ulrich.wiehe@nokia.com |  | 29.510, 29.571, 29.504 | 96 | 49 |  |  | Fri 03/06/22 | Tue 06/06/23
1425 | 0 | Rel-18 Other Security aspects | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1426 | 950019 | Security Assurance Specification for AKMA Anchor Function Function (AAnF) | SCAS_5G_AAnF | 1 | Rel-18 | S3 | 2022-03-10 08:00 | 2023-03-03 17:00 | 100% | SP-220197 |  | Xiaoting Huang, China Mobile | huangxiaoting@chinamobile.com | ; 4/6/22: 0%->10; 13/7/22: 33.537 added;; 11/12/22: 10%->70; 17/3/23: 70%->90; 8/6/23: 90%->95; 15/3/24: 95%->100 | 33.926 ; 33.537 | 95 | 48 |  |  | Thu 10/03/22 | Fri 15/03/24
1427 | 990044 | 5G Security Assurance Specification (SCAS) for the Policy Control Function (PCF) | SCAS_5G_PCF | 1 | Rel-18 | S3 | 2023-03-16 08:00 | 2023-12-12 17:00 | 100% | SP-230157 |  | Andreas, Joerg, BSI Germany | joerg.andreas@bsi.bund.de | ; 31/3/23: 33.528 added;; 7/9/23: 0%->40; 7/9/23: FCD:09/09/2023->12/23; 15/3/24: 40%->100 | 33.926 ; 33.528 | 99 | 50 |  |  | Thu 16/03/23 | Fri 15/03/24
1428 | 980021 | IETF DTLS protocol profile for AKMA and GBA | AKMA_GBA_DTLS | 1 | Rel-18 | S3 | 2022-12-09 08:00 | 2023-06-06 17:00 | 100% | SP-221143 |  | Liu, yuze, ZTE | liu.yuze@zte.com.cn | ; 8/6/23: 0%->90; 7/9/23: 90%->100 | 33.535; 33.220; 33.222 | 98 | 50 |  |  | Fri 09/12/22 | Thu 07/09/23
1429 | 980023 | IETF OSCORE protocol profiles for GBA and AKMA | AKMA_GBA_OSCORE | 1 | Rel-18 | S3 | 2022-12-09 08:00 | 2023-09-09 17:00 | 100% | SP-221146 |  | Tsiatsis, Vlasios, Ericsson | vlasios.tsiatsis@ericsson.com | ; 8/6/23: 0%->80; 7/9/23: FCD:06/06/2023->/23; 15/3/24: 80%->100 | 33.535; 33.220; 33.222 | 98 | 50 |  |  | Fri 09/12/22 | Fri 15/03/24
1430 | 950022 | SCAS for split-gNB product classes | SCAS_5G_split_gNB | 1 | Rel-18 | S3 | 2022-03-10 08:00 | 2023-03-03 17:00 | 100% | SP-220200 |  | Escott, Adrian, Qualcomm Incorporated | aescott@qti.qualcomm.com | ; 4/6/22: 0%->5; 13/7/22: 33.742 added;; 12/9/22: 5%->25; 11/12/22: 25%->60; 17/3/23: 60%->85; 17/3/23: 33.523 added;; 8/6/23: 85%->99; 15/3/24: 99%->100 | 33.926 ; 33.742; 33.523 | 95 | 48 |  |  | Thu 10/03/22 | Fri 15/03/24
1431 | 1010019 | Home network triggered primary authentication | HN_Auth | 1 | Rel-18 | S3 | 2022-03-10 08:00 | 2024-03-03 17:00 | 100% | SP-221147 |  | He Li, Huawei | LIHE2@HUAWEI.COM | ; 15/3/24: 99%->100 | 33.501; 33.535 | 98 | 50 |  |  | Fri 09/12/22 | Fri 15/03/24
1432 | 950020 | Study of Security aspect of home network triggered primary authentication | FS_HN_Auth | 2 | Rel-18 | S3 | 2022-03-10 08:00 | 2022-12-12 17:00 | 100% | SP-220198 |  | He Li, Huawei | LIHE2@HUAWEI.COM | 4/6/22: 0%->30; 12/9/22: 30%->60; 11/12/22: 60%->80; 17/3/23: 80%->100 |  | 95 | 48 |  |  | Thu 10/03/22 | Fri 17/03/23
1433 | 980024 | Security aspects of home network triggered primary authentication | HN_Auth | 2 | Rel-18 | S3 | 2022-12-09 08:00 | 2023-06-06 17:00 | 100% | SP-221147 |  | He Li, Huawei | LIHE2@HUAWEI.COM | ; 7/9/23: 0%->100 | 33.501; 33.535 | 98 | 50 |  |  | Fri 09/12/22 | Thu 07/09/23
1434 | 1010001 | CT aspects of home network triggered primary authentication | HN_Auth | 2 | Rel-18 | C4 | 2023-09-09 08:00 | 2024-03-03 17:00 | 100% | CP-232028 |  | Jing, Hao, Huawei | hao.jing@huawei.com |  | 29.503, 29.504, 29.505, 29.518 | 98 | 50 |  |  | Fri 09/12/22 | NA
1435 | 950018 | Study on AKMA Phase 2 | FS_AKMA_Ph2 | 1 | Rel-18 | S3 | 2022-03-10 08:00 | 2022-12-12 17:00 | 100% | SP-220991 |  | Xiaoting Huang, China Mobile | huangxiaoting@chinamobile.com | 4/6/22: 0%->15; 13/7/22: 33.737 added;; 12/9/22: 15%->35; 23/9/22: WID:SP-220327->SP-220991; 11/12/22: 35%->70; 17/3/23: 70%->80; 8/6/23: 80%->95; 15/3/24: 95%->100 | 33.737 | 95 | 48 |  |  | Thu 10/03/22 | Fri 15/03/24
1436 | 990040 | AKMA phase 2 | AKMA_Ph2 | 1 | Rel-18 | S3 | 2023-03-16 08:00 | 2023-09-09 17:00 | 100% | SP-230153 |  | Huang Xiaoting, China Mobile | huangxiaoting@chinamobile.com | ; 8/6/23: 0%->95; 15/3/24: 95%->100 | 33.535 | 99 | 50 |  |  | Thu 16/03/23 | Fri 15/03/24
1437 | 940016 | Study of privacy of identifiers over radio access | FS_Id_Prvc | 1 | Rel-18 | S3 | 2021-12-13 08:00 | 2023-03-03 17:00 | 100% | SP-211364 |  | Brusilovsky, Alec, Interdigital | alec.brusilovsky@interdigital.com | 7/1/22: 33.870 added;; 12/3/22: 0%->5; 4/6/22: 5%->10; 12/9/22: 10%->12; 17/3/23: 12%->25; 8/6/23: 25%->40; 7/9/23: 40%->80; 15/3/24: 80%->100 | 33.870 | 94 | 48 |  |  | Mon 13/12/21 | Fri 15/03/24
1438 | 820007 | Study on Security Impacts of Virtualisation | FS_SIV | 1 | Rel-18 | S3 | 2018-12-13 08:00 | 2022-12-09 17:00 | 100% | SP-181236 |  | Alex Leadbeater, BT Plc | alex.leadbeater@bt.com | 20/3/19: 0%->2¦20/3/19: 0%->2; 31/5/19: 2%->10; 13/9/19: FCD:19/09/2019->12/20; 13/9/19: 10%->12; 6/12/19: 12%->45; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 45%-> ; |  | 82 | 42 |  |  | Thu 06/12/18 | Thu 07/09/23
1439 | 960038 | Study on Zero Trust Security principles in mobile networks | FS_ZTS | 1 | Rel-18 | S3 | 2022-06-02 08:00 | 2023-03-03 17:00 | 100% | SP-220674 |  | Sheeba Backia Mary B, Lenovo | smary@lenovo.com | 13/7/22: 33.894 added; 17/8/22: WID:SP-220536->SP-220674; 12/9/22: 0%->6; 11/12/22: 6%->25; 17/3/23: 25%->30; 8/6/23: 30%->40; 7/9/23: 40%->100 | 33.894 | 96 | 49 |  |  | Thu 02/06/22 | Thu 07/09/23
1440 | 960039 | Study of Security aspects on User Consent for 3GPP Services Phase 2 | FS_UC3S_Ph2 | 1 | Rel-18 | S3 | 2022-06-02 08:00 | 2023-03-03 17:00 | 100% | SP-220537 |  | Rong Wu, Huawei, | Raina.wu@huawei.com | 13/7/22: 33.896 added;; 12/9/22: 0%->10; 11/12/22: 10%->50; 17/3/23: 50%->100 | 33.896 | 96 | 49 |  |  | Thu 02/06/22 | Fri 17/03/23
1441 | 1000004 | Security aspects on User Consent for 3GPP services Phase 2 | UC3S_SEC_Ph2 | 1 | Rel-18 | S3 | 2023-05-01 08:00 | 2023-06-06 17:00 | 100% | SP-230557 |  | Rong Wu, Huawei Technologies, | Raina.wu@huawei.com | ; 15/3/24: 0%->100 | 33.501 | 100 | 51 |  |  | Thu 08/06/23 | Fri 15/03/24
1442 | 1010013 | Security Assurance Specification for 5G Phase 3 | SCAS_5G_Ph3 | 1 | Rel-18 | S3 | 2023-09-06 08:00 | 2024-03-03 17:00 | 100% | SP-230867 |  | Wu, Rong, Huawei Technologies Co., Ltd. | Raina.wu@huawei.com | ; 8/12/23: 0%->10; 15/3/24: 10%->100 | 33.926 | 101 | 51 |  |  | Wed 06/09/23 | Fri 15/03/24
1443 | 0 | Rel-18 NR-only: topics other than band | - | 1 | Rel-18 |  | 2019-03-07 07:00 | 2019-03-07 07:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1444 | 950073 | NR demodulation performance evolution | NR_demod_enh3 | 1 | Rel-18 |  | 2022-03-15 08:00 | 2024-12-12 17:00 | 91% | RP-241292 |  | China Telecom |  | compare REL-16 NR_perf_enh, REL-17 NR_demod_enh2; no Core part; TR 38.8XX ; 29/3/23: WID:RP-220932->RP-230314; 6/10/23: WID:RP-230314->RP-232685; 2/1/24: WID:RP-232685->RP-233586; 23/7/24: WID:RP-233586->RP-241292 |  | 95 | 48 |  |  | Tue 05/04/22 | Tue 23/07/24
1445 | 1001061 | Core part: NR demodulation performance evolution | NR_demod_enh3-Core | 2 | Rel-18 | R4 | 2023-06-07 08:00 | 2023-12-12 17:00 | 100% | RP-241292 | RP-233584 | Jingzhou Wu, China Telecom | wujingzhou@chinatelecom.cn | 6/9/23: Compl:0%->33%; Stat Rep: ->RP-232250; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn; ; 8/12/23: Compl:33%->100%; Stat Rep: RP-232250->RP-233584; |  | 100 | 51 |  |  | Thu 29/06/23 | Fri 08/12/23
1446 | 950273 | Perf. part: NR demodulation performance evolution | NR_demod_enh3-Perf | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2024-06-06 17:00 | 100% | RP-241292 | RP-241293 | Jingzhou Wu, China Telecom | wujingzhou@chinatelecom.cn | compare REL-16 NR_perf_enh, REL-17 NR_demod_enh2; no Core part; TR 38.8XX ; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221287; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn12/7/22: WID:RP-2...;... | 38.878 | 95 | 48 |  |  | Tue 05/04/22 | Thu 13/06/24
1447 | 1040105 | UE Conformance - NR demodulation performance evolution | NR_demod_enh3-UEConTest | 2 | Rel-18 | R5 | 2024-06-06 08:00 | 2025-12-12 17:00 | 80% | RP-241298 | RP-252548 | China Telecom |  | 4/9/24: FCD:12/12/2025->25/12/2024; Compl:0%->8%; Stat Rep: ->RP-241995; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:8%->41%; Stat Rep: RP-241995->RP-242854; ; 6/3/25: FCD:24/06/2025->12/12/2025; Compl:41%->57%; Stat Rep: RP-242854->RP-250378; ; 6/6/25: |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 11/09/25
1448 | 991045 | NR channel raster enhancement | NR_channel_raster_enh | 1 | Rel-18 | R4 | 2023-03-06 08:00 | 2026-09-09 17:00 | 39% | RP-234025 |  | Ericsson |  | 2/1/24: WID:RP-230813->RP-234025 |  | 99 | 50 |  |  | Fri 07/04/23 | Tue 02/01/24
1449 | 991145 | Core part: NR channel raster enhancement | NR_channel_raster_enh-Core | 2 | Rel-18 | R4 | 2023-03-06 08:00 | 2023-11-13 09:00 | 95% | RP-234025 | RP-233392 | Christian Bergljung, Ericsson | Christian.Bergljung@ericsson.com | ; 7/6/23: Compl:0%->25%; ;...; 6/9/23: Compl:25%->50%; WID: RP-230813->RP-231469; Stat Rep: ->RP-231756; Rapporteur: Ericsson->Christian Bergljung, Ericsson; Rap eMail: ->Christian.Bergljung@ericsson.com; ; 8/12/23: FCD:12/12/2023->01/03/2024; Compl:50%-> |  | 99 | 50 |  |  | Fri 07/04/23 | Fri 08/12/23
1450 | 1090062 | UE Conformance - Channel raster enhancement | NR_channel_raster_enh-UEConTest | 2 | Rel-18 | R5 | 2025-09-09 08:00 | 2026-09-09 17:00 | 0% | RP-252544 |  | China Telecom |  | tested: REL-18 WI NR_channel_raster_enh |  | 109 | 55 |  |  | Mon 29/09/25 | NA
1451 | 981042 | Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) | 4Rx_NR_bands_R18 | 1 | Rel-18 |  | 2022-12-13 08:00 | 2025-06-06 17:00 | 100% | RP-240251 |  | ZTE |  | 29/3/23: WID:RP-223541->RP-230137; 6/10/23: WID:RP-230137->RP-231844; 2/1/24: WID:RP-231844->RP-234004; 2/4/24: WID:RP-234004->RP-240251 |  | 98 | 50 |  |  | Mon 09/01/23 | Tue 02/04/24
1452 | 981142 | Core part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) | 4Rx_NR_bands_R18-Core | 2 | Rel-18 | R4 | 2022-12-13 08:00 | 2024-03-01 17:00 | 100% | RP-240251 | RP-240252 | Wubin, Zhou, ZTE | zhou.wubin@zte.com.cn | 17/3/23: Compl:0%->30%; Stat Rep: ->RP-230138; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 7/6/23: Compl:30%->35%; 6/9/23: Compl:35%->60%; WID: RP-230137->RP-231119; Stat Rep: RP-230138->RP-231845; ; 8/12/23: FCD:12/12/2023-... |  | 98 | 50 |  |  | Mon 09/01/23 | Thu 14/03/24
1453 | 981242 | Stopped - Perf. part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) | 4Rx_NR_bands_R18-Perf | 2 | Rel-18 | R4 | 2022-12-13 08:00 | 2024-03-01 17:00 | 100% | RP-240251 | RP-240252 | Wubin, Zhou, ZTE | zhou.wubin@zte.com.cn | 17/3/23: Compl:0%->30%; Stat Rep: ->RP-230138; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 7/6/23: Compl:30%->35%; 6/9/23: Compl:35%->60%; WID: RP-230137->RP-231119; Stat Rep: RP-230138->RP-231845; ; 8/12/23: FCD:12/12/2023-... |  | 98 | 50 |  |  | Mon 09/01/23 | Tue 02/04/24
1454 | 1040102 | UE Conformance - 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) | 4Rx_NR_bands_R18-UEConTest | 2 | Rel-18 | R5 | 2024-06-06 08:00 | 2025-06-06 17:00 | 100% | RP-250164 | RP-250990 | ZTE |  | 4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->13%; Stat Rep: ->RP-241772; ; 6/12/24: Compl:13%->52%; Stat Rep: RP-241772->RP-242810; ; 24/1/25: WID:RP-241093->RP-242811; 6/3/25: FCD:14/02/2025->06/06/2025; Compl:52%->95%; Stat Rep: RP-242810->RP-250163; |  | 104 | 53 |  |  | Tue 23/07/24 | Fri 06/06/25
1455 | 970085 | High power UE (power class 1.5) for NR FR1 TDD single band | HPUE_NR_FR1_TDD_R18 | 1 | Rel-18 |  | 2022-09-12 08:00 | 2025-06-06 17:00 | 72% | RP-223499 |  | CMCC |  | 9/1/23: WID:RP-222351->RP-223499 |  | 97 | 49 |  |  | Wed 19/10/22 | Mon 09/01/23
1456 | 970185 | Core part: High power UE (power class 1.5) for NR FR1 TDD single band | HPUE_NR_FR1_TDD_R18-Core | 2 | Rel-18 | R4 | 2022-09-12 08:00 | 2023-12-12 17:00 | 100% | RP-223499 | RP-233448 | Chunxia Guo, CMCC | guochunxia@chinamobile.com | 9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->30%; Stat Rep: ->RP-223053; Rapporteur: CMCC->Chunxia Guo, CMCC; Rap eMail: ->guochunxia@chinamobile.com; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-223053->RP-230280; 17/3/23: 38.895 added;; ;...;... | 38.895 | 97 | 49 |  |  | Wed 19/10/22 | Fri 08/12/23
1457 | 970285 | Perf. part: High power UE (power class 1.5) for NR FR1 TDD single band | HPUE_NR_FR1_TDD_R18-Perf | 2 | Rel-18 | R4 | 2023-01-31 09:00 | 2023-12-12 17:00 | 0% | RP-223499 | RP-223053 | Chunxia Guo, CMCC | guochunxia@chinamobile.com | 9/12/22: FCD:12/12/2023->01/12/2023; Stat Rep: ->RP-223053; Rapporteur: CMCC->Chunxia Guo, CMCC; Rap eMail: ->guochunxia@chinamobile.com; |  | 97 | 49 |  |  | Wed 19/10/22 | Fri 09/12/22
1458 | 1000053 | UE Conformance - High power UE (power class 1.5) for NR FR1 TDD single band | HPUE_NR_FR1_TDD_R18-UEConTest | 2 | Rel-18 | R5 | 2023-06-08 08:00 | 2025-06-06 17:00 | 100% | RP-241199 | RP-241200 | Dan SONG (CMCC), Yuxin Hao (Huawei), CMCC, Huawei | songdan@chinamobile.com, haoyuxin@huawei.com | 21/9/23: Compl:0%->29%; Stat Rep: ->RP-232245; Rapporteur: CMCC->Dan SONG (CMCC), Yuxin Hao (Huawei), CMCC, Huawei; Rap eMail: ->songdan@chinamobile.com, haoyuxin@huawei.com; ; 8/12/23: Compl:29%->35%; Stat Rep: RP-232245->RP-233416; ; 14/3/24: FCD:05/... |  | 100 | 51 |  |  | Thu 29/06/23 | Tue 23/07/24
1459 | 970086 | High power UE (power class 2) for NR FR1 FDD single band | HPUE_NR_FR1_FDD_R18 | 1 | Rel-18 |  | 2022-09-12 08:00 | 2024-12-12 17:00 | 100% | RP-241314 |  | China Unicom |  | 9/1/23: WID:RP-222625->RP-222967; 29/3/23: WID:RP-222967->RP-230352; 6/10/23: WID:RP-230352->RP-232216; 2/1/24: WID:RP-232216->RP-233031; 2/4/24: WID:RP-233031->RP-240120; 23/7/24: WID:RP-240120->RP-241314 |  | 97 | 49 |  |  | Wed 19/10/22 | Tue 23/07/24
1460 | 970186 | Core part: High power UE (power class 2) for NR FR1 FDD single band | HPUE_NR_FR1_FDD_R18-Core | 2 | Rel-18 | R4 | 2022-09-12 08:00 | 2024-06-06 17:00 | 100% | RP-241314 | RP-241315 | Basaier Jialade, China Unicom | basejld@chinaunicom.cn | 9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222965; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222965->RP-230353; 17/3/23: ...;... | 38.896 | 97 | 49 |  |  | Wed 19/10/22 | Thu 13/06/24
1461 | 970286 | Perf. part: High power UE (power class 2) for NR FR1 FDD single band | HPUE_NR_FR1_FDD_R18-Perf | 2 | Rel-18 | R4 | 2022-09-12 08:00 | 2024-06-06 17:00 | 100% | RP-241314 | RP-241315 | Basaier Jialade, China Unicom | basejld@chinaunicom.cn | 9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222965; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222965->RP-230353; ;...; 6/9/23:... |  | 97 | 49 |  |  | Wed 19/10/22 | Thu 13/06/24
1462 | 1000051 | UE Conformance - High power UE (power class 2) for NR FR1 FDD single band | HPUE_NR_FR1_FDD_R18-UEConTest | 2 | Rel-18 | R5 | 2023-06-08 08:00 | 2025-09-09 17:00 | 100% | RP-251979 | RP-251978 | Shi，Yu, China Unicom | shiyu19@chinaunicom.cn | 6/9/23: Compl:0%->5%; Stat Rep: ->RP-231549; Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn; ; 8/12/23: Stat Rep: RP-231549->RP-232773; ; 2/1/24: WID:RP-230869->RP-232774; 14/3/24: FCD:05/06/2024->12/12/2024; Compl:... |  | 100 | 51 |  |  | Thu 29/06/23 | Mon 29/09/25
1463 | 970087 | High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band | HPUE_NR_FR1_TDD_intra_CA_R18 | 1 | Rel-18 |  | 2022-09-12 08:00 | 2024-06-06 17:00 | 100% | RP-241254 |  | Huawei |  | 9/1/23: WID:RP-222647->RP-223356; 29/3/23: WID:RP-223356->RP-230479; 6/10/23: WID:RP-230479->RP-232377; 2/1/24: WID:RP-232377->RP-233975; 2/4/24: WID:RP-233975->RP-240428; 23/7/24: WID:RP-240428->RP-241254 |  | 97 | 49 |  |  | Wed 19/10/22 | Tue 23/07/24
1464 | 970187 | Core part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band | HPUE_NR_FR1_TDD_intra_CA_R18-Core | 2 | Rel-18 | R4 | 2022-09-12 08:00 | 2024-06-06 17:00 | 100% | RP-241254 | RP-241253 | Lingyu Kong, Huawei, HiSilicon | konglingyu4@hisilicon.com | 9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->20%; WID: RP-222647->RP- 222647; Stat Rep: ->RP-223355; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->30%; W..... | 38.897 | 97 | 49 |  |  | Wed 19/10/22 | Thu 13/06/24
1465 | 970287 | Stopped - Perf. part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band | HPUE_NR_FR1_TDD_intra_CA_R18-Perf | 2 | Rel-18 | R4 | 2022-09-13 08:00 | 2024-03-01 17:00 | 100% | RP-240428 | RP-233204 | Lingyu Kong, Huawei, HiSilicon | konglingyu4@hisilicon.com | 9/12/22: FCD:12/12/2023->01/12/2023; WID: RP-222647->RP- 222647; Stat Rep: ->RP-223355; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; 17/3/23: WID: RP-223356->RP- 223356; Stat Rep: RP-223355->RP-230478; ; ... |  | 97 | 49 | 102 |  | Wed 19/10/22 | Tue 02/01/24
1466 | 970089 | Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) | HPUE_FR1_TDD_NR_CADC_SUL_R18 | 1 | Rel-18 |  | 2022-09-12 08:00 | 2024-06-06 17:00 | 100% | RP-241302 |  | China Telecom |  | 9/1/23: WID:RP-222623->RP-223496; 29/3/23: WID:RP-223496->RP-230309; 6/10/23: WID:RP-230309->RP-232256; 2/1/24: WID:RP-232256->RP-233561; 2/4/24: WID:RP-233561->RP-240763; 23/7/24: WID:RP-240763->RP-241302 |  | 97 | 49 |  |  | Wed 19/10/22 | Tue 23/07/24
1467 | 970189 | Core part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) | HPUE_FR1_TDD_NR_CADC_SUL_R18-Core | 2 | Rel-18 | R4 | 2022-09-12 08:00 | 2024-06-06 17:00 | 100% | RP-241302 | RP-241303 | Lei GAO, China Telecom | gaol8@chinatelecom.cn | 9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-222941; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-222941->RP-230310; ...;... | 38.899 | 97 | 49 |  |  | Wed 19/10/22 | Thu 13/06/24
1468 | 970289 | Stopped: Perf. part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) | HPUE_FR1_TDD_NR_CADC_SUL_R18-Perf | 2 | Rel-18 | R4 | 2022-09-12 08:00 | 2022-09-12 17:00 | 100% | RP-241302 | RP-241303 | Lei GAO, China Telecom | gaol8@chinatelecom.cn | 9/12/22: FCD:12/12/2023->01/12/2022; Stat Rep: ->RP-222941; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; 17/3/23: FCD:01/12/2022->12/12/2023; Stat Rep: RP-222941->RP-230310; ;...; 6/9/23: WID: RP-230309->RP-23... |  | 97 | 49 |  |  | Wed 19/10/22 | Tue 23/07/24
1469 | 970090 | Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1) | HPUE_FR1_FDD_NR_CADC_R18 | 1 | Rel-18 |  | 2022-09-12 08:00 | 2024-06-06 17:00 | 100% | RP-241317 |  | China Unicom |  | 9/1/23: WID:RP-222626->RP-222968; 29/3/23: WID:RP-222968->RP-230354; 2/1/24: WID:RP-230354->RP-234017; 2/4/24: WID:RP-234017->RP-240123; 23/7/24: WID:RP-240123->RP-241317 |  | 97 | 49 |  |  | Wed 19/10/22 | Tue 23/07/24
1470 | 970190 | Core part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1) | HPUE_FR1_FDD_NR_CADC_R18-Core | 2 | Rel-18 | R4 | 2022-09-12 08:00 | 2024-06-06 17:00 | 100% | RP-241317 | RP-241318 | Basaier Jialade, China Unicom | basejld@chinaunicom.cn | 9/12/22: FCD:12/06/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222966; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222966->RP-230355; 17/3/23: ...;... | 38.850 | 97 | 49 |  |  | Wed 19/10/22 | Thu 13/06/24
1471 | 970290 | Stopped - Perf. Part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1) | HPUE_FR1_FDD_NR_CADC_R18-Perf | 2 | Rel-18 | R4 | 2022-09-12 08:00 | 2024-03-01 17:00 | 100% | RP-240123 | RP-241318 | Basaier Jialade, China Unicom | basejld@chinaunicom.cn | 9/12/22: FCD:12/06/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222966; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222966->RP-230355; ;...; 6/9/23:... |  | 97 | 49 | 102 |  | Wed 19/10/22 | Thu 13/06/24
1472 | 970083 | Adding new channel bandwidth(s) support to existing NR bands | NR_bands_R18_BWs | 1 | Rel-18 |  | 2022-09-08 08:00 | 2024-03-01 17:00 | 100% | RP-232952 |  | Ericsson |  | 9/1/23: WID:RP-222629->RP-222898; 29/3/23: WID:RP-222898->RP-230756; 6/10/23: WID:RP-230756->RP-231706; 2/1/24: WID:RP-231706->RP-232952 |  | 97 | 49 |  |  | Fri 23/09/22 | Tue 02/01/24
1473 | 970183 | Core part: Adding new channel bandwidth(s) support to existing NR bands | NR_bands_R18_BWs-Core | 2 | Rel-18 | R4 | 2022-09-08 08:00 | 2024-03-01 17:00 | 100% | RP-232952 | RP-240275 | Dominique Everaere, Ericsson | dominique.everaere@erisson.com | 9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->2%; Stat Rep: ->RP-222899; Rapporteur: Ericsson->Dominique Everaere, Ericsson; Rap eMail: ->dominique.everaere@erisson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:2%->5%; Stat Rep: RP-222899->RP-230..... |  | 97 | 49 |  |  | Fri 23/09/22 | Thu 14/03/24
1474 | 970081 | Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirement for NR UEs | NR_MIMO_OTA_enh | 1 | Rel-18 | R4 | 2022-09-08 08:00 | 2025-06-06 17:00 | 100% | RP-240736 |  | CAICT |  | 9/1/23: WID:RP-222668->RP-223509; 6/10/23: WID:RP-223509->RP-232679; 6/10/23: 38.761 added;; 2/1/24: WID:RP-232679->RP-233742; 2/4/24: WID:RP-233742->RP-240736 | 38.761 | 97 | 49 |  |  | Fri 23/09/22 | Tue 02/04/24
1475 | 970181 | Core part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirement for NR UEs | NR_MIMO_OTA_enh-Core | 2 | Rel-18 | R4 | 2022-09-08 08:00 | 2023-12-12 17:00 | 100% | RP-240736 | RP-241290 | Zhu, Siting, CAICT | zhusiting@caict.ac.cn | 9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223185; Rapporteur: CAICT->Zhu, Siting, CAICT; Rap eMail: ->zhusiting@caict.ac.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->35%; Stat Rep: RP-223185->RP-230367; ...; 6/9/23: Com... |  | 97 | 49 |  |  | Fri 23/09/22 | Thu 13/06/24
1476 | 970281 | Perf. Part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirement for NR UEs | NR_MIMO_OTA_enh-Perf | 2 | Rel-18 | R4 | 2022-09-12 08:00 | 2024-06-06 17:00 | 100% | RP-240736 | RP-241290 | Zhu, Siting, CAICT | zhusiting@caict.ac.cn | 9/12/22: FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-223185; Rapporteur: CAICT->Zhu, Siting, CAICT; Rap eMail: ->zhusiting@caict.ac.cn; 17/3/23: Stat Rep: RP-223185->RP-230367; ;...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:20%->30%; Stat Rep: RP-2303... |  | 97 | 49 |  |  | Fri 23/09/22 | Thu 13/06/24
1477 | 1040112 | UE Conformance - Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirements for NR UEs | NR_MIMO_OTA_enh-UEConTest | 2 | Rel-18 | R5 | 2024-06-06 08:00 | 2025-06-06 17:00 | 100% | RP-241504 | RP-251177 | Apple |  | 4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->45%; ; 6/12/24: Compl:45%->65%; Stat Rep: ->RP-242479; ; 6/3/25: FCD:14/02/2025->06/06/2025; Compl:65%->80%; Stat Rep: RP-242479->RP-250154; ; 6/6/25: Compl:80%->100%; Stat Rep: RP-250154->RP-251177; |  | 104 | 53 |  |  | Tue 23/07/24 | Fri 06/06/25
1478 | 981047 | Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells | NR_2SUL_cell_combos_R18 | 1 | Rel-18 |  | 2022-12-13 08:00 | 2024-03-01 17:00 | 100% | RP-240796 |  | CMCC |  | 29/3/23: WID:RP-223553->RP-230719; 6/10/23: WID:RP-230719->RP-232688; 2/1/24: WID:RP-232688->RP-233446; 2/4/24: WID:RP-233446->RP-240796 |  | 98 | 50 |  |  | Mon 09/01/23 | Tue 02/04/24
1479 | 981147 | Core part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells | NR_2SUL_cell_combos_R18-Core | 2 | Rel-18 | R4 | 2022-12-13 08:00 | 2024-03-01 17:00 | 100% | RP-240796 | RP-240159 | Xiaoran ZHANG, CMCC | zhangxiaoran@chinamobile.com | 17/3/23: Compl:0%->10%; Stat Rep: ->RP-230298; Rapporteur: CMCC->Xiaoran ZHANG, CMCC; Rap eMail: ->zhangxiaoran@chinamobile.com; 17/3/23: 38.718-00-02 added;; 31/3/23: Stat Rep: RP-230298->RP-230718; ;...; 6/9/23: Compl:30%->50%; Stat Rep: RP-230718->... | 38.718-00-02 | 98 | 50 |  |  | Mon 09/01/23 | Thu 14/03/24
1480 | 981247 | Stopped - Perf. part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells | NR_2SUL_cell_combos_R18-Perf | 2 | Rel-18 | R4 | 2022-12-13 08:00 | 2024-03-01 17:00 | 100% | RP-240796 | RP-233445 | Xiaoran ZHANG, CMCC | zhangxiaoran@chinamobile.com | 17/3/23: FCD:12/12/2023->06/06/2024; Compl:0%->10%; Stat Rep: ->RP-230298; Rapporteur: CMCC->Xiaoran ZHANG, CMCC; Rap eMail: ->zhangxiaoran@chinamobile.com; 31/3/23: FCD:06/06/2024->12/12/2023; Stat Rep: RP-230298->RP-230718; ;...; 6/9/23: Compl:30%->... |  | 98 | 50 |  |  | Mon 09/01/23 | Tue 02/04/24
1481 | 941012 | NR support for dedicated spectrum less than 5MHz for FR1 | NR_FR1_lessthan_5MHz_BW | 1 | Rel-18 |  | 2021-12-13 08:00 | 2024-12-12 17:00 | 98% | RP-234027 |  | Nokia |  | 5/4/22: WID:RP-213603->RP-220401; 23/9/22: WID:RP-220401->RP-222645; 29/3/23: WID:RP-222645->RP-230186; 6/10/23: WID:RP-230186->RP-231713; 2/1/24: WID:RP-231713->RP-234027 |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 02/01/24
1482 | 941112 | Core part: NR support for dedicated spectrum less than 5MHz for FR1 | NR_FR1_lessthan_5MHz_BW-Core | 2 | Rel-18 | R4 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-234027 | RP-232749 | Man Hung Ng, Nokia | man_hung.ng@nokia.com | ; 22/3/22: Stat Rep: ->RP-220402 6/6/22: CD:12/12/2023->13/12/2022 6/6/22: Stat Rep: RP-220402->RP-221415; 20/6/22: FCD:13/12/2022->23/12/2022; Rapporteur: Nokia->Toni L hteensuo, Nokia; Rap eMail: ->toni.h.lahteensuo@nokia.com13/7/22: FCD:23/12/20...;... |  | 94 | 48 |  |  | Thu 06/01/22 | Fri 08/12/23
1483 | 941212 | Perf. part: NR support for dedicated spectrum less than 5MHz for FR1 | NR_FR1_lessthan_5MHz_BW-Perf | 2 | Rel-18 | R4 | 2021-12-15 08:00 | 2024-06-06 17:00 | 100% | RP-233963 | RP-240063 | Man Hung Ng, Nokia | man_hung.ng@nokia.com | ; 22/3/22: CD:23/06/2023->12/06/2024; 22/3/22: Stat Rep: ->RP-220402 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220402->RP-221415; 20/6/22: Rapporteur: Nokia->Toni L hteensuo, Nokia; Rap eMail: ->toni.h.lahteensuo@nokia.com13/7/22: ...;... |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 23/07/24
1484 | 1030060 | UE Conformance - NR support for dedicated spectrum less than 5MHz for FR1 | NR_FR1_lessthan_5MHz_BW-UEConTest | 2 | Rel-18 | R5 | 2024-03-03 08:00 | 2025-12-12 17:00 | 95% | RP-250882 | RP-251953 | Nokia |  | 13/6/24: Compl:0%->22%; Stat Rep: ->RP-240908; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:22%->43%; Stat Rep: RP-240908->RP-241737; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:43%->46%; Stat Rep: RP-241737->RP-242457; ; 6/3/25: FCD:28/05/2025->12/12/202 |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
1485 | 940093 | Enhancement of NR Dynamic Spectrum Sharing (DSS) | NR_DSS_enh | 1 | Rel-18 |  | 2021-12-13 08:00 | 2024-06-06 17:00 | 100% | RP-232957 |  | Ericsson |  | compare REL-17 WI NR_DSS-Core; 12/7/22: WID:RP-213575->RP-221622; 2/1/24: WID:RP-221622->RP-232957 |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 02/01/24
1486 | 940193 | Core part: Enhancement of NR Dynamic Spectrum Sharing (DSS) | NR_DSS_enh-Core | 2 | Rel-18 | R1 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-232957 | RP-232956 | Ravikiran Nory, Ericsson | ravikiran.nory@ericsson.com | compare REL-17 WI NR_DSS-Core; 22/3/22: Stat Rep: ->RP-220589 ; 6/6/22: Compl:0%->40% ; 20/6/22: Rapporteur: Ericsson->Ravikiran Nory, Ericsson; Rap eMail: ->ravikiran.nory@ericsson.com13/7/22: FCD:23/12/2022->12/20 ; ...; 9/12/22: FCD:23/12/2022->01... |  | 94 | 48 |  |  | Thu 06/01/22 | Fri 08/12/23
1487 | 940293 | Perf. part: Enhancement of NR Dynamic Spectrum Sharing (DSS) | NR_DSS_enh-Perf | 2 | Rel-18 | R1 | 2021-12-15 08:00 | 2024-06-06 17:00 | 100% | RP-232957 | RP-241174 | Ravikiran Nory, Ericsson | ravikiran.nory@ericsson.com | ; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220589 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220589->RP-221621; 20/6/22: WG: R4->R1; Rapporteur: Ericsson->Ravikiran Nory, Ericsson; Rap eMail: ->ravikiran.nory@ericsson... |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 23/07/24
1488 | 940094 | Multi-carrier enhancements for NR | NR_MC_enh | 1 | Rel-18 |  | 2021-12-13 08:00 | 2024-12-12 17:00 | 99% | RP-234012 |  | NTT DOCOMO |  | 5/4/22: WID:RP-213577->RP-220834; 12/7/22: WID:RP-220834->RP-221435; 23/9/22: WID:RP-221435->RP-222251; 2/1/24: WID:RP-222251->RP-234012 |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 02/01/24
1489 | 940194 | Core part: Multi-carrier enhancements for NR | NR_MC_enh-Core | 2 | Rel-18 | R1 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-240321 | RP-241266 | Hiroki Harada, NTT DOCOMO, INC. | hiroki.harada.sv@nttdocomo.com | ; 22/3/22: CD:23/06/2023->12/06/2023; 22/3/22: Stat Rep: ->RP-220616 ; 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: NTT DOCOMO->Hiroki Harada, NTT DOCOMO, INC.; Rap eMail: ->hiroki.harada@docomo-lab.com13/7/22: FCD:23/12/2022->12/20 ...; 23/9/22: WID:RP-... |  | 94 | 48 |  |  | Thu 06/01/22 | Thu 13/06/24
1490 | 940294 | Perf. part: Multi-carrier enhancements for NR | NR_MC_enh-Perf | 2 | Rel-18 | R1 | 2021-12-15 08:00 | 2024-06-06 17:00 | 100% | RP-240321 | RP-241266 | Hiroki Harada, NTT DOCOMO, INC. | hiroki.harada.sv@nttdocomo.com | ; 22/3/22: Stat Rep: ->RP-220616 6/6/22: CD:12/12/2023->24/06/2022 6/6/22: Stat Rep: RP-220616->RP-221436; 20/6/22: WG: R4->R1; Rapporteur: NTT DOCOMO->Hiroki Harada, NTT DOCOMO, INC.; Rap eMail: ->hiroki.harada@docomo-lab.com13/7/22: FCD:24/06/2...;... |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 23/07/24
1491 | 1030070 | UE Conformance - Multi-carrier enhancements for NR | NR_MC_enh-UEConTest | 2 | Rel-18 | R5 | 2024-03-03 08:00 | 2025-12-12 17:00 | 97% | RP-251461 | RP-252547 | China Telecom |  | 13/6/24: Compl:0%->18%; Stat Rep: ->RP-241301; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:18%->80%; Stat Rep: RP-241301->RP-242000; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:80%->87%; Stat Rep: RP-242000->RP-242852; ; 6/3/25: FCD:28/05/2025->12/12/202 |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
1492 | 940095 | Further NR coverage enhancements | NR_cov_enh2 | 1 | Rel-18 |  | 2021-12-13 08:00 | 2024-12-12 17:00 | 91% | RP-241295 |  | China Telecom |  | compare REL-17 WI NR_cov_enh; 5/4/22: WID:RP-213579->RP-220937; 12/7/22: WID:RP-220937->RP-221858; 2/1/24: WID:RP-221858->RP-233558; 23/7/24: WID:RP-233558->RP-241295 |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 23/07/24
1493 | 940195 | Core part: Further NR coverage enhancements | NR_cov_enh2-Core | 2 | Rel-18 | R1 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-241295 | RP-233557 | Nanxi LI, China Telecom | linanxi@chinatelecom.cn | compare REL-17 WI NR_cov_enh; 22/3/22: Stat Rep: ->RP-220566 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: WID: RP-220937->RP- 220937 ; 6/6/22: Stat Rep: RP-220566->RP-221282; 20/6/22: Rapporteur: China Telecom->Nanxi LI, China Telecom; Rap eMail: ->li... |  | 94 | 48 |  |  | Thu 06/01/22 | Fri 08/12/23
1494 | 940295 | Perf. part: Further NR coverage enhancements | NR_cov_enh2-Perf | 2 | Rel-18 | R1 | 2021-12-15 08:00 | 2024-06-06 17:00 | 100% | RP-241295 | RP-241294 | Nanxi LI, China Telecom | linanxi@chinatelecom.cn | ; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220566 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: WID: RP-220937->RP- 220937 6/6/22: Stat Rep: RP-220566->RP-221282; 20/6/22: WG: R4->R1; Rapporteur: China Telecom->Nanxi LI, China Telecom; R... |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 23/07/24
1495 | 1030069 | UE Conformance - Further NR coverage enhancements | NR_cov_enh2-UEConTest | 2 | Rel-18 | R5 | 2024-03-03 08:00 | 2025-12-12 17:00 | 76% | RP-240345 | RP-252546 | China Telecom |  | 13/6/24: Compl:0%->5%; Stat Rep: ->RP-241300; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->28%; Stat Rep: RP-241300->RP-241992; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:28%->29%; Stat Rep: RP-241992->RP-242851; ; 6/3/25: FCD:28/05/2025->12/12/2025; |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
1496 | 940096 | NR MIMO evolution for downlink and uplink | NR_MIMO_evo_DL_UL | 1 | Rel-18 |  | 2021-12-13 08:00 | 2024-12-12 17:00 | 85% | RP-233028 |  | Samsung |  | compare REL-16 WI NR_eMIMO and REL-17 WI NR_feMIMO; 9/1/23: WID:RP-213598->RP-223276; 2/1/24: WID:RP-223276->RP-233028 |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 02/01/24
1497 | 940196 | Core part: NR MIMO evolution for downlink and uplink | NR_MIMO_evo_DL_UL-Core | 2 | Rel-18 | R1 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-233028 | RP-232913 | Eko Onggosanusi, Samsung | eko.o@samsung.com | compare REL-16 WI NR_eMIMO and REL-17 WI NR_feMIMO; 22/3/22: Stat Rep: ->RP-220669 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com13/7/22: FCD:23/12/2022->12/20 ;...; 9/12/22: FCD:23/12/202... |  | 94 | 48 |  |  | Thu 06/01/22 | Fri 08/12/23
1498 | 940296 | Perf. part: NR MIMO evolution for downlink and uplink | NR_MIMO_evo_DL_UL-Perf | 2 | Rel-18 | R1 | 2021-12-15 08:00 | 2024-06-06 17:00 | 100% | RP-233028 | RP-241282 | Eko Onggosanusi, Samsung | eko.o@samsung.com | ; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220669 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: Stat Rep: RP-220669->RP-221393; 20/6/22: WG: R4->R1; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com13/7/...;... |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 23/07/24
1499 | 1030072 | UE Conformance - NR MIMO evolution for downlink and uplink | NR_MIMO_evo_DL_UL-UEConTest | 2 | Rel-18 | R5 | 2024-03-03 08:00 | 2025-12-12 17:00 | 60% | RP-250103 | RP-252079 | Samsung |  | 13/6/24: Compl:0%->5%; Stat Rep: ->RP-241279; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->19%; Stat Rep: RP-241279->RP-241982; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:19%->37%; Stat Rep: RP-241982->RP-242596; ; 6/3/25: FCD:28/05/2025->12/12/2025; |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
1500 | 940082 | Study on evolution of NR duplex operation | FS_NR_duplex_evo | 1 | Rel-18 | R1 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-223041 | RP-233435 | Fei WANG, CMCC | wangfei@chinamobile.com | 21/1/22: 38.858 added;; 22/3/22: Stat Rep: ->RP-220632; 5/4/22: WID:RP-213591->RP-220633 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: CMCC->Fei WANG, CMCC; Rap eMail: ->wangfei@chinamobile.com12/7/22: WID:RP-220633->RP-221352; 13/7/22: FCD:23/12...; 23/... | 38.858 | 94 | 48 |  |  | Thu 06/01/22 | Fri 08/12/23
1501 | 970079 | NR network-controlled repeaters | NR_netcon_repeater | 1 | Rel-18 |  | 2022-09-08 08:00 | 2024-06-06 17:00 | 100% | RP-232886 |  | ZTE |  | 9/1/23: WID:RP-222673->RP-223505; 29/3/23: WID:RP-223505->RP-230175; 2/1/24: WID:RP-230175->RP-232886 |  | 97 | 49 |  |  | Fri 23/09/22 | Tue 02/01/24
1502 | 970179 | Core part: NR network-controlled repeaters | NR_netcon_repeater-Core | 2 | Rel-18 | R1 | 2022-09-08 08:00 | 2023-12-12 17:00 | 100% | RP-232886 | RP-240930 | Nan Zhang, ZTE | Zhang.nan152@zte.com.cn | 9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->80%; Stat Rep: ->RP-222874; Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:80%->90%; WID: RP-222673->RP-223505; Stat Rep: RP-222874->RP..... |  | 97 | 49 |  |  | Fri 23/09/22 | Thu 13/06/24
1503 | 970279 | Perf. part: NR network-controlled repeaters | NR_netcon_repeater-Perf | 2 | Rel-18 | R1 | 2022-09-12 08:00 | 2024-06-06 17:00 | 100% | RP-232886 | RP-240930 | Nan Zhang, ZTE | Zhang.nan152@zte.com.cn | 9/12/22: WG: R4->R1; FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-222874; Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn; 17/3/23: WID: RP-222673->RP-223505; Stat Rep: RP-222874->RP-230174; ...; 6/9/23: FCD:06/06/2023->06/06/2024;... |  | 97 | 49 |  |  | Fri 23/09/22 | Tue 23/07/24
1504 | 940083 | Study on NR network-controlled repeaters | FS_NR_netcon_repeater | 2 | Rel-18 | R1 | 2022-09-08 08:00 | 2024-06-05 17:00 | 100% | RP-221229 | RP-221231 | Nan Zhang, ZTE | Zhang.nan152@zte.com.cn | compare REL-17 WI NR_repeaters; TR 38.8xx; 21/1/22: 38.867 added;; 22/3/22: Stat Rep: ->RP-220214 6/6/22: Compl:0%->40% ; 20/6/22: Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn12/7/22: WID:RP-213700->RP-221229 ;...; 23/9/22: 0%->10 | 38.867 | 94 | 48 |  |  | Thu 06/01/22 | Fri 23/09/22
1505 | 940098 | Further NR mobility enhancements | NR_Mob_enh2 | 1 | Rel-18 |  | 2021-12-13 08:00 | 2024-12-12 17:00 | 94% | RP-233970 |  | MediaTek |  | compare REL-16 WI NR_Mob_enh; 12/7/22: WID:RP-213565->RP-221799; 23/9/22: WID:RP-221799->RP-222332; 9/1/23: WID:RP-222332->RP-223520; 2/1/24: WID:RP-223520->RP-233970 |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 02/01/24
1506 | 940198 | Core part: Further NR mobility enhancements | NR_Mob_enh2-Core | 2 | Rel-18 | R2 | 2021-12-13 08:00 | 2024-03-01 17:00 | 100% | RP-233970 | RP-241347 | Li-Chuan Tseng, MediaTek Inc. | li-chuan.tseng@mediatek.com | compare REL-16 WI NR_Mob_enh; 22/3/22: CD:12/12/2023->12/09/2023; 22/3/22: Stat Rep: ->RP-220760 6/6/22: CD:12/09/2023->23/09/2022 6/6/22: Stat Re ; 20/6/22: Acronym:NR_Mob_enh2-Core->NR_mob_enh2-Core; Rapporteur: MediaTek->Li-Chuan Tseng, MediaTek Inc... |  | 94 | 48 |  |  | Thu 06/01/22 | Thu 13/06/24
1507 | 940298 | Perf. part: Further NR mobility enhancements | NR_Mob_enh2-Perf | 2 | Rel-18 | R2 | 2021-12-15 08:00 | 2024-06-06 17:00 | 100% | RP-233970 | RP-241347 | Li-Chuan Tseng, MediaTek Inc. | li-chuan.tseng@mediatek.com | ; 22/3/22: CD:24/06/2024->12/12/2023; 22/3/22: Stat Rep: ->RP-220760 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: Stat Rep: RP-220760->RP-221557; 20/6/22: Acronym:NR_Mob_enh2-Perf->NR_mob_enh2-Perf; WG: R4->R2; Rapporteur: MediaTek->Li-Chuan Tseng, Me... |  | 94 | 48 |  |  | Thu 06/01/22 | Thu 13/06/24
1508 | 1040108 | UE Conformance - Further NR mobility enhancements | NR_Mob_enh2-UEConTest | 2 | Rel-18 | R5 | 2024-06-06 08:00 | 2025-12-12 17:00 | 80% | RP-241348 | RP-252501 | Mediatek |  | 4/9/24: FCD:12/12/2025->25/12/2024; Compl:0%->20%; Stat Rep: ->RP-242047; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:20%->40%; Stat Rep: RP-242047->RP-242990; ; 6/3/25: FCD:24/06/2025->12/12/2025; Compl:40%->55%; Stat Rep: RP-242990->RP-250475; ; 6/6/2 |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 11/09/25
1509 | 941003 | In-Device Co-existence (IDC) enhancements for NR and MR-DC | NR_IDC_enh | 1 | Rel-18 |  | 2021-12-13 08:00 | 2026-06-06 17:00 | 76% | RP-233485 |  | Xiaomi |  | MR-DC: Multi-RAT Dual Connectivity; no Perf. part; 12/7/22: WID:RP-213589->RP-221281; 2/1/24: WID:RP-221281->RP-233485 |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 02/01/24
1510 | 941103 | Core part: In-Device Co-existence (IDC) enhancements for NR and MR-DC | NR_IDC_enh-Core | 2 | Rel-18 | R2 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-233485 | RP-233484 | Yumin Wu, Xiaomi | wuyumin@xiaomi.com | MR-DC: Multi-RAT Dual Connectivity; no Perf. part; 20/6/22: Acronym:NR_IDC_enh-Core->NR_IDC_Enh-Core; FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221280; Rapporteur: Xiaomi->Yumin Wu, Xiaomi; Rap eMail: ->wuyumin@xiaomi.com13/7/22: FCD:23/12/2022->1...;... |  | 94 | 48 |  |  | Thu 06/01/22 | Fri 08/12/23
1511 | 1040104 | UE Conformance - In-Device Co-existence (IDC) enhancements for NR and MR-DC | NR_IDC_enh-UEConTest | 2 | Rel-18 | R5 | 2024-06-06 08:00 | 2026-06-06 17:00 | 60% | RP-251764 | RP-252595 | CMCC |  | 4/9/24: FCD:06/06/2026->26/06/2025; Compl:0%->5%; Stat Rep: ->RP-241948; ; 6/12/24: FCD:06/06/2025->05/06/2026; Compl:5%->18%; Stat Rep: RP-241948->RP-242978; ; 6/3/25: FCD:23/10/2025->05/06/2026; Compl:18%->39%; Stat Rep: RP-242978->RP-250252; ; 6/6/25: |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 11/09/25
1512 | 950072 | BS/UE EMC enhancements for NR and LTE | NR_LTE_EMC_enh | 1 | Rel-18 |  | 2022-03-15 08:00 | 2023-12-12 17:00 | 100% | RP-233976 |  | Ericsson |  | compare REL-15 WI AASenh_BS_LTE_UTRA ; 2/1/24: WID:RP-220916->RP-233976 |  | 95 | 48 |  |  | Tue 05/04/22 | Tue 02/01/24
1513 | 950172 | Core part: BS/UE EMC enhancements for NR and LTE | NR_LTE_EMC_enh-Core | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2023-12-12 17:00 | 100% | RP-233976 | RP-233683 | Aurelian Bria, Ericsson | Aurelian.Bria@ericsson.com | compare REL-15 WI AASenh_BS_LTE_UTRA ; 6/6/22: CD:15/06/2023->23/09/2022 ; 6/6/22: Stat Rep: ->RP-221165; 20/6/22: Rapporteur: Ericsson->Aurelian Bria, Ericsson; Rap eMail: ->aurelian.bria@ericsson.com13/7/22: FCD:23/09/2022->09/20 ;...; 9/12/22: FCD... |  | 95 | 48 |  |  | Tue 05/04/22 | Fri 08/12/23
1514 | 950272 | Perf. part: BS/UE EMC enhancements for NR and LTE | NR_LTE_EMC_enh-Perf | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2023-12-12 17:00 | 100% | RP-233976 | RP-233683 | Aurelian Bria, Ericsson | Aurelian.Bria@ericsson.com | compare REL-15 WI AASenh_BS_LTE_UTRA 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221165; 20/6/22: Rapporteur: Ericsson->Aurelian Bria, Ericsson; Rap eMail: ->aurelian.bria@ericsson.com13/7/22: FCD:23/12/2022->12/20...; 9/12/22: FCD:23/12... |  | 95 | 48 |  |  | Tue 05/04/22 | Fri 08/12/23
1515 | 950075 | Air-to-ground network for NR | NR_ATG | 1 | Rel-18 |  | 2022-03-15 08:00 | 2025-06-06 17:00 | 91% | RP-240732 |  | CMCC |  | TR 38.8xx ; 12/7/22: WID:RP-220962->RP-221369; 29/3/23: WID:RP-221369->RP-230279; 2/1/24: WID:RP-230279->RP-234023; 2/4/24: WID:RP-234023->RP-240732 |  | 95 | 48 |  |  | Tue 05/04/22 | Tue 02/04/24
1516 | 950175 | Core part: Air-to-ground network for NR | NR_ATG-Core | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2023-12-12 17:00 | 100% | RP-240732 | RP-240158 | Guo Chunxia, CMCC | guochunxia@chinamobile.com | TR 38.8xx 6/6/22: CD:15/12/2023->23/12/20226/6/22: Stat Rep: ->RP-221370; 20/6/22: Rapporteur: CMCC->Shao Zhe, CMCC; Rap eMail: ->Shaozhe@chinamobile.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep... |  | 95 | 48 |  |  | Tue 05/04/22 | Thu 14/03/24
1517 | 950275 | Perf. part: Air-to-ground network for NR | NR_ATG-Perf | 2 | Rel-18 | R4 | 2022-03-16 08:00 | 2024-03-01 17:00 | 100% | RP-240732 | RP-240158 | Guo Chunxia, CMCC | guochunxia@chinamobile.com | 6/6/22: CD:15/03/2024->24/03/2023 6/6/22: Stat Rep: ->RP-221370; 20/6/22: Rapporteur: CMCC->Shao Zhe, CMCC; Rap eMail: ->Shaozhe@chinamobile.com13/7/22: FCD:24/03/2023->03/20 ;...; 9/12/22: FCD:24/03/2023->01/03/2024; Stat Rep: RP-221370->RP-2230... |  | 95 | 48 |  |  | Tue 05/04/22 | Thu 14/03/24
1518 | 1020087 | UE Conformance - Air-to-ground network for NR | NR_ATG-UEConTest | 2 | Rel-18 | R5 | 2023-12-13 08:00 | 2025-12-12 17:00 | 80% | RP-240750 | RP-252596 | Dan SONG, CMCC | songdan@chinamobile.com | 14/3/24: Compl:0%->50%; Stat Rep: ->RP-240148; Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com; ; 2/4/24: WID:RP-233412->RP-240750. corrected: Rel-19->Rel-18; 13/6/24: WID: RP-240750->RP-233412; Stat Rep: RP-240148->RP-241201; ; ... |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 11/09/25
1519 | 950076 | NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | NR_RF_FR2_req_Ph3 | 1 | Rel-18 |  | 2022-03-15 08:00 | 2025-03-03 17:00 | 92% | RP-240940 |  | Nokia |  | compare REL-16 WI NR_RF_FR2_req_enh and REL-17 WI NR_RF_FR2_req_enh2 ; 12/7/22: WID:RP-220967->RP-221862; 23/9/22: WID:RP-221862->RP-222228; 9/1/23: WID:RP-222228->RP-222909; 2/1/24: WID:RP-222909->RP-232791; 23/7/24: WID:RP-232791->RP-240940 |  | 95 | 48 |  |  | Tue 05/04/22 | Tue 23/07/24
1520 | 950176 | Core part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | NR_RF_FR2_req_Ph3-Core | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2023-12-12 17:00 | 100% | RP-240940 | RP-240939 | Primary: Hisashi Onozawa Secondary: Juan Zhang, Nokia Xiaomi | hisashi.onozawa@nokia.com zhangjuan8@xiaomi.com | compare REL-16 WI NR_RF_FR2_req_enh and REL-17 WI NR_RF_FR2_req_enh2 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com13/7/22: FCD:23/12/2022->12/20...;... | 38.891 | 95 | 48 |  |  | Tue 05/04/22 | Thu 13/06/24
1521 | 950276 | Perf. part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | NR_RF_FR2_req_Ph3-Perf | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2024-06-06 17:00 | 100% | RP-240940 | RP-240939 | Primary: Hisashi Onozawa Secondary: Juan Zhang, Nokia Xiaomi | hisashi.onozawa@nokia.com zhangjuan8@xiaomi.com | ; 6/6/22: CD:15/03/2024->24/03/2023 ; 6/6/22: Stat Rep: ->RP-221207; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com13/7/22: FCD:24/03/2023->03/20 ; ;...; 9/12/22: FCD:24/03/2023->01/03/2024; Compl:10%... |  | 95 | 48 |  |  | Tue 05/04/22 | Thu 13/06/24
1522 | 1030065 | UE Conformance - NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | NR_RF_FR2_req_Ph3-UEConTest | 2 | Rel-18 | R5 | 2024-03-03 08:00 | 2025-12-12 17:00 | 80% | RP-240125 | RP-251506 | Apple |  | 13/6/24: Compl:0%->5%; Stat Rep: ->RP-241175; ; 4/9/24: FCD:03/03/2025->25/03/2025; Compl:5%->15%; Stat Rep: RP-241175->RP-242219; ; 6/12/24: Compl:15%->40%; Stat Rep: RP-242219->RP-242600; ; 6/3/25: FCD:12/11/2024->06/06/2025; Stat Rep: RP-242600->RP-250 |  | 103 | 52 |  |  | Tue 02/04/24 | Tue 30/09/25
1523 | 950077 | Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | NR_FR2_multiRX_DL | 1 | Rel-18 |  | 2022-03-15 08:00 | 2023-11-30 17:00 | 80% | RP-241534 | RP-223153 | Bin Han, Qualcomm Incorporated | binhan@qti.qualcomm.com | ; 12/7/22: WID:RP-220974->RP-221753; 9/12/22: Acronym:NR_FR2_multiRX_DL->FS_NR_FR2_OTA_enh; FCD:01/03/2024->01/12/2023; Compl:11%->25%; WID: RP-221753->RP-222652; Stat Rep: ->RP-223153; Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail:... |  | 95 | 48 |  |  | Tue 05/04/22 | Tue 23/07/24
1524 | 950177 | Core part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | NR_FR2_multiRX_DL-Core | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2023-12-12 17:00 | 100% | RP-241534 | RP-241535 | Sumant Iyer, Qualcomm Inc. | sumanti@qti.qualcomm.com | 6/6/22: CD:15/09/2023->23/09/2022 6/6/22: WID: RP-220974->R4-220974 6/6/22: Stat Rep: ->RP-221225; 20/6/22: Stat Rep: RP-221225->RP-221225 / 1752; Rapporteur: Qualcomm->Sumant Iyer, Qualcomm Inc.; Rap eMail: ->sumanti@qti.qualcomm.com13/7/22: FC...;... | 38.751 | 95 | 48 |  |  | Tue 05/04/22 | Thu 13/06/24
1525 | 950277 | Perf. part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | NR_FR2_multiRX_DL-Perf | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2024-06-06 17:00 | 100% | RP-241534 | RP-241535 | Sumant Iyer, Qualcomm Inc. | sumanti@qti.qualcomm.com | 6/6/22: CD:15/03/2024->24/09/2022 6/6/22: WID: RP-220974->R4-220974 6/6/22: Stat Rep: ->RP-221225; 20/6/22: FCD:24/09/2022->24/03/2023; Stat Rep: RP-221225->RP-221225 / 1752; Rapporteur: Qualcomm->Sumant Iyer, Qualcomm Inc.; Rap eMail: ->sumanti@qt... |  | 95 | 48 |  |  | Tue 05/04/22 | Thu 13/06/24
1526 | 1040113 | UE Conformance - Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | NR_FR2_multiRX_DL-UEConTest | 2 | Rel-18 | R5 | 2024-06-06 08:00 | 2025-12-12 17:00 | 45% | RP-241653 | RP-252050 | Qualcomm |  | 4/9/24: FCD:12/12/2025->25/12/2024; Compl:0%->5%; Stat Rep: ->RP-242040; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:5%->9%; Stat Rep: RP-242040->RP-242898; ; 6/3/25: FCD:24/06/2025->12/12/2025; Compl:9%->20%; Stat Rep: RP-242898->RP-250396; ; 6/6/25: C |  | 104 | 53 |  |  | Tue 23/07/24 | Thu 11/09/25
1527 | 950078 | Even Further RRM enhancement for NR and MR-DC | NR_RRM_enh3 | 1 | Rel-18 |  | 2022-03-15 08:00 | 2024-06-06 17:00 | 100% | RP-233496 |  | Apple |  | compare REL-16 WI NR_RRM_enh and REL-17 WI NR_RRM_enh2; RAN1/2 impact to be checked ; 12/7/22: WID:RP-220977->RP-221696; 2/1/24: WID:RP-221696->RP-233496 |  | 95 | 48 |  |  | Tue 05/04/22 | Tue 02/01/24
1528 | 950178 | Core part: Even Further RRM enhancement for NR and MR-DC | NR_RRM_enh3-Core | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2023-12-12 17:00 | 100% | RP-221696 | RP-241267 | Jie Cui, Apple | jie_cui@apple.com | compare REL-16 WI NR_RRM_enh and REL-17 WI NR_RRM_enh2; RAN1/2 impact to be checked ; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221697; Rapporteur: Apple->Jie Cui, Apple; Rap eMail: ->jie_cui@apple.com13/7/22: FCD:23/12/2022->12/20; ...; 9/1... |  | 95 | 48 |  |  | Tue 05/04/22 | Thu 13/06/24
1529 | 950278 | Perf. part: Even Further RRM enhancement for NR and MR-DC | NR_RRM_enh3-Perf | 2 | Rel-18 | R4 | 2022-03-17 08:00 | 2024-06-06 17:00 | 100% | RP-221696 | RP-241267 | Jie Cui, Apple | jie_cui@apple.com | 6/6/22: CD:15/06/2024->24/06/2022 6/6/22: Stat Rep: ->RP-221697; 20/6/22: Rapporteur: Apple->Jie Cui, Apple; Rap eMail: ->jie_cui@apple.com13/7/22: FCD:24/06/2022->06/20 ; ...; 9/12/22: FCD:24/06/2023->01/06/2024; WID: RP-220977->RP-221696; Stat ... |  | 95 | 48 |  |  | Tue 05/04/22 | Thu 13/06/24
1530 | 950080 | Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) | NR_ENDC_RF_FR1_enh2 | 1 | Rel-18 |  | 2022-03-15 08:00 | 2025-06-06 17:00 | 84% | RP-233186 |  | Huawei |  | compare REL-16 WI NR_RF_FR1 and REL-17 WI NR_RF_FR1_enh ; 12/7/22: WID:RP-220987->RP-221496; 9/1/23: WID:RP-221496->RP-223478; 29/3/23: WID:RP-223478->RP-230753; 6/10/23: WID:RP-230753->RP-232366; 2/1/24: WID:RP-232366->RP-233186 |  | 95 | 48 |  |  | Tue 05/04/22 | Tue 02/01/24
1531 | 950180 | Core part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) | NR_ENDC_RF_FR1_enh2-Core | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2023-12-12 17:00 | 100% | RP-233186 | RP-233185 | Primary: Ye Liu Secondary: Yuta Oguma, Huawei NTT DOCOMO, INC. | leo.liuye@huawei.com yuuta.oguma.yt@nttdocomo.com | compare REL-16 WI NR_RF_FR1 and REL-17 WI NR_RF_FR1_enh 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221495; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com13/7/22: FCD:23/12/2022->12/20; 13/7...;... | 38.881 | 95 | 48 |  |  | Tue 05/04/22 | Fri 08/12/23
1532 | 950280 | Perf. part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) | NR_ENDC_RF_FR1_enh2-Perf | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2024-06-06 17:00 | 100% | RP-232366 | RP-241240 | Primary: Ye Liu Secondary: Yuta Oguma, Huawei NTT DOCOMO, INC. | leo.liuye@huawei.com yuuta.oguma.yt@nttdocomo.com | ; 6/6/22: CD:15/06/2024->24/06/2022 ; 6/6/22: Stat Rep: ->RP-221495; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com13/7/22: FCD:24/06/2022->06/20 ; ;...; 9/12/22: FCD:23/06/2023->31/05/2024; Compl:10%->20... |  | 95 | 48 |  |  | Tue 05/04/22 | Thu 13/06/24
1533 | 1030066 | UE Conformance - Further RF requirements enhancement for NR and EN-DC in frequency range 1 | NR_ENDC_RF_FR1_enh2-UEConTest | 2 | Rel-18 | R5 | 2024-03-03 08:00 | 2025-12-12 17:00 | 59% | RP-251489 | RP-252646 | Huawei |  | 13/6/24: Compl:0%->5%; Stat Rep: ->RP-241377; ; 4/9/24: FCD:06/06/2025->25/06/2025; Compl:5%->12%; Stat Rep: RP-241377->RP-242074; ; 6/12/24: Compl:12%->34%; Stat Rep: RP-242074->RP-243091; ; 6/3/25: FCD:17/01/2025->12/12/2025; Compl:34%->35%; Stat Rep: R |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 11/09/25
1534 | 950081 | Support of intra-band non-collocated EN-DC/NR-CA deployment | NonCol_intraB_ENDC_NR_CA | 1 | Rel-18 |  | 2022-03-15 08:00 | 2023-12-12 17:00 | 97% | RP-233513 |  | KDDI |  | ; 12/7/22: WID:RP-221012->RP-221809; 23/9/22: WID:RP-221809->RP-222309; 29/3/23: WID:RP-222309->RP-230742; 2/1/24: WID:RP-230742->RP-233513 |  | 95 | 48 |  |  | Tue 05/04/22 | Tue 02/01/24
1535 | 950181 | Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment | NonCol_intraB_ENDC_NR_CA-Core | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2023-05-30 10:00 | 95% | RP-233513 | RP-232113 | Yasuki Suzuki, KDDI | ui-suzuki@kddi.com | ; 20/6/22: FCD:15/09/2023->23/09/2022; Stat Rep: ->RP-221742; Rapporteur: KDDI->Yasuki Suzuki; Rap eMail: ->ui-suzuki@kddi.com13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/2022->01/09/2023; Compl:10%->20%; Stat Rep: RP-221742->RP-222956;... |  | 95 | 48 |  |  | Tue 05/04/22 | Wed 06/09/23
1536 | 950281 | Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment | NonCol_intraB_ENDC_NR_CA-Perf | 2 | Rel-18 | R4 | 2022-03-16 08:00 | 2023-12-12 17:00 | 100% | RP-233513 | RP-232113 | Yasuki Suzuki, KDDI | ui-suzuki@kddi.com | ; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221742; Rapporteur: KDDI->Yasuki Suzuki; Rap eMail: ->ui-suzuki@kddi.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: RP-221742->RP-222956; Rapporteur: Yas... |  | 95 | 48 |  |  | Tue 05/04/22 | Tue 02/04/24
1537 | 950082 | Further enhancements on NR and MR-DC measurement gaps and measurements without gaps | NR_MG_enh2 | 1 | Rel-18 |  | 2022-03-15 08:00 | 2025-12-12 17:00 | 91% | RP-234021 |  | MediaTek |  | compare REL-14 WI LTE_meas_gap_enh and REL-17 WI NR_MG_enh ; 5/4/22: WID:RP-221018 ->RP-220772; 23/9/22: WID:RP-220772->RP-222337; 29/3/23: WID:RP-222337->RP-230755; 6/10/23: WID:RP-230755->RP-232440; 2/1/24: WID:RP-232440->RP-234021 |  | 95 | 48 |  |  | Tue 05/04/22 | Tue 02/01/24
1538 | 950182 | Core part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps | NR_MG_enh2-Core | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2023-12-12 17:00 | 100% | RP-232440 | RP-241349 | Tsang-Wei (Ato) YU, Meng ZHANG, MediaTek Inc., Intel Corporation | ato.yu@mediatek.com, meng.zhang@intel.com | compare REL-14 WI LTE_meas_gap_enh and REL-17 WI NR_MG_enh ; 20/6/22: FCD:15/12/2023->23/12/2022; WID: RP-220772->RP-221018; Stat Rep: ->RP-221560; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato... |  | 95 | 48 |  |  | Tue 05/04/22 | Thu 13/06/24
1539 | 950282 | Perf. part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps | NR_MG_enh2-Perf | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2024-06-06 17:00 | 100% | RP-232440 | RP-241349 | Tsang-Wei (Ato) YU, Meng ZHANG, MediaTek Inc., Intel Corporation | ato.yu@mediatek.com, meng.zhang@intel.com | ; 6/6/22: CD:15/06/2024->24/06/2022 ; 6/6/22: WID: RP-220772->RP-221018 ; 6/6/22: Stat Rep: ->RP-221560; 20/6/22: Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato.yu@mediatek.com, rui.huang@int... |  | 95 | 48 |  |  | Tue 05/04/22 | Thu 13/06/24
1540 | 1050132 | UE Conformance - Further enhancements on NR and MR-DC measurement gaps and measurements without gaps | NR_MG_enh2-UEConTest | 2 | Rel-18 | R5 | 2024-09-09 08:00 | 2025-12-12 17:00 | 70% | RP-242046 | RP-252502 | Mediatek |  | 6/12/24: Compl:0%->10%; Stat Rep: ->RP-242994; ; 24/1/25: WID:RP-242046->RP-242995; 6/3/25: FCD:24/07/2025->12/12/2025; Compl:10%->35%; WID: RP-242995->RP-242046; Stat Rep: RP-242994->RP-250477; ; 6/6/25: Compl:35%->55%; Stat Rep: RP-250477->RP-251293; ; |  | 105 | 53 |  |  | Thu 26/09/24 | Thu 11/09/25
1541 | 941001 | Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR | NR_DualTxRx_MUSIM | 1 | Rel-18 | R2 | 2021-12-13 08:00 | 2025-06-06 17:00 | 100% | RP-233071 |  | vivo |  | compare REL-17 WI LTE_NR_MUSIM-Core; no Perf. part; 5/4/22: WID:RP-213584->RP-220955; 9/1/23: WID:RP-220955->RP-223492; 29/3/23: WID:RP-223492->RP-230751; 2/1/24: WID:RP-230751->RP-233071 |  | 94 | 48 |  |  | Thu 06/01/22 | Tue 02/01/24
1542 | 941101 | Core part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR | NR_DualTxRx_MUSIM-Core | 2 | Rel-18 | R2 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-233071 | RP-233070 | Xiaodong Yang, vivo | Yangxiaodong5g@vivo.com | 6/6/22: CD:12/09/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221273; 20/6/22: Rapporteur: vivo->Xiaodong Yang, vivo; Rap eMail: ->Yangxiaodong5g@vivo.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: RP... |  | 94 | 48 |  |  | Thu 06/01/22 | Fri 08/12/23
1543 | 950283 | Perf. Part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR | NR_DualTxRx_MUSIM-Perf | 2 | Rel-18 | R2 | 2022-03-15 08:00 | 2024-06-06 17:00 | 100% | RP-231461 | RP-241045 | Xiaodong Yang, vivo | Yangxiaodong5g@vivo.com | 20/6/22: WG: R4->R2; FCD:14/06/2024->24/06/2022; Stat Rep: ->RP-221273; Rapporteur: vivo->Xiaodong Yang, vivo; Rap eMail: ->Yangxiaodong5g@vivo.com13/7/22: FCD:24/06/2022->06/20 ;...; 17/3/23: FCD:06/06/2023->06/06/2024; Stat Rep: RP-221273->RP-2303... |  | 95 | 48 |  |  | Sat 04/06/22 | Thu 13/06/24
1544 | 1030061 | UE Conformance - Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR | NR_DualTxRx_MUSIM-UEConTest | 2 | Rel-18 | R5 | 2024-03-03 08:00 | 2025-06-06 17:00 | 100% | RP-250895 | RP-250894 | China Telecom |  | 13/6/24: Compl:0%->5%; Stat Rep: ->RP-240909; ; 4/9/24: FCD:06/06/2025->25/06/2025; Compl:5%->14%; Stat Rep: RP-240909->RP-241957; ; 6/12/24: Compl:14%->72%; Stat Rep: RP-241957->RP-242471; ; 6/3/25: FCD:17/01/2025->06/06/2025; Compl:72%->90%; Stat Rep: R |  | 103 | 52 |  |  | Tue 02/04/24 | Fri 18/07/25
1545 | 0 | Rel-18 NR-only: band related | - | 1 | Rel-18 |  | 2019-03-07 07:00 | 2019-03-07 07:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1546 | 991042 | Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76 | NR_FDD_ULn28_DLn75_n76 | 1 | Rel-18 | R4 | 2023-03-06 08:00 | 2023-12-12 17:00 | 100% | RP-233245 |  | Vodafone |  | 6/10/23: WID:RP-230791->RP-232636; 2/1/24: WID:RP-232636->RP-233245 |  | 99 | 50 |  |  | Fri 07/04/23 | Tue 02/01/24
1547 | 991142 | Core part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76 | NR_FDD_ULn28_DLn75_n76-Core | 2 | Rel-18 | R4 | 2023-03-06 08:00 | 2023-12-12 17:00 | 100% | RP-233245 | RP- 233244 | Wael Boukley Hasan, Vodafone | Wael.boukleyhasan@vodafone.com | ; 7/6/23: Compl:0%->43%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:43%->80%; WID: RP-230791->RP-231476; Stat Rep: ->RP-231747; Rapporteur: Vodafone->Wael Boukley Hasan, Vodafone; Rap eMail: ->Wael.boukleyhasan@vodafone.com; ; 21/9/23: FCD:22/09/2023->1... |  | 99 | 50 |  |  | Fri 07/04/23 | Fri 08/12/23
1548 | 991242 | Perf. part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76 | NR_FDD_ULn28_DLn75_n76-Perf | 2 | Rel-18 | R4 | 2023-03-06 08:00 | 2023-12-12 17:00 | 100% | RP-233245 | RP- 233244 | Wael Boukley Hasan, Vodafone | Wael.boukleyhasan@vodafone.com | 6/9/23: FCD:09/09/2023->23/09/2023; WID: RP-230791->RP-231476; Stat Rep: ->RP-231747; Rapporteur: Vodafone->Wael Boukley Hasan, Vodafone; Rap eMail: ->Wael.boukleyhasan@vodafone.com; ; 21/9/23: FCD:23/09/2023->12/12/2023; Stat Rep: RP-231747->RP-232630; ; |  | 99 | 50 |  |  | Fri 07/04/23 | Fri 08/12/23
1549 | 991044 | Complete the specification support for BandWidth Part operation without restriction in NR | NR_BWP_wor | 1 | Rel-18 | R4 | 2023-03-06 08:00 | 2024-06-06 17:00 | 100% | RP-233999 |  | Vodafone |  | 6/10/23: WID:RP-230805->RP-232677; 2/1/24: WID:RP-232677->RP-233999 |  | 99 | 50 |  |  | Fri 07/04/23 | Tue 02/01/24
1550 | 991144 | Core part: Complete the specification support for BandWidth Part operation without restriction in NR | NR_BWP_wor-Core | 2 | Rel-18 | R4 | 2023-03-06 08:00 | 2023-12-12 17:00 | 100% | RP-232677 | RP-241057 | Diogo Martins, Vodafone | diogo.martins@vodafone.com | ; 7/6/23: Compl:0%->40%; 6/9/23: Compl:40%->60%; WID: RP-230805->RP-231486; Stat Rep: ->RP-231924; Rapporteur: Vodafone->Diogo Martins, Vodafone; Rap eMail: ->diogo.martins@vodafone.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-231924->RP-233039; ; 14/... |  | 99 | 50 |  |  | Fri 07/04/23 | Thu 13/06/24
1551 | 991244 | Perf. part: Complete the specification support for BandWidth Part operation without restriction in NR | NR_BWP_wor-Perf | 2 | Rel-18 | R4 | 2023-03-08 08:00 | 2024-06-06 17:00 | 100% | RP-232677 | RP-241057 | Diogo Martins, Vodafone | diogo.martins@vodafone.com | ; 7/6/23: CD:06/06/2024->06/06/2023; 6/9/23: FCD:06/06/2023->06/06/2024; WID: RP-230805->RP-231486; Stat Rep: ->RP-231924; Rapporteur: Vodafone->Diogo Martins, Vodafone; Rap eMail: ->diogo.martins@vodafone.com; ; 8/12/23: Stat Rep: RP-231924->RP-233039... |  | 99 | 50 |  |  | Fri 07/04/23 | Thu 13/06/24
1552 | 1010055 | Introduction of NR bands n31 and n72 | NR_bands_n31_n72 | 1 | Rel-18 | R4 | 2023-09-09 08:00 | 2023-12-12 17:00 | 100% | RP-233950 |  | Nokia |  | 2/1/24: WID:RP-232691->RP-233950 |  | 101 | 51 |  |  | Fri 06/10/23 | Tue 02/01/24
1553 | 1011055 | Core part: Introduction of NR bands n31 and n72 | NR_bands_n31_n72-Core | 2 | Rel-18 | R4 | 2023-09-09 08:00 | 2023-12-12 17:00 | 100% | RP-233950 | RP-233181 | Petri Vasenkari, Nokia | petri.j.vasenkari@nokia.com | 8/12/23: Compl:0%->100%; Stat Rep: ->RP-233181; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; |  | 101 | 51 |  |  | Fri 06/10/23 | Fri 08/12/23
1554 | 1012055 | Perf. part: Introduction of NR bands n31 and n72 | NR_bands_n31_n72-Perf | 2 | Rel-18 | R4 | 2023-09-09 08:00 | 2023-12-12 17:00 | 100% | RP-233950 | RP-233181 | Petri Vasenkari, Nokia | petri.j.vasenkari@nokia.com | 8/12/23: FCD:06/06/2024->12/12/2023; Compl:0%->100%; Stat Rep: ->RP-233181; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; |  | 101 | 51 |  |  | Fri 06/10/23 | Fri 08/12/23
1555 | 991046 | Enhancement for 700/800/900MHz band combinations for NR | NR_700800900_combo_enh | 1 | Rel-18 | R4 | 2023-03-06 08:00 | 2023-12-12 17:00 | 100% | RP-233991 |  | CATT |  | 6/10/23: WID:RP-230764->RP-232680; 2/1/24: WID:RP-232680->RP-233991 |  | 99 | 50 |  |  | Fri 07/04/23 | Tue 02/01/24
1556 | 991146 | Core part: Enhancement for 700/800/900MHz band combinations for NR | NR_700800900_combo_enh-Core | 2 | Rel-18 | R4 | 2023-03-06 08:00 | 2023-12-12 17:00 | 100% | RP-233991 | RP-233005 | Shan Huiping, CATT | shanhuiping@catt.cn | ; 7/6/23: Compl:0%->50%; 6/9/23: Compl:50%->80%; WID: RP-230764->RP-231450; Stat Rep: ->RP-231833; Rapporteur: CATT->Shan Huiping, CATT; Rap eMail: ->shanhuiping@catt.cn; ; 8/12/23: Compl:80%->100%; Stat Rep: RP-231833->RP-233005; |  | 99 | 50 |  |  | Fri 07/04/23 | Fri 08/12/23
1557 | 991246 | Stopped - Perf. part: Enhancement for 700/800/900MHz band combinations for NR | NR_700800900_combo_enh-Perf | 2 | Rel-18 | R4 | 2023-03-06 08:00 | 2023-12-12 17:00 | 100% | RP-233991 | RP-231833 | Shan Huiping, CATT | shanhuiping@catt.cn | 6/9/23: WID: RP-230764->RP-231450; Stat Rep: ->RP-231833; Rapporteur: CATT->Shan Huiping, CATT; Rap eMail: ->shanhuiping@catt.cn¦01/24: stopped at 0% at RAN#102 |  | 99 | 50 | 102 |  | Fri 07/04/23 | Tue 02/01/24
1558 | 981044 | Introduction of NR TDD band in 1670-1675 MHz (n54) | NR_TDD_n54 | 1 | Rel-18 |  | 2022-12-12 08:00 | 2023-03-03 17:00 | 100% | RP-230062 |  | Ligado Networks |  | 29/3/23: WID:RP-223514->RP-230062 |  | 98 | 50 |  |  | Mon 09/01/23 | Wed 29/03/23
1559 | 981144 | Core part: Introduction of NR TDD band in 1670-1675 MHz (n54) | NR_TDD_n54-Core | 2 | Rel-18 | R4 | 2022-12-12 08:00 | 2023-03-03 17:00 | 100% | RP-230062 | RP-230061 | Ojas Choksi, Ligado Networks | ojas.choksi@ligado.com | 17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230061; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; |  | 98 | 50 |  |  | Mon 09/01/23 | Fri 17/03/23
1560 | 981244 | Perf. part: Introduction of NR TDD band in 1670-1675 MHz (n54) | NR_TDD_n54-Perf | 2 | Rel-18 | R4 | 2022-12-12 08:00 | 2023-03-03 17:00 | 100% | RP-230062 | RP-230061 | Ojas Choksi, Ligado Networks | ojas.choksi@ligado.com | 17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230061; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; |  | 98 | 50 |  |  | Mon 09/01/23 | Fri 17/03/23
1561 | 981045 | Introduction of 900 MHz NR band in the US | NR_900MHz_US | 1 | Rel-18 |  | 2022-12-13 08:00 | 2023-08-22 17:00 | 25% | RP-234044 |  | Anterix |  | 29/3/23: WID:RP-223529->RP-230723; 2/1/24: WID:RP-230723->RP-234044 |  | 98 | 50 |  |  | Mon 09/01/23 | Tue 02/01/24
1562 | 981145 | Core Part: Introduction of 900 MHz NR band in the US | NR_900MHz_US-Core | 2 | Rel-18 | R4 | 2022-12-13 08:00 | 2023-08-22 17:00 | 25% | RP-234044 | RP-231956 | Gene Fong, Qualcomm Incorporated | gfong@qti.qualcomm.com | 17/3/23: Compl:0%->5%; Stat Rep: ->RP-230348; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 21/9/23: Compl:5%->25%; Stat Rep: RP-230348->RP-231956; Rapporteur: Emil Olbrich, Anterix->Gene Fong, Qualcomm Incorporated; Ra |  | 98 | 50 |  |  | Mon 09/01/23 | Thu 21/09/23
1563 | 981245 | Perf. part: Introduction of 900 MHz NR band in the US | NR_900MHz_US-Perf | 2 | Rel-18 | R4 | 2022-12-13 08:00 | 2023-08-22 17:00 | 25% | RP-234044 | RP-231956 | Gene Fong, Qualcomm Incorporated | gfong@qti.qualcomm.com | 17/3/23: Stat Rep: ->RP-230348; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 21/9/23: Compl:0%->25%; Stat Rep: RP-230348->RP-231956; Rapporteur: Emil Olbrich, Anterix->Gene Fong, Qualcomm Incorporated; Rap eMail: eolbr |  | 98 | 50 |  |  | Mon 09/01/23 | Thu 21/09/23
1564 | 961010 | Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) | NR_CADC_R18_2BDL_xBUL | 1 | Rel-18 |  | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241222 |  | ZTE |  | 23/9/22: WID:RP-221876->RP-222079; 9/1/23: WID:RP-222079->RP-222904; 29/3/23: WID:RP-222904->RP-230133; 6/10/23: WID:RP-230133->RP-231840; 2/1/24: WID:RP-231840->RP-232920; 2/4/24: WID:RP-232920->RP-240761; 23/7/24: WID:RP-240761->RP-241222 |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 23/07/24
1565 | 961110 | Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) | NR_CADC_R18_2BDL_xBUL-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241222 | RP-241223 | Wubin, Zhou, ZTE | zhou.wubin@zte.com.cn | 9/9/22: Comp...; 23/9/22: 38.718-02-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222905; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:2..... | 38.718-02-01 | 96 | 49 |  |  | Wed 03/08/22 | Thu 13/06/24
1566 | 961210 | Stopped - Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) | NR_CADC_R18_2BDL_xBUL-Perf | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-03-01 17:00 | 100% | RP-240761 | RP-241223 | Wubin, Zhou, ZTE | zhou.wubin@zte.com.cn | 9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222905; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222905->..... |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 23/07/24
1567 | 961011 | Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) | NR_CADC_R18_3BDL_xBUL | 1 | Rel-18 |  | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241089 |  | ZTE |  | 23/9/22: WID:RP-221877->RP-222092; 9/1/23: WID:RP-222092->RP-222834; 29/3/23: WID:RP-222834->RP-230084; 6/10/23: WID:RP-230084->RP-231860; 2/1/24: WID:RP-231860->RP-233231; 2/4/24: WID:RP-233231->RP-240166; 23/7/24: WID:RP-240166->RP-241089 |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 23/07/24
1568 | 961111 | Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) | NR_CADC_R18_3BDL_xBUL-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241089 | RP-241090 | Zhifeng Ma, ZTE | ma.zhifeng@zte.com.cn | 9/9/22: Comp...; 23/9/22: 38.718-03-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->15%; Stat Rep: ->RP-222835; Rapporteur: ZTE->Zhifeng Ma, ZTE; Rap eMail: ->ma.zhifeng@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:1..... | 38.718-03-01 | 96 | 49 |  |  | Wed 03/08/22 | Thu 13/06/24
1569 | 961211 | Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) | NR_CADC_R18_3BDL_xBUL-Perf | 2 | Rel-18 | R4 | 2022-06-16 08:00 | 2024-06-06 17:00 | 100% | RP-241089 | RP-241090 | Zhifeng Ma, ZTE | ma.zhifeng@zte.com.cn | 9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222835; Rapporteur: ZTE->Zhifeng Ma, ZTE; Rap eMail: ->ma.zhifeng@zte.com.cn; 17/3/23: Compl:0%->40%; Stat Rep: RP-222835->RP-230085; ...; 6/9/23: Compl:60%->75%; WID: RP... |  | 96 | 49 |  |  | Wed 03/08/22 | Thu 13/06/24
1570 | 961013 | High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe | NR_RAIL_HPUE_n100_n101 | 1 | Rel-18 |  | 2022-12-01 11:00 | 2023-12-12 17:00 | 0% | RP-221878 |  | Union Internationale Chemins de Fer (UIC) |  |  |  | 96 | 49 |  |  | Wed 03/08/22 | NA
1571 | 961113 | Core part: High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe | NR_RAIL_HPUE_n100_n101-Core | 2 | Rel-18 | R4 | 2022-12-01 11:00 | 2023-12-12 17:00 | 0% | RP-221878 | RP-222544 | Union Internationale Chemins de Fer (UIC) |  |  |  | 96 | 49 |  |  | Wed 03/08/22 | NA
1572 | 961007 | Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) | NR_CA_R18_Intra | 1 | Rel-18 |  | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241140 |  | Ericsson |  | 23/9/22: WID:RP-221835->RP-222105; 9/1/23: WID:RP-222105->RP-222846; 29/3/23: WID:RP-222846->RP-230067; 6/10/23: WID:RP-230067->RP-231623; 2/1/24: WID:RP-231623->RP-233990; 2/4/24: WID:RP-233990->RP-240238; 23/7/24: WID:RP-240238->RP-241140 |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 23/07/24
1573 | 961107 | Core part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) | NR_CA_R18_Intra-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241140 | RP-241139 | Per Lindell, Ericsson | per.lindell@ericsson.com | 9/9/22: CD:1...; 23/9/22: 38.718-01-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->71%; Stat Rep: ->RP-222845; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/..... | 38.718-01-01 | 96 | 49 |  |  | Wed 03/08/22 | Thu 13/06/24
1574 | 961207 | Stopped - Perf. part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) | NR_CA_R18_Intra-Perf | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-03-01 17:00 | 100% | RP-241140 | RP-241139 | Per Lindell, Ericsson | per.lindell@ericsson.com | 9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->71%; Stat Rep: ->RP-222845; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:71%->57%; Stat Rep..... |  | 96 | 49 | 102 |  | Wed 03/08/22 | Thu 13/06/24
1575 | 961008 | Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) | NR_CADC_R18_yBDL_xBUL | 1 | Rel-18 |  | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241327 |  | Ericsson |  | 23/9/22: WID:RP-221838->RP-222318; 9/1/23: WID:RP-222318->RP-223438; 29/3/23: WID:RP-223438->RP-230421; 6/10/23: WID:RP-230421->RP-231738; 2/1/24: WID:RP-231738->RP-233696; 2/4/24: WID:RP-233696->RP-240501; 23/7/24: WID:RP-240501->RP-241327 |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 23/07/24
1576 | 961108 | Core part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) | NR_CADC_R18_yBDL_xBUL-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241327 | RP-241328 | Reihaneh Malekafzaliardakani, Ericsson | reihaneh.malekafzaliardakani@ericsson.com | 9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:25%->29%; Stat Rep: ->RP-222911; Rapporteur: Ericsson->Reihaneh Malekafzaliardakani, Ericsson; Rap eMail: ->reihaneh.malekafzaliardakani@ericsson.com; 17/3/23: FCD:30/11/2023->1..... |  | 96 | 49 |  |  | Wed 03/08/22 | Thu 13/06/24
1577 | 961208 | Perf. part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) | NR_CADC_R18_yBDL_xBUL-Perf | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241327 | RP-241328 | Reihaneh Malekafzaliardakani, Ericsson | reihaneh.malekafzaliardakani@ericsson.com | 9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:25%->29%; Stat Rep: ->RP-222911; Rapporteur: Ericsson->Reihaneh Malekafzaliardakani, Ericsson; Rap eMail: ->reihaneh.malekafzaliardakani@ericsson.com; 17/3/23: FCD:30/11/2023->1..... |  | 96 | 49 |  |  | Wed 03/08/22 | Thu 13/06/24
1578 | 960097 | APT 600MHz NR band | NR_600MHz_APT | 1 | Rel-18 |  | 2022-06-15 08:00 | 2023-03-03 17:00 | 100% | RP-230060 |  | Spark NZ Ltd |  | 9/1/23: WID:RP-221778->RP-223265; 29/3/23: WID:RP-223265->RP-230060 |  | 96 | 49 |  |  | Wed 03/08/22 | Wed 29/03/23
1579 | 960197 | Core part: APT 600MHz NR band | NR_600MHz_APT-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2023-03-03 17:00 | 100% | RP-221778 | RP-230053 | Mansoor Shafi, Spark New Zealand | Mansoor.shafi@spark.co.nz | 9/9/22: Comp...; 23/9/22: 38.892 added;; 9/12/22: FCD:22/12/2022->01/03/2023; Compl:10%->95%; Stat Rep: ->RP-222803; Rapporteur: Spark NZ Ltd->Mansoor Shafi, Spark New Zealand; Rap eMail: ->Mansoor.shafi@spark.co.nz; 17/3/23: Compl:95%->... | 38.892 | 96 | 49 |  |  | Wed 03/08/22 | Fri 17/03/23
1580 | 960297 | Perf. part: APT 600MHz NR band | NR_600MHz_APT-Perf | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2023-03-03 17:00 | 100% | RP-221778 | RP-230053 | Mansoor Shafi, Spark New Zealand | Mansoor.shafi@spark.co.nz | 9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:10%->60%; Stat Rep: ->RP-222803; Rapporteur: Spark NZ Ltd->Mansoor Shafi, Spark New Zealand; Rap eMail: ->Mansoor.shafi@spark.co.nz; 17/3/23: Compl:60%->100%; WID: RP-223265->RP... |  | 96 | 49 |  |  | Wed 03/08/22 | Fri 17/03/23
1581 | 960098 | Stopped - Introduction of additional 6GHz NR licensed bands | NR_6GHz_add_bands | 1 | Rel-18 |  | 2022-06-16 08:00 | 2023-12-12 17:00 | 100% | RP-222498 |  | Huawei |  | 23/9/22: WID:RP-221845->RP-22249801/24: stopped at 0% at RAN#102 |  | 96 | 49 | 102 |  | Wed 03/08/22 | Tue 02/01/24
1582 | 960198 | Stopped - Core part: Introduction of additional 6GHz NR licensed bands | NR_6GHz_add_bands-Core | 2 | Rel-18 | R4 | 2022-06-16 08:00 | 2023-12-12 17:00 | 100% | RP-222498 | RP-233184 | Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation | liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn | 9/9/22: CD:1…; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-221845->RP-222498; Stat Rep: ->RP-223341; Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation¦01/24: stopped at 0% at RAN#102... |  | 96 | 49 | 102 |  | Wed 03/08/22 | Tue 02/01/24
1583 | 960298 | Stopped - Perf. part: Introduction of additional 6GHz NR licensed bands | NR_6GHz_add_bands-Perf | 2 | Rel-18 | R4 | 2022-06-16 08:00 | 2023-12-12 17:00 | 100% | RP-222498 | RP-233184 | Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation | liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn | 9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-221845->RP-222498; Stat Rep: ->RP-223341; Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation; Rap eMail: ->liu...; 8/12/23: S |  | 96 | 49 | 102 |  | Wed 03/08/22 | Tue 02/01/24
1584 | 960095 | Additional NR bands for UL-MIMO in Rel-18 | NR_bands_UL_MIMO_R18 | 1 | Rel-18 |  | 2022-06-15 08:00 | 2024-12-12 17:00 | 100% | RP-240422 |  | Huawei |  | 23/9/22: WID:RP-221844->RP-222509; 9/1/23: WID:RP-222509->RP-223516; 6/10/23: WID:RP-223516->RP-232374; 2/1/24: WID:RP-232374->RP-234040; 2/4/24: WID:RP-234040->RP-240422 |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 02/04/24
1585 | 960195 | Core part: Additional NR bands for UL-MIMO in Rel-18 | NR_bands_UL_MIMO_R18-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-03-01 17:00 | 100% | RP-240422 | RP-240421 | Xiang Gao, Huawei | gaoxiang74@huawei.com | 9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->15%; Stat Rep: ->RP-223351; Rapporteur: Huawei->Xiang Gao, Huawei; Rap eMail: ->gaoxiang74@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; Stat Rep: RP-223..... |  | 96 | 49 |  |  | Wed 03/08/22 | Thu 14/03/24
1586 | 960295 | stopped - Perf. part: Additional NR bands for UL-MIMO in Rel-18 | NR_bands_UL_MIMO_R18-Perf | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-03-01 17:00 | 100% | RP-240422 | RP-233198 | Xiang Gao, Huawei | gaoxiang74@huawei.com | 9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-223351; Rapporteur: Huawei->Xiang Gao, Huawei; Rap eMail: ->gaoxiang74@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; Stat Rep: RP-2233.....; 8/12/23: F |  | 96 | 49 | 102 |  | Wed 03/08/22 | Tue 02/01/24
1587 | 1000050 | UE Conformance - Additional NR bands for UL-MIMO in Rel-18 | NR_bands_UL_MIMO_R18-UEConTest | 2 | Rel-18 | R5 | 2023-06-08 08:00 | 2025-06-06 17:00 | 100% | RP-251511 | RP-251509 | Shi，Yu, China Unicom | shiyu19@chinaunicom.cn | 6/9/23: Compl:0%->49%; Stat Rep: ->RP-231550; Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn; ; 8/12/23: Stat Rep: RP-231550->RP-232771; ; 2/1/24: WID:RP-230868->RP-232772; 14/3/24: FCD:05/06/2024->12/12/2024; Stat ... |  | 100 | 51 |  |  | Thu 29/06/23 | Fri 18/07/25
1588 | 960093 | Enhancements of NR shared spectrum bands | NR_unlic_enh | 1 | Rel-18 |  | 2022-06-15 08:00 | 2023-06-06 17:00 | 99% | RP-230730 |  | Apple |  | 23/9/22: WID:RP-221813->RP-222174; 29/3/23: WID:RP-222174->RP-230730 |  | 96 | 49 |  |  | Wed 03/08/22 | Wed 29/03/23
1589 | 960193 | Core part: Enhancements of NR shared spectrum bands | NR_unlic_enh-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2023-06-06 17:00 | 100% | RP-230730 | RP-230729 | Daniel Popp, Apple Inc. | d_popp@apple.com | 9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:15%->50%; Stat Rep: ->RP-223194; Rapporteur: Apple->Daniel Popp, Apple Inc.; Rap eMail: ->d_popp@apple.com; 17/3/23: FCD:03/03/2023->08/09/2023; Compl:50%->85%; Stat Rep: RP-223... |  | 96 | 49 |  |  | Wed 03/08/22 | Wed 07/06/23
1590 | 960293 | Perf. part: Enhancements of NR shared spectrum bands | NR_unlic_enh-Perf | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2023-02-16 10:00 | 99% | RP-230730 | RP-230729 | Daniel Popp, Apple Inc. | d_popp@apple.com | 9/12/22: FCD:15/03/2023->01/03/2023; Compl:0%->50%; Stat Rep: RP-222175->RP-223194; Rapporteur: Apple->Daniel Popp, Apple Inc.; Rap eMail: ->d_popp@apple.com; 17/3/23: Compl:50%->100%; Stat Rep: RP-223194->RP-230152; 31/3/23: FCD:03/03/2023->06/06... |  | 96 | 49 |  |  | Wed 03/08/22 | Fri 31/03/23
1591 | 950071 | Introduction of LTE TDD band in 1670-1675 MHz | LTE_TDD_1670_1675MHz | 1 | Rel-18 |  | 2022-03-15 08:00 | 2023-12-12 17:00 | 100% | RP-222831 |  | Ligado Networks |  | 9/1/23: WID:RP-220971->RP-222831 |  | 95 | 48 |  |  | Tue 05/04/22 | Mon 09/01/23
1592 | 950171 | Core part: Introduction of LTE TDD band in 1670-1675 MHz | LTE_TDD_1670_1675MHz-Core | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2022-12-01 17:00 | 100% | RP-222831 | RP-222830 | Ojas Choksi, Ligado Networks | ojas.choksi@ligado.com | ; 6/6/22: Compl:0%->15% ; 6/6 ; 20/6/22: Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com ...; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:50%->100%; Stat Rep: RP-221061->RP-222830; 9/1/23: 100%->100 |  | 95 | 48 |  |  | Tue 05/04/22 | Mon 09/01/23
1593 | 950271 | Perf. part: Introduction of LTE TDD band in 1670-1675 MHz | LTE_TDD_1670_1675MHz-Perf | 2 | Rel-18 | R4 | 2022-03-15 08:00 | 2022-12-01 17:00 | 100% | RP-222831 | RP-222830 | Ojas Choksi, Ligado Networks | ojas.choksi@ligado.com | ; 6/6/22: CD:15/12/2022->22/12/2022; 6/6/22: Stat Rep: ->RP-221061; 20/6/22: Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:0%->100%; Stat Rep: RP-221061->RP... |  | 95 | 48 |  |  | Tue 05/04/22 | Mon 09/01/23
1594 | 991032 | UE Conformance - Introduction of LTE TDD band in 1670 – 1675 MHz | LTE_TDD_1670_1675MHz-UEConTest | 2 | Rel-18 | R5 | 2023-03-03 08:00 | 2023-12-12 17:00 | 100% | RP-232783 | RP-232784 | Ojas Choksi, Ligado Networks | ojas.choksi@ligado.com | ; 7/6/23: Compl:0%->83%; 7/6/23: CD:09/09/2023->...; 6/9/23: Compl:83%->99%; WID: RP-230063->RP-230907; Stat Rep: ->RP-231546; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ; 6/10/23: WID:RP-230907->RP... |  | 99 | 50 |  |  | Wed 29/03/23 | Tue 02/01/24
1595 | 960092 | Study on UE support of regionally-defined subsets of an NR band | FS_NR_subset_band_support | 1 | Rel-18 | RP | 2022-06-15 08:00 | 2023-03-03 17:00 | 100% | RP-223556 | RP-230340 | Gene Fong, Qualcomm Incorporated | gfong@qti.qualcomm.com | 23/9/22: FCD:15/12/2022->12/20; 23/9/22: 0%->40; 23/9/22: WID:RP-221872->RP-222220; 23/9/22: 38.893 added;; 9/1/23: WID:RP-222220->RP-223556; 29/3/23: FCD:12/12/2023->03/23; 29/3/23: 40%->100; 31/3/23: Stat Rep: RP-222222->RP-230340; Rapporteur: Qualcomm- | 38.893 | 96 | 49 |  |  | Tue 12/07/22 | Fri 31/03/23
1596 | 1000058 | UE Conformance - New Rel-18 NR licensed bands and extension of existing NR bands | NR_lic_bands_BW_R18-UEConTest | 1 | Rel-18 | R5 | 2023-06-08 08:00 | 2024-12-12 17:00 | 100% | RP-243089 | RP-243088 | Yuxin Hao, Huawei Technologies. Co., Ltd. | haoyuxin@huawei.com | 6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232360; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ; 6/10/23: WID:RP-231249->RP-232361; 8/12/23: FCD:06/06/2024->06/06/2025; Stat Rep... |  | 100 | 51 |  |  | Thu 29/06/23 | Fri 24/01/25
1597 | 0 | Rel-18 Other NR and LTE | - | 1 | Rel-18 |  | 2019-03-07 07:00 | 2019-03-07 07:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1598 | 1010053 | Rel-18 basket WI 3Tx NR inter-band UL Carrier Aggregation (CA) and EN-DC | R18_3Tx_NR_CA_ENDC | 1 | Rel-18 | R4 | 2023-09-09 08:00 | 2024-06-06 17:00 | 100% | RP-241149 |  | Oppo |  | 2/1/24: WID:RP-232674->RP-232941; 2/4/24: WID:RP-232941->RP-240307; 23/7/24: WID:RP-240307->RP-241149 |  | 101 | 51 |  |  | Fri 06/10/23 | Tue 23/07/24
1599 | 1011053 | Core pat: Rel-18 basket WI 3Tx NR inter-band UL Carrier Aggregation (CA) and EN-DC | R18_3Tx_NR_CA_ENDC-Core | 2 | Rel-18 | R4 | 2023-09-09 08:00 | 2024-06-06 17:00 | 100% | RP-241149 | RP-241150 | Jinqiang Xing, OPPO | xingjinqiang@oppo.com | 8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->30%; Stat Rep: ->RP-232940; Rapporteur: Oppo->Jinqiang Xing, OPPO; Rap eMail: ->xingjinqiang@oppo.com; ; 4/1/24: 38.880 added;; 14/3/24: FCD:01/03/2024->06/06/2024; Compl:30%->70%; Stat Rep: RP-232940->RP... | 38.88 | 101 | 51 |  |  | Fri 06/10/23 | Thu 13/06/24
1600 | 970088 | Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) | HPUE_FR1_DC_LTE_NR_R18 | 1 | Rel-18 |  | 2022-09-12 08:00 | 2024-06-06 17:00 | 100% | RP-241144 |  | Ericsson |  | 9/1/23: WID:RP-222660->RP-222848; 29/3/23: WID:RP-222848->RP-230069; 6/10/23: WID:RP-230069->RP-231625; 2/1/24: WID:RP-231625->RP-233977; 2/4/24: WID:RP-233977->RP-240241; 23/7/24: WID:RP-240241->RP-241144 |  | 97 | 49 |  |  | Wed 19/10/22 | Tue 23/07/24
1601 | 970188 | Core part: Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) | HPUE_FR1_DC_LTE_NR_R18-Core | 2 | Rel-18 | R4 | 2022-09-12 08:00 | 2024-06-06 17:00 | 100% | RP-241144 | RP-241143 | Per Lindell, Ericsson | per.lindell@ericsson.com | 9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->14%; Stat Rep: ->RP-222847; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:14%->19%; Stat Rep: RP-222847->RP-230068; 17/...;... | 38.898 | 97 | 49 |  |  | Wed 19/10/22 | Thu 13/06/24
1602 | 970288 | Stopped - Perf. part: Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) | HPUE_FR1_DC_LTE_NR_R18-Perf | 2 | Rel-18 | R4 | 2022-09-12 08:00 | 2023-12-12 17:00 | 100% | RP-241144 | RP-240240 | Per Lindell, Ericsson | per.lindell@ericsson.com | 9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->14%; Stat Rep: ->RP-222847; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:14%->19%; Stat Rep: RP-222847->RP-230068; ;...; 6... |  | 97 | 49 | 102 |  | Wed 19/10/22 | Tue 23/07/24
1603 | 1000054 | UE Conformance - Rel-18 High Power UE for NR CA and DC; and NR and LTE DC Configurations; | HPUE_NR_CADC_NR_LTE_DC_R18-UEConTest | 1 | Rel-18 | R5 | 2023-06-08 08:00 | 2025-12-12 17:00 | 95% | RP-231199 | RP-252545 | Lei GAO, China Telecom | gaol8@chinatelecom.cn | 6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232259; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; ; 8/12/23: FCD:06/06/2024->06/06/2025; Compl:5%->15%; Stat Rep: RP-232259->RP-233565; ; 14/3... |  | 100 | 51 |  |  | Thu 29/06/23 | Thu 11/09/25
1604 | 961012 | High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands | LTE_NR_HPUE_FWVM_R18 | 1 | Rel-18 |  | 2022-06-15 08:00 | 2024-12-12 17:00 | 100% | RP-240941 |  | Nokia |  | 19/10/22: acronym corrected; 9/1/23: WID:RP-221841->RP-223424; 6/10/23: WID:RP-223424->RP-231615; 2/1/24: WID:RP-231615->RP-233180; 2/4/24: WID:RP-233180->RP-240361; 23/7/24: WID:RP-240361->RP-240941 |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 23/07/24
1605 | 961112 | Core part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands | LTE_NR_HPUE_FWVM_R18-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-240941 | RP-240942 | Petri Vasenkari, Nokia | petri.j.vasenkari@nokia.com | 9/9/22: Comp...; 23/9/22: 37.829 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; WID: RP-222058->RP-221841; Stat Rep: ->RP-222825; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; 17/3/23:..... | 37.829 | 96 | 49 |  |  | Wed 03/08/22 | Thu 13/06/24
1606 | 1000059 | UE Conformance - High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands in Rel-18 | LTE_NR_HPUE_FWVM_R18-UEConTest | 2 | Rel-18 | R5 | 2023-06-08 08:00 | 2024-12-12 17:00 | 100% | RP-242837 | RP-242836 | Tuomo S yn j kangas, Nokia | tuomo.saynajakangas@nokia.com | 6/9/23: Compl:0%->18%; Stat Rep: ->RP-231612; Rapporteur: Nokia->Tuomo S yn j kangas, Nokia; Rap eMail: ->tuomo.saynajakangas@nokia.com; ; 6/10/23: WID:RP-231429->RP-231613; 8/12/23: WID: RP-231615->RP-231613; Stat Rep: RP-231612->RP-232856; ; 14/3/24:... |  | 100 | 51 |  |  | Thu 29/06/23 | Fri 24/01/25
1607 | 1000057 | UE Conformance - Rel-18 NR CA and DC; and NR and LTE DC Configurations | NR_CADC_NR_LTE_DC_R18-UEConTest | 1 | Rel-18 | R5 | 2023-06-08 08:00 | 2025-12-12 17:00 | 76% | RP-240285 | RP-252645 | Chunying GU, Huawei Technologies. Co., Ltd. | guchunying@huawei.com | 6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232359; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ; 8/12/23: FCD:06/06/2024->06/06/2025; Stat Rep: RP-232359->RP-233767; ; 14/3/24: ... |  | 100 | 51 |  |  | Thu 29/06/23 | Thu 11/09/25
1608 | 981041 | 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC | 4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC | 1 | Rel-18 |  | 2022-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-234046 |  | Oppo |  | 29/3/23: WID:RP-223517->RP-230161; 6/10/23: WID:RP-230161->RP-231719; 2/1/24: WID:RP-231719->RP-234046 |  | 98 | 50 |  |  | Mon 09/01/23 | Tue 02/01/24
1609 | 981141 | Core part: 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC | 4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC-Core | 2 | Rel-18 | R4 | 2022-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-234046 | RP-232937 | Jinqiang Xing, OPPO | xingjinqiang@oppo.com | 17/3/23: Compl:0%->10%; Stat Rep: ->RP-230160; Rapporteur: Oppo->Jinqiang Xing, OPPO; Rap eMail: ->xingjinqiang@oppo.com; ; 29/6/23: 10%->70; 6/9/23: Compl:70%->85%; WID: RP-230161->RP-231013; Stat Rep: RP-231012->RP-231718; ; 8/12/23: Compl:85%->100%; S |  | 98 | 50 |  |  | Mon 09/01/23 | Fri 08/12/23
1610 | 1020088 | UE Conformance - 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC | 4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC-UEConTest | 1 | Rel-18 | R5 | 2023-12-13 08:00 | 2025-03-03 17:00 | 100% | RP-250447 | RP-250446 | Yaping ZHANG, Huawei | zhangyaping13@huawei.com | 14/3/24: Compl:0%->7%; Stat Rep: ->RP-240289; Rapporteur: Huawei->Yaping ZHANG, Huawei; Rap eMail: ->zhangyaping13@huawei.com; 2/4/24: corrected: rel-19->Rel-18; 13/6/24: Compl:7%->26%; Stat Rep: RP-240289->RP-241376; ; 4/9/24: FCD:06/06/2025->25/06/2025; |  | 102 | 52 |  |  | Tue 02/01/24 | Thu 03/04/25
1611 | 970084 | Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 | LTE_NR_Simult_RxTx_R18 | 1 | Rel-18 |  | 2022-09-08 08:00 | 2024-09-09 17:00 | 100% | RP-241251 |  | Huawei |  | 9/1/23: WID:RP-222648->RP-223354; 2/1/24: WID:RP-223354->RP-234002; 2/4/24: WID:RP-234002->RP-240425; 23/7/24: WID:RP-240425->RP-241251 |  | 97 | 49 |  |  | Fri 23/09/22 | Tue 23/07/24
1612 | 970184 | Core part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 | LTE_NR_Simult_RxTx_R18-Core | 2 | Rel-18 | R4 | 2022-09-08 08:00 | 2024-06-06 17:00 | 100% | RP-241251 | RP-241250 | Dan Hu, Huawei | hudan11@huawei.com | 9/12/22: Acronym:LTE_NR_Simult_RxTx_R18-Core->LTE_NR _Simult_RxTx_R18-Core; FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223353; Rapporteur: Huawei->Dan Hu, Huawei; Rap eMail: ->hudan11@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; C..... | 38.894 | 97 | 49 |  |  | Fri 23/09/22 | Thu 13/06/24
1613 | 970284 | Stopped - Perf. part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 | LTE_NR_Simult_RxTx_R18-Perf | 2 | Rel-18 | R4 | 2022-09-08 08:00 | 2024-03-01 17:00 | 100% | RP-240425 | RP-233201 | Dan Hu, Huawei | hudan11@huawei.com | 9/12/22: Acronym:LTE_NR_Simult_RxTx_R18-Perf->LTE_NR _Simult_RxTx_R18-Perf; FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223353; Rapporteur: Huawei->Dan Hu, Huawei; Rap eMail: ->hudan11@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; C..... |  | 97 | 49 | 102 |  | Fri 23/09/22 | Tue 02/01/24
1614 | 1030068 | UE Conformance - Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 | LTE_NR_Simult_RxTx_R18-UEConTest | 2 | Rel-18 | R5 | 2024-03-03 08:00 | 2024-09-09 17:00 | 100% | RP-242077 | RP-242076 | Huawei |  | 13/6/24: Compl:0%->58%; Stat Rep: ->RP-241379; ; 4/9/24: FCD:06/06/2025->24/09/2024; Compl:58%->100%; Stat Rep: RP-241379->RP-242076; ; 26/9/24: WID:RP-240292->RP-242077 |  | 103 | 52 |  |  | Tue 02/04/24 | Thu 26/09/24
1615 | 970082 | Enhancement of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | NR_FR1_TRP_TRS_enh | 1 | Rel-18 |  | 2022-09-08 08:00 | 2025-06-06 17:00 | 100% | RP-234064 |  | Vivo |  | 9/1/23: WID:RP-222669->RP-223112; 2/1/24: WID:RP-223112->RP-234064 |  | 97 | 49 |  |  | Fri 23/09/22 | Tue 02/01/24
1616 | 970182 | Core part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) | NR_FR1_TRP_TRS_enh-Core | 2 | Rel-18 | R4 | 2022-09-08 08:00 | 2024-12-23 17:00 | 100% | RP-234064 | RP-241829 | Wang, Ruixin, vivo | ruixin.wang@vivo.com | 9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-223111; Rapporteur: Vivo->Wang, Ruixin, vivo; Rap eMail: ->ruixin.wang@vivo.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-223111->RP-230375; 17/3/23: 38.87...;... | 38.87 | 97 | 49 |  |  | Fri 23/09/22 | Wed 04/09/24
1617 | 970282 | Perf. Part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) | NR_FR1_TRP_TRS_enh-Perf | 2 | Rel-18 | R4 | 2022-09-12 08:00 | 2024-09-09 17:00 | 100% | RP-242327 | RP-241829 | Wang, Ruixin, vivo | ruixin.wang@vivo.com | 9/12/22: FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-223111; Rapporteur: Vivo->Wang, Ruixin, vivo; Rap eMail: ->ruixin.wang@vivo.com; 17/3/23: Compl:0%->5%; Stat Rep: RP-223111->RP-230375; ;...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:20%->30%; Stat ... |  | 97 | 49 |  |  | Fri 23/09/22 | Thu 26/09/24
1618 | 1040111 | UE Conformance - Enhancement of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | NR_FR1_TRP_TRS_enh-UEConTest | 2 | Rel-18 | R5 | 2024-06-06 08:00 | 2025-06-06 17:00 | 100% | RP-251502 | RP-251178 | Apple |  | 4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->5%; Stat Rep: ->RP-241899; ; 6/12/24: Compl:5%->30%; Stat Rep: RP-241899->RP-242480; ; 24/1/25: WID:RP-241503->RP-242602; 6/3/25: FCD:14/02/2025->06/06/2025; Compl:30%->70%; WID: RP-242602->RP-241503; Stat Re |  | 104 | 53 |  |  | Tue 23/07/24 | Fri 18/07/25
1619 | 961009 | Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) | NR_SUL_combos_R18 | 1 | Rel-18 |  | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241248 |  | Huawei |  | 23/9/22: WID:RP-221839->RP-222507; 9/1/23: WID:RP-222507->RP-223537; 29/3/23: WID:RP-223537->RP-230475; 6/10/23: WID:RP-230475->RP-232372; 2/1/24: WID:RP-232372->RP-233197; 2/4/24: WID:RP-233197->RP-240420; 23/7/24: WID:RP-240420->RP-241248 |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 23/07/24
1620 | 961109 | Core part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) | NR_SUL_combos_R18-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241248 | RP-241247 | Zhang, Peng, Huawei | zhangpeng169@huawei.com | 9/9/22: Comp...; 23/9/22: 37.718-00-00 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->20%; Stat Rep: ->RP-223349; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023..... | 37.718-00-00 | 96 | 49 |  |  | Wed 03/08/22 | Thu 13/06/24
1621 | 961209 | Stopped - Perf. Part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) | NR_SUL_combos_R18-Perf | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-03-01 17:00 | 100% | RP-241248 | RP-241247 | Zhang, Peng, Huawei | zhangpeng169@huawei.com | 9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->20%; Stat Rep: ->RP-223349; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP..... |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 23/07/24
1622 | 961001 | Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) | DC_R18_1BLTE_1BNR_2DL2UL | 1 | Rel-18 |  | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241233 |  | CHTTL |  | 23/9/22: WID:RP-221264->RP-222091; 9/1/23: WID:RP-222091->RP-223078; 29/3/23: WID:RP-223078->RP-230338; 6/10/23: WID:RP-230338->RP-232302; 2/1/24: WID:RP-232302->RP-233242; 2/4/24: WID:RP-233242->RP-240482; 23/7/24: WID:RP-240482->RP-241233 |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 23/07/24
1623 | 961101 | Core part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) | DC_R18_1BLTE_1BNR_2DL2UL-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241233 | RP-241219 | Bo-Han Hsieh (Tank), CHTTL | pohanhsieh@cht.com.tw | 9/9/22: Comp...; 23/9/22: 37.718-11-11 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; WID: RP-222091->RP-222091 Revised WID: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL); Stat Rep: ->RP-223077;... | 37.718-11-11 | 96 | 49 |  |  | Wed 03/08/22 | Thu 13/06/24
1624 | 961201 | Perf. part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) | DC_R18_1BLTE_1BNR_2DL2UL-Perf | 2 | Rel-18 | R4 | 2022-06-16 08:00 | 2024-06-06 17:00 | 100% | RP-241233 | RP-241219 | Bo-Han Hsieh (Tank), CHTTL | pohanhsieh@cht.com.tw | 9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-222091->RP-222091 Revised WID: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL); Stat Rep: ->RP-223077; Rapporteur: CHTTL->Bo-Han Hsieh (Tank), CHTT... |  | 96 | 49 |  |  | Wed 03/08/22 | Thu 13/06/24
1625 | 961002 | Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) | DC_R18_xBLTE_yBNR_zDL3UL | 1 | Rel-18 |  | 2022-06-15 08:00 | 2024-06-06 17:00 | 87% | RP-241274 |  | Samsung |  | 23/9/22: WID:RP-221400->RP-222237; 2/1/24: WID:RP-222237->RP-233989; 2/4/24: WID:RP-233989->RP-240374; 23/7/24: WID:RP-240374->RP-241274 |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 23/07/24
1626 | 961102 | Core part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) | DC_R18_xBLTE_yBNR_zDL3UL-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241274 | RP-241273 | Yuanyuan Zhang, Samsung | Tina55.zhang@samsung.com | 9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222924; Rapporteur: Samsung->Yuanyuan Zhang, Samsung; Rap eMail: ->Tina55.zhang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Re..... |  | 96 | 49 |  |  | Wed 03/08/22 | Thu 13/06/24
1627 | 961202 | Perf. part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) | DC_R18_xBLTE_yBNR_zDL3UL-Perf | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2023-06-27 12:00 | 70% | RP-241274 | RP-241273 | Yuanyuan Zhang, Samsung | Tina55.zhang@samsung.com | 9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222924; Rapporteur: Samsung->Yuanyuan Zhang, Samsung; Rap eMail: ->Tina55.zhang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Re..... |  | 96 | 49 |  |  | Wed 03/08/22 | Thu 13/06/24
1628 | 961003 | Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) | DC_R18_xBLTE_2BNR_yDL2UL | 1 | Rel-18 |  | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241052 |  | LG Electronics |  | 23/9/22: WID:RP-221800->RP-221944; 9/1/23: WID:RP-221944->RP-222840; 29/3/23: WID:RP-222840->RP-230725; 6/10/23: WID:RP-230725->RP-231723; 2/1/24: WID:RP-231723->RP-233488; 2/4/24: WID:RP-233488->RP-240758; 23/7/24: WID:RP-240758->RP-241052 |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 23/07/24
1629 | 961103 | Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) | DC_R18_xBLTE_2BNR_yDL2UL-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241052 | RP-241053 | Sang-Wook Lee, LG Electronics | sangwook1.lee@lge.com | 9/9/22: Comp...; 23/9/22: 37.718-11-21 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222841; Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; 17/3/23: FCD:30/11/2..... | 37.718-11-21 | 96 | 49 |  |  | Wed 03/08/22 | Thu 13/06/24
1630 | 961203 | Stopped - Perf. Part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) | DC_R18_xBLTE_2BNR_yDL2UL-Perf | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-03-01 17:00 | 100% | RP-241052 | RP-241053 | Sang-Wook Lee, LG Electronics | sangwook1.lee@lge.com | 9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222841; Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30..... |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 23/07/24
1631 | 961004 | Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) | DC_R18_2BLTE_1BNR_3DL2UL | 1 | Rel-18 |  | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241245 |  | Huawei |  | 23/9/22: WID:RP-221832->RP-222505; 9/1/23: WID:RP-222505->RP-223348; 29/3/23: WID:RP-223348->RP-230473; 6/10/23: WID:RP-230473->RP-232370; 2/1/24: WID:RP-232370->RP-233987; 2/4/24: WID:RP-233987->RP-240417; 23/7/24: WID:RP-240417->RP-241245 |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 23/07/24
1632 | 961104 | Core part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) | DC_R18_2BLTE_1BNR_3DL2UL-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241245 | RP-241244 | Liehai Liu, Huawei | liuliehai@huawei.com | 9/9/22: Comp...; 23/9/22: 37.718-21-11 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; Stat Rep: ->RP-223347; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Co..... | 37.718-21-11 | 96 | 49 |  |  | Wed 03/08/22 | Thu 13/06/24
1633 | 961204 | Stopped - Perf. part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) | DC_R18_2BLTE_1BNR_3DL2UL-Perf | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-03-01 17:00 | 100% | RP-241245 | RP-233192 | Liehai Liu, Huawei | liuliehai@huawei.com | 9/9/22: Comp…; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; Stat Rep: ->RP-223347; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:30%->50%¦01/24: stopped at 85% at RAN#102 |  | 96 | 49 | 102 |  | Wed 03/08/22 | Tue 02/01/24
1634 | 961005 | Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) | DC_R18_xBLTE_1BNR_yDL2UL | 1 | Rel-18 |  | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241166 |  | Nokia |  | 23/9/22: WID:RP-221833->RP-222312; 9/1/23: WID:RP-222312->RP-222876; 29/3/23: WID:RP-222876->RP-230090; 6/10/23: WID:RP-230090->RP-232248; 2/1/24: WID:RP-232248->RP-233988; 2/4/24: WID:RP-233988->RP-240384; 23/7/24: WID:RP-240384->RP-241166 |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 23/07/24
1635 | 961105 | Core part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) | DC_R18_xBLTE_1BNR_yDL2UL-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241166 | RP-241165 | Johannes Hejselbaek, Nokia | johannes.hejselbaek@nokia.com | 9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222875; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; S..... |  | 96 | 49 |  |  | Wed 03/08/22 | Thu 13/06/24
1636 | 961205 | Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) | DC_R18_xBLTE_1BNR_yDL2UL-Perf | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-03-01 17:00 | 100% | RP-241166 | RP-240382 | Johannes Hejselbaek, Nokia | johannes.hejselbaek@nokia.com | 9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222875; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:5%->10%; Stat Rep: RP-2228..... |  | 96 | 49 |  |  | Wed 03/08/22 | Thu 14/03/24
1637 | 961006 | Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) | DC_R18_xBLTE_yBNR_zDL2UL | 1 | Rel-18 |  | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241225 |  | ZTE |  | 23/9/22: WID:RP-221834->RP-222094; 9/1/23: WID:RP-222094->RP-222906; 29/3/23: WID:RP-222906->RP-230135; 6/10/23: WID:RP-230135->RP-231842; 2/1/24: WID:RP-231842->RP-232923; 2/4/24: WID:RP-232923->RP-240760; 23/7/24: WID:RP-240760->RP-241225 |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 23/07/24
1638 | 961106 | Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) | DC_R18_xBLTE_yBNR_zDL2UL-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241225 | RP-24xxxx | Wubin Zhou, ZTE | Zhou.wubin@zte.com.cn | 9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222907; Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->Cao.aijun@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222907->RP-..... |  | 96 | 49 |  |  | Wed 03/08/22 | Thu 13/06/24
1639 | 961206 | Stopped - Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) | DC_R18_xBLTE_yBNR_zDL2UL-Perf | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-03-01 17:00 | 100% | RP-240760 | RP-24xxxx | Wubin Zhou, ZTE | Zhou.wubin@zte.com.cn | 9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222907; Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->Cao.aijun@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222907->RP-..... |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 23/07/24
1640 | 960096 | Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band | NR_LTE_V2X_PC5_combos_R18 | 1 | Rel-18 |  | 2022-06-15 08:00 | 2023-12-12 17:00 | 100% | RP-230390 |  | CATT |  | 23/9/22: WID:RP-221879->RP-222385; 29/3/23: WID:RP-222385->RP-230390 |  | 96 | 49 |  |  | Wed 03/08/22 | Wed 29/03/23
1641 | 960196 | Core part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band | NR_LTE_V2X_PC5_combos_R18-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2023-12-12 17:00 | 100% | RP-230390 | RP-233006 | Qiuge Guo, CATT | guoqiuge@catt.cn | 9/9/22: Comp...; 23/9/22: 37.878 added;; 17/3/23: FCD:23/12/2022->12/12/2023; Compl:5%->50%; Stat Rep: ->RP-230389; Rapporteur: CATT->Qiuge Guo, CATT; Rap eMail: ->guoqiuge@catt.cn; ; 6/9/23: Stat Rep: RP-230389->RP-231834; ; 8/12/23: Compl:5 | 37.878 | 96 | 49 |  |  | Wed 03/08/22 | Fri 08/12/23
1642 | 960296 | Perf. part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band | NR_LTE_V2X_PC5_combos_R18-Perf | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2023-12-12 17:00 | 100% | RP-230390 | RP-233006 | Qiuge Guo, CATT | guoqiuge@catt.cn | 9/9/22: CD:1...; 9/12/22: Acronym:NR_LTE_V2X_PC5_combos_R18-Perf->NR_LTE_V2X_PC5_combos_R18-Core; FCD:23/12/2022->01/12/2023; Compl:0%->50%; Stat Rep: ->RP-223146; Rapporteur: CATT->Qiuge Guo, CATT; Rap eMail: ->guoqiuge@catt.cn; 17/3/23..... |  | 96 | 49 |  |  | Wed 03/08/22 | Fri 08/12/23
1643 | 960094 | Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink | DL_intrpt_combos_TxSW_R18 | 1 | Rel-18 |  | 2022-06-15 08:00 | 2025-06-06 17:00 | 100% | RP-233588 |  | China Telecom | LTE, NR | 23/9/22: WID:RP-221843->RP-222288; 2/1/24: WID:RP-222288->RP-233588 |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 02/01/24
1644 | 960194 | Core part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink | DL_intrpt_combos_TxSW_R18-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2023-12-12 17:00 | 100% | RP-233588 | RP-233587 | Liu, Bo, China Telecom | liubo1@chinatelecom.cn | 9/9/22: Comp...; 23/9/22: 37.877 added;; 17/3/23: FCD:23/12/2022->12/12/2023; Compl:10%->99%; WID: RP-222288->RP-221843 RP-222288; Stat Rep: ->RP-230319; Rapporteur: China Telecom->Liu, Bo, China Telecom; Rap eMail: LTE, NR->liubo1@chinate... | 37.877 | 96 | 49 |  |  | Wed 03/08/22 | Fri 08/12/23
1645 | 960294 | Perf. part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink | DL_intrpt_combos_TxSW_R18-Perf | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2023-12-12 17:00 | 100% | RP-233588 | RP-233587 | Liu, Bo, China Telecom | liubo1@chinatelecom.cn | 9/9/22: CD:1...; 9/12/22: Acronym:DL_intrpt_combos_TxSW_R18-Perf->DL_intrpt_combos_TxSW_R18-Core; FCD:23/12/2022->01/12/2023; Compl:0%->20%; WID: RP-222288->RP-221843 RP-222288; Stat Rep: ->RP-222939; Rapporteur: China Telecom->Liu, Bo, Ch... |  | 96 | 49 |  |  | Wed 03/08/22 | Fri 08/12/23
1646 | 1050129 | UE Conformance - Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink | DL_intrpt_combos_TxSW_R18-UEConTest | 2 | Rel-18 | R5 | 2024-09-09 08:00 | 2025-06-06 17:00 | 100% | RP-251465 | RP-251464 | China Telecom |  | 6/12/24: Compl:0%->67%; Stat Rep: ->RP-242853; ; 6/3/25: FCD:24/07/2025->12/12/2025; Compl:67%->69%; Stat Rep: RP-242853->RP-250380; ; 6/6/25: FCD:Fri 12/12/25->Fri 06/06/25; Compl:69%->100%; Stat Rep: RP-250380->RP-251464; ; 18/7/25: WID:RP-242001->RP-2 |  | 105 | 53 |  |  | Thu 26/09/24 | Fri 18/07/25
1647 | 0 | Rel-18 Other LTE-only | - | 1 | Rel-18 |  | 2019-03-07 07:00 | 2019-03-07 07:00 | 0% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1648 | 960099 | Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL | LTE_CA_R18_xBDL_yBUL | 1 | Rel-18 |  | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241242 |  | Huawei | LTE | 23/9/22: WID:RP-221831->RP-222503; 9/1/23: WID:RP-222503->RP-223489; 29/3/23: WID:RP-223489->RP-230471; 6/10/23: WID:RP-230471->RP-232368; 2/1/24: WID:RP-232368->RP-233927; 2/4/24: WID:RP-233927->RP-240414; 23/7/24: WID:RP-240414->RP-241242 |  | 96 | 49 |  |  | Wed 03/08/22 | Tue 23/07/24
1649 | 960199 | Core part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL | LTE_CA_R18_xBDL_yBUL-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-06-06 17:00 | 100% | RP-241242 | RP-241241 | Mohammad Abdi Abyaneh, Huawei- HiSilicon | Mohammad.abdi.abyaneh@huawei.com | 9/9/22: Comp...; 23/9/22: 36.718-02-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:20%->35%; Stat Rep: ->RP-223345; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei; Rap eMail: LTE->Mohammad.abdi.abyaneh@huawei.com; 17/3/23: FCD:..... | 36.718-02-01 | 96 | 49 |  |  | Wed 03/08/22 | Thu 13/06/24
1650 | 960299 | Stopped - Perf. part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL | LTE_CA_R18_xBDL_yBUL-Perf | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2024-03-01 17:00 | 100% | RP-240414 | RP-233189 | Mohammad Abdi Abyaneh, Huawei- HiSilicon | Mohammad.abdi.abyaneh@huawei.com | 9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:20%->35%; Stat Rep: ->RP-223345; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei; Rap eMail: LTE->Mohammad.abdi.abyaneh@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Stat R.....; 2/1/24: St |  | 96 | 49 | 102 |  | Wed 03/08/22 | Tue 02/01/24
1651 | 961000 | LTE intra-band contiguous Carrier Aggregation for band 8 | LTE_CA_intra_B8 | 1 | Rel-18 | R4 | 2022-06-15 08:00 | 2022-12-22 17:00 | 100% | RP-221846 |  | China Mobile | LTE |  |  | 96 | 49 |  |  | Wed 03/08/22 | NA
1652 | 961100 | Core part: LTE intra-band contiguous Carrier Aggregation for band 8 | LTE_CA_intra_B8-Core | 2 | Rel-18 | R4 | 2022-06-15 08:00 | 2022-12-22 17:00 | 100% | RP-221846 |  | China Mobile | LTE | 9/9/22: Comp...; 9/1/23: 99%->100 |  | 96 | 49 |  |  | Wed 03/08/22 | Mon 09/01/23
1653 | 1080079 | UE Conformance - Rel-18 LTE CA Configurations | LTE_CA_R18-UEConTest | 1 | Rel-18 | R5 | 2025-06-06 08:00 | 2026-09-09 17:00 | 5% | RP-251457 | RP-252550 | China Telecom |  | tested: REL-18 WI LTE_CA_R18_xBDL_yBUL-Core; compare: LTE_CA_R17, LTE_CA_R16, LTE_CA_R15, LTE_CA_R14 ; 11/9/25: FCD:Wed 09/09/26->Tue 08/09/26; Compl:0%->5%; Stat Rep: ->RP-252550; |  | 108 | 55 |  |  | Fri 18/07/25 | Thu 11/09/25
1654 | 1010054 | High Power UE (Power Class 2) for LTE FDD Band 14 | HPUE_LTE_FDD_B14 | 1 | Rel-18 | R4 | 2023-09-09 08:00 | 2024-03-01 17:00 | 100% | RP-232946 |  | AT&T |  | 2/1/24: WID:RP-232676->RP-232946 |  | 101 | 51 |  |  | Fri 06/10/23 | Tue 02/01/24
1655 | 1011054 | Core part: High Power UE (Power Class 2) for LTE FDD Band 14 | HPUE_LTE_FDD_B14-Core | 2 | Rel-18 | R4 | 2023-09-09 08:00 | 2024-03-01 17:00 | 100% | RP-232946 | RP-240075 | Borsato, Ron | ronald.borsato@att.com | 8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->50%; Stat Rep: ->RP-232945; Rapporteur: AT&T->Borsato, Ron; Rap eMail: ->ronald.borsato@att.com; ; 4/1/24: 36.770 added;; 14/3/24: Compl:50%->100%; Stat Rep: RP-232945->RP-240075; List of Impacted TS & TR up | 36.77 | 101 | 51 |  |  | Fri 06/10/23 | Thu 14/03/24
1656 | 1012054 | Perf. part: High Power UE (Power Class 2) for LTE FDD Band 14 | HPUE_LTE_FDD_B14-Perf | 2 | Rel-18 | R4 | 2023-09-09 08:00 | 2024-03-01 17:00 | 100% | RP-232946 | RP-240075 | Borsato, Ron | ronald.borsato@att.com | 8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->80%; Stat Rep: ->RP-232945; Rapporteur: AT&T->Borsato, Ron; Rap eMail: ->ronald.borsato@att.com; ; 14/3/24: Compl:80%->100%; Stat Rep: RP-232945->RP-240075; |  | 101 | 51 |  |  | Fri 06/10/23 | Thu 14/03/24
1657 | 981048 | Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 | LTE_bands_R18_M1_M2_NB1_NB2 | 1 | Rel-18 |  | 2022-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-232892 |  | Ericsson |  | 2/1/24: WID:RP-222824->RP-232892 |  | 98 | 50 |  |  | Mon 09/01/23 | Tue 02/01/24
1658 | 981148 | Core part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 | LTE_bands_R18_M1_M2_NB1_NB2-Core | 2 | Rel-18 | R4 | 2022-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-232892 | RP- 232891 | Chunhui Zhang, Ericsson | Chunhui.Zhang@ericsson.com | 17/3/23: Compl:0%->99%; Stat Rep: ->RP-230462; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 6/9/23: Stat Rep: RP-230462->RP-231880; ; 8/12/23: Compl:99%->100%; Stat Rep: RP-231880->RP- 232891; |  | 98 | 50 |  |  | Mon 09/01/23 | Fri 08/12/23
1659 | 981248 | Perf. part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 | LTE_bands_R18_M1_M2_NB1_NB2-Perf | 2 | Rel-18 | R4 | 2022-12-13 08:00 | 2023-12-12 17:00 | 100% | RP-232892 | RP- 232891 | Chunhui Zhang, Ericsson | Chunhui.Zhang@ericsson.com | 17/3/23: Compl:0%->99%; Stat Rep: ->RP-230462; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 6/9/23: Stat Rep: RP-230462->RP-231880; ; 8/12/23: Compl:99%->100%; Stat Rep: RP-231880->RP- 232891; |  | 98 | 50 |  |  | Mon 09/01/23 | Fri 08/12/23
1660 | 981046 | Introduction of 900 MHz LTE band in the US | LTE_900MHz_US | 1 | Rel-18 |  | 2022-12-12 08:00 | 2025-03-03 17:00 | 86% | RP-230722 |  | Anterix |  | 29/3/23: WID:RP-223530->RP-230722 |  | 98 | 50 |  |  | Mon 09/01/23 | Wed 29/03/23
1661 | 981146 | Core part: Introduction of 900 MHz LTE band in the US | LTE_900MHz_US-Core | 2 | Rel-18 | R4 | 2022-12-12 08:00 | 2023-06-06 17:00 | 100% | RP-230722 | RP-231218 | Emil Olbrich, Anterix | eolbrich@anterix.com | 17/3/23: Compl:0%->20%; Stat Rep: ->RP-230264; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 29/6/23: 20%->100 |  | 98 | 50 |  |  | Mon 09/01/23 | Thu 29/06/23
1662 | 981246 | Perf. part: Introduction of 900 MHz LTE band in the US | LTE_900MHz_US-Perf | 2 | Rel-18 | R4 | 2022-12-12 08:00 | 2023-04-13 15:00 | 10% | RP-230722 | RP-231218 | Emil Olbrich, Anterix | eolbrich@anterix.com | 17/3/23: Compl:0%->10%; Stat Rep: ->RP-230264; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; |  | 98 | 50 |  |  | Mon 09/01/23 | Fri 17/03/23
1663 | 1030064 | UE Conformance - Introduction of 900 MHz LTE band in the US | LTE_900MHz_US-UEConTest | 2 | Rel-18 | R5 | 2024-03-03 08:00 | 2025-09-09 17:00 | 100% | RP-251938 | RP-251937 | Nokia |  | 13/6/24: Compl:0%->85%; Stat Rep: ->RP-240915; ; 4/9/24: FCD:03/03/2025->25/03/2025; Stat Rep: RP-240915->RP-241747; ; 6/12/24: Stat Rep: RP-241747->RP-242838; ; 6/3/25: FCD:12/11/2024->06/06/2025; Stat Rep: RP-242838->RP-250081; ; 6/6/25: FCD:Fri 06/06/2 |  | 103 | 52 |  |  | Tue 02/04/24 | Mon 29/09/25
1664 | 981040 | Maximum Power Reduction Requirements (MPR) for LTE intra-band Carrier Aggregation (CA) with a Component Carrier (CC) gap larger than 35 MHz | LTE_intra_CA_MPR_35MHz_gap | 1 | Rel-18 |  | 2022-12-12 08:00 | 2023-03-03 17:00 | 100% | RP-230705 |  | Huawei |  | 29/3/23: WID:RP-223511->RP-230705 |  | 98 | 50 |  |  | Mon 09/01/23 | Wed 29/03/23
1665 | 981140 | Core part: Maximum Power Reduction Requirements (MPR) for LTE intra-band Carrier Aggregation (CA) with a Component Carrier (CC) gap larger than 35 MHz | LTE_intra_CA_MPR_35MHz_gap-Core | 2 | Rel-18 | R4 | 2022-12-12 08:00 | 2023-03-03 17:00 | 100% | RP-230705 | RP-230480 | Mohammad Abdi Abyaneh, Huawei, HiSilicon | Mohammad.abdi.abyaneh@huawei.com | 17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230480; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei, HiSilicon; Rap eMail: ->Mohammad.abdi.abyaneh@huawei.com; |  | 98 | 50 |  |  | Mon 09/01/23 | Fri 17/03/23
1666 | 991040 | Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths | LTE600_US_lowCBW | 1 | Rel-18 | R4 | 2023-05-29 16:00 | 2023-12-12 17:00 | 0% | RP-230745 |  | T-Mobile USA |  |  |  | 99 | 50 |  |  | Wed 29/03/23 | NA
1667 | 991140 | Core part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths | LTE600_US_lowCBW-Core | 2 | Rel-18 | R4 | 2023-05-29 16:00 | 2023-12-12 17:00 | 0% | RP-230745 |  | T-Mobile USA |  | ; 7/6/23: CD:06/06/2023->12/12/2023 |  | 99 | 50 |  |  | Wed 29/03/23 | Wed 07/06/23
1668 | 991240 | Perf. part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths | LTE600_US_lowCBW-Perf | 2 | Rel-18 | R4 | 2023-05-29 16:00 | 2023-12-12 17:00 | 0% | RP-230745 |  | T-Mobile USA |  | ; 7/6/23: CD:09/09/2023->12/12/2023 |  | 99 | 50 |  |  | Wed 29/03/23 | Wed 07/06/23
1669 | 0 | Rel-18 RAN Studies | - | 1 | Rel-18 |  | 2017-12-15 08:00 | 2017-12-15 08:00 | 34% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1670 | 991031 | Study on enhancement for sub-1GHz NR band combinations | FS_NR_sub1GHz_combo_enh | 1 | Rel-18 | R4 | 2023-03-03 08:00 | 2023-09-08 17:00 | 100% | RP-231141 | RP-232661 | Zhang, Peng, Huawei | zhangpeng169@huawei.com | ; 7/6/23: Compl:0%->86%; 7/6/23: CD:06/06/2023->09/09/2023; 6/9/23: FCD:09/09/2023->12/12/2023; Compl:86%->80%; WID: RP-230789->RP-231141; Stat Rep: ->RP-232378; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ; 21/9/23: FC |  | 99 | 50 |  |  | Wed 29/03/23 | Thu 21/09/23
1671 | 991030 | Study on self-evaluation towards the IMT-2020 submission of the 3GPP Satellite Radio Interface Technology | FS_IMT2020_SAT_eval | 1 | Rel-18 | RP | 2023-03-03 08:00 | 2023-12-12 17:00 | 100% | RP-231945 | RP-231944 | Asbj rn Gr vlen, Ericsson | asbjorn.grovlen@ericsson.com | 29/6/23: 0%->20; 21/9/23: Compl:20%->40%; WID: RP-230736->RP-231945; Stat Rep: RP-231291->RP-231944; Rapporteur: Asbjörn Grövlen, Ericsson->Asbj rn Gr vlen, Ericsson; ; 21/9/23: 37.911 added;; 2/1/24: 40%->100 | 37.911 | 99 | 50 |  |  | Wed 29/03/23 | Tue 02/01/24
1672 | 970078 | Study on Ambient IoT (Internet of Things) in RAN | FS_Ambient_IoT_RAN | 1 | Rel-18 | RP | 2022-09-08 08:00 | 2023-09-08 17:00 | 100% | RP-232404 | RP-232403 | Matthew Webb, Huawei | matthew.webb@huawei.com | 9/1/23: WID:RP-222685->RP-223396; 17/3/23: 38.848 added;; 31/3/23: Compl:0%->50%; WID: RP-223396->RP-222685; Stat Rep: ->RP-230669; Rapporteur: Huawei->Matthew Webb, Huawei; Rap eMail: ->matthew.webb@huawei.com; ; 29/6/23: 50%->60; 29/6/23: FCD:06/06/... | 38.848 | 97 | 49 |  |  | Fri 23/09/22 | Fri 06/10/23
1673 | 950067 | Study on simplification of band combination specification for NR and LTE | FS_SimBC | 1 | Rel-18 | R4 | 2022-03-15 08:00 | 2023-12-12 17:00 | 100% | RP-231468 | RP-233234 | Zhifeng Ma, ZTE Corporation | ma.zhifeng@zte.com.cn | TR 37.8xx; LTE only combos will not be considered ; 20/6/22: FCD:15/06/2023->23/06/2022; Stat Rep: ->RP-221266 / 1769; Rapporteur: ZTE->Zhifeng Ma, ZTE Corporation; Rap eMail: ->ma.zhifeng@zte.com.cn12/7/22: WID:RP-220956->RP-221790; 13/7/22: FCD:...;... | 38.846 | 95 | 48 |  |  | Tue 05/04/22 | Fri 08/12/23
1674 | 950068 | Study on NR frequency range 2 (FR2) Over-the-Air (OTA) testing enhancements | FS_NR_FR2_OTA_enh | 1 | Rel-18 | R4 | 2022-03-15 08:00 | 2023-12-12 17:00 | 100% | RP-233171 | RP-233170 | Bin Han, Qualcomm Incorporated | binhan@qti.qualcomm.com | compare REL-16 SI FS_NR_test_methods and REL-17 SI FS_FR2_enhTestMethods; TR 38.3xx ; 6/6/22: CD:15/12/2023->23/12/2022; 6/6/22: Stat Rep: ->RP-221391; 20/6/22: Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com... | 38.871 | 95 | 48 |  |  | Tue 05/04/22 | Tue 02/01/24
1675 | 950069 | Study on NR base station (BS) RF requirement evolution | FS_NR_BS_RF_evo | 1 | Rel-18 | R4 | 2022-03-15 08:00 | 2023-06-06 17:00 | 100% | RP-222501 | RP-230469 | Liehai Liu, Huawei | liuliehai@huawei.com | for NR FR2 mmWave BSs; TR 38.8xx 6/6/22: CD:15/06/2023->23/06/20226/6/22: Stat Rep: ->RP-221530; 20/6/22: Rapporteur: Huawei->Richard Kybett, Huawei; Rap eMail: ->Richard.kybett@huawei.com13/7/22: FCD:23/06/2022->06/20; 13/7/22: 38.877 added;;...; 23/... | 38.877 | 95 | 48 |  |  | Tue 05/04/22 | Wed 07/06/23
1676 | 950070 | Study on enhancement for 700/800/900MHz band combinations for NR | FS_NR_700800900_combo_enh | 1 | Rel-18 | R4 | 2022-03-03 08:00 | 2023-03-03 17:00 | 100% | RP-222554 | RP-230388 | Huiping Shan, CATT | shanhuiping@catt.cn | TR 38.8xx ; 6/6/22: CD:08/06/2021->23/03/2023; 6/6/22: Stat Rep: ->RP-221460; 20/6/22: Rapporteur: CATT->Yuexia Song, CATT; Rap eMail: ->songyuexia@catt.cn12/7/22: WID:RP-221016->RP-221464; 13/7/22: 38.872 added ; ;...; 23/9/22: WID:RP-221464->RP-2225... | 38.872 | 95 | 48 |  |  | Tue 05/04/22 | Fri 17/03/23
1677 | 850071 | Study on enhanced test methods for FR2 NR UEs | FS_FR2_enhTestMethods | 1 | Rel-18 | R4 | 2019-09-19 08:00 | 2022-06-22 17:00 | 100% | RP-221574 | RP-221575 | Anatoliy IOFFE, Ruixin WANG, Aida Vera LOPEZ, Apple Inc., vivo, Intel Corporation | aioffe@apple.com, ruixin.wang@vivo.com, aida.l.vera.lopez@intel.com | TR 38.8XX; 14/1/20: WID:RP-192322->RP-192430; 28/7/20: WID:RP-192430->RP-201110; 25/9/20: WID:RP-201110->RP-201862; 7/4/21: WID:RP-201862->RP-210633; 2/7/21: WID:RP-210633->RP-211600; ; 04/22: Rel-17->Rel-18 ; ; 20/6/22: Rapporteur: Apple->Anatoliy ... |  | 85 | 43 |  |  | Tue 08/10/19 | Tue 12/07/22
1678 | 890040 | Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths | FS_NR_eff_BW_util | 1 | Rel-18 | R4 | 2020-09-17 08:00 | 2023-03-03 17:00 | 100% | RP-222618 | RP-230579 | Esther Sienkiewicz, Ericsson | esther dot sienkiewicz at ericsson dot com | TR 38.8xx ; 6/1/21: WID:RP-202103->RP-202339; 7/4/21: WID:RP-202339->RP-210706; 2/7/21: WID:RP-210706->RP-211468; 13/9/21: Compl:0%->50%; ; 6/1/22: WID:RP‑211468->RP-213657 ; 5/4/22: WID:RP-213657->RP-220461; 04/22: Rel-17->Rel-18; ; 20/6/22: Rappor... | 38.844 | 89 | 45 |  |  | Fri 25/09/20 | Fri 17/03/23
1679 | 0 | Rel-18 Network automation | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1680 | 990118 | Enablers for Network Automation for 5G phase 3 | eNA_Ph3 | 1 | Rel-18 |  | 2021-12-20 08:00 | 2024-03-03 17:00 | 100% | SP-221345 |  | Aihua Li, China Mobile | liaihua@chinamobile | 10/12/22: 0%->25 | 23.501; 23.502; 23.503; 23.288 | 99 | 50 |  |  | Fri 09/12/22 | Sat 10/12/22
1681 | 940073 | Study on Enablers for Network Automation for 5G - phase 3 | FS_eNA_Ph3 | 2 | Rel-18 | S2 | 2021-12-20 08:00 | 2022-12-12 17:00 | 100% | SP-220678 |  | Aihua Li, China Mobile | liaihua@chinamobile.com | 21/1/22: 23.700-81 added;; 21/1/22: 23.700-85 added;; 12/3/22: 0%->13; 4/6/22: 13%->50; 21/6/22: WID:SP-211650->SP-220678; 12/9/22: 50%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100 | 23.700-81; 23.700-85 | 94 | 48 |  |  | Sun 19/12/21 | Sat 10/12/22
1682 | 950021 | Study on security aspects of enablers for Network Automation for 5G - phase 3 | FS_eNA_SEC_Ph3 | 2 | Rel-18 | S3 | 2022-03-10 08:00 | 2023-03-03 17:00 | 100% | SP-220199 |  | Chang Liu, China Mobile | liuchangyjy@chinamobile.com | 4/6/22: 0%->10; 13/7/22: 33.738 added;; 12/9/22: 10%->35; 11/12/22: 35%->60; 17/3/23: 60%->80; 8/6/23: 80%->95; 15/3/24: 95%->100 | 33.738 | 95 | 48 |  |  | Thu 10/03/22 | Fri 15/03/24
1683 | 990042 | Security aspects of enablers for Network Automation for 5G - phase 3 | eNA_Ph3_SEC | 2 | Rel-18 | S3 | 2023-03-16 08:00 | 2023-09-09 17:00 | 100% | SP-230155 |  | Chang Liu, China Mobile | liuchangyjy@chinamobile.com | ; 8/6/23: 0%->65; 15/3/24: 65%->100 | 33.501 | 99 | 50 |  |  | Thu 16/03/23 | Fri 15/03/24
1684 | 980020 | (stage 2 of eNA_Ph3) Enablers for Network Automation for 5G phase 3 | eNA_Ph3 | 2 | Rel-18 | S2 | 2022-12-09 08:00 | 2023-06-06 17:00 | 100% | SP-230110 |  | Aihua Li, China Mobile | liaihua@chinamobile | 10/12/22: 0%->25; 15/3/23: 13%->65; 15/3/23: WID:SP-221345->SP-230110; 8/6/23: 65%->100 | 23.501; 23.502; 23.503; 23.288 | 98 | 50 |  |  | Fri 09/12/22 | Thu 08/06/23
1685 | 990010 | CT3 aspects of eNA_Ph3 | eNA_Ph3 | 2 | Rel-18 | C3 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240079 |  | Zhennning Huang, China Mobile | huangzhenning@chinamobile.com | ; 6/6/23: Compl:15%->65% | 29.507.29.508.29.122.29.513.29.517.29.519.29.520.29.522.29.523.29.525.29.551.29.552.29.574.29.575.29.576.29.591.29.503.29.504.29.505.29.510.29.515.29.518.29.564.29.571 | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
1686 | 990104 | CT4 aspects of eNA_Ph3 | eNA_Ph3 | 2 | Rel-18 | C4 | 2023-03-13 08:00 | 2024-03-03 17:00 | 100% | CP-240079 |  | Zhennning Huang, China Mobile | huangzhenning@chinamobile.com | ; 6/6/23: Compl:5%->30% | 29.507.29.508.29.122.29.513.29.517.29.519.29.520.29.522.29.523.29.525.29.551.29.552.29.574.29.575.29.576.29.591.29.503.29.504.29.505.29.510.29.515.29.518.29.564.29.571 | 99 | 50 |  |  | Fri 09/12/22 | Tue 06/06/23
1687 | 980039 | Enhancement of Network Automation Enablers | eNetAE | 1 | Rel-18 | C3 | 2022-12-15 08:00 | 2024-03-03 17:00 | 100% | CP-231191 |  | Xuefei Zhang, Huawei | summer.xuefei@huawei.com | ; 6/6/23: Compl:70%->90%; 6/6/23: CD:12/12/2023->03/03/2024; ;... | 29.517; 29.520; 29.522; 29.552; 29.574; 29.575; 29.576; 29.591 | 96 | 49 |  |  | Fri 03/06/22 | Tue 06/06/23
1688 | 0 | Rel-18 other Studies | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1689 | 860010 | Guidelines for Extra-territorial 5G Systems | FS_5GET | 1 | Rel-18 | S1 | 2019-12-06 08:00 | 2021-12-10 17:00 | 100% | SP-191042 |  | Cyril MICHEL,Thales | cyril.michel@thalesaleniaspace.com | 12/9/20: 0%->20; 5/12/20: 20%->40; 19/3/21: FCD:11/09/2020->12/21; 19/3/21: 40%->50; 11/6/21: 50%->60; 13/9/21: 60%->80; 10/12/21: 80%->100 |  | 86 | 44 |  |  | Fri 06/12/19 | Fri 10/12/21
1690 | 960002 | Study on NRF API enhancements to avoid signalling and storing of redundant data | FS_NRFe | 1 | Rel-18 | C4 | 2022-06-02 08:00 | 2023-09-09 17:00 | 100% | CP-231022 |  | Wiehe, Ulrich, Nokia | Ulrich.wiehe@nokia.com | 13/7/22: 29.831 added;; 6/6/23: Compl:50%->60%; 30/6/23: WID:CP-221088->CP-231022 | 29.xxx; 29.831 | 96 | 49 |  |  | Mon 20/06/22 | Fri 30/06/23
1691 | 0 | Rel-18 Management-only Features | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1692 | 1000007 | Management of cloud-native Virtualized Network Functions | MCVNF | 1 | Rel-18 | S5 | 2023-06-30 08:00 | 2024-03-03 17:00 | 100% | SP-230764 |  | China Mobile Guangjing Cao | caoguangjing@chinamobile.com | ; 7/9/23: 0%->30; 8/12/23: 30%->95; 14/3/24: 95%->100 | 28.531; 28.533; 28.526 | 100 | 51 |  |  | Fri 30/06/23 | Thu 14/03/24
1693 | 1000011 | Charging enhancement for Network Slice based wholesale in roaming | CHNSWO | 1 | Rel-18 | S5 | 2023-05-01 08:00 | 2023-06-06 17:00 | 100% | SP-230625 |  | Maryse Gardella, MATRIXX Software, | Maryse dot Gardella at Matrixx dot com | ; 8/12/23: 0%->100 | 32.240; 32.255; 32.256; 32.291; 32.298 | 100 | 51 |  |  | Thu 08/06/23 | Fri 08/12/23
1694 | 1000014 | Network and Service Operations for Energy Utilities | NSOEU | 1 | Rel-18 | S5 | 2023-06-08 08:00 | 2024-03-03 17:00 | 100% | SP-230632 |  | Erik Guttman , Samsung; | <erik.guttman@samsung.com | ; 30/6/23: 28.318 added;; 7/9/23: 0%->30; 8/12/23: 30%->60; 4/1/24: 28.879 added;; 14/3/24: 60%->100 | 28.552; 28.554; 28.622 ; 28.318; 28.879 | 100 | 51 |  |  | Thu 08/06/23 | Thu 14/03/24
1695 | 980026 | Study on CHF Segmentation | FS_CHFSeg | 1 | Rel-18 | S5 | 2022-12-12 08:00 | 2024-03-03 17:00 | 100% | SP-221160 |  | João Rodrigues, Nokia | joao.a.rodrigues@nokia.com | 17/3/23: 0%->5; 17/3/23: 28.840 added;; 8/6/23: 5%->12; 7/9/23: 12%->18; 8/12/23: 18%->55; 8/12/23: FCD:09/09/2023->/2024; 14/3/24: 55%->100 | 28.840 | 98 | 50 |  |  | Fri 09/12/22 | Thu 14/03/24
1696 | 980029 | Management of Trace/MDT phase 2 | 5GMDT_Ph2 | 1 | Rel-18 | S5 | 2022-12-12 08:00 | 2024-03-03 17:00 | 100% | SP-230777 |  | Swaminathan, Sivaramakrishnan, Nokia | sivaramakrishnan<dot>swaminathan<at>nokia<dot>com | ; 8/6/23: 0%->; 30/6/23: WID:SP-221163->SP-230777; 7/9/23: 0%->40; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 40%->90; 14/3/24: 90%->100 | 28.621; 28.622; 28.623; 32.421; 32.422; 32.423 | 98 | 50 |  |  | Fri 09/12/22 | Thu 14/03/24
1697 | 940037 | Enhancements of EE for 5G Phase 2 | EE5GPLUS_Ph2 | 1 | Rel-18 | S5 | 2021-12-10 08:00 | 2023-12-12 17:00 | 100% | SP-211441 |  | Cornily Jean-Michel, Huawei | jean.michel.cornily@huawei.com | ; 12/9/22: 0%->10; 12/9/22: FCD:10/03/2023->06/23; 11/12/22: 10%->25; 17/3/23: 25%->30; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 30%->35; 7/9/23: 35%->55; 8/12/23: 55%->100 | 28.310; 28.552; 28.554; 28.541 | 94 | 48 |  |  | Fri 10/12/21 | Fri 08/12/23
1698 | 940014 | Security Assurance Specification for Management Function (MnF) | SCAS_5G_MF | 1 | Rel-18 | S3 | 2021-12-10 08:00 | 2022-12-09 17:00 | 100% | SP-211362 |  | Noamen Ben Henda, Huawei Technologies Co., Ltd. | noamen.ben.henda@huawei.com | ; 7/1/22: 33.526 added;; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->60; 11/12/22: 60%->75; 17/3/23: 75%->85; 8/6/23: 85%->95; 7/9/23: 95%->100 | 33.926 ; 33.526 | 94 | 48 |  |  | Fri 10/12/21 | Thu 07/09/23
1699 | 960023 | Multimedia Messaging Service Charging using service-based interface | MMS_CH_SBI | 1 | Rel-18 | S5 | 2022-06-02 08:00 | 2022-12-12 17:00 | 100% | SP-220689 |  | Törnkvist, Robert, Ericsson AB | robert(dot)tornkvist(at)Ericson(dot)com | ; 17/8/22: WID:SP-220486->SP-220689; 12/9/22: 0%->25; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 25%->100 | 32.240; 32.270; 32.290; 32.291; 32.298 | 96 | 49 |  |  | Thu 02/06/22 | Sun 11/12/22
1700 | 960025 | 5G performance measurements and KPIs phase 3 | PM_KPI_5G_Ph3 | 1 | Rel-18 | S5 | 2022-06-02 08:00 | 2024-03-03 17:00 | 100% | SP-240271 |  | Chen, Xiumin, China Telecom | (chenxiumin<at>chinatelecom<dot>cn) | ; 17/8/22: WID:SP-220489->SP-220690; 12/9/22: 0%->15; 11/12/22: 15%->50; 17/3/23: 50%->60; 8/6/23: 60%->70; 8/6/23: 70%->; 7/9/23: 70%->80; 8/12/23: 80%->99; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-220690->SP-231710; 4/1/24: 28.558 added;; 14/3... | 28.552; 32.425; 28.554; 28.550 ; 28.558 | 96 | 49 |  |  | Thu 02/06/22 | Tue 02/04/24
1701 | 870027 | Enhancement of QoE Measurement Collection | eQoE | 1 | Rel-18 | S5 | 2020-03-25 08:00 | 2023-12-12 17:00 | 100% | SP-200193 |  | Bagher Zadeh, Ericsson | Bagher Zadeh <at>ericsson<dot>ericsson | ; 5/12/20: 0%->5; 21/3/21: 5%->15; 11/6/21: 15%->20; 13/9/21: 20%->40; 13/9/21: FCD:Thu 16/09/->03/22; 13/12/21: 40%->60; 12/3/22: 60%->90; 4/6/22: 90%->95; 4/6/22: FCD:11/03/2022->12/22; Rel-17->Rel-18; 12/9/22: 95%->70; 12/9/22: FCD:12/12/2022->12/2... | 28.307; 28.308; 28.309; 28.404; 28.405; 28.406; 28.622; 28.623; 28.533 | 87 | 44 |  |  | Fri 06/12/19 | Thu 08/06/23
1702 | 950036 | Enhanced Edge Computing Management | eECM | 1 | Rel-18 | S5 | 2022-03-10 08:00 | 2024-03-03 17:00 | 100% | SP-230775 |  | Deepanshu Gautam, Samsung | deepanshu<dot>g<at>samsung<dot>com | ; 4/6/22: 0%->10; 12/9/22: 10%->35; 11/12/22: 35%->50; 17/3/23: 50%->50; 17/3/23: FCD:03/03/2023->12/23; 17/3/23: FCD:12/12/2023->/23; 17/3/23: 50%->100; 30/6/23: WID:SP-220154->SP-230775; 8/12/23: 100%->70; 8/12/23: FCD:03/03/2023->/2024; 14/3/24: 70%-> | 28.541; 28.538; 28.552; 28.554; 28.531; 28.532 | 95 | 48 |  |  | Thu 10/03/22 | Thu 14/03/24
1703 | 890016 | Study on access control for management service | FS_MNSAC | 1 | Rel-17 | S5 | 2020-09-16 08:00 | 2021-09-08 17:00 | 100% | SP-200853 |  | Jing Ping, Nokia | jing.ping@nokia-sbell.com | 25/9/20: WID:SP-200764->SP-200853; 5/12/20: 0%->5; 21/3/21: 5%->35; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 35%->80; 11/6/21: FCD:Wed 08/09/->09/21; 13/9/21: 80%->100 |  | 89 | 45 |  |  | Fri 11/09/20 | Mon 13/09/21
1704 | 930010 | Access control for management service | MSAC | 1 | Rel-18 | S5 | 2021-09-10 08:00 | 2024-03-03 17:00 | 100% | SP-231711 |  | Clifton Fernandes, Nokia | Clifton.fernandes@nokia.com | ; 12/3/22: 0%->60; 4/6/22: 60%->67; 4/6/22: FCD:10/12/2021->12/22; Rel-17->Rel-18; 11/12/22: 67%->68; 11/12/22: FCD:12/12/2022->12/23; 17/3/23: 68%->69; 8/6/23: 69%->72; 7/9/23: 72%->73; 8/12/23: 73%->75; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP... | 28.319 | 93 | 47 |  |  | Fri 10/09/21 | Thu 14/03/24
1705 | 940033 | Network slice provisioning enhancement | eNETSLICE_PRO | 1 | Rel-18 | S5 | 2021-09-10 08:00 | 2023-12-12 17:00 | 100% | SP-211434 |  | Deepanshu Gautam , Samsung | deepanshu<dot>g<at>samsung<dot>com | ; 12/3/22: 0%->50; 4/6/22: 50%->85; 4/6/22: FCD:11/03/2022->09/22; Rel=-17->Rel-18; 12/9/22: 85%->85; 12/9/22: FCD:12/09/2022->12/12/22; 11/12/22: 85%->90; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 90%->90; 17/3/23: FCD:03/03/2023->12/23; 7/9/23: 90%->100 | 28.531; 28.541 | 94 | 48 |  |  | Fri 10/12/21 | Thu 07/09/23
1706 | 890017 | Study on YANG PUSH | FS_YANG | 1 | Rel-18 | S5 | 2020-09-16 08:00 | 2022-03-10 17:00 | 100% | SP-200765 |  | Lengyel, Balazs, Ericsson | balazs.lengyel@ericsson.com | 5/12/20: 0%->5; 21/3/21: 5%->10; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 10%->10; 13/9/21: FCD:Wed 08/09/->12/21; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 8/12/23: 10%->100 |  | 89 | 45 |  |  | Thu 10/09/20 | Fri 08/12/23
1707 | 910028 | Study on Continuous integration continuous delivery support for 3GPP NFs. | FS_CICDNS | 1 | Rel-18 | S5 | 2021-03-18 08:00 | 2022-03-11 17:00 | 100% | SP-211427 |  | Vaishnavi, Ishan, Lenovo | ivaishnavi@lenovo.com | ; 11/6/21: 0%->15; 13/9/21: 15%->30; 13/9/21: FCD:Fri 10/09/->12/21; 13/12/21: 30%->75; 13/12/21: FCD:Fri 10/12/->03/22; 7/1/22: 28.901 added;12/3/22: Rel-17->Rel-18; 4/6/22: 75%->100 | New ; 28.901 | 91 | 46 |  |  | Thu 18/03/21 | Sat 04/06/22
1708 | 910031 | Study on Enhancement of service-based management architecture | FS_eSBMA | 1 | Rel-18 | S5 | 2021-03-18 08:00 | 2023-06-06 17:00 | 100% | SP-210136 |  | Lan Zou, Huawei | zoulan@huawei.com | ; 11/6/21: 0%->10; 13/9/21: 10%->15; 13/12/21: 15%->45; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 4/6/22: 45%->60; 12/9/22: 60%->75; 12/9/22: FCD:11/03/2022->03/23; 11/12/22: 75%->80; 17/3/23: 80%->85; 17/3/23: FCD:03/03/2023->/23; 8/6/23 | New | 91 | 46 |  |  | Thu 18/03/21 | Thu 08/06/23
1709 | 990026 | Service based management architecture | eSBMA | 1 | Rel-18 | S5 | 2023-03-16 08:00 | 2024-03-03 17:00 | 100% | SP-231443 |  | Zhang Kai, Huawei | kai.zhangkai@huawei.com | ; 31/3/23: 28.111 added;; 30/6/23: WID:SP-230174->SP-230776; 7/9/23: 0%->10; 21/9/23: 32.161 added;; 8/12/23: 10%->55; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-230776->SP-231443; 4/1/24: 28.871 added;; 14/3/24: 55%->100 | 32.404; 28.622; 28.623; 32.300; 28.532; 28.545; 28.532; 28.532; 28.532; 28.158; 28.532 ; 28.111; 32.161; 28.871 | 99 | 50 |  |  | Thu 16/03/23 | Thu 14/03/24
1710 | 940034 | Study on Enhancement of the management aspects related to NWDAF | FS_MANWDAF | 1 | Rel-18 | S5 | 2021-12-13 08:00 | 2023-06-06 17:00 | 100% | SP-211435 |  | ZHAO, Song, China Telecom | zhaosong1@chinatelecom.cn | 7/1/22: 28.864 added;; 4/6/22: 0%->30; 12/9/22: 30%->65; 11/12/22: 65%->75; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 75%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 75%->100 | 28.864 | 94 | 48 |  |  | Mon 13/12/21 | Thu 08/06/23
1711 | 990031 | Management Aspects related to NWDAF | MANWDAF | 1 | Rel-18 | S5 | 2023-03-16 08:00 | 2023-12-12 17:00 | 100% | SP-230181 |  | Niu, Yuxia, China Telecom | niuyx@chinatelecom.cn | ; 8/6/23: 0%->50; 7/9/23: 50%->75; 8/12/23: 75%->100; 4/1/24: 28.877 added; | 28.541; 28.552; 28.554 ; 28.877 | 99 | 50 |  |  | Thu 16/03/23 | Thu 04/01/24
1712 | 940035 | Study on enhancement of management of non-public networks | FS_OAM_eNPN | 1 | Rel-18 | S5 | 2021-12-13 08:00 | 2023-03-03 17:00 | 100% | SP-230185 |  | ZHANG, Kai, Huawei | kai.zhangkai@huawei.com | 7/1/22: 28.907 added;; 4/6/22: 0%->40; 12/9/22: 40%->80; 11/12/22: 80%->90; 11/12/22: FCD:12/12/2022->/23; 16/3/23: WID:SP-211436->SP-230185; 17/3/23: 90%->100 | 28.907 | 94 | 48 |  |  | Mon 13/12/21 | Fri 17/03/23
1713 | 940036 | Study on new aspects of EE for 5G networks Phase 2 | FS_EE5G_Ph2 | 1 | Rel-18 | S5 | 2021-12-13 08:00 | 2023-06-06 17:00 | 100% | SP-211440 |  | Cornily Jean-Michel, Orange | jean.michel.cornily@huawei.com | 7/1/22: 28.913 added;; 4/6/22: 0%->10; 12/9/22: 10%->25; 11/12/22: 25%->50; 17/3/23: 50%->50; 8/6/23: 50%->100 | 28.913 | 94 | 48 |  |  | Mon 13/12/21 | Thu 08/06/23
1714 | 940038 | Study on Deterministic Communication Service Assurance | FS_DCSA | 1 | Rel-18 | S5 | 2021-12-13 08:00 | 2024-03-03 17:00 | 100% | SP-240269 |  | <Zhang>, <Jian>, <Huawei> | justincn.zhang@huawei.com | 7/1/22: 28.865 added;; 4/6/22: 0%->30; 12/9/22: 30%->32; 12/9/22: FCD:12/12/2023->12/22; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 32%->45; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 45%->60; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 60%->; 8/12/23: 60%->92; 14/3/... | 28.865 | 94 | 48 |  |  | Mon 13/12/21 | Tue 02/04/24
1715 | 940041 | Study on evaluation of autonomous network levels | FS_ANLEVA | 1 | Rel-18 | S5 | 2021-12-13 08:00 | 2024-03-03 17:00 | 100% | SP-211445 |  | Cao Xi, China Mobile | caoxi@chinamobile.com | 7/1/22: 28.909 added;; 4/6/22: 0%->10; 11/12/22: 10%->10; 8/6/23: 10%->60; 8/6/23: FCD:10/03/2023->12/24; 7/9/23: 60%->70; 7/9/23: FCD:12/12/2024->/24; 8/12/23: 70%->80; 14/3/24: 80%->100 | 28.909 | 94 | 48 |  |  | Mon 13/12/21 | Thu 14/03/24
1716 | 940042 | Study on enhancement of autonomous network levels | FS_eANL | 1 | Rel-18 | S5 | 2021-12-13 08:00 | 2023-12-12 17:00 | 100% | SP-211446 |  | Cao Xi, China Mobile | caoxi@chinamobile.com | 7/1/22: 28.910 added;; 4/6/22: 0%->25; 12/9/22: 25%->30; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 30%->30; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 30%->75; 8/6/23: FCD:03/03/2023->12/23; 7/9/23: 75%->85; 8/12/23: 85%->100 | 28.910 | 94 | 48 |  |  | Mon 13/12/21 | Fri 08/12/23
1717 | 940046 | Study on enhanced intent driven management services for mobile networks | FS_eIDMS_MN | 1 | Rel-18 | S5 | 2021-12-13 08:00 | 2023-06-06 17:00 | 100% | SP-211450 |  | Xu Ruiyue, Huawei | Xuruiyue@huawei.com | 7/1/22: 28.912 added;; 4/6/22: 0%->40; 12/9/22: 40%->80; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 80%->90; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 90%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 90%->100 | 28.912 | 94 | 48 |  |  | Mon 13/12/21 | Thu 08/06/23
1718 | 950027 | Study on Basic SBMA enabler enhancements | FS_eSBMAe | 1 | Rel-18 | S5 | 2022-03-10 08:00 | 2023-06-06 17:00 | 100% | SP-230774 |  | Pollakowski, Olaf, Nokia | olaf.pollakowski@nokia.com | 5/4/22: 28.831 added;; 4/6/22: 0%->10; 12/9/22: 10%->25; 11/12/22: 25%->35; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 35%->70; 8/6/23: 70%->100; 30/6/23: WID:SP-220145->SP-230774 | 28.831 | 95 | 48 |  |  | Thu 10/03/22 | Fri 30/06/23
1719 | 950029 | Study on alignment with ETSI MEC for Edge computing management | FS_MEC_ECM | 1 | Rel-18 | S5 | 2022-03-10 08:00 | 2023-06-06 17:00 | 100% | SP-220147 |  | Shitao Li, Huawei | lishitao<at>huawei<dot>com | 5/4/22: 28.903 added;; 4/6/22: 0%->15; 12/9/22: 15%->50; 12/9/22: FCD:12/09/2022->03/23; 17/3/23: 50%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100 | 28.903 | 95 | 48 |  |  | Thu 10/03/22 | Thu 08/06/23
1720 | 950030 | Study on Management Aspect of 5GLAN | FS_5GLAN_Mgt | 1 | Rel-18 | S5 | 2022-03-10 08:00 | 2023-03-03 17:00 | 100% | SP-220324 |  | Xiaowen Sun, CMCC | sunxiaowen@chinamobile.com | 5/4/22: 28.833 added;; 4/6/22: 0%->25; 12/9/22: 25%->65; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 65%->98; 17/3/23: 98%->100; 8/6/23: 100%-> | 28.833 | 95 | 48 |  |  | Thu 10/03/22 | Thu 08/06/23
1721 | 990027 | Management Aspect of 5GLAN | 5GLAN_Mgt | 1 | Rel-18 | S5 | 2023-03-16 08:00 | 2023-12-12 17:00 | 100% | SP-230175 |  | Yushuang Hu, CMCC, | huyushuang@chinamobile.com | ; 8/6/23: 0%->45; 7/9/23: 45%->90; 8/12/23: 90%->100 | 28.541; 28.552; 28.554 | 99 | 50 |  |  | Thu 16/03/23 | Fri 08/12/23
1722 | 950032 | Study on Management of Cloud Native Virtualized Network Functions | FS_MCVNF | 1 | Rel-18 | S5 | 2022-03-10 08:00 | 2023-06-06 17:00 | 100% | SP-220150 |  | China Mobile Guangjing Cao | caoguangjing@chinamobile.com | 5/4/22: 28.834 added;; 4/6/22: 0%->5; 12/9/22: 5%->30; 11/12/22: 30%->70; 17/3/23: 70%->95; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100; 4/1/24: 28.869 added; | 28.834; 28.869 | 95 | 48 |  |  | Thu 10/03/22 | Thu 04/01/24
1723 | 950033 | Study on Management Aspects of 5G MOCN Network Sharing Phase2 | FS_MANS_ph2 | 1 | Rel-18 | S5 | 2022-03-10 08:00 | 2023-06-06 17:00 | 100% | SP-220151 |  | Zhaoning Wang, ChinaUnicom | wangzn18@chinaunicom.cn | 5/4/22: 28.835 added;; 4/6/22: 0%->30; 12/9/22: 30%->75; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 75%->90; 17/3/23: 90%->94; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 94%->100; 4/1/24: 28.878 added; | 28.835; 28.878 | 95 | 48 |  |  | Thu 10/03/22 | Thu 04/01/24
1724 | 1000012 | Management Aspects of 5G Network Sharing Phase2 | MANS_ph2 | 1 | Rel-18 | S5 | 2023-06-08 08:00 | 2024-03-03 17:00 | 100% | SP-230629 |  | Wang Zhaoning, China Unicom, | wangzn18@chinaunicom.cn, | ; 7/9/23: 0%->30; 8/12/23: 30%->60; 14/3/24: 60%->100 | 32.130; 28.541; 28.552 | 100 | 51 |  |  | Thu 08/06/23 | Thu 14/03/24
1725 | 950034 | Study on Management of Trace/MDT phase 2 | FS_5GMDT_Ph2 | 1 | Rel-18 | S5 | 2022-03-10 08:00 | 2023-06-06 17:00 | 100% | SP-230773 |  | Sivaramaskrishnan Swaminathan, Nokia | sivaramakrishnan.swaminathan@nokia.com | 5/4/22: 28.837 added;; 4/6/22: 0%->15; 12/9/22: 15%->25; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 25%->35; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 35%->60; 8/6/23: 60%->100; 30/6/23: WID:SP-220152->SP-230773 | 28.837 | 95 | 48 |  |  | Thu 10/03/22 | Fri 30/06/23
1726 | 950035 | Study on Fault Supervision Evolution | FS_FSEV | 1 | Rel-18 | S5 | 2022-03-10 08:00 | 2024-03-03 17:00 | 100% | SP-220153 |  | Deng LingLi (China Mobile) |  | 5/4/22: 28.830 added;; 4/6/22: 0%->10; 12/9/22: 10%->20; 8/6/23: 20%->; 8/6/23: 20%->30; 8/6/23: FCD:03/03/2023->/24; 7/9/23: 30%->40; 8/12/23: 40%->65; 14/3/24: 65%->100 | 28.830 | 95 | 48 |  |  | Thu 10/03/22 | Thu 14/03/24
1727 | 960024 | Study on measurement data collection to support RAN intelligence | FS_MEDACO_RAN | 1 | Rel-18 | S5 | 2022-06-02 08:00 | 2022-12-12 17:00 | 100% | SP-220488 |  | Chou, Joey, Intel | joey<dot>chou<at>intel<dot>com | 12/9/22: 0%->10; 11/12/22: 10%->100; 8/6/23: 100%-> |  | 96 | 49 |  |  | Thu 02/06/22 | Thu 08/06/23
1728 | 920020 | Study on Nchf charging services phase 2 | FS_NCHF_Ph2 | 1 | Rel-18 | S5 | 2021-06-11 08:00 | 2023-12-12 17:00 | 100% | SP-210390 |  | Tornkvist, Robert, Ericsson AB | robert(dot)tornkvist(at)Ericsson(dot)com | 12/3/22: 0%->40; 4/6/22: 40%->60; 4/6/22: FCD:11/03/2022->03/23; 21/6/22: 60%->100. 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->70; 11/12/22: 70%->94; 11/12/22: 94%->75; 17/3/23: 75%->98; 17/3/23: 98%->88; 8/6/23... |  | 92 | 47 |  |  | Fri 11/06/21 | Fri 08/12/23
1729 | 990029 | CHF Distributed Availability | DIST_CH | 1 | Rel-18 | S5 | 2023-03-16 08:00 | 2023-09-09 17:00 | 100% | SP-230179 |  | João Rodrigues, Nokia | joao.a.rodrigues@nokia.com | ; 8/12/23: 0%->100 | 32.240; 32.290 | 99 | 50 |  |  | Thu 16/03/23 | Fri 08/12/23
1730 | 920021 | Study on 5G roaming charging architecture for wholesale and retail scenarios | FS_CHROAM | 1 | Rel-18 | S5 | 2021-06-11 08:00 | 2023-09-09 17:00 | 100% | SP-210391 |  | Tornkvist, Robert, Ericsson AB | robert(dot)tornkvist(at)Ericsson(dot)com | 13/9/21: 0%->10; 12/3/22: 10%->50; 4/6/22: 50%->100; 4/6/22: FCD:11/03/2022->03/23; 4/6/22: 100%->75; 4/6/22: 0%->75; 21/6/22: 75%->100 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->85; 11/12/22: 85%->90; 17/3/23: ... |  | 92 | 47 |  |  | Fri 11/06/21 | Thu 07/09/23
1731 | 1010017 | Charging for roaming and additional actor using CHF to CHF interface | CHRACHF | 1 | Rel-18 | S5 | 2023-09-06 08:00 | 2024-03-03 17:00 | 100% | SP-231153 |  | Törnkvist, Robert, Ericsson AB | robert(dot)tornkvist(at)Ericsson(dot)com | ; 8/12/23: 0%->40; 14/3/24: 40%->100 | 32.240; 32.255; 32.256; 32.290; 32.291; 32.298 | 101 | 51 |  |  | Wed 06/09/23 | Thu 14/03/24
1732 | 970030 | Methodology for deprecation | OAM_MetDep | 1 | Rel-18 | S5 | 2022-09-12 08:00 | 2023-03-10 17:00 | 100% | SP-220843 |  | Lengyel, Balázs, Ericsson | balazs.lengyel@ericsson.com | ; 11/12/22: 0%->95; 17/3/23: 95%->100 | 32.156; 32.160 | 97 | 49 |  |  | Sun 11/09/22 | Fri 17/03/23
1733 | 970029 | Study on Data management phase 2 | FS_MADCOL_ph2 | 1 | Rel-18 | S5 | 2022-09-12 08:00 | 2024-03-03 17:00 | 100% | SP-220842 |  | Pollakowski, Olaf, Nokia | olaf.pollakowski@nokia.com | ; 23/9/22: 28.842 added;; 11/12/22: 0%->5; 11/12/22: FCD:12/06/2023->/23; 17/3/23: 5%->10; 8/6/23: 10%->25; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 25%->45; 8/12/23: 45%->80; 4/1/24: 28.873 added;; 14/3/24: 80%->100 | ; 28.842; 28.873 | 97 | 49 |  |  | Sun 11/09/22 | Thu 14/03/24
1734 | 970032 | Study on Time Sensitive Networking (TSN) Charging | FS_TSNCH | 1 | Rel-18 | S5 | 2022-09-12 08:00 | 2023-12-12 17:00 | 100% | SP-220979 |  | CHEN SHAN, Huawei | chenshan@huawei.com | 23/9/22: 28.839 added;; 11/12/22: 0%->10; 17/3/23: 10%->25; 8/6/23: 25%->70; 8/6/23: FCD:06/06/2023->12/23; 7/9/23: 70%->100 | 28.839 | 97 | 49 |  |  | Sun 11/09/22 | Thu 07/09/23
1735 | 1010014 | Charging Aspects of TSN | TSN_CH | 1 | Rel-18 | S5 | 2023-09-06 08:00 | 2024-03-03 17:00 | 100% | SP-240268 |  | Deng, Yimeng, Huawei, | dengyimeng at huawei dot com | ; 21/9/23: 32.282 added;; 8/12/23: 0%->60; 14/3/24: 60%->100; 2/4/24: WID:SP-231151->SP-240268 | 32.240; 32.254; 32.255; 32.291; 32.298; 32.297 ; 32.282 | 101 | 51 |  |  | Wed 06/09/23 | Tue 02/04/24
1736 | 990032 | Charging Aspects for NSSAA | NSSAA_CH | 1 | Rel-18 | S5 | 2023-03-16 08:00 | 2024-03-03 17:00 | 100% | SP-230182 |  | Gerald Görmer, MATRIXX Software | Gerald dot Goermer at Matrixx dot com | ; 31/3/23: 28.204 added;; 8/6/23: 0%->10; 7/9/23: 10%->40; 8/12/23: 40%->80; 14/3/24: 80%->100 | 32.240; 32.290; 32.291; 32.298; 32.297 ; 28.204 | 99 | 50 |  |  | Thu 16/03/23 | Thu 14/03/24
1737 | 990033 | Management Aspects of NTN | OAM_NTN | 1 | Rel-18 | S5 | 2023-03-16 08:00 | 2023-12-12 17:00 | 100% | SP-230183 |  | Sun Mingrui, China Unicom | sunmr19@chinaunicom.cn | ; 7/9/23: 0%->30; 8/12/23: 30%->100 | 28.541; 28.552; 28.554; 28.658 | 99 | 50 |  |  | Thu 16/03/23 | Fri 08/12/23
1738 | 990034 | Management of non-public networks phase 2 | OAM_NPN_Ph2 | 1 | Rel-18 | S5 | 2023-03-16 08:00 | 2024-03-03 17:00 | 100% | SP-230184 |  | ZHANG, Kai, Huawei | kai.zhangkai@huawei.com | ; 8/6/23: 0%->10; 7/9/23: 10%->40; 8/12/23: 40%->65; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 65%->100 | 28.557; 28.541; 28.531; 28.533; 28.552 | 99 | 50 |  |  | Thu 16/03/23 | Thu 14/03/24
1739 | 0 | Rel-18 service-based aspects | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1740 | 920022 | Study on Standardising Automated Certificate Management in SBA | FS_ACM_SBA | 1 | Rel-18 | S3 | 2021-06-11 08:00 | 2023-03-03 17:00 | 100% | SP-220325 |  | BT, Niraj Rathod | Niraj.rathod@bt.com | Was previously listed under Rel-18 but according to SA#92 report, it is Rel-17; 1/10/21: 33.876 added;; 10/3/22: WID:SP-210419->SP-220195. Rel-17->Rel-18; 12/3/22: 0%->5; 12/3/22: FCD:10/06/2022->9/22; 4/6/22: 5%->35; 12/9/22: 35%->60; 17/3/23: 60%->90... | 33.876 | 92 | 47 |  |  | Fri 11/06/21 | Thu 08/06/23
1741 | 990037 | Automated certificate management in SBA | ACM_SBA | 1 | Rel-18 | S3 | 2023-03-16 08:00 | 2023-09-09 17:00 | 100% | SP-230768 |  | Peinado, German, Nokia | german.peinado@nokia.com | ; 8/6/23: 0%->35; 30/6/23: WID:SP-230150->SP-230768; 7/9/23: 35%->100 | 33.310 | 99 | 50 |  |  | Thu 16/03/23 | Thu 07/09/23
1742 | 980022 | Security Aspects of the 5G Service Based Architecture Phase 2 | 5G_eSBA_Ph2 | 1 | Rel-18 | S3 | 2022-12-09 08:00 | 2023-03-03 17:00 | 100% | SP-221145 |  | Anja Jerichow, Nokia | anja.jerichow@nokia.com | ; 8/6/23: 0%->95; 15/3/24: 95%->100 | 33.501 | 98 | 50 |  |  | Fri 09/12/22 | Fri 15/03/24
1743 | 960052 | Service Based Interface Protocol Improvements Release 18 | SBIProtoc18 | 1 | Rel-18 |  | 2022-06-03 08:00 | 2023-12-12 17:00 | 100% | CP-221083 |  | Wang Rong, China Mobile, wangrongyjy@chinamobile.com |  |  | 29.507; 29.508; 29.512; 29.514; 29.517; 29.519; 29.520; 29.521; 29.523; 29.525; 29.534; 29.535; 29.537; 29.551; 29.554; 29.557; 29.565; 29.574; 29.575; 29.576; 29.580; 29.591; 29.594; 29.675 | 96 | 49 |  |  | Fri 03/06/22 | NA
1744 | 960001 | CT4 aspects of SBIProtoc18 | SBIProtoc18 | 2 | Rel-18 | C4 | 2022-06-03 08:00 | 2023-12-12 17:00 | 100% | CP-221083 |  | Wang Rong, China Mobile, wangrongyjy@chinamobile.com |  | ; 6/6/23: Compl:25%->50% | 29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.515; 29.518; 29.524; 29.531; 29.532; 29.536; 29.540; 29.541; 29.542; 29.544; 29.550; 29.555; 29.556; 29.559; 29.562; 29.563; 29.564; 29.571; 29.572; 29.573; 29.577; 29.578; 29.579; | 96 | 49 |  |  | Fri 03/06/22 | Tue 06/06/23
1745 | 960060 | CT3 aspects of SBIProtoc18 | SBIProtoc18 | 2 | Rel-18 | C3 | 2022-06-03 08:00 | 2023-12-12 17:00 | 100% | CP-221083 |  | Wang Rong, China Mobile, wangrongyjy@chinamobile.com |  | ; 9/6/23: 30%->60 | 29.507; 29.508; 29.512; 29.514; 29.517; 29.519; 29.520; 29.521; 29.523; 29.525; 29.534; 29.535; 29.537; 29.551; 29.554; 29.557; 29.565; 29.574; 29.575; 29.576; 29.580; 29.591; 29.594; 29.675 | 96 | 49 |  |  | Fri 03/06/22 | Fri 09/06/23
1746 | 960004 | Study on GBA_U Based APIs | FS_GBA_U_API | 1 | Rel-18 | C6 | 2022-06-03 08:00 | 2023-03-03 17:00 | 100% | CP-221185 |  | Huo Weijing, China Mobile | huoweijing@chinamobile.com | 13/7/22: 31.822 added | 31.121 ; 31.822 | 96 | 49 |  |  | Fri 03/06/22 | Wed 13/07/22
1747 | 1000003 | GBA_U Based APIs | GBA_U_APIs | 1 | Rel-18 | C6 | 2023-06-07 08:00 | 2024-03-03 17:00 | 100% | CP-231353 |  | Huo Weijing(China Mobile) | huoweijing@chinamobile.com | ; 30/6/23: 31.122 added; | 31.102; 31.130; 31.116 ; 31.122 | 100 | 51 |  |  | Wed 07/06/23 | Fri 30/06/23
1748 | 800045 | Study on IETF QUIC Transport for Service Based Interfaces | FS_QUIC | 1 | Rel-18 | C4 | 2023-12-12 17:00 | 2023-12-12 17:00 | 100% | CP-183245 |  | Qi Caixia, Huawei | caixia.qi@huawei.com | 6/8/18: 29.893 added;¦10/9/18: 0%->40¦10/12/18: FCD:03/19->06/19¦10/12/18: WID:CP-181194->CP-183245¦14/3/19: 50%->75; 31/5/19: 75%->80. 02/07/20: moved Rel-16->Rel-17; 13/9/20: FCD:12/06/2019->09/21; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22:rel-17->18 | New; 29.893 | 80 | 41 |  |  | Wed 06/06/18 | Mon 13/09/21
1749 | 0 | Rel-18 other aspects | - | 1 | Rel-18 |  | 2016-03-15 08:00 | 2016-03-15 08:00 | 100% | - | - | - | - | - | - |  |  |  |  | Fri 29/08/14 | Fri 29/08/14
1750 | 920042 | (Small) Technical Enhancements and Improvements for Rel-18 | TEI18 | 1 | Rel-18 |  | 2021-03-12 08:00 | 2022-07-24 10:00 | 0% | [6 empty] | 92 | 47 |  |  | Mon 15/06/15 | Mon 15/06/15
1751 | 920003 | Lawful Interception Rel-18 | LI18 | 1 | Rel-18 | S3LI | 2021-03-12 08:00 | 2022-12-02 14:00 | 96% | SP-230241 |  | Koen Jaspers, PIDS | kbj@xs4all.nl | 10/9/21: WID:SP-210300->SP-210830; 4/6/22: 0%->5; 12/9/22: 5%->15; 11/12/22: 15%->20; 16/3/23: FCD:03/03/2023->/2023; 16/3/23: WID:SP-210830->SP-230241. Rapporteur changed from Alex Leadbeater; 31/3/23: 33.928 added;; 5/9/24: 20%->90; 5/12/24: 90%->96 | 33.128;33.127;33.126;33.108;33.107 ; 33.928 | 92 | 47 |  |  | Fri 11/06/21 | Thu 05/12/24
1752 | 959999 | Limbo: code to be used for not-approved CRs related to never-approved WIDs | Limbo | 1 | - |  | 2019-03-07 08:00 | 2019-03-07 17:00 | 0% | - | - | - | - | "Dummy" is a temporary code for CRs related to not-yet-approved WIDs. If a WID ended up not being approved at pleanry, then all related CRs have to be changed from "Dummy" to "Limbo" |  | 95 | 48 |  |  | Sun 13/03/22 | NA
1753 | 999999 | Test - (Small) Technical Enhancements and Improvements for Rel-18 | TEI18_Test | 1 | Rel-18 | R5 | 2022-01-05 08:00 | 2023-03-16 17:00 | 100% |  |  |  |  | 8/6/23: 0%->100 |  | 99 | 50 |  |  | Thu 08/06/23 | Thu 08/06/23
1754 | 1040002 | Update of conformance test specifications to Rel-18 | UEConTest_R18 | 1 | Rel-18 | C6 | 2023-06-29 08:00 | 2025-06-06 17:00 | 100% | CP-241022 |  | Arne Marquordt, COMPRION GmbH | amarquordt@comprion.com |  |  | 92 | 47 |  |  | Thu 12/08/21 | NA