## Slide 1: FS_PIN Status Update Study on Personal IoT Networks
Adrian Buckley
vivo Mobile Communications Co Ltd
FS_PIN Rapporteur
3GPP TSG-SA WG1 Meeting #91e
Electronic Meeting, 24 August - 2 September 2020
Notes: 1

## Slide 2: FS_PIN Progress
Progress made at this meeting
  TR Skeleton
  TR Scope
  5 use cases approved
  .
Work/Study Item Completion: 15%
Controversial issues
  None identified
Notes: 1

## Slide 3: FS_PIN Planning
Planning for subsequent meetings
  SA1#92e (11/2020): 40%
    Use cases e.g. tour guide etc.
      New ones, updating existing, resubmissions
  SA1#92ebis (01/2021): 70%
    Additional use cases
    Requirements / KPI consolidation
  SA1#93e (03/2021): 100%
    Requirements / KPI consolidation
    Conclusions
    Draft WID
Notes: 1

## Slide 4: Work plan between meetings
Email discussion
  Overview
  New use cases and enhancements (requirements extraction etc) to existing use cases.
  Definition and alignment of terms
Telephone conference
  As needed end Sep / start Oct
    1-7th October Chinese golden week
Notes: 1

## Slide 5: FS_PIN Completion Date
Current expected completion dates:
  For information: SA#91 (03/2020)
  For approval: SA#91 (03/2021)
Have these dates been changed at this meeting? y
  If yes, previous target completion dates:
    For information: 12/2020 SA#90
    For approval: 03/2021 SA#91
Notes: 1

## Slide 6: FS_PIN History
This WI has been agreed at SA1#90e / SA#88
  Agreed WID is in tdoc S1-202287 / SP-200592
History of completion rates
  SA1#91e (08/2020): 15%
Notes: 1