## Slide 1: FS_AMMT Status Update Study on AI/ML Model Transfer in 5GS
Jia SHEN
OPPO
FS_AMMT Rapporteur
3GPP TSG-SA WG1 Meeting #92e
Electronic Meeting, 10-19 November 2020
Notes: 1

## Slide 2: FS_AMMT Progress
Progress made at this meeting
  9 use cases were updated:
    Split AI/ML image recognition
    Enhanced media recognition: Deep Learning Based Vision Applications
    Media quality enhancement: Video streaming upgrade
    Split control for robotics
    Session-specific model transfer split computation operations
    AI/ML model distribution for image recognition
    AI/ML model distribution for speech recognition
    Real time media editing with on-board AI inference
    Data Transfer Disturbance in Multi-agent multi-device ML Operations
  2 new use cases were added (13 use cases in all):
    AI Model Management as a Service
    Flocking Use Case
Work/Study Item Completion: 80%
Controversial issues
  None
Notes: 1

## Slide 3: FS_AMMT Planning
Planning for subsequent meetings
  SA1#93e (2021‑02‑23): <100%>
    Complete all use cases and KPI requirements
    Consolidate potential requirements
    Conclusions
Notes: 1

## Slide 4: Work plan between meetings
Email discussion
  Will be arranged if necessary.
Telephone conference
  Remaining issues (especially the performance requirements) of the use cases
  In Feb. 2021
Notes: 1

## Slide 5: <WI Code> Completion Date
Current expected completion dates:
  For approval: SA#91e (03/2021)
Have these dates been changed at this meeting? <n>
Notes: 1

## Slide 6: AMMT_FS History
This WI has been approved at SA1#88 / SA>#nn>
  <Agreed/Approved> WID is in tdoc <S1-193606 / SP-191040>
History of completion rates
  SA1#88 (2019-11-18): 0%
  SA1#91 (2020-9-2): 40%
Notes: 1