## Slide 1: 5TRS Status Update 5G Timing Resiliency System
Betsy Covell
Nokia
5TRS Rapporteur
3GPP TSG-SA WG1 Meeting #93e
Electronic Meeting, 22 February – 4 March 2021
Notes: 1

## Slide 2: 5TRS Progress
Progress made at this meeting
  CR adding requirements and KPIs to 22.261
  CR adding reference text to 22.104
Work/Study Item Completion: 100%
Controversial issues
  none
Notes: 1

## Slide 3: 5TRS Completion Date
Current expected completion dates:
  For approval: SA#92e (06/2021)
Have these dates been changed at this meeting? n
Notes: 1

## Slide 4: 5TRS History
This WI has been revised at SA1#94e
History of completion rates
  SA1#93e (03/2021): 0%
  SA1#94e (05/2021): 100%
Notes: 1