## Sheet1
SA WG2 Meeting #127-bis
May 28 - June 1, Newport Beach, USA | [13 empty] | S2-185414
Source: SA WG2 Chairman
Title: SA2 Work Planning Worksheet
Document for: Endorsement
Agenda Item: 7.2
Work Item / Release: All / Rel-15 and later
Abstract of the contribution: A revision of this document will capture agreements during work planning as SA2 preparations for TSG SA and/or for future SA2 meetings.
1. Introduction
This paper provides the overview of the work item status at the time of the work planning session.
The budget figures show the estimates for the expected work or show the status reached so far.
Any shown budget figures may require further consolidation.
[10 empty] | Jun 17 |  | Aug 17 |  | Okt 17 |  | Nov 17 |  | Jan 18 |  | Feb 18 |  | Apr 18 |  | May 18 |  | Jul 18 |  | Aug 18 |  | Oct 18 |  | Nov 18 |  | Jan 19 |  | Feb 19 |  | Apr/May
|  | Target | status estimation (%) |  |  |  | acc./plan. | planned | accumul. | SA2#122 |  | SA2#122bis |  | SA2#123 |  | SA2#124 |  | SA2#125 |  | SA2#126 |  | SA2#127 |  | SA2#127-bis |  | SA2#128 |  | SA2#128-bis |  | SA2#129 |  | SA2#129-bis |  | SA2#130 |  | SA2#130
| Work Item | date | Q1/18 | Q2/18 | Q3/18 | Q4/18 | TUs (%) | TUs | TUs | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | updated
| FS_eV2XARC | 2018-09-01 | 25 |  |  |  | 33 | 20 | 6.6 | 2 | 2.3 | 2 | 1 |  |  |  |  | 2 | 1.3 | 2 | 1 | 1 |  | 1 | 1 | 2 |  | 2 |  | 3 |  | 3 | [6 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3
| FS_ATSSS | 2018-09-17 | 20 |  |  |  | 39.3636 | 11 | 4.33 |  |  | 1 | 1.33 |  |  |  |  | 2 | 1 | 2 | 1 | 1 |  | 1 | 1 | 1 |  | 1 |  | 1 |  | 1 | [6 empty] | 2018-02-14 | 7.5.18 rapporteur confirmed
| FS_5WWC | 2018-12-17 | 25 |  |  |  | 40.2143 | 14 | 5.63 |  |  | 1 | 1.33 |  |  |  |  | 2 | 1.3 | 1 | 1 | 1 |  | 2 | 2 | 2 |  | 2 |  | 2 |  | 1 | [6 empty] | 2018-02-12 | 16.5.18 rapporteur confirmed
| FS_Parlos | 2018-06-17 | 45 |  |  |  | 57.1429 | 7 | 4 |  |  | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | [10 empty] | 2018-02-13 | 16.5.18 rapporteur asked for extending by a quarter
| FS_ENTRADE | 2018-09-01 | 20 |  |  |  | 50 | 6 | 3 | [8 empty] | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 |  | 1 | [10 empty] | 2018-02-08 | 15.5.18 rapporteur confirmed
| FS_eNA | 2018-09-01 | 15 |  |  |  | 25.3846 | 13 | 3.3 | [8 empty] | 1 | 1.3 | 2 | 1 | 1 |  | 1 | 1 | 2 |  | 2 |  | 2 |  | 2 | [6 empty] | 2018-02-12 | 7.5.18 rapporteur increased to 2-2-2-2
| FS_CIoT_5G | 2018-09-01 | 20 |  |  |  | 26.8 | 25 | 6.7 | [8 empty] | 3 | 2 | 4 | 1 | 3 |  | 3 | 3.7 | 3 |  | 3 |  | 3 |  | 3 | [6 empty] | 2018-02-16 | 9.5.18 rapporteur confirmed
| FS_ETSUN | 2018-09-01 | 25 |  |  |  | 30 | 11 | 3.3 | [8 empty] | 1 | 1 | 2 | 1 | 2 |  | 2 | 1.3 | 2 |  | 2 | [11 empty] | 9.5.18 rapporteur confirmed, potentialy needs extension
| FS_LLC_Mob | 2018-09-01 | 35 |  |  |  | 45 | 6 | 2.7 | [8 empty] | 1 | 1 | 1 | 1 | 1 |  | 1 | 0.7 | 1 |  | 1 | [10 empty] | no change | 10.5.18 rapporteur confirmed
| FS_eLCS | 2018-12-17 | 15 |  |  |  | 33 | 10 | 3.3 | [8 empty] | 1 | 1.3 | 2 | 1 | 2 |  | 1 | 1 | 1 |  | 1 |  | 1 |  | 1 | [6 empty] | 09.04.2018 rapporteur proposed some reduction | 07.05.2018 rapporteur proposed to go for 1TU/meeting
| FS_eIMS5G | 2018-09-01 | 20 |  |  |  | 33 | 10 | 3.3 | [8 empty] | 1 | 1.3 | 1 | 1 | 1 |  | 1 | 1 | 2 |  | 2 |  | 1 |  | 1 | [6 empty] | 2018-02-06 | 7.5.18 rapporteur confirmed
| INOBEAR | 2018-06-01 | 60 |  |  |  | 62.5 | 4 | 2.5 | [8 empty] | 1 | 1 | 1 | 1 | 1 |  | 1 | 0.5
| FS_5G-SRVCC | 2018-09-17 |  |  |  |  | 25 | 4 | 1 | [12 empty] | 1 |  | 1 | 1 | 1 |  | 1 | [10 empty] | 2018-02-08 | 15.5.18 rapporteur confirmed
| FS_5G_URLLC | 2018-12-17 |  |  |  |  | 10 | 10 | 1 | [12 empty] | 1 |  | 1 | 1 | 2 |  | 2 |  | 2 |  | 2 | [6 empty] | 2018-02-07
| FS_eSBA | 2018-12-17 |  |  |  |  | 9.2857 | 14 | 1.3 | [12 empty] | 1 |  | 1 | 1.3 | 3 |  | 3 |  | 3 |  | 3 | [7 empty] | 9.5.18 rapporteur +1 for July
| FS_eNS | 2018-12-17 |  |  |  |  | 16.6667 | 6 | 1 | [12 empty] | 1 |  | 1 | 1 | 1 |  | 1 |  | 1 |  | 1 | [6 empty] | 2018-02-14 | 7.5.18 rapporteur: Oct&Nov 0.5 > 1
| FS_AAI_LTE_NR | Mar 19 |  |  |  |  | 12.5 | 8 | 1 | [12 empty] | 1 |  | 1 | 1 | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  | 2018-02-13 | 16.5.18 rapporteur confirmed
| FS_EPS_URACE | 2018-12-17 |  |  |  |  | 16.6667 | 6 | 1 | [12 empty] | 1 |  | 1 | 1 | 1 |  | 1 |  | 1 |  | 1 | [7 empty] | 10.5.18 rapporteur confirmed
| [FS_5GSAT_ARCH] | Mar 19 | [23 empty] | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  | 1 |  |  |  | 9.5.18 initial estimates by rapporteur to be
| [FS_FLADN] | Mar 19 | [23 empty] | 0.5 |  | 0.5 |  | 1 |  | 1 |  | 1 | [5 empty] | 9.5.18 initial estimates by rapporteur to be
| [FS_NG_RTC] | Mar 19 | [23 empty] | 1 |  | 2 |  | 2 |  | 2 |  | 2 |  | 1 |  |  |  | 7.5.18 initial estimates by rapporteur to be
| [FS_5G_TLSA] | 2018-12-17 | [23 empty] | 1 |  | 1 |  | 1 |  | 1 | [7 empty] | 7.5.18 initial estimates by rapporteur to be
| [vertical / LAN] | 2018-12-17 | [23 empty] | 2 |  | 2 |  | 2 |  | 2 | [7 empty] | 7.5.18 initial estimates by rapporteur to be
| [FS_RACS] | 2018-09-17 | [23 empty] | 1 |  | 1 |  | 1 |  | 1 | [7 empty] | 9.5.18 initial estimates by rapporteur to be
| [DPBDT] | 2018-12-17 | [23 empty] | 0.5 |  | 0.5 |  | 0.5 |  | 0.5
| Maint 6.1 on 5GS |  | 98 |  |  |  | 57.2807 | 114 | 65.3 | [8 empty] | 25 | 24 | 25 | 25 | 14 |  | 14 | 16.3 | 10 |  | 10 |  | 8 |  | 8
| Maint 5.1 / 6.1 | [6 empty] | 30 | 24 | 3 | 4 | 3 | 3 | 3 | 4.5 | 3 | 2.5 | 3 | 3.5 | 3 | 3 | 2 |  | 2 | 3.5 | 2 |  | 2 |  | 2 |  | 2
| Maint 5.2 / 6.2 | [6 empty] | 8.25 | 2.13 | 1 | 0.5 | 1 | 0.33 | 1 | 0 | 0.25 | 0.3 | 1 | 0 | 1 | 1 | 0.5 |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5 |  | 0.5
| Maint 5.3 / 6.3 | [6 empty] | 5.25 | 2 | 1 | 0.5 | 1 |  | 1 | 0 | 0.25 |  | 1 | 0 | 1 | 1 | 0 |  | 0 | 0.5 | 0 |  | 0 |  | 0 |  | 0
| Maint 5.4 / 6.4 | [6 empty] | 8.5 | 4.15 | 1 | 1 | 1 | 0.1 | 1 | 0.25 | 0.5 | 0.3 | 1 | 1 | 1 | 1 | 0.5 |  | 0.5 | 0.5 | 0.5 |  | 0.5 |  | 0.5 |  | 0.5
| TEI 3GPP acc | [6 empty] | 2 | 1.6 |  |  |  |  | 1 | 1 | 1 | 0.6
| TEI PCC/QoS | [6 empty] | 1 | 0.8 | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.3
| TEI n3GPP | [6 empty] | 0 | 0
| TEI IMS/rel. | [6 empty] | 4 | 2 | 1.5 | 0.5 |  |  | 0.5 | 0.5 | 1 | 0.5 |  |  |  |  | 0.5 |  | 0.5 | 0.5
| sum | [8 empty] | 10 | 9.3 | 11 | 8.09 | 7.5 | 6.25 | 6.5 | 4.5 | 48 | 43 | 51 | 43 | 39.5 | 0 | 39.5 | 42.8 | 47 | 0 | 48 | 0 | 40.5 | 0 | 39.5 | 0 | 5 | 0 | 3 | 0
There should be not more than 42 planned TUs!