## Sheet1
SA WG2 Meeting #131
Feb 25 - Mar 1, 2019, Tenerife, Spain | [13 empty] | S2-1902842 rev of 1965
Source: SA WG2 Chairman
Title: SA2 Work Planning Worksheet
Document for: Endorsement
Agenda Item: 7.2
Work Item / Release: All / Rel-15 and later
Abstract of the contribution: A revision of this document will capture agreements during work planning as SA2 preparations for TSG SA and/or for future SA2 meetings.
1. Introduction
This paper provides the overview of the work item status at the time of the work planning session.
The budget figures show the estimates for the expected work or show the status reached so far.
Any shown budget figures may require further consolidation.
[10 empty] | Jun 17 |  | Aug 17 |  | Okt 17 |  | Nov 17 |  | Jan 18 |  | Feb 18 |  | Apr 18 |  | May 18 |  | Jul 18 |  | Aug 18 |  | Oct 18 |  | Nov 18 |  | Jan 19 |  | Feb 19 |  | Apr 19 |  | May 19
|  | Target | status estimation (%) |  |  |  | acc./plan. | planned | accumul. | SA2#122 |  | SA2#122bis |  | SA2#123 |  | SA2#124 |  | SA2#125 |  | SA2#126 |  | SA2#127 |  | SA2#127-bis |  | SA2#128 |  | SA2#128-bis |  | SA2#129 |  | SA2#129-bis |  | SA2#130 |  | SA2#131 |  | SA2#132 |  | SA2#133 |  | Q3/Q4
| Work Item | date | Q1/18 | Q2/18 | Q3/18 | Q4/18 | TUs (%) | TUs | TUs | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | Plan | Actl. | plan | updated |  | before SA#81 | #129bis planning input | #131 planning input
| FS_5GSAT_ARCH | Mar 19 |  |  | 15 |  | 64.2857 | 7 | 4.5 | [16 empty] | 1 | 1 | 1 | 0.7 | 1 | 0.5 | 2 | 1.3 | 1 | 1 | 1 |  | 1 |  | 1 |  | 3 |  | 28.5.18 updated by rapporteur | 23.8.18 agreed during SA2 work planning to move 1TU from Oct to Jan | 18.11. rapporteur proposes to distribute the remaining 7TUs to 1 TU per meeting until Sep 2019
| FS_5G_URLLC | 2018-12-17 |  | 15 | 60 |  | 103 | 10 | 10.3 | [12 empty] | 1 | 0.5 | 1 | 1.1 | 2 | 1.7 | 2 | 1.8 | 2 | 1.6 | 2 | 2.6 |  | 1 | [7 empty] | 2018-02-07 |  |  | 5.11. rapporteur: possibly additional study conclusions in Q1
| 5G_URLLC | 2019-06-01 |  |  |  |  | 12.5 | 8 | 1 | [24 empty] | 2 | 1 | 2 |  | 2 |  | 2 |  |  | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 5.11. rapporteur input, possibly additional study conclusions in Q1 | 11.2. rapporteur confirms 2 + 2
| FS_CIoT_5G | 2018-12-01 | 20 | 50 | 70 |  | 90 | 28 | 25.2 | [8 empty] | 3 | 2 | 4 | 1 | 3 | 3 | 3 | 3.2 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 4 | [9 empty] | 2018-02-16 | 31.5.18 rapporteur updated | 10.8.18 rapporteur increases to 2*3.5TU due to multicast aspects, asked to change to 4 in Oct and 3 in Nov during work planning
| CIOT_5G | 2019-06-01 |  |  |  |  | 29.1667 | 12 | 3.5 | [24 empty] | 3 | 3.5 | 3 |  | 3 |  | 3 |  |  | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 28.11. rapporteur input | 9.2. rapporteur confirms 3 + 3
| FS_eV2XARC | 2018-12-01 | 25 | 35 | 58 |  | 96 | 20 | 19.2 | 2 | 2.3 | 2 | 1 |  |  |  |  | 2 | 1.3 | 2 | 1 | 1 | 1.3 | 1 | 1.5 | 2 | 2 | 2 | 2.5 | 3 | 3.3 | 3 | 3 | [9 empty] | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures
| eV2XARC | 2019-06-01 |  |  |  |  | 29.1667 | 12 | 3.5 | [24 empty] | 3 | 3.5 | 3 |  | 3 |  | 3 |  |  | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 30.10. rapporteur input | 7.2. rapporteur confirms 3 + 3
| FS_eNA | 2018-12-01 | 15 | 30 | 50 |  | 102 | 15 | 15.3 | [8 empty] | 1 | 1.3 | 2 | 1 | 1 | 1.1 | 1 | 1.3 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3.6 | [9 empty] | 2018-02-12 | 7.5.18 rapporteur increased to 2-2-2-2 | 9.8.18 rapporteur confirms figures
| eNA | 2019-06-01 |  |  |  |  | 27.5 | 12 | 3.3 | [24 empty] | 3 | 3.3 | 3 |  | 3 |  | 3 |  |  | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 3.11. rapporteur input | 12.2. rapporteur confirms 3 + 3
| FS_eNS | 2018-12-17 |  | 10 | 50 |  | 110 | 9 | 9.9 | [12 empty] | 1 | 1 | 1 | 0.5 | 1 | 1 | 2 | 2.3 | 2 | 2.3 | 2 | 2.3 |  | 0.5 | [7 empty] | 2018-02-14 | 31.5.18 rapporteur update | 11.8.18 rapporteur confirms figures, asked to increase to 2TUs in Nov during work planning | 17.11. rapporteur: possibly additional study conclusions in Q1
| eNS | 2019-06-01 |  |  |  |  | 10 | 5 | 0.5 | [24 empty] | 1.5 | 0.5 | 1.5 |  | 1 |  | 1 |  |  | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 17.11. rapporteur input, includes one TUs in Q1 for additional study conclusions, if required | 7.2. rapporteur confirms 1 + 1
| FS_Vertical_LAN | 2018-12-17 |  |  | 25 |  | 113 | 10 | 11.3 | [16 empty] | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3.3 | [10 empty] | 7.5.18 initial estimates by rapporteur to be | 9.8.18 rapporteur increases Q4 to 2*3TU {1 per 5G-LAN, Type-a/b, TSN related} | 6.11. rapporteur: possibly additional study conclusions in Q1
| V_LAN | 2019-06-01 |  |  |  |  | 30 | 12 | 3.6 | [24 empty] | 3 | 3.6 | 3 |  | 3 |  | 3 |  |  | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 6.11. rapporteur input, possibly additional study conclusions in Q1 | 6.2. rapporteur confirms 3 + 3
| FS_ATSSS | 2018-12-17 | 20 | 40 | 70 |  | 99.4167 | 12 | 11.93 |  |  | 1 | 1.33 |  |  |  |  | 2 | 1 | 2 | 1 | 1 | 1.3 | 1 | 1.3 | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 2 | [9 empty] | 2018-02-14 | 7.5.18 rapporteur confirmed | 11.8.18 rapporteur confirms figures, asked to increase to 2TUs in Oct during work planning | 17.11. rapporteur: possibly additional study conclsuions in Q1
| ATSSS | 2019-06-01 |  |  |  |  | 22.2222 | 9 | 2 | [24 empty] | 2 | 2 | 2 |  | 3 |  | 2 |  |  | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 17.11. rapporteur input, includes Q1 time for additional study conslusions in Q1 | 11.2. rapporteur updates 2 + 2 to 3 + 2
| FS_eLCS | 2019-03-17 | 15 | 45 | 55 |  | 103.6364 | 11 | 11.4 | [8 empty] | 1 | 1.3 | 2 | 1 | 2 | 1.3 | 1 | 1 | 1 | 1.5 | 1 | 1.3 | 1 | 2 | 2 | 2 | [9 empty] | 09.04.2018 rapporteur proposed some reduction | 07.05.2018 rapporteur proposed to go for 1TU/meeting | 6.8.18 rapporteur increases Q4 to 2*2TU and extends to Q1
| eLCS | 2019-06-01 |  |  |  |  | 20 | 10 | 2 | [24 empty] | 2 | 2 | 3 |  | 2 |  | 3 |  |  | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 5.11. rapporteur input, budget incl. continuing also the study in 1H19 | 8.2. rapporteur confirms 2 + 3
| FS_eSBA | 2018-12-17 |  | 15 | 60 |  | 95.7143 | 14 | 13.4 | [12 empty] | 1 | 1 | 1 | 1.3 | 3 | 2.3 | 3 | 2.5 | 3 | 3 | 3 | 3.3 | [10 empty] | 9.5.18 rapporteur +1 for July | 8.8.18 rapporteur confirms figures
| eSBA | 2019-06-01 |  |  |  |  | 22.5 | 12 | 2.7 | [24 empty] | 3 | 2.7 | 3 |  | 3 |  | 3 |  |  | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 14.11. rapporteur input | 12.2. rapporteur confirms 3 + 3
| FS_5WWC | 2018-12-17 | 25 | 35 | 60 |  | 108.3125 | 16 | 17.33 |  |  | 1 | 1.33 |  |  |  |  | 2 | 1.3 | 1 | 1 | 1 | 1.3 | 2 | 2.3 | 2 | 2.3 | 2 | 2 | 2 | 2.2 | 3 | 3.6 | [9 empty] | 2018-02-12 | 16.5.18 rapporteur confirmed | 13.8.18 rapporteur increases for Nov to 2TUs anticipating more BBF interactions
| 5WWC | 2019-06-01 |  |  |  |  | 22 | 10 | 2.2 | [24 empty] | 2 | 2.2 | 3 |  | 2 |  | 3 |  |  | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 14.11. rapporteur input | 8.2. rapporteur confirms 2 + 3
| FS_ETSUN | 2018-12-01 | 25 | 40 | 66 |  | 63.9706 | 13.6 | 8.7 | [8 empty] | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 0.5 | 2 | 1.3 | 2 | 1.3 | 1.3 | 1.3 | 1.3 | 1.3 | [10 empty] | 31.5.18 rapporteur extends | 8.8.18 rapporteur proposes to extend until Dec
| ETSUN | 2019-06-01 |  |  |  |  | 22.2222 | 4.5 | 1 | [24 empty] | 1 | 1 | 1 |  | 1.5 |  | 1 |  |  | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 12.11. rapporteur input | 11.2. rapporteur updates 2 + 1 to 1.5 + 1
| FS_eIMS5G | 2019-06-01 | 20 | 40 | 40 |  | 110 | 6 | 6.6 | [8 empty] | 1 | 1.3 | 1 | 1 | 1 | 1.3 | 1 | 1 | [2] |  | [2] |  |  |  | [1] |  | 2 | 2 | 0 | [6 empty] | 2018-02-06 | 7.5.18 rapporteur confirmed | 9.8.18 rapporteur considers to un-pause in Nov | 29.10. rapporteur input, striving for normative results in Q2 as considered with the earlier updated SID and WF in S2-188023
| eIMS5G | 2019-06-01 |  |  |  |  | 0 | 3 | 0 | [28 empty] | 1.5 |  | 1.5 |  |  | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 12.11. rapporteur input | 6.2. rapporteur updates 2 + 1 to 1.5 + 1.5 for a normative WI
| FS_RACS | 2018-12-17 |  |  | 40 |  | 107.1429 | 7 | 7.5 | [16 empty] | 1 | 1 | 1 | 1.2 | 2 | 2 | 1 | 1.3 | 1 | 2 | 1 | [7 empty] | 9.5.18 initial estimates by rapporteur to be | 9.8.18 rapporteur confirms figures, increases to 2TUs in Oct during work planning | 13.11. rapporteur input
| RACS | 2019-06-01 |  |  |  |  | 0 | 2 | 0 | [28 empty] | 1 |  | 1 |  |  | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 13.11. rapporteur input | 12.2. rapporteur confirms 1 + 1
| FS_5G-SRVCC | 2018-09-17 |  | 80 | 100 |  | 107.5 | 4 | 4.3 | [12 empty] | 1 | 1 | 1 | 1 | 1 | 1.3 | 1 | 1 | [13 empty] | 2018-02-08 | 15.5.18 rapporteur confirmed | 10.8.18 rapporteur adds 0.5TU in Q4 assuming RAN dependencies may delay, work planning remobved it, assume it may be scheduled without reserving
| 5G-SRVCC | Mar 19 |  |  |  |  | 70 | 1 | 0.7 | [20 empty] | [1] |  | [1] |  | 0.5 | 0.7 | 0.5 | [8 empty] | 10.8.18 rapporteur adds 2*1TU in Q4 proposing normative work | 5.11. rapporteur input, 1 TU in Jan or Feb | 11.2. rapporteur confirms
| FS_LLC_Mob | 2018-09-01 | 35 | 75 | 75 |  | 80 | 4 | 3.2 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 0.7 | 1 | 0.5 | [1] |  | [1] |  | [0.5] |  | [0.5] | [10 empty] | no change | 10.5.18 rapporteur confirmed | 13.8.18 rapporteur considers to un-pause in Q4 for some conclusions
| FS_FLADN | Mar 19 |  |  |  |  | #DIV/0! | 0 | 0 | [16 empty] | [0.5] |  | [0.5] |  | [0.5] |  | [0.5] |  | [0,5] |  | [0,5] | [7 empty] | 9.5.18 initial estimates by rapporteur to be | 7.8.18 rapporteur shifts budget by a quarter | 30.10. rapporteur input, all on study | 7.2. rapporteur confirms 1 + 1
| FS_EPS_URACE | 2018-12-17 |  | 10 | 10 |  | 25 | 2 | 0.5 | [12 empty] | 1 | 0.3 | 1 | 0.2 | [1] |  | [1] |  | [1] |  | [1] | [11 empty] | 10.5.18 rapporteur confirmed | 13.8.18 rapporteur considers to un-pause in Q4
| xBDT | 2018-12-17 |  |  |  |  | #DIV/0! | 0 | 0 | [16 empty] | [0.5] |  | [0.5] |  | [0.5] |  | [0.5] |  | [0,5] |  | [0,5] |  | 0.5 |  | 0.3 |  |  |  |  | 10.8.18 rapporteur shifts budget by a quarter | 3.11. rapporteur input | 6.2. rapporteur requests 0.5 + 0.3
| FS_Parlos | 2018-09-17 | 45 | 70 | 100 |  | 107.1429 | 7 | 7.5 |  |  | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.3 | 1 | 1.2 | [13 empty] | 2018-02-13 | 16.5.18 rapporteur asked for extending by a quarter
| Parlos | Mar 19 |  |  |  |  | 40 | 2.5 | 1 | [20 empty] | [1] |  | [1] |  | 1 | 1 | 1 |  | 0.5 | [7 empty] | 7.11. rapporteur input | 7.2. rapporteur updates 1 + 1 to 0.5 + 0
| FS_ENTRADE | 2018-09-01 | 20 | 70 | 70 |  | 100 | 4 | 4 | [8 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [1] |  | [1] | [5 empty] | [0,5] |  | [0,5] | [6 empty] | 2018-02-08 | 15.5.18 rapporteur confirmed | 10.8.18 rapporteur assumes will be considered for Q1 | 5.11. rapporteur: 1 TU in Jan or Feb concluding the TR and 1 TU in Apr or May for normative | 11.2. rapporteur confirms
| FS_AAI_LTE_NR | Mar 19 |  | 30 | 30 |  | 100 | 2 | 2 | [12 empty] | 1 | 1 | 1 | 1 | [1] |  | [1] |  | [1] |  | [1] |  | [2] |  | [2] | [6 empty] | 2018-02-13 | 16.5.18 rapporteur confirmed | 7.8.18 rapporteur confirms remaining budget | 7.11. rapporteur input, normative work in Q2 | 18.2. rapporteur confirms 1 + 1
| FS_NG_RTC | Mar 19 |  |  |  |  | #DIV/0! | 0 | 0 | [16 empty] | [1] |  | [2] |  |  |  | [1] |  | [1] |  | [1] | [7 empty] | 7.5.18 initial estimates by rapporteur to be | 13.8.18 rapporteur considers to un-pause in Q4; reducing earlier requested budget | 5.11. rapporteur input, 3 meetings SI and 1 on WI
| FS_UDICoM | 2018-12-17 |  |  | 30 |  | 74.2857 | 7 | 5.2 | [16 empty] | 1 | 0.7 | 0.5 | 0.8 | 1.5 | 1 | 1 | 1.3 | 1.5 | 1.4 | 1.5 | [8 empty] | 8.8.18 rapporteur provides intial figures | 28.11. Rapporteur: conclude in Jan and do related normative work in Feb
| UDICoM | 2019-06-01 |  |  |  |  | 0 | 0.5 | 0 | [28 empty] | 0.5 |  |  |  |  | 2018-02-05 | 7.5.18 rapporteur increased to 2-2-3-3 | 7.8.18 rapporteur confirms figures | 28.11. Rapporteur: conclude in Jan and do related normative work in Feb | 15.2. rapporteur requests 0.5 + 0, which depends also on study conclusions
| FS_ID_UAS-SA2 | 2020-03-01 |  |  |  |  | #DIV/0! | 0 | 0 | [32 empty] | 2 |  | 7.5.18 initial estimates by rapporteur to be | 13.8.18 rapporteur considers to un-pause in Q4; reducing earlier requested budget | 28.11. rapporteur input: no work in Q1 | 7.2. rapporteur requests 2 + 2 + 2
| FS_Multi SIM | 2020-03-01 | [44 empty] | 11.2. rapporteur requests 1 + 1.5
| Maint 6.1 on 5GS |  | 98 | 100 |  |  | 109.5652 | 138 | 151.2 | [8 empty] | 25 | 24 | 25 | 25 | 14 | 19 | 14 | 19 | 12 | 15 | 12 | 15 | 10 | 13.7 | 10 | 11.5 | 8 | 9 | 8 |  | 6 |  | 6
| Maint 5.1 / 6.1 | [6 empty] | 32 | 33.5 | 3 | 4 | 3 | 3 | 3 | 4.5 | 3 | 2.5 | 3 | 3.5 | 3 | 3 | 2 | 3 | 2 | 3.5 | 2 | 1.5 | 2 | 1 | 2 | 2 | 2 | 1.3 | 1 | 0.7 | 1 |  | 1 |  | 1
| Maint 5.2 / 6.2 | [6 empty] | 8.25 | 2.88 | 1 | 0.5 | 1 | 0.33 | 1 | 0 | 0.25 | 0.3 | 1 | 0 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.25 | 0.5 |  | 0.5 |  | 0.5 |  | 0.5
| Maint 5.3 / 6.3 | [6 empty] | 5.25 | 1.5 | 1 | 0.5 | 1 |  | 1 | 0 | 0.25 |  | 1 | 0 | 1 | 1 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| Maint 5.4 / 6.4 | [6 empty] | 8.5 | 6.15 | 1 | 1 | 1 | 0.1 | 1 | 0.25 | 0.5 | 0.3 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.4 | 0.5 |  | 0.5 | 0.2 | 0.5 | 1 | 0.5 | 0.2 |  | 0.2
| TEI16 EPS RFSPext | [6 empty] | 1.5 | 0.8 | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.3 | [16 empty] | [0,5] |  | 0.5 | [9 empty] | 28.11. proponents: 0.5TU in Q?
| TEI16 EPS EtherType | [6 empty] | 0.5 | 0 | [24 empty] | [1] |  | 0.5 |  | 0.5 | [7 empty] | 28.11. proponents: 1TU in Q1
| TEI16 slice based overload control | [36 empty] | 1
| TEI16 Monitoring Event Config | [36 empty] | 1
| TEI16 PCF selection | [36 empty] | 1
| TEI16 on EATF | [38 empty] | 0.5
| TEI IMS/rel. | [6 empty] | 5 | 2.1 | 1.5 | 0.5 |  |  | 0.5 | 0.5 | 1 | 0.5 |  |  |  |  | 0.5 | 0.5 | 0.5 | 0.1 | 0.5 |  | 0.5
| sum | [8 empty] | 10 | 9.3 | 11 | 8.09 | 6.5 | 5.25 | 5.5 | 3.9 | 47 | 42 | 50 | 42 | 38.5 | 42.6 | 38.5 | 42.95 | 42.5 | 42.9 | 43 | 44.8 | 43.8 | 47.9 | 43.3 | 47.9 | 41.5 | 44.8 | 42.5 | 0 | 42 | 0 | 38.3 | 0
There should be not more than 42 planned TUs!