## Slide 1: FS_NG_RTC Status Report
Yi Jiang (Rapporteur)
China Mobile

## Slide 2: FS_NG_RTC status at SA2#152E
WI Code | Work Item Title | WP | Target Date | WID#
FS_NG_RTC | Study on system architecture for next generation real time communication services | 55%->79% | Sep. 2022 | 940066
General
  33 contributions from 7 companies were submitted and 32 was handled
  Solution updates
    KI#1 (IMS Data Channel): solution 7 and 16 were updated
    KI#2 (AR Telephony Communication): solution 9 is updated
    KI#3 (third party specific user identities): solution 10, 12 and 13 were updated
    KI#4 (SBA for media control): solution 14 was updated
  New solutions
    KI#1 (IMS Data Channel): 6 new solutions were proposed and 3 were agreed
  Evaluation and conclusions
    Evaluations and conclusions on all KIs were proposed and general conclusions to KI#1, KI#2 and KI#3 were agreed
    Conclusions to KI#4 is postponed
  TR 23.700-87 was sent to plenary for information
  A LS on media negotiation for AR is sent to SA4
  RAN impacts and dependencies:
  None
Next steps:
  Continue the solution evaluation and conclusions in SA2#153E
  Start normative work on some aspects of concluded KIs
  Send the TR to plenary for approval

## Slide 3: FS_NG_RTC status at SA#97E
WI Code | Work Item Title | WP | Target Date | WID#
FS_NG_RTC | Study on system architecture for next generation real time communication services | 55%->79% | Sep. 2022 | 940066
General
  There are 4 KIs and 22 solutions currently captured in the TR
    KI#1 (IMS Data Channel): 12 solutions
    KI#2 (AR Telephony Communication): 2 solutions
    KI#3 (third party specific user identities): 5 solutions
    KI#4 (SBA for media control): 3 solutions
  Other WG dependencies
  Coordination with SA3 on security aspects of third party specific ID
  Coordination with SA4 on media negotiation
  Remaining issues
  The interaction between DCSF and IMS AS for DC event report
  How to identify the application used in application DC and ensure the same application is downloaded to originating and terminating UEs
  Whether using a new functional entity EDS can be agreed as a solution for KI#3
  Whether using CRS can be agreed as a procedure to deliver third party ID for KI#3.
  No consensus could be reached to introduce a new optional function UMF in Rel-18
Next steps for SA2#153E:
  Continue the solution evaluation and conclusions in SA2#153E
  Start normative work on some aspects of concluded KIs

## Slide 4: FS_NG_RTC work plan updates
  4 TUs for study were used
  2 TUs left for study conclusion and normative phase
  The work plan is updated according to the progress at #152E:
  #150E meeting: finalized the KIs (no new KI proposal afterwards) and discuss solutions
  #151E meeting: continue the solution discussions including solution updates; start to evaluate solutions if possible; send TR to June Plenary for information
  #152E meeting: proposing, updating and merging solutions and try to finalize the evaluation and conclusion; send TR to Sept. Plenary for information and for approval; NG_RTC WID approved
  #153 meeting: continue the solution evaluation and conclusions and start normative work for concluded KIs;
  #154AH and #155 meeting: complete normative work
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23
 |  |  |  | #149E | #150E | #151E | #152E | #153E | #154 | #154AH | #155
SID/WID | Study Phase TU | Normative TU | Total TU |  |  |  |  |  |  |  | 
FS_NG_RTC | 4 | 2 | 6 | 1 | 1 | 1 | 1 | 1 | 0 | 0.5 | 0.5