## Slide 1: SA WG2 Status for 5WWC
Laurent Thiébaut
Nokia

## Slide 2
TR/KI2 for N3IWF concluded + WID submitted in August only for KI2/N3IWF. TR sent for information in August;
in October: Conclude TR/KI2 for TNGF, finish KI1 solution update and do Normative work for KI2/N3IWF (3 CR, ONE for each of 501/502/503)
January meeting conclude (evaluation and conclusions) on KI 1 (different handling of different devices) using BBF/CableLabs feedback. Normative work for KI1 and KI2 for TNGF in Q1 2023. WID update in January based on the conclusions
TR can only be approved in March
Very possible that we need an exception
Overall plan
Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | 
#149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | Total TU
0,5 | 0,5 | 0 | 0,5 | 0,5 | 0 | 0,25 | 0,25 | 2,5

## Slide 3
General
  in August
    Completed all KI2 solutions
    concluded on KI 2 (slicing for Non 3GPP)/N3IWF case
    Agreed on a WID targeting KI2/N3IWF case
  October: Conclude TR/KI2 for TNGF, finish KI1 solution update and do Normative work for KI2/ N3IWF
  No 5WWC work in November (reduce number of topics at F2F meeting)
    As 5WWC_Ph2 (study part) will not be on the agenda in Q4, the TR will only conclude Q1/23
  January meeting conclude on KI 1 (different handling of devices) using BBF/CableLabs feedback
  WID update at January meeting to include normative work for KI1
  Normative work for KI1 in Q1 2023
WI Code | Work Item Title | WP | Target Date | WID#
FS_5WWC_Ph2 | Study on the support for 5WWC, | 60% > 80% | Sep  March, 23 | S2-2204899

## Slide 4
  RAN and SA3 impacts and dependencies:
  None for RAN
  SA3 has started a related study
Contentious Issue:
  None
Focus for the Next Meeting (October):
  Conclude TR/KI2 for TNGF, finish KI1 solution update and do Normative work for KI2/ N3IWF
Overall Plan:
  See dedicated slide
Risks:
  KI1 completion only in Q1 2023 (due to late feedback from BBF/CableLabs)