## Slide 1: eNS_Ph3 Status Report after SA2#154-AH(E)
Jinguo Zhu
ZTE

## Slide 2: eNS_Ph3 status after SA2#154AHE
General
  No further change
WI Code | Work Item Title | WP | Target Date | WID#
FS_eNS_Ph3 | Study on Network Slicing Phase3 | 100%->100% | Dec 2022 | SP-211641

## Slide 3: eNS_Ph3 status after SA2#154AHE
General
  501 CRs on KI#1,KI#4,KI#5 and KI#6 are approved. All 502/503 CRs are postponed
  For KI#2 SA2 will do alignment after CT1 complete the work
  For KI#3 and KI#5, two LSs are sent to RAN2/RAN3 to ask feedback on the RAN impact
Contentious Issue:
  For KI#1, whether both, the PCF and the NSSF options are specified or one of the option is FFS.
  For KI#6, whether UDM or PCF is used for the PDU session inactivity timers is FFFS
  RAN impacts and dependencies:
  RAN feedback on the LS are needed in order to progress on KI#3 and KI#5
Other WG dependencies
  For KI#2, SA2 will do alignment after CT1 complete the work
Focus of the Next Meeting (SA2#155):
  Focus on 501 CRs to address remaining issues
  Start discussion and approval of 502/503 CRs
WI Code | Work Item Title | WP | Target Date | WID#
eNS_Ph3 | Network Slicing Phase3 | 5%->20% | Jun 2023 | SP-221135

## Slide 4: Overall plan
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | Apr,23 | May,23 | 
SID/WID | Study TU | Normative TU | Total TU | #149 | #150 | #151 | #152 | #153 | #154 | #154AH | #155 | #156 | #157 | 
FS_eNS_Ph3 | 8 | 4.25 | 12.25 | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 1 | 1.25 | 1 | 
SA2#149 Feb’22: TR skeleton, arch assumptions, KIs
SA2#150 Apr’22: solutions discussions, and KIs. Finalize the KIs. Last meeting for Kis.
SA2#151 May’22: continue the solution discussions and start to evaluate solutions; SA2#152 Aug’22: solution updates (last meeting for new solution and solution update),finalize the evaluation and conclusion ; TR for information; WID for approval
SA2#153 Oct’22: finalize the conclusions for the KIs
  SA2#154 Nov’22: Evaluation on KI#3 and finalize the conclusions that have interim conclusion, Normative work, TR for approval, WID approval
SA2#154AH: Normative work, focus on 501 CR
SA2#155 meeting: Focus on remaining 501 CRs, start discussion and approval of 502/503 CRs
SA2#156 meeting: 502&503 CRs, Update taking RAN WG feedback into account for KI#3+5
SA2#157 meeting: 502&503 CRs