## Slide 1: FS_NG_RTC/NG_RTC Status Report
Yi Jiang (Rapporteur)
China Mobile

## Slide 2: FS_NG_RTC/NG_RTC work plan updates
  The TUs has been adjusted according to the delay of TR conclusion
    The total TU is currently increased from 6 to 8.5
    5 TU has been used to conclude the study, 1.5 TU has been used for normative phase
    2 meetings and 2 TUs are left for completing normative work
  The work plan is updated according to the progress at #154AHE and #155:
  #154AH meeting: conclude TR; start normative work
  #155 to #156 meetings: continue normative work
  #157 meeting: complete normative work
 |  |  |  | Feb, 22 | Apr, 22 | May, 22 | Aug, 22 | Oct, 22 | Nov, 22 | Jan, 23 | Feb, 23 | Apr, 23 | May, 23
 |  |  |  | #149 | #150 | #151 | #152 | #153 | #154 | #154AHE | #155 | #156E | #157
SID/WID | Study Phase TU | Normative TU | Total TU |  |  |  |  |  |  |  |  |  | 
FS_NG_RTC/NG_RTC | 5 | 2.5 | 7.5 | 1 | 1 | 1 | 1 | 0.5 | 0 | 1 | 1 | 1 | 1

## Slide 3: FS_NG_RTC status after SA2#154AH
General
  This is the last meeting for study phase
  19 contributions were submitted and were all handled
  For KI#1 (IMS Data Channel), procedures and corresponding IMS AS/DCMF services for solution 20 was updated and agreed.
  Remaining editor’s note in KI#2 (AR communication) is removed.
  KI#1 is concluded in this meeting
  Consensus on solution to KI#3 was not reached, thus KI#3 will not progress in normative phase
  In R18 IMS DC is not exempted when data off is activated, a LS is sent to SA1 accordingly
  RAN impacts and dependencies:
  None
Next steps:
  Continue normative work on KI#1, KI#2 and KI#4.
WI Code | Work Item Title | WP | Target Date | WID#
FS_NG_RTC | Study on system architecture for next generation real time communication services | 85%->100% | March, 2023 | 940066

## Slide 4: NG_RTC status after SA2#154AHE and #155
General
  4 contributions to #154AHE and 19 contributions to #155 were submitted
  Architectures and main procedures of IMS DC were agreed
  Enhancement to NRF based DCSF service registration and discovery was agreed
  Services of IMS AS and DCMF are agreed
  Documents for KI#2 and KI#4 were not handled due to time limit
  RAN impacts and dependencies:
  None
Next steps:
  Continue normative work on KI#1, KI#2 and KI#4
  Synchronize with SA4 outcome
WI Code | Work Item Title | WP | Target Date | WID#
NG_RTC | System architecture for next generation real time communication services | 0%->60% | June, 2023 | 970014