## Slide 1: 🛩🛩 UAS_Ph3 🛩🛩 Status Report
LaeYoung Kim (LG Electronics), Shabnam Sultana (Ericsson)
(Rapporteurs)

## Slide 2: UAS_Ph3 Status at SA#110
Progress since SA#109
  1 CR to TS 23.256 was agreed.
  Reply LS on USS changeover procedure was sent to SA3.
  Reply LS on clarification of UAV regulation was sent to RAN3.
  The following two incoming LSs related to NTZ (No-Transmit Zone) were forwarded to TSG SA and TSG RAN for information with no action requested.
    LS from ECC Project Team 1 on Harmonised standard of relevant components of ECC Decision (22)07 on 'Harmonised framework on aerial UE usage in MFCN harmonised bands'
    LS from ETSI TC MSG/TFES: Reply Liaison Statement on harmonised standard of relevant components of ECC Decision (22)07 on 'Harmonised framework on aerial UE usage in MFCN harmonised bands'
     Since 3GPP consolidated response has been already sent from SA#109 (SP-251254), SA2 does not expect SA and RAN to provide any additional LS response to ECC CEPT and ETSI TC MSG/TFES.
  Impacts and dependencies on other WGs
  None.
Outstanding issues
  None.
Next steps
  Maintenance work and alignments based on feedback from and progress in other WGs.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 09/09/2024 | 100% | SP-231801 | 100% | 
1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 12/12/2024 | 100% | SP-240997 | 100% | 

## Slide 3: UAS_Ph3 Status after SA2#172
  Progress at SA2#172
  One CR to TS 23.256 was agreed.
  Reply LS on clarification of UAV regulation was sent to RAN3.
  The following incoming LS was forwarded to TSG SA and TSG RAN for information with no action requested.
    LS from ETSI TC MSG/TFES: Reply Liaison Statement on harmonised standard of relevant components of ECC Decision (22)07 on 'Harmonised framework on aerial UE usage in MFCN harmonised bands'
  Impacts and dependencies on other WGs
  None.
Outstanding issues
  None.
Next steps
  Maintenance work and alignments based on feedback from and progress in other WGs.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 09/09/2024 | 100% | SP-231801 | 100% | 
1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 12/12/2024 | 100% | SP-240997 | 100% | 

## Slide 4: BACKUP

## Slide 5: UAS_Ph3 Status after SA2#171
  Progress at SA2#171
  No CR was agreed.
  Reply LS on USS changeover procedure was sent to SA3.
  LS from ECC Project Team 1 on Harmonised standard of relevant components of ECC Decision (22)07 on "Harmonised framework on aerial UE usage in MFCN harmonised bands" was forwarded to SA and RAN for information with no action requested.
    Since 3GPP consolidated response has been already sent from SA#109 (SP-251254), SA2 does not expect TSG RAN and TSG SA to provide any additional LS response to ECC CEPT.
  Impacts and dependencies on other WGs
  RAN3: Procedures for altitude reporting for aerial UEs
Outstanding issues
  None.
Next steps
  Maintenance work and alignments based on feedback from and progress in other WGs including:
    Response to RAN3 LS on clarification of UAV regulation (related to altitude reporting for aerial UEs).
     UAS_Ph3 is not on SA2#172 agenda (Please refer to S2-2509751), so the postponed RAN3 LS needs to be handled under AI#19.49 at SA2#172.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 09/09/2024 | 100% | SP-231801 | 100% | 
1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 12/12/2024 | 100% | SP-240997 | 100% | 

## Slide 6
WID Estimated TUs: Total 3 TUs for Normative Work
UAS_Ph3 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#164 | August 2024 | 1 | 1 | Start normative work
SA2#165 | October 2024 | 1 | 1 | Continue normative work
SA2#166 | November 2024 | 1 | 1 | Complete 99% of normative work including the exiting ENs resolution • In TS 23.256, three ENs in: - §New 4.4.1.1.X (USS changeover, pre-flight planning related) - §5.2.2.2, §5.13.1 (USS changeover related) • In TS 23.502, one EN in: - §5.2.2.3.1 (USS changeover related)
TSG SA#106 | December 2024 |  |  | Rel-19 Stage 2 freeze
SA2#166-Ad Hoc-e | January 2025 | 1.5 | 0.5 (14 CRs, 1 LS in and 1 LS out) | Maintenance work and normative work including the remaining EN resolution • In TS 23.256 §5.13.2 (USS changeover)
SA2#167 | February 2025 |  | 3 CRs | Maintenance work and Complete 100% of normative work
SA2#168 | April 2025 | 0.5 | 0.5 | Maintenance work and alignments/clarification based on feedback/question from and progress in other WGs.
SA2#169 | May 2025 | 0 | 0 | Not on the agenda and no progress
SA2#170 | August 2025 | 0.5 | 0.5 | Maintenance work and alignments based on feedback from and progress in other WGs including: • Work related to CT3 LS on Time To Collision prediction accuracy.
SA2#171 | October 2025 | 0.5 | 0.5 | Reply LS on USS changeover procedure was sent to SA3.
 | Total | 3+3 | 3+2 | 

## Slide 7: UAS_Ph3 Status at SA#109
Progress since SA#108
  3 CRs to TS 23.256 and 2 CRs to TS 23.288 were agreed.
  Reply LS on time to collision prediction accuracy was sent to CT3.
  LS was sent to RAN and SA to request guidance on Reply Liaison Statement on harmonised standard of relevant components of ECC Decision (22)07 on “Harmonised framework on aerial UE usage in MFCN” harmonised bands.
  Impacts and dependencies on other WGs
  RAN3: Procedures for altitude reporting for aerial UEs
  SA3: USS changeover procedure
Outstanding issues
  None.
Next steps
  Maintenance work and alignments based on feedback from and progress in other WGs.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 09/09/2024 | 100% | SP-231801 | 100% | 
1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 12/12/2024 | 100% | SP-240997 | 100% | 

## Slide 8: UAS_Ph3 Status after SA2#170
  Progress at SA2#170
  3 CRs to TS 23.256 and 2 CRs to TS 23.288 were agreed.
  Reply LS on time to collision prediction accuracy was sent to CT3.
  LS was sent to RAN and SA to request guidance on Reply Liaison Statement on harmonised standard of relevant components of ECC Decision (22)07 on “Harmonised framework on aerial UE usage in MFCN” harmonised bands.
  Impacts and dependencies on other WGs
  RAN3: Procedures for altitude reporting for aerial UEs
  SA3: USS changeover procedure
Outstanding issues
  None.
Next steps
  Maintenance work and alignments based on feedback from and progress in other WGs including:
    Response to SA3 LS on USS changeover procedure.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 09/09/2024 | 100% | SP-231801 | 100% | 
1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 12/12/2024 | 100% | SP-240997 | 100% | 

## Slide 9
WID Estimated TUs: Total 3 TUs for Normative Work
UAS_Ph3 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#164 | August 2024 | 1 | 1 | Start normative work
SA2#165 | October 2024 | 1 | 1 | Continue normative work
SA2#166 | November 2024 | 1 | 1 | Complete 99% of normative work including the exiting ENs resolution • In TS 23.256, three ENs in: - §New 4.4.1.1.X (USS changeover, pre-flight planning related) - §5.2.2.2, §5.13.1 (USS changeover related) • In TS 23.502, one EN in: - §5.2.2.3.1 (USS changeover related)
TSG SA#106 | December 2024 |  |  | Rel-19 Stage 2 freeze
SA2#166-Ad Hoc-e | January 2025 | 1.5 | 0.5 (14 CRs, 1 LS in and 1 LS out) | Maintenance work and normative work including the remaining EN resolution • In TS 23.256 §5.13.2 (USS changeover)
SA2#167 | February 2025 |  | 3 CRs | Maintenance work and Complete 100% of normative work
SA2#168 | April 2025 | 0.5 | 0.5 | Maintenance work and alignments/clarification based on feedback/question from and progress in other WGs.
SA2#169 | May 2025 | 0 | 0 | Not on the agenda and no progress
SA2#170 | August 2025 | 0.5 | 0.5 | Maintenance work and alignments based on feedback from and progress in other WGs including: • Work related to CT3 LS on Time To Collision prediction accuracy.
 | Total | 3+2.5 | 3+1.5 | 

## Slide 10: UAS_Ph3 Status at SA#108
Progress since SA#107
  4 CRs to TS 23.256 and 1 CR to TS 23.502 were agreed.
  Reply LS on UAV regulation was sent to RAN3.
  The issue on Using Nnef_RetrieveInfoUAVFlight_Get in the procedure for USS changeover during a UAV flight which has dependency on CT3 was resolved per LS from CT3 (S2-2502810) and no additional action needed by SA2.
  Impacts and dependencies on other WGs
  RAN3: Procedures for altitude reporting for aerial UEs  alignments expected to be progressed during Q3 meeting.
  SA3: check USS list aspect progressed in SA3 and follow-up if necessary
Outstanding issues
  None.
Next steps
  Maintenance work and alignments based on feedback from and progress in other WGs.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 09/09/2024 | 100% | SP-231801 | 100% | 
1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 12/12/2024 | 100% | SP-240997 | 100% | 

## Slide 11: UAS_Ph3 Status after SA2#169
  Progress at SA2#169
  Not on the agenda and no progress.
  Impacts and dependencies on other WGs
  RAN3: Procedures for altitude reporting for aerial UEs  alignments expected to be progressed during Q3 meeting.
  SA3: check USS list aspect progressed in SA3 and follow-up if necessary
Outstanding issues
  None.
Next steps
  Maintenance work and alignments based on feedback from and progress in other WGs including:
    Work related to SA3 LS on USS changeover procedure.
    Work related to CT3 LS on Time To Collision prediction accuracy.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 09/09/2024 | 100% | SP-231801 | 100% | 
1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 12/12/2024 | 100% | SP-240997 | 100% | 

## Slide 12
WID Estimated TUs: Total 3 TUs for Normative Work
UAS_Ph3 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#164 | August 2024 | 1 | 1 | Start normative work
SA2#165 | October 2024 | 1 | 1 | Continue normative work
SA2#166 | November 2024 | 1 | 1 | Complete 99% of normative work including the exiting ENs resolution • In TS 23.256, three ENs in: - §New 4.4.1.1.X (USS changeover, pre-flight planning related) - §5.2.2.2, §5.13.1 (USS changeover related) • In TS 23.502, one EN in: - §5.2.2.3.1 (USS changeover related)
TSG SA#106 | December 2024 |  |  | Rel-19 Stage 2 freeze
SA2#166-Ad Hoc-e | January 2025 | 1.5 | 0.5 (14 CRs, 1 LS in and 1 LS out) | Maintenance work and normative work including the remaining EN resolution • In TS 23.256 §5.13.2 (USS changeover)
SA2#167 | February 2025 |  | 3 CRs | Maintenance work and Complete 100% of normative work
SA2#168 | April 2025 | 0.5 | 0.5 | Maintenance work and alignments/clarification based on feedback/question from and progress in other WGs.
SA2#169 | May 2025 | 0 | 0 | Not on the agenda and no progress
SA2#170 | August 2025 | 0.5?? |  | Maintenance work and alignments based on feedback from and progress in other WGs including: • Work related to SA3 LS on USS changeover procedure. • Work related to CT3 LS on Time To Collision prediction accuracy.
 | Total | 3+2 | 3+1 | 

## Slide 13: UAS_Ph3 Status after SA2#168
  Progress at SA2#168
  4 CRs to TS 23.256 and 1 CR to TS 23.502 were agreed.
  Reply LS on UAV regulation was sent to RAN3.
  The issue on Using Nnef_RetrieveInfoUAVFlight_Get in the procedure for USS changeover during a UAV flight which has dependency on CT3 was resolved per LS from CT3 (S2-2502810) and no additional action needed by SA2.
  Impacts and dependencies on other WGs
  RAN3: Procedures for altitude reporting for aerial UEs  alignments expected to be progressed during Q2/Q3 meetings.
  SA3: check USS list aspect progressed in SA3 and follow-up if necessary
Outstanding issues
  None.
Next steps
  Maintenance work and alignments based on feedback from and progress in other WGs.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 09/09/2024 | 100% | SP-231801 | 100% | 
1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 12/12/2024 | 100% | SP-240997 | 100% | 

## Slide 14
WID Estimated TUs: Total 3 TUs for Normative Work
UAS_Ph3 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#164 | August 2024 | 1 | 1 | Start normative work
SA2#165 | October 2024 | 1 | 1 | Continue normative work
SA2#166 | November 2024 | 1 | 1 | Complete 99% of normative work including the exiting ENs resolution • In TS 23.256, three ENs in: - §New 4.4.1.1.X (USS changeover, pre-flight planning related) - §5.2.2.2, §5.13.1 (USS changeover related) • In TS 23.502, one EN in: - §5.2.2.3.1 (USS changeover related)
TSG SA#106 | December 2024 |  |  | Rel-19 Stage 2 freeze
SA2#166-Ad Hoc-e | January 2025 | 1.5 | 0.5 (14 CRs, 1 LS in and 1 LS out) | Maintenance work and normative work including the remaining EN resolution • In TS 23.256 §5.13.2 (USS changeover)
SA2#167 | February 2025 |  | 3 CRs | Maintenance work and Complete 100% of normative work
SA2#168 | April 2025 | 0.5 | 0.5 | Maintenance work and alignments/clarification based on feedback/question from and progress in other WGs.
 | Total | 3+2 | 3+1 | 

## Slide 15: UAS_Ph3 Status at SA#107
Progress since SA#106
  10 CRs to TS 23.256 and 1 CR to TS 23.502 were agreed.
  Impacts and dependencies on other WGs
  CT3: Using Nnef_RetrieveInfoUAVFlight_Get in the procedure for USS changeover during a UAV flight
  RAN3: Procedures for altitude reporting for aerial UEs
   CT3 and RAN3 related aspects are expected to be progressed during Q2 meetings.
  SA3: check USS list aspect progressed in SA3 and follow-up if necessary
Outstanding issues
  None.
Next steps
  Maintenance work and alignments based on feedback from and progress in other WGs.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 09/09/2024 | 100% | SP-231801 | 100% | 
1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 12/12/2024 | 99% | SP-240997 | 100% | 

## Slide 16: UAS_Ph3 Status after SA2#167
  Progress at SA2#166AH-E
  8 CRs to TS 23.256 and 1 CR to TS 23.502 were agreed.
  Progress at SA2#167
  2 CRs to TS 23.256 were agreed addressing dependency/clarifications with other WGs.
  Impacts and dependencies on other WGs
  CT3: Using Nnef_RetrieveInfoUAVFlight_Get in the procedure for USS changeover during a UAV flight
  RAN3: Procedures for altitude reporting for aerial UEs
   CT3 and RAN3 related aspects are expected to be progressed during Q2 meetings.
  SA3: check USS list aspect progressed in SA3 and follow-up if necessary
Outstanding issues
  None.
Next steps
  Maintenance work and alignments based on feedback from and progress in other WGs.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 09/09/2024 | 100% | SP-231801 | 100% | 
1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 12/12/2024 | 99% | SP-240997 | 100% | 

## Slide 17
WID Estimated TUs: Total 3 TUs for Normative Work
UAS_Ph3 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#164 | August 2024 | 1 | 1 | Start normative work
SA2#165 | October 2024 | 1 | 1 | Continue normative work
SA2#166 | November 2024 | 1 | 1 | Complete 99% of normative work including the exiting ENs resolution • In TS 23.256, three ENs in: - §New 4.4.1.1.X (USS changeover, pre-flight planning related) - §5.2.2.2, §5.13.1 (USS changeover related) • In TS 23.502, one EN in: - §5.2.2.3.1 (USS changeover related)
TSG SA#106 | December 2024 |  |  | Rel-19 Stage 2 freeze
SA2#166-Ad Hoc-e | January 2025 | 1.5 | 0.5 (14 CRs, 1 LS in and 1 LS out) | Maintenance work and normative work including the remaining EN resolution • In TS 23.256 §5.13.2 (USS changeover)
SA2#167 | February 2025 |  | 3 CRs | Maintenance work and Complete 100% of normative work
SA2#168/169 | 2025/Q2 |  |  | Maintenance work and alignments based on feedback from and progress in other WGs.
 | Total | 3+1.5 | 3+0.5 | 

## Slide 18: UAS_Ph3 Status at SA#106
Progress since SA#105
  12 CRs to TS 23.256, 1 CR to TS 23.502 and 2 CRs to TS 23.288 were agreed.
  All work tasks in the WID (listed below) were captured mainly in TS 23.256.
    WT#1: NEF services enhancements
      Pre-flight planning and in-flight monitoring for UAV UEs; C2 communication reliability; Changeover from one USS to another USS for UAV UE assisted by 5GC; ※ Security spec reference added
    WT#2: Network-assisted/ground-based mechanism for DAA (Detect And Avoid)
    WT#3: Support no-transmit zones for UAV UEs
  One LS on Clarification of Nnef_RetrieveInfoUAVFlight_Get service operation sent to CT3.
  One Reply LS on UAV regulation sent to RAN3.
      Incoming LS from RAN3 (S2-2411303/R3-245815) is not directly related to UAS_Ph3 work. Reply from SA2 provides information using flight information for UAV UEs from NG-RAN to AMF is required for UAS_Ph3 which can be potentially reused for the related work RAN3 requested in parts, while informing that no such requirements nor solutions exist for non-UAV legacy devices.
  Impacts and dependencies on other WGs
  CT3: Using Nnef_RetrieveInfoUAVFlight_Get in the procedure for USS changeover during a UAV flight
  RAN2/3: Procedures for altitude reporting for aerial UEs
Outstanding issues
  None.
Next steps
  Maintenance work and alignments based on feedback from and progress in other WGs.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 12/12/2024 | 85% | SP-241287 | 99% | 
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 09/09/2024 | 100% | SP-231801 | 100% | 

## Slide 19: UAS_Ph3 Status after SA2#166
  Progress since SA2#166
  7 CRs to TS 23.256 (4 CRs are revisions of agreed CRs at SA2#165), 1 CR to TS 23.502 and 1 CR to TS 23.288 (revision of agreed CR at SA2#165) were agreed.
  One LS on Clarification of Nnef_RetrieveInfoUAVFlight_Get service operation sent to CT3.
  One Reply LS on UAV regulation sent to RAN3.
    Incoming LS from RAN3 (S2-2411303/R3-245815) is not directly related to UAS_Ph3 work. Reply from SA2 provides information using flight information for UAV UEs from NG-RAN to AMF is required for UAS_Ph3 which can be potentially reused for the related work RAN3 requested in parts, while informing that no such requirements nor solutions exist for non-UAV legacy devices.
    RAN and CT3 related aspects may be delayed until SA2#168 meeting due to WG meeting time plan for Q1/2025.
  Impacts and dependencies on other WGs
  CT3: Using Nnef_RetrieveInfoUAVFlight_Get in the procedure for USS changeover during a UAV flight
  RAN2/3: Procedures for altitude reporting for aerial UEs
Outstanding issues
  None.
Next steps
  Maintenance work and alignments based on feedback from and progress in other WGs.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 12/12/2024 | 85% | SP-241287 | 99% | 
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 09/09/2024 | 100% | SP-231801 | 100% | 

## Slide 20
Total 3 TUs for Normative Work
UAS_Ph3 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#164 | August 2024 | 1 | 1 | Start normative work
SA2#165 | October 2024 | 1 | 1 | Continue normative work
SA2#166 | November 2024 | 1 | 1 | Complete 99% of normative work including the exiting ENs resolution • In TS 23.256, three ENs in: - §New 4.4.1.1.X (USS changeover, pre-flight planning related) - §5.2.2.2, §5.13.1 (USS changeover related) • In TS 23.502, one EN in: - §5.2.2.3.1 (USS changeover related)
SA2#166-Ad Hoc-e | January 2025 |  |  | Maintenance work and alignments based on feedback from and progress in other WGs.
SA2#167 | February 2025 |  |  | Maintenance work and alignments based on feedback from and progress in other WGs.
 | Total | 3 | 3 | 

## Slide 21: UAS_Ph3 Status after SA2#165
  Progress since SA2#165
  9 CRs to TS 23.256 and 2 CRs to TS 23.288 were agreed.
  All work tasks in the WID (listed below) were captured mainly in TS 23.256.
    WT#1: NEF services enhancements
      Pre-flight planning and in-flight monitoring for UAV UEs
      C2 communication reliability
      Changeover from one USS to another USS for UAV UE assisted by 5GC
    WT#2: Network-assisted/ground-based mechanism for DAA (Detect And Avoid)
    WT#3: Support no-transmit zones for UAV UEs
  RAN impacts and dependencies
  None.
Outstanding issues
  None.
Next steps
  Finalize the normative work in accordance with the conclusions drawn by the TR and as specified in the WID.
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | 09/09/2024 | 100% | SP-231801 | 100% | 
1040037 | (Stage 2 of) UAS, UAV and UAM Phase 3 | UAS_Ph3 | 12/12/2024 | 65% | SP-241287 | 85% | 

## Slide 22
Total 3 TUs for Normative Work
UAS_Ph3 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#164 | August 2024 | 1 | 1 | Start normative work
SA2#165 | October 2024 | 1 | 1 | Continue normative work
SA2#166 | November 2024 | 1 | 1 | Complete normative work including the exiting ENs resolution • In TS 23.256, four ENs in: - §New 4.4.1.1.X (USS changeover, pre-flight planning related) - §5.2.2.2, §5.13.1, §5.13.2 (USS changeover related) • In TS 23.502, one EN in: - §5.2.2.3.1 (USS changeover related)
 | Total | 3 | 3 | 

## Slide 23: FS_UAS_Ph3 & UAS_Ph3 Status at SA#105
Progress since SA#104
  FS_UAS_Ph3
    TR 23.700-59 sent to TSG SA for Approval.
    2 pCRs were agreed to include:
      For KI#3, based on RAN feedback and SA2 discussion, final conclusion was made that NTZ enforcement related impact is limited to UAV UE only. No impact on RAN and CN.
      For KI#2, conclusion was updated to add Relative Location of UAVs provided by Ranging Service.
  UAS_Ph3
    8 CRs to TS 23.256, 1 CR to TS 23.288 and 1 CR to TS 23.502 were agreed.
    Revised WID sent for approval to SA#105.
  RAN impacts and dependencies
  None.
Outstanding issues
  None.
Next steps
  Finalize the normative work in accordance with the conclusions drawn by the TR and as specified in the WID.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph3 | Study on Phase 3 for UAS, UAV and UAM | 90% -> 100% | September 2024 | SP-231801
UAS_Ph3 | Phase 3 for UAS, UAV and UAM | 0% -> 65% | December 2024 | SP-240997

## Slide 24: FS_UAS_Ph3 Status after SA2#164
  Progress since SA2#164
  TR 23.700-59 sent to TSG SA for Approval.
  2 pCRs were agreed to include:
    For KI#3, based on RAN feedback and SA2 discussion, final conclusion was made that NTZ enforcement related impact is limited to UAV UE only. No impact on RAN and CN.
    For KI#2, conclusion was updated to add Relative Location of UAVs provided by Ranging Service.
  RAN impacts and dependencies
  None.
Outstanding issues
  None.
Next steps
  None.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph3 | Study on Phase 3 for UAS, UAV and UAM | 90% -> 100% | September 2024 | SP-231801

## Slide 25: UAS_Ph3 Status after SA2#164
  Progress since SA2#164
  8 CRs to TS 23.256, 1 CR to TS 23.288 and 1 CR to TS 23.502 were agreed.
  Revised WID sent for approval to SA#105.
  RAN impacts and dependencies
  None.
Outstanding issues
  None.
Next steps
  Finalize the normative work in accordance with the conclusions drawn by the TR and as specified in the WID.
WI Code | Work Item Title | WP | Target Date | WID#
UAS_Ph3 | Phase 3 for UAS, UAV and UAM | 0% -> 65% | December 2024 | SP-240997

## Slide 26: FS_UAS_Ph3 Status at SA#104
Progress since SA#103
  TR 23.700-59 sent to TSG SA for Information.
  For KI#3, updates to KI description and Architectural Assumptions/Requirements agreed based on the Reply LSs from TSG RAN and ETSITC MSG/TFES.
  New solutions agreed (2 solutions for KI#1 on multiple USS, 3 solutions for KI#1 on C2 communication reliability, 3 solutions for KI#3).
  Conclusions for KI#1 (for all 3 sub-Key Issues) and Conclusions for KI#2 agreed. Interim Conclusions for KI#3 agreed.
  LS sent to RAN (RAN2/RAN3 CCed) on NTZ solution impacts to RAN
  RAN impacts and dependencies
  No-Transmit Zones (KI#3) may require RAN feedback for final conclusion.
Outstanding issues
  No-Transmit Zones (KI#3) aspects need further work.
Next steps
  Final conclusion on KI#3 based on RAN feedback.
  Rapporteurs propose to use the NWM process during June/July (SA2 chair has established for Rel-19 SIs/WIs to progress specific issues during SA2#163) to try and progress some of the open and outstanding issues.
  Start normative work for KI#1&2 in Q3 and normative work for KI#3 in Q4.
  TR 23.700-59 sent to TSG SA for Approval.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph3 | Study on Phase 3 for UAS, UAV and UAM | 50% -> 90% | June 2024 | SP-231801

## Slide 27: FS_UAS_Ph3 Status after SA2#163
  Progress since SA2#163
  TR 23.700-59 v0.4.0 is available and sent to TSG SA for Information.
  30 Tdocs submitted (including revision before meeting): 6 Tdocs for solution updates, 22 Tdoc for evaluations/conclusions, 1 Tdoc for pre-SA2#163 NWM discussion summary and 1 Tdoc for LS Out on KI#3.
  12 Tdocs handled about solution updates, conclusions and LS Out.
  Solution updates agreed regarding KI#1 on C2 reliability (1 solution), KI#3 (3 solutions).
  Conclusions for KI#1 (for all 3 sub-Key Issues) and Conclusions for KI#2 agreed. Interim Conclusions for KI#3 agreed.
  LS about NTZ sent to TSG RAN (RAN2 and RAN3 CCed).
  WID for normative work agreed.
  RAN impacts and dependencies
  No-Transmit Zones (KI#3) may require RAN feedback for final conclusion.
Outstanding issues
  No-Transmit Zones (KI#3) aspects need further work.
Next steps
  Final conclusion on KI#3 based on RAN feedback.
  Rapporteurs propose to use the NWM process during June/July (SA2 chair has established for Rel-19 SIs/WIs to progress specific issues during SA2#163) to try and progress some of the open and outstanding issues.
  Start normative work for KI#1&2 in Q3 and normative work for KI#3 in Q4.
  TR 23.700-59 sent to TSG SA for Approval.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph3 | Study on Phase 3 for UAS, UAV and UAM | 73% -> 90% | June 2024 | SP-231801

## Slide 28
Total 6.5 TUs
  3.5 TUs for Study Phase
  3 TUs for Normative Work
FS_UAS_Ph3 Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2 #160AH-e | Jan 2024 | 0.5 | 0.5 | TR 23.700-59 Skeleton, Scope, Arch Assumptions, Key Issues
SA2#161 | Feb 2024 | 1 | 1 | Start solutions discussion, Attempt to close new Key Issue
SA2#162 | Apr 2024 | 1 | 1 | Solution Updates, Final meeting for new solutions, if time permits resolve ENs considered critical, prioritize new solutions for issues not yet addressed or not covered by the existing solutions, Start evaluations (if possible); For KI#3, attempt to send LS to RAN WGs to check/get feedback on solutions
SA2#163 | May 2024 | 1 | 1 | Solution Updates (focus on KI#3), Evaluations and Conclusions (※ Conclusions are prioritized: For KI#3, attempt to conclude aspects/principles without RAN dependency) TR 23.700-59 sent to SA for one-step Approval For KI#3, attempt to send LS to RAN WGs to check/get feedback on solutions
 | Total | 3.5 | 3.5 | 

## Slide 29: FS_UAS_Ph3 Status after SA2#162
  Progress since SA2#162
  TR 23.700-59 v0.3.0 is available.
  33 Tdocs submitted: 20 Tdocs for new solution, 10 Tdocs for solution updates, 1 Tdoc for Architectural Assumptions, 1 Tdoc is for new terms and 1 Tdoc for LS Out.
  20 Tdocs handled mainly about new solutions and KI#3 related Architectural Assumptions/Requirements.
    New solutions agreed regarding: KI#1 on C2 reliability (3 solutions), KI#1 on multiple USS (2 solutions), KI#3 (3 solutions).
    Solution update agreed regarding KI#1 on flight planning/monitoring (1 solution).
    For KI#3, updates to KI description and Architectural Assumptions/Requirements agreed based on the Reply LSs from TSG RAN and ETSITC MSG/TFES.
  Due to TU budget/quota, 10 Tdocs for solution updates could not be handled.
  RAN impacts and dependencies
  No-Transmit Zones (KI#3) has RAN dependency: RAN aspects require RAN input to be able to make progress on normative work in SA2.
Contentious issues
  Regarding aerial UEs not supporting 3GPP Rel-19 NTZ mechanism, requirement to 3GPP system and how to handle them need to be addressed during the study and conclusion of KI#3 and coordination with RAN WGs.
Next steps
  Solution Updates (Prioritize KI#3 to address LS feedback & contentious aspects), Evaluations and Conclusions (※ Conclusions are prioritized).
  TR 23.700-59 sent to SA for one-step Approval.
  LS to RAN WGs to check/get feedback on KI#3 solutions.
  Propose WI to start normative work in Q3 for KI#1&2 and normative work for KI#3 in Q4.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph3 | Study on Phase 3 for UAS, UAV and UAM | 50% -> 73% | June 2024 | SP-231801

## Slide 30: FS_UAS_Ph3 Status at SA#103
Progress since SA#102
  Study started with SA2#160AH-e.
  TR 23.700-59 v0.2.0 is available.
  At SA2#160AH-e: TR skeleton, Scope, Terms, Architecture Assumptions/Requirements, 3 Key Issues to cover the WTs in the SID and Annex including background information about No-Transmit Zones agreed.
  At SA2#161: New solutions agreed (3 solutions for KI#1 on flight planning/monitoring, 3 solutions for KI#2, 3 solutions for KI#3).
  Outgoing LSs
    Reply LS sent to SA6 on Coordination of work for UAS_Ph3.
    LS sent to ETSI TC MSG/TFES on No-Transmit Zones according to ECC decision 22(07).
    LS sent to RAN and RAN2 to clarify the requirements for No-Transmit Zones.
  RAN impacts and dependencies
  No-Transmit Zones (KI#3) has RAN dependency, timely feedback/input needed to resolve differing views
Contentious issues
  KI#3 may be at risk not to complete by May, 2024 if common understanding cannot be reached
Next steps
  Solution discussions, Evaluations, Conclusions, TR sent to SA for one-step Approval
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph3 | Study on Phase 3 for UAS, UAV and UAM | 0% -> 50% | June 2024 | SP-231801

## Slide 31: FS_UAS_Ph3 Status after SA2#161
  Progress since SA2#161
  TR 23.700-59 v0.2.0 is available.
  25 Tdocs were submitted: 24 Tdocs are for new solution and 1 Tdoc is for new terms.
  12 Tdocs were handled about: KI#1 on flight planning/monitoring, KI#1 on C2 reliability, KI#2 and KI#3.
    New solutions agreed regarding KI#1 on flight planning/monitoring (3 solutions), KI#2 (3 solutions), KI#3 (3 solutions).
    Cf.) No solution yet regarding KI#1 on C2 reliability, KI#1 on multiple USS.
  Due to TU budget/quota, 13 Tdocs could not be handled about KI#1 on multiple USS and KI#3.
  LS sent to RAN and RAN2 to clarify the requirements for No-Transmit Zones.
  RAN impacts and dependencies
  No-Transmit Zones (KI#3) has RAN dependency/requires RAN input to be able to make progress/finalization in SA2.
Contentious issues
  KI#3 needs clarification in regards to scope and some technical aspects, without common understanding, this KI may be at risk not to complete by May, 2024.
Next steps
  At SA2#162, continue solution discussions and start evaluations (if possible).
    Tdocs unhandled at SA2#161 will be prioritized (if not covered by the existing solutions) for handling if re-submitted.
    New solutions and resolving ENs considered critical will be prioritized than solution updates.
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph3 | Study on Phase 3 for UAS, UAV and UAM | 15% -> 50% | June 2024 | SP-231801

## Slide 32: FS_UAS_Ph3 Status after SA2#160AH-e
  Progress since SA2#160AH-e
  Study started with SA2#160AH-e.
  TR 23.700-59 v0.1.0 is available.
  22 TDocs were submitted and 2 Tdocs proposing new KIs could not be handled due to TU budget/quota.
    The contents of the not handled Tdocs were also considered when discussing the related new Key Issues.
  pCRs for TR skeleton, Scope, Terms, Architecture Assumptions/Requirements, 3 Key Issues to cover the WTs in the SID and Annex including background information about No-Transmit Zones have been agreed.
  Key Issue related to No-Transmit Zones has pending EN to be resolved.
  Reply LS sent to SA6 on Coordination of work for UAS_Ph3.
  LS sent to ETSI TC MSG/TFES on No-Transmit Zones according to ECC decision 22(07).
  RAN impacts and dependencies
  RAN dependency is expected related to No-Transmit Zones
Contentious issues
  None
Next steps
  Start solution discussions for agreed Key Issues in next meeting
WI Code | Work Item Title | WP | Target Date | WID#
FS_UAS_Ph3 | Study on Phase 3 for UAS, UAV and UAM | 0% -> 15% | June 2024 | SP-231801