## Slide 1: TEI20_NEPS WI Status Report
Alessio Casati(Rapporteur)
Nokia
SA WG2 Meeting #172
17 – 21 November, 2025, Dallas, US
Tdoc S2-2511289

## Slide 2
Progress since SA#109:
  Two CRs (one for 23.501 and one for 23.502) were agreed at SA2#171,
  Revisions of agreed CRs at SA2#171 were further agreed at SA2#172
    Added the support for NSSAA over EPS and work is now complete
Impacts and dependencies on other WGs:
  CT1 to define the Pending indicator in PCO, the indication of the support of the NSSAA over EPC indicator in PCO and a UE MM Core Network capability indication of support of the feature. Align stage three text to the stage two CRs where needed in CT1 specifications .
Next steps:
  N/A
TEI20_NEPS status at SA#110
UID | Name | Acronym | Old% | New% | Target Date | WID | Change or comment
1090005 | Support of NSSAA in EPS | TEI20_NEPS | 0% | 100% | Dec 2025 | SP-251210 | Work completed at SA2#172

## Slide 3
TEI20_NEPS status report after SA2#171
UID | Name | Acronym | Old% | New% | Target Date | WID | Change or comment
1090005 | Support of NSSAA in EPS | TEI20_NEPS | 0% | 90% | Dec 2025 | SP-251210 | 0.5 TU still available at SA2#172
Progress in SA2#171
  Two CRs agreed (TS 23.501 and TS 23.502).
  This TEI20 WI is 90% complete
  RAN impacts and dependencies
  None
Contentious issues
  None
Next steps
  Resolve editor’s notes on the need of indication or UE MM capability in 5GS and on the storage in UDM of the outcome of NSSAA at SMF+PGW-C and AMF.

## Slide 4
TEI20_NEPS status report after SA2#172
UID | Name | Acronym | Old% | New% | Target Date | WID | Change or comment
1090005 | Support of NSSAA in EPS | TEI20_NEPS | 90% | 100% | Dec 2025 | SP-251210 | Work complete at SA2#172
Progress in SA2#172
  Revisions of the CRs agreed at SA2#172 agreed (one for TS 23.501 and one for TS 23.502).
  This TEI20 WI is 100% complete
  RAN impacts and dependencies
  None
Contentious issues
  None
Next steps
  None

## Slide 5
TEI20_NEPS Work plan
Meeting | Date | Planned TU’s | Actual TU’s | Action plan
SA2#171 | October 2025 | 0.5 | 0.5 | Initial CRs submitted
SA2#172 | November 2025 | 0.5 | 0.5 | Handle ENs in CRs and complete the work