3GPP TSG-SA WG4 Adhoc Meeting on Rel-20	S4-251204

Online, 10 July 2025

3GPP TSG-SA WG4 Meeting #133e	S4-25XXXX

Online, 21-25 July 2025

# Source:	Tencent

# Title:	[FS_3DGS_MED] Work Plan v0.1

# Document for:	Agreement

# Agenda Item:	17.2

# Introduction

Over the past two years, 3D Gaussian Splatting (3DGS) has emerged as a breakthrough in real-time, photorealistic 3D rendering. By representing a scene as a collection of anisotropic Gaussian ellipsoids, 3DGS offering high visual fidelity. Its lightweight rasterization pipeline makes it uniquely attractive for mobile platforms, and early demonstrations have already drawn significant interest from both academia and industry.

To unlock large-scale, consumer-grade deployment, mobile devices must be able not only to receive and render 3DGS content, but also to capture and share their own scenes. Within 3GPP, Working Group SA4 is the natural forum to assess these challenges and opportunities. This work plan therefore launches a Study Item whose goals are to:

- Identify the use cases for mobile devices that demonstrate the practical applications of 3DGS contents.

- Analyze the 3DGS representation format

  - identify the relevance and complexity of the parameters of the primitives. This includes the size of the 3d model and the associated processing requirements.

  - Assess how well 3DGS representations fulfill content provider creative intent and define related quality parameters and evaluation criteria.

- Address the content generation aspects including:

  - mobile device processing and the mapping on the XR device architecture

  - and network-based processing, identifying the benefits of edge/cloud operations.

- Analyze the workflow and 3GPP service integration (such as messaging) and identify the media requirements to support the scenario.

- Identify the target bitrates and potential traffic characteristics of 3DGS for the selected scenarios and investigate the associated compression aspects.

- In parallel of the above objectives: Develop an end-to-end reference implementation for content delivery, covering the entire pipeline from content creation on a server or on the UE and, through compression, transmission, to rendering on a mobile device platform. This work could serve as a basis for future developments and be used in the evaluations carried out during this study.

It is expected to coordinate with external organizations working on 3DGS such as MPEG, Khronos and Metaverse Standards Forum.

The pages that follow outline the phased tasks, deliverables, and collaborations needed to achieve these objectives within the scope of Release 19.

It is proposed to complete this study by March 2027 (SA#115).

# Time Plan

The following time plan for the execution of the FS_3DGS_MED study item objectives is proposed in the following table.

| Meeting | Study on Media Energy Consumption Exposure and Evaluation Framework phase 2 |
| --- | --- |
| SA4#133-e (21-25 Jul. 2025, online) | - Approve New Study Item FS_3DGS_MED |
| SA#109 (16-19 Sep. 2025, Beijing, CN) |  |
| SA4#134 - Nov. 2025, Dallas) | - Start 1: Identify the use cases for mobile devices that demonstrate the practical applications of 3DGS contents - Start 2: Analyze the 3DGS representation format - Start 6: Develop an end-to-end reference implementation (mobile renderer) |
| SA#110 (09-12 Dec. 2025, Baltimore, US) |  |
| SA4#135 (2-13 Feb. 2026, India) | - Complete 1: Identify the use cases for mobile devices that demonstrate the practical applications of 3DGS contents - Continue 2: Analyze the 3DGS representation format - Continue 6: Develop an end-to-end reference implementation (mobile renderer) |
| SA#111 (10-13 Mar. 2026, Japan, JP) |  |
| SA4#135e (13-17 Apr. 2026 e-meeting) | - Complete 2: Analyze the 3DGS representation format - Start 3: Address the content generation aspects - Start 4: Analyze the workflow and 3GPP service integration - Continue 6: Develop an end-to-end reference implementation (mobile renderer) |
| SA4#136 (11-15 May 2026, Montreal) | - Continue 3: Address the content generation aspects - Continue 4: Analyze the workflow and 3GPP service integration - Continue 6: Develop an end-to-end reference implementation (Capture & generation) |
| SA#112 (09-12 Jun. 2026, Singapore) |  |
| SA4#137e (24-28 Aug. 2026, e-meeting) | - Complete 3: Address the content generation aspects - Complete 4: Analyze the workflow and 3GPP service integration - Continue 6: Develop an end-to-end reference implementation (Capture & generation) |
| SA#113 (15-18 Sep. 2026, EU) |  |
| SA4#137e-bis (12-16 Oct. 2026, e-meeting) | - Start 5: Identify the target bitrates and potential traffic characteristics - Continue 6: Develop an end-to-end reference implementation (Capture & generation) |
| SA4#138 (16-20 Nov. 2026, North America) | - Continue 5: Identify the target bitrates and potential traffic characteristics - Continue 6: Develop an end-to-end reference implementation (system integration) - Start the TR conclusions and the identification of normative work - Send the TR to SA for information |
| SA#114 (08-11 Dec. 2026, US) | - Present the TR for information |
| SA4#139 (22-26 Feb .2027, Korea) | - Complete 5: Identify the target bitrates and potential traffic characteristics - Complete 6: Develop an end-to-end reference implementation (system integration) - Complete the TR conclusions and the identification of normative work - Send the TR to SA for approval |
| SA#115 ( xx-xx Mar. 2027, xxx) | - Present the TR for approval |

# Proposal

We propose the above Work Plan for the SA4 team's consideration.