## TDoc_List
TDoc | Title | Source | Chairman's notes | Contact | Contact ID | Type | For | Abstract | Secretary Remarks | Agenda item sort order | Agenda item | Deadline for email approval (CEST ) | SWG TDoc Status | Plenary agenda item for SWG output Tdocs | Agenda item description | TDoc sort order within agenda item | TDoc Status | Reservation date | Uploaded | Is revision of | Revised to | Release | Spec | Version | Related WIs | CR | CR revision | CR category | TSG CR Pack | Reply to | To | Cc | Original LS | Reply in
S4-200558 | Proposed Work Plan for FS_5GVideo | Qualcomm Incorporated |  | Thomas Stockhammer | 60397 | Work Plan | Agreement |  |  | 55 | 10.7 |  | available |  | FS_5GVideo (Feasibility Study on 5G Video Codec Characteristics) | 0 | available | 2020-03-31 04:32 | 2020-03-31 06:19 |  |  | Rel-17 |  |  | FS_5GVideo
S4-200559 | Proposed Skeleton TR26.9xx: 5G Video Characterization | Qualcomm Incorporated |  | Thomas Stockhammer | 60397 | discussion | Agreement |  |  | 55 | 10.7 |  | available |  | FS_5GVideo (Feasibility Study on 5G Video Codec Characteristics) | 0 | available | 2020-03-31 04:32 | 2020-03-31 10:59 |  |  | Rel-17 |  |  | FS_5GVideo
S4-200560 | Draft CR26.9xx 5GVideo Scenario Template | Qualcomm Incorporated | FG: should be a pCR | Thomas Stockhammer | 60397 | discussion | Agreement |  |  | 55 | 10.7 |  | available |  | FS_5GVideo (Feasibility Study on 5G Video Codec Characteristics) | 0 | available | 2020-03-31 04:32 | 2020-03-31 12:14 |  |  | Rel-17 |  |  | FS_5GVideo
S4-200561 | Draft CR26.9xx 5GVideo Scenario Full HD | Qualcomm Incorporated | FG: should be a pCR | Thomas Stockhammer | 60397 | discussion | Agreement |  |  | 55 | 10.7 |  | available |  | FS_5GVideo (Feasibility Study on 5G Video Codec Characteristics) | 0 | available | 2020-03-31 04:32 | 2020-03-31 21:46 |  |  | Rel-17 |  |  | FS_5GVideo
S4-200562 | 5G Video - Summary of Offline Discussions | Qualcomm Incorporated |  | Thomas Stockhammer | 60397 | discussion | Agreement |  |  | 55 | 10.7 |  | available |  | FS_5GVideo (Feasibility Study on 5G Video Codec Characteristics) | 0 | available | 2020-03-31 04:32 | 2020-03-31 16:27 |  |  | Rel-17 |  |  | FS_5GVideo
S4-200569 | 4K and 8K TV scenarios for FS_5GVideo | ATEME, InterDigital | FG: n/a, Late | Thibaud Biatek | 85719 | discussion | Agreement |  |  | 55 | 10.7 |  | reserved |  | FS_5GVideo (Feasibility Study on 5G Video Codec Characteristics) | 0 | reserved | 2020-03-31 11:33 |  |  |  | Rel-17 |  |  | FS_5GVideo
S4-200520 | New SID on 5G Glass-type AR/MR Devices | Samsung Electronics France SA | FG: Moved to Video SWG 10.8 | Hakju Ryan Lee | 66259 | SID new | Approval |  |  | 70 | 10.8 |  | available |  | New Work / New Work Items and Study Items | 0 | available | 2020-03-30 00:55 | 2020-03-31 07:02 |  |  | Rel-17
S4-200587 | Draft LS reply on QoS mapping procedure | Ericsson LM | NL: Agreed via email on April 2, 21:25 CEST | Frederic Gabin | 18030 | LS out | Approval |  |  | 63 | 11.3 | 20:00 4/2 | agreed | 5.2 | Reports and liaisons from other groups | 0 | available | 2020-03-31 13:38 | 2020-03-31 19:55 | [10 empty] | S4-200534 | CT3 | CT1 | S4-191277
S4-200570 | Correction of 3gpp-qos-hint examples | Ericsson LM | NL: Agreed via email on April 2, 21:33 CEST | Frederic Gabin | 18030 | CR | Agreement |  |  | 65 | 11.5 | 20:00 4/2 | agreed | 15.7 | CRs to completed features in Release 16 | 0 | available | 2020-03-31 13:38 | 2020-03-31 19:55 |  |  | Rel-16 | 26.114 | 16.5.2 | 5G_MEDIA_MTSI_ext | 0497 |  | F
S4-200571 | Bandwidth for open offer | Ericsson LM | FG: move to 11.5, NL: sent for email approval at 23:50 CEST April 2, request for more time by Orange | Frederic Gabin | 18030 | discussion | Agreement |  |  | 69 | 11.5 | 20:00 4/6 | available |  | Others including TEI | 0 | available | 2020-03-31 13:38 | 2020-03-31 19:55
S4-200608 | Setting b=AS in presence of an open offer | Fraunhofer IIS | FG: move to 11.5, NL: sent for email approval at 23:50 CEST April 2, request for more time by Orange | Stefan Doehla | 45140 | draftCR | Discussion |  |  | 69 | 11.5 | 20:00 4/6 | available |  | Others including TEI | 0 | available | 2020-03-31 20:13 | 2020-03-31 20:15 |  |  | Rel-16 | 26.114 | 16.5.2 | TEI16 |  |  | F
S4-200519 | Time Plan for E_FLUS Work Item v0.12.0 | QUALCOMM Incorporated (Rapporteur) |  | Nikolai Leung | 38562 | Work Plan | Agreement |  |  | 66 | 11.6 |  | available |  | E_FLUS (Enhancements to Framework for Live Uplink Streaming) | 0 | available | 2020-03-28 03:35 | 2020-03-31 19:29 |  |  | Rel-16 |  |  | E_FLUS
S4-200521 | Correction of References | Samsung R&D Institute India | NL: chair suggested to change Cat F to Cat D. Revised into S4-200644 | Hyun-Koo Yang | 86763 | CR | Agreement |  |  | 66 | 11.6 | 20:00 4/2 | revised |  | E_FLUS (Enhancements to Framework for Live Uplink Streaming) | 0 | available | 2020-03-30 07:36 | 2020-03-31 03:05 |  | S4-200644 | Rel-16 | 26.238 | 16.4.2 | E_FLUS | 0018 |  | F
S4-200644 | Correction of References | Samsung R&D Institute India |  | Hyun-Koo Yang | 86763 | CR | Agreement |  |  | 66 | 11.6 |  | reserved |  | E_FLUS (Enhancements to Framework for Live Uplink Streaming) | 0 | reserved | 2020-03-30 07:36 | 2020-03-31 03:05 |  |  | Rel-16 | 26.238 | 16.4.2 | E_FLUS | 0018 | 1 | D
S4-200523 | Clarification on uplink assistance | Samsung R&D Institute India | NL: Agreed via email on April 2, 21:48 CEST. Converting to a formal CR. | Hyun-Koo Yang | 86763 | draftCR | Agreement |  |  | 66 | 11.6 | 20:00 4/2 | revised |  | E_FLUS (Enhancements to Framework for Live Uplink Streaming) | 0 | available | 2020-03-30 07:52 | 2020-03-31 03:05 |  | S4-200645 | Rel-16 | 26.238 | 16.4.2 | E_FLUS |  |  | F
S4-200645 | Clarification on uplink assistance | Samsung R&D Institute India |  | Hyun-Koo Yang | 86763 | draftCR | Agreement |  |  | 66 | 11.6 |  | reserved |  | E_FLUS (Enhancements to Framework for Live Uplink Streaming) | 0 | reserved | 2020-03-30 07:52 | 2020-03-31 03:05 |  |  | Rel-16 | 26.238 | 16.4.2 | E_FLUS |  |  | F
S4-200524 | Update and correction of FLUS source systems | Samsung R&D Institute India | NL: sent for email agreement 23:50 on 4/2 | Hyun-Koo Yang | 86763 | draftCR | Agreement |  |  | 66 | 11.6 | 20:00 4/3 | available |  | E_FLUS (Enhancements to Framework for Live Uplink Streaming) | 0 | available | 2020-03-30 07:57 | 2020-03-31 03:05 |  |  | Rel-16 | 26.238 | 16.4.2 | E_FLUS |  |  | F
S4-200525 | Update, correction and clarification of text | Samsung R&D Institute India | NL: chair suggested to change Cat F to Cat D. Agreed and formalizing into a CR. | Hyun-Koo Yang | 86763 | draftCR | Agreement |  |  | 66 | 11.6 | 20:00 4/2 | revised |  | E_FLUS (Enhancements to Framework for Live Uplink Streaming) | 0 | available | 2020-03-30 08:02 | 2020-03-31 03:05 |  | S4-200646 | Rel-16 | 26.238 | 16.4.2 | E_FLUS |  |  | F
S4-200646 | Update, correction and clarification of text | Samsung R&D Institute India |  | Hyun-Koo Yang | 86763 | draftCR | Agreement |  |  | 66 | 11.6 |  | reserved |  | E_FLUS (Enhancements to Framework for Live Uplink Streaming) | 0 | reserved | 2020-03-30 08:02 | 2020-03-31 03:05 |  |  | Rel-16 | 26.238 | 16.4.2 | E_FLUS |  |  | F
S4-200550 | Sink Capabilities in FLUS | Tencent | NL: sent for email discussion to merge into S4-200643 | Iraj Sodagar | 83049 | CR | Approval | Fixing the lack of interoperability in the sink capabilities signaling. |  | 66 | 11.6 | 18:00 4/6 | reserved |  | E_FLUS (Enhancements to Framework for Live Uplink Streaming) | 0 | available | 2020-03-31 04:15 | 2020-03-31 18:00 |  |  | Rel-16 | 26.238 | 16.4.2 | E_FLUS | 0019 |  | C
S4-200551 | Sink Configuration in FLUS | Tencent | NL: sent for email discussion to merge into S4-200643 | Iraj Sodagar | 83049 | CR | Approval |  |  | 66 | 11.6 | 18:00 4/6 | reserved |  | E_FLUS (Enhancements to Framework for Live Uplink Streaming) | 0 | available | 2020-03-31 04:24 | 2020-03-31 18:04 |  |  | Rel-16 | 26.238 | 16.4.2 | E_FLUS | 0020 |  | F
S4-200578 | Correction of F-C Stage 3 | Ericsson LM | NL: sent for email discussion to merge into S4-200643 | Frederic Gabin | 18030 | draftCR | Agreement |  |  | 66 | 11.6 | 18:00 4/6 | available |  | E_FLUS (Enhancements to Framework for Live Uplink Streaming) | 0 | available | 2020-03-31 13:38 | 2020-03-31 19:55 |  |  | Rel-16 | 26.238 | 16.4.2 | E_FLUS
S4-200589 | Draft CR TS 26.238 Media Codec Profile for E_FLUS | QUALCOMM, Incorporated | NL: Agreed via email on April 2, 21:48 CEST. Revising into a formal CR in Tdoc S4-200642 | Nikolai Leung | 38562 | draftCR | Agreement |  |  | 66 | 11.6 | 20:00 4/2 | revised |  | E_FLUS (Enhancements to Framework for Live Uplink Streaming) | 0 | available | 2020-03-31 14:36 | 2020-03-31 19:29 |  | S4-200642 | Rel-16 | 26.238 | 16.4.2 | E_FLUS |  |  | B
S4-200642 | Media Codec Profile for E_FLUS | QUALCOMM, Incorporated |  | Nikolai Leung | 38562 | draftCR | Agreement |  |  | 66 | 11.6 |  | reserved |  | E_FLUS (Enhancements to Framework for Live Uplink Streaming) | 0 | available |  |  |  |  | Rel-16 | 26.238 | 16.4.2 | E_FLUS |  |  | B
S4-200603 | E_FLUS: Discovery of FLUS sinks using a Sink Discovery Server | Samsung Research America | NL: sent for email discussion to merge into S4-200643 | Prakash Kolan | 84349 | discussion |  |  |  | 66 | 11.6 | 18:00 4/6 | available |  | E_FLUS (Enhancements to Framework for Live Uplink Streaming) | 0 | available | 2020-03-31 18:36 | 2020-03-31 18:52 |  |  | Rel-16 | 26.238
S4-200604 | Discovery Server for FLUS Sinks | Samsung Research America | NL: sent for email discussion to merge into S4-200643 | Prakash Kolan | 84349 | draftCR |  |  |  | 66 | 11.6 | 18:00 4/6 | available |  | E_FLUS (Enhancements to Framework for Live Uplink Streaming) | 0 | available | 2020-03-31 18:44 | 2020-03-31 18:52 |  |  | Rel-16 | 26.238 | 16.4.2 | E_FLUS
S4-200613 | The resource addressing in FLUS | Tencent | NL: sent for email discussion to merge into S4-200643 | Iraj Sodagar | 83049 | draftCR | Approval |  |  | 66 | 11.6 | 18:00 4/6 | available |  | E_FLUS (Enhancements to Framework for Live Uplink Streaming) | 0 | available | 2020-03-31 21:50 | 2020-03-31 21:55 |  |  | Rel-16 | 26.238 | 16.4.2 | E_FLUS
S4-200506 | Proposed Timeplan for ITT4RT (v0.6.0) | Intel (Rapporteur) |  | Ozgur Oyman | 44803 | Work Plan | Agreement |  |  | 67 | 11.7 |  | available |  | ITT4RT (Support of Immersive Teleconferencing and Telepresence for Remote Terminals) | 0 | available | 2020-03-26 20:09 | 2020-03-31 18:07
S4-200507 | ITT4RT Permanent Document - Requirements, Working Assumptions and Potential Solutions (v0.6.0) | Intel (Rapporteur) | FG: revised before submission deadline | Ozgur Oyman | 44803 | other | Agreement |  |  | 67 | 11.7 |  | revised |  | ITT4RT (Support of Immersive Teleconferencing and Telepresence for Remote Terminals) | 0 | revised | 2020-03-26 20:11 | 2020-03-31 19:00 |  | S4-200609
S4-200508 | Updated ITT4RT WID | Intel, Nokia Corporation, Huawei Technologies Co. Ltd. |  | Ozgur Oyman | 44803 | WID revised | Agreement |  |  | 67 | 11.7 |  | available |  | ITT4RT (Support of Immersive Teleconferencing and Telepresence for Remote Terminals) | 0 | available | 2020-03-26 20:14 | 2020-03-30 18:03 |  |  | Rel-17 |  |  | ITT4RT
S4-200543 | Scene Description for Overlays and Beyond | Qualcomm India Pvt Ltd |  | Imed Bouazizi | 84417 | discussion |  |  |  | 67 | 11.7 |  | available |  | ITT4RT (Support of Immersive Teleconferencing and Telepresence for Remote Terminals) | 0 | available | 2020-03-30 15:56 | 2020-03-31 18:07
S4-200546 | ITT4RT: An Alternative Potential Solution on Viewport Information Signaling | Intel |  | Ozgur Oyman | 44803 | discussion | Agreement |  |  | 67 | 11.7 |  | available |  | ITT4RT (Support of Immersive Teleconferencing and Telepresence for Remote Terminals) | 0 | available | 2020-03-30 17:53 | 2020-03-30 18:03
S4-200595 | ITT4RT: Improvements of Signaling the FOV information using RTCP feedback | Tencent |  | Rohit Abhishek | 86016 | discussion | Agreement |  |  | 67 | 11.7 |  | available |  | ITT4RT (Support of Immersive Teleconferencing and Telepresence for Remote Terminals) | 0 | available | 2020-03-31 17:16 | 2020-03-31 17:26 |  |  | Rel-17
S4-200609 | ITT4RT Permanent Document - Requirements, Working Assumptions and Potential Solutions (v0.6.1) | Intel (Rapporteur) |  | Ozgur Oyman | 44803 | other | Agreement |  |  | 67 | 11.7 |  | available |  | ITT4RT (Support of Immersive Teleconferencing and Telepresence for Remote Terminals) | 0 | available | 2020-03-31 20:14 | 2020-03-31 20:28 | S4-200507
S4-200548 | Proposed Work Plan for FS_FLUS_NBMP | Tencent |  | Iraj Sodagar | 83049 | Work Plan | Agreement |  |  | 68 | 11.8 |  | available |  | FS_FLUS_NBMP (Feasibility Study on the use of NBMP in E_FLUS) | 0 | available | 2020-03-31 00:29 | 2020-03-31 00:52
S4-200549 | Workflow example for FS_FLUS_NBMP | Tencent | FG: revised before submission deadline | Iraj Sodagar | 83049 | CR | Approval |  |  | 68 | 11.8 |  | revised |  | FS_FLUS_NBMP (Feasibility Study on the use of NBMP in E_FLUS) | 0 | revised | 2020-03-31 01:36 | 2020-03-31 18:04 |  | S4-200607 | Rel-17 | 26.939 | 16.1.0 | FLUS | 0009 |  | B
S4-200552 | TR Skeleton | Tencent |  | Iraj Sodagar | 83049 | discussion | Agreement |  |  | 68 | 11.8 |  | available |  | FS_FLUS_NBMP (Feasibility Study on the use of NBMP in E_FLUS) | 0 | available | 2020-03-31 04:27 | 2020-03-31 17:40 |  |  | Rel-17
S4-200607 | Workflow example for FS_FLUS_NBMP | Tencent |  | Iraj Sodagar | 83049 | discussion | Agreement |  |  | 68 | 11.8 |  | available |  | FS_FLUS_NBMP (Feasibility Study on the use of NBMP in E_FLUS) | 0 | available | 2020-03-31 19:31 | 2020-03-31 19:38 | S4-200549 |  | Rel-17 | 26.939 |  | FLUS
S4-200616 | MBS SWG report at SA4#108-e | SA4 MBS SWG Chairman | FG: to be produced at the end of all MBS SWG sessions |  |  | report | Approval |  |  |  | 13.2
S4-200591 | Corrections and clarifications for consumption reporting | Tencent | FG: move to 7.4 | Zhuoyun Zhang | 78278 | CR | Approval |  |  | 92 | 7.4 |  | available |  | 5GMSA (5G Media streaming architecture) | 0 | available | 2020-03-31 15:26 | 2020-03-31 15:51 |  |  | Rel-16 | 26.501 | 16.3.1 | 5GMSA | 0016 |  | F
S4-200593 | Network assistance provided by 5GMSu AF | Tencent | FG: move to 7.4 | Zhuoyun Zhang | 78278 | CR | Approval |  |  | 92 | 7.4 |  | available |  | 5GMSA (5G Media streaming architecture) | 0 | available | 2020-03-31 15:37 | 2020-03-31 15:51 |  |  | Rel-16 | 26.501 | 16.3.1 | 5GMSA | 0017 |  | F
S4-200344 | Agenda for the SA4#108-e (Electronic Meeting) | Ericsson LM | FG: Withdrawn | Frederic Gabin | 18030 | agenda |  |  |  | 1 | 2 |  | withdrawn |  | Approval of the agenda and registration of documents | 0 | withdrawn | 2020-03-13 13:20
S4-200345 | Agenda for SA4#108-e (Electronic Meeting) | Ericsson LM | FG: Withdrawn | Frederic Gabin | 18030 | agenda | Approval |  |  | 1 | 2 |  | withdrawn |  | Approval of the agenda and registration of documents | 0 | withdrawn | 2020-03-13 13:24
S4-200401 | Agenda for SA4#108-e (Electronic Meeting) | Ericsson LM | FG: Withdrawn | Frederic Gabin | 18030 | agenda | Approval |  |  | 1 | 2 |  | withdrawn |  | Approval of the agenda and registration of documents | 0 | withdrawn | 2020-03-13 14:07
S4-200501 | Agenda for the Electronic Meeting SA4#108-e | SA4 Chairman (Ericsson) | FG: triggered and approved immediately by email 02/04 00:01 CEST. Has been available for 3 weeks. Note: request received to handle FS_XRTraffic under Video SWG from SA4#109 | Jayeeta Saha | 85340 | agenda | Approval |  |  | 1 | 2 | n/a | available |  | Approval of the agenda and registration of documents | 0 | approved | 2020-03-25 12:45 | 2020-03-25 12:52
S4-200527 | Guidelines for SA4#108-e as Electronic Meeting | SA WG4 Chairman, Vice-chairmen, Secretary and SWG chairmen | FG: triggered and noted immediately by email 02/04 00:01 CEST. | Frederic Gabin | 18030 | other | Information |  |  | 1 | 2 | n/a | available |  | Approval of the agenda and registration of documents | 0 | noted | 2020-03-30 12:28 | 2020-03-30 14:00
S4-200547 | Invitation Links (GTM) to the SA4#108-e Meeting from April 06-09,2020 | 3GPP MCC | FG: triggered and noted immediately by email 02/04 00:01 CEST. | Jayeeta Saha | 85340 | other | Information |  | This document contains the meeting links for SA4#108-e from April 06 - 09, 2020 | 1 | 2 | n/a | available |  | Approval of the agenda and registration of documents | 0 | noted | 2020-03-30 20:13 | 2020-03-31 21:27
S4-200502 | Draft report of SA4#107 held in Wroclaw | 3GPP MCC | FG: triggered by email 02/04 11:08 CEST. Deadline 03/04 0900 CEST. FG: no comments received. Approved. | Jayeeta Saha | 85340 | report | Approval |  |  | 3 | 4 | n/a | available |  | Approval of previous meeting report | 0 | approved | 2020-03-25 13:07 | 2020-03-31 18:07
S4-200515 | Draft Report for MTSI SWG 11 Feb 2020 Teleconference #4 on ITT4RT | MTSI SWG Chair | FG: triggered by email 02/04 11:08 CEST. Deadline 03/04 0900 CEST. FG: no comments received. Approved. | Nikolai Leung | 38562 | report | Approval |  |  | 5 | 5.1 | n/a | available |  | SA4 SWG ad hoc meetings | 0 | approved | 2020-03-28 03:35 | 2020-03-31 19:29
S4-200516 | Draft Report for MTSI SWG 26 Feb 2020 Teleconference #2 on RTCPVer | MTSI SWG Chair | FG: triggered by email 02/04 11:08 CEST. Deadline 03/04 0900 CEST. FG: no comments received. Approved. | Nikolai Leung | 38562 | report | Approval |  |  | 5 | 5.1 | n/a | available |  | SA4 SWG ad hoc meetings | 0 | approved | 2020-03-28 03:35 | 2020-03-31 19:29
S4-200517 | Draft Report for MTSI SWG 20 March 2020 Teleconference #5 on ITT4RT | MTSI SWG Chair | FG: triggered by email 02/04 11:08 CEST. Deadline 03/04 0900 CEST. FG: no comments received. Approved. | Nikolai Leung | 38562 | report | Approval |  |  | 5 | 5.1 | n/a | available |  | SA4 SWG ad hoc meetings | 0 | approved | 2020-03-28 03:35 | 2020-03-31 19:29
S4-200518 | Draft Report for MTSI-MBS SWG 23 Mar 2020 Teleconference #12 on E_FLUS | MTSI SWG Chair | FG: triggered by email 02/04 11:08 CEST. Deadline 03/04 0900 CEST. FG: no comments received. Approved. | Nikolai Leung | 38562 | report | Approval |  |  | 5 | 5.1 | n/a | available |  | SA4 SWG ad hoc meetings | 0 | approved | 2020-03-28 03:35 | 2020-03-31 19:29
S4-200581 | Report of SA4 SQ SWG conf. call on HaNTE (3rd March 2020) | SA4 SQ SWG interim Chairman | FG: triggered by email 02/04 11:29 CEST. Deadline 03/04 0900 CEST. FG: no comments received. Approved. | Frederic Gabin | 18030 | report | Approval |  |  | 5 | 5.1 | n/a | available |  | SA4 SWG ad hoc meetings | 0 | approved | 2020-03-31 13:38 | 2020-03-31 14:53 | [5 empty] | HaNTE
S4-200582 | Report of MBS SWG ad-hoc telco on FS_TyTrac (31st January 2020) | SA4 MBS SWG Chairman | FG: triggered by email 02/04 11:30 CEST. Deadline 03/04 0900 CEST. FG: no comments received. Approved. | Frederic Gabin | 18030 | report | Approval |  |  | 5 | 5.1 | n/a | available |  | SA4 SWG ad hoc meetings | 0 | approved | 2020-03-31 13:38 | 2020-03-31 14:53 | [5 empty] | FS_TyTrac
S4-200583 | Report of SA4 MBS SWG Telco on 5GMS3 (6th February 2020) | SA4 MBS SWG Chairman | FG: triggered by email 02/04 11:37 CEST. Deadline 03/04 0900 CEST. FG: no comments received. Approved. | Frederic Gabin | 18030 | report | Approval |  |  | 5 | 5.1 | n/a | available |  | SA4 SWG ad hoc meetings | 0 | approved | 2020-03-31 13:38 | 2020-03-31 14:53 | [5 empty] | 5GMS3
S4-200584 | Report of SA4 MBS SWG Telco on 5GMS3 (13th February 2020) | SA4 MBS SWG Chairman | FG: triggered by email 02/04 11:37 CEST. Deadline 03/04 0900 CEST. FG: no comments received. Approved. | Frederic Gabin | 18030 | report | Approval |  |  | 5 | 5.1 | n/a | available |  | SA4 SWG ad hoc meetings | 0 | approved | 2020-03-31 13:38 | 2020-03-31 14:53 | [5 empty] | 5GMS3
S4-200585 | Report of SA4 MBS SWG Telco on 5GMS3 (12th March 2020) | SA4 MBS SWG Chairman | FG: triggered by email 02/04 11:37 CEST. Deadline 03/04 0900 CEST. FG: no comments received. Approved. | Frederic Gabin | 18030 | report | Approval |  |  | 5 | 5.1 | n/a | available |  | SA4 SWG ad hoc meetings | 0 | approved | 2020-03-31 13:38 | 2020-03-31 14:53 | [5 empty] | 5GMS3
S4-200586 | Report of SA4 MBS SWG Telco on 5GMS3 (27th March 2020) | SA4 MBS SWG Chairman | FG: triggered by email 02/04 11:37 CEST. Deadline 03/04 0900 CEST. FG: no comments received. Approved. | Frederic Gabin | 18030 | report | Approval |  |  | 5 | 5.1 | n/a | available |  | SA4 SWG ad hoc meetings | 0 | approved | 2020-03-31 13:38 | 2020-03-31 14:53 | [5 empty] | 5GMS3
S4-200526 | Brief report from SA#87-e on SA4 matters | SA4 Chairman (Ericsson) | FG: triggered by email 02/04 11:41 CEST. Deadline 03/04 0900 CEST. Email comment by Thomas Stockhammer <tsto@qti.qualcomm.com> For information wrt to this document and specifically with respect to slide 4: “TD SP 200049 was revised to SP 200263 TS 26.117 5G Media Streaming (5GMS); Speech and Audio Profiles, v2.0.1 (Release 16) for editorial modifications.” - I have uploaded the diff between the SA4 agreed doc 1.1.0 and the one that was finally approved 2.0.1 to the drafts folder: https://www.3gpp.org/Ftp/tsg_sa/WG4_CODEC/TSGS4_108-e/Inbox/Drafts/26.117-201-diff-110.docx - The bugfixes were predominantly wrong references as well as the cover page said Technical Report instead of Technical Specification. - Thanks for Jayeeta and the editHelp team for catching this Otherwise, I have no comments. | Jayeeta Saha | 85340 | report | Information |  |  | 6 | 5.2 | n/a | available |  | Other 3GPP groups | 0 | noted | 2020-03-30 08:47 | 2020-03-30 17:19
S4-200530 | Reply LS on support for eCall over NR | TSG SA | FG: triggered by email 02/04 11:41 CEST. Deadline 03/04 0900 CEST. To be noted FG: no comments received. | Jayeeta Saha | 85340 | LS in | Action | This LS is regarding to find any limitation either from performance or regulatory perspective to support eCall over IMS (NG-eCall) over NR. TSG SA believes that the changes required in order to allow support for eCall over IMS (NG-eCall) over NR are minimal. CRs should be prepared for TSGs #88 in June 2020 in order to maximise the possibility of including this in Release 16. TSG SA therefore requests the involved WGs (SA2, SA5, RAN2, CT1, RAN5) to identify specification changes needed to support eCall in IMS over NR (with 5G Core) and to prepare the required CRs. |  | 6 | 5.2 | n/a | available |  | Other 3GPP groups | 0 | noted | 2020-03-30 14:42 | 2020-03-30 19:21 |  |  | Rel-16
S4-200532 | LS on support for eCall over NR | SA WG2 | FG: triggered by email 02/04 11:41 CEST. Deadline 03/04 0900 CEST. To be noted FG: no comments received. | Jayeeta Saha | 85340 | LS in | Action | In Release 14, support for eCall was extended from the CS domain to eCall in IMS over LTE access. In Release 15 the related functionality for eCall in IMS was specified for the 5G System. However Release 15 TS 23.501 prohibits eCall in IMS over NR with 5GCore (see annex 2). This prohibition was included because there were concerns that the relevant studies had not been performed by other working groups (e.g. by SA WG4 or by ETSI groups) for performance of eCall over NR. As a result, the 5GS in Release 15 only supports eCall in IMS over LTE. As eCall devices (e.g. cars) can have a long life, in order to allow the refarming of spectrum from LTE to NR and/or the removal of the CS domain core network, SA WG2 believes that 3GPP work should be undertaken to remove this restriction on the use of NR. Hence SA WG2 invites TSG SA to coordinate and potentially task other WGs, e.g. SA WG4, to investigate whether they see any problems with 3GPP introducing support for eCall in IMS over NR with 5GCore. |  | 6 | 5.2 | n/a | available |  | Other 3GPP groups | 0 | noted | 2020-03-30 14:42 | 2020-03-30 19:19
S4-200534 | LS Reply on QoS mapping procedure for FLUS | CT WG3 | FG: triggered by email 02/04 15:19 CEST. Deadline 03/04 1200 CEST. To be allocated to MTSI SWG | Jayeeta Saha | 85340 | LS in |  | This LS is regarding the LS (C3-201033/S4-191277) on QoS mapping procedure for FLUS from SA4. CT3 has mentioned that, the group has studied the subject and specified the functionality in the agreed CRs. The functionality has been specified according to the following principles: - SDP media level "a=label:flus" is conveyed to the PCRF/PCF as a new FLUS identifier included at media component level. - SDP media level "3gpp-qos-hint" attribute is conveyed to the PCRF/PCF as two separate parameters to indicate the desired maximum latency and desired maximum loss rate for the related media. - FLUS identifier and optionally information on desired maximum latency and/or desired maximum loss rate may be used by the PCRF/PCF to derive QCI/5QI information. - New QCI values have been defined in order to consider specific values for FLUS and get aligned with SA2 TS 23.203. |  | 6 | 5.2 | 03APR 1200 | available |  | Other 3GPP groups | 0 | available | 2020-03-30 14:42 | 2020-03-30 19:20 |  |  | Rel-16 | [11 empty] | S4-200587
S4-200531 | LS/o on synchronization of Y.DNI-fr “Framework and Requirements of Decentralized Trustworthy Network Infrastructure” in Q2/13 | ITU-T Study Group 13 | FG: triggered by email 02/04 15:53 CEST. Deadline 03/04 1200 CEST. To be noted | Jayeeta Saha | 85340 | LS in | Action | This document contains ITU-T Recommendation Y.DNI-fr: “Framework and Requirements of Decentralized Trustworthy Network infrastructure”, output of Q2/13 meeting, Geneva, 2-13 Mar 2020. This output draft is based on TD332(WP3/13), output of Q2/13 meeting, Geneva, 14-25 Oct, 2019, and amendments according to 2-13 March Q2/13 Rapporteur meeting agreements based on meeting discussions and review of contribution from Huawei |  | 7 | 5.3 | 03APR 1200 | available |  | Other groups | 0 | available | 2020-03-30 14:42 | 2020-03-30 19:19
S4-200533 | Common Media Client Data CTA-5004 (community review) | Consumer Technology Association’s WAVE | FG: triggered by email 02/04 15:57 CEST. Deadline 03/04 1200 CEST. To be allocated to MBS SWG | Jayeeta Saha | 85340 | LS in | Action | For the past six months, the Consumer Technology Association’s WAVE project has had a Work Group developing the “CTA-5004 Common Media Client Data” specification. This standard defines a simple means by which every media player can communicate data with each media object request and have it received and processed consistently by every CDN. This information can be useful in log analysis, QoS monitoring and delivery optimization. Session identification allows thousands of individual server log lines to be interpreted as a single user session, leading to a clearer picture of end-user quality of service. Bitrate, buffer and segment signaling allow CDNs to fine-tune and optimize their midgress traffic by intelligently reacting to the time constraints implicit in each request. Device and content IDs across a multi-CDN delivery surface allow performance problems to be cross-correlated with player software versions or specific devices. In combination, this transferred data should improve the quality-of-service offered by CDNs, which in turn will improve the quality-of-experience enjoyed by consumers. SA4 members are asked to review the document for clarity, applicability and to file any issues at https://github.com/cta-wave/common-media-client-data/issues, clearly identifying who they are and what organization they represent. At this stage we are not looking for input on new parameters to include in this first version, but rather whether the existing parameters are clear, useful and practical. All feedback should be received by April 6th. |  | 7 | 5.3 | 03APR 1200 | available |  | Other groups | 0 | available | 2020-03-30 14:42 | 2020-03-30 19:20
S4-200535 | LS about the availability of ISG ARF reference architecture for an AR solution | ETSI ISG ARF (Augmented Reality Framework) | FG: triggered by email 02/04 15:59 CEST. Deadline 03/04 1200 CEST. To be allocated to Video SWG | Jayeeta Saha | 85340 | LS in | Action | ETSI Industry Specification Group AR Framework (ISG ARF) is currently developing a framework for the interoperability of AR components, systems and services and would like to inform your organization of the availability for community review of the final draft of the reference architecture it has developed. The final draft specification is availble in the link below:https://docbox.etsi.org/ISG/ARF/Open/ARF-003v0034.pdf The same has been sent to 3GPP SA4 for necessary actions regaridng the same. |  | 7 | 5.3 | 03APR 1200 | available |  | Other groups | 0 | available | 2020-03-30 14:42 | 2020-03-30 19:20
S4-200536 | Liaison Statement from SC 29/WG 11 to 3GPP SA4 on CMAF [SC 29/WG 11 N 19163] | ISO/IEC JTC 1/SC 29/WG 11 | FG: triggered by email 02/04 15:25 CEST together with postponed LS 016. Deadline 03/04 1200 CEST. To be noted. | Jayeeta Saha | 85340 | LS in | Information | In accordance with Recommendation 21.4.2 at the 129th WG 11 Meeting, 2020-01- 13/17, Brussels, Belgium, the SC 29 Secretariat sends this liaison statement to 3GPP SA4. [Requested action: For SC 29's information] |  | 7 | 5.3 | 03APR 1200 | available |  | Other groups | 0 | available | 2020-03-30 14:42 | 2020-03-30 19:20
S4-200537 | Audio ‘Headset’ Requirements in 3GPP TS 26.132 | GCF CAG#61 | FG: for action. Draft reply proposed in 605. To be handled by SQ SWG FG: triggered by email 02/04 16:04 CEST. Deadline 03/04 1200 CEST. To be allocated to SQ SWG | Jayeeta Saha | 85340 | LS in | Action | Concerns within the GCF membership regarding the ‘Headset’ requirements referenced in TS26.132 which have been used in GCF’s audio work item (WI-252). GCF CAG would like to kindly ask 3GPP SA4’s opinion on 1. Suitability of above test cases for inclusion as conformance tests given the concerns raised as outlined in the above summary. 2. If the above test cases are performance test cases rather than conformance. |  | 7 | 5.3 | 03APR 1200 | available |  | Other groups | 0 | available | 2020-03-30 14:42 | 2020-03-30 19:20
S4-200538 | Liaison to 3GPP SA4 PHASE 1 TECHNICAL SPECIFICATION ON ABR MULTICAST | DVB Technical Module, TM-Mcast | FG: for information. CR proposed separatly. Proposed to be noted. Trigger 02/04 am | Jayeeta Saha | 85340 | LS in | Action | DVB Project recently published a new technical specification on the use of dynamic adaptive media streaming in IP-based networks - BlueBook A176 (second edition) whch specifies data plane and control plane operations, a session configuration document schema and two mandatory multicast media transport protocols. In particular, the media transport protocol specified in Annex F is based on the MBMS Download Profile that 3GPP has specified in TS 26.346 Annex L.4. Comments from SA4 on use of the 3GPP FLUTE profile are invited. Some minor issues with the MBMS Download Profile has been identified and 3GPP members participating in DVB TM-Mcast would like to propose a draft Change Request to the SA4 MBS subworking group in due course to address these issues |  | 7 | 5.3 |  | available |  | Other groups | 0 | available | 2020-03-30 14:42 | 2020-03-30 19:21
S4-200605 | Draft reply LS on Audio Headset Requirements in 3GPP TS 26.132 | Sony Corporation | FG: proposed reply to 537. To be handled by SQ SWG. FG: triggered by email 02/04 16:04 CEST. Deadline 03/04 1200 CEST. To be allocated to SQ SWG | Peter Isberg | 82130 | LS out | Agreement |  |  | 7 | 5.3 | 03APR 1200 | available |  | Other groups | 0 | available | 2020-03-31 18:50 | 2020-03-31 18:53 | [11 empty] | GCF CAG |  | S4-200537
S4-200528 | Draft EVS SWG Agenda | EVS SWG Chairman |  | Imre Varga | 16587 | agenda |  |  |  | 9 | 7 |  | available |  | Enhanced Voice Service (EVS) SWG | 0 | available | 2020-03-30 13:09 | 2020-03-30 13:15
S4-200566 | Two field issues with EVS - Revised | HuaWei Technologies Co., Ltd |  | Huan-yu Su | 79844 | other | Agreement |  |  | 12 | 7.3 |  | available |  | CRs to Features in Release 15 and earlier | 0 | available | 2020-03-31 05:40 | 2020-03-31 05:58 | S4-200128
S4-200592 | Corrections to EVS Fixed-Point Source Code | Ericsson LM, Fraunhofer IIS, VoiceAge Corporation |  | Markus Multrus | 59926 | draftCR | Discussion |  |  | 12 | 7.3 |  | available |  | CRs to Features in Release 15 and earlier | 0 | available | 2020-03-31 15:33 | 2020-03-31 15:36 |  |  | Rel-16 | 26.442 | 15.1.0 | EVS_codec |  |  | F
S4-200610 | dCR 26445 Clarifications on ch-aw-recv | Orange |  | Stephane Ragot | 32055 | draftCR | Agreement |  |  | 12 | 7.3 |  | available |  | CRs to Features in Release 15 and earlier | 0 | available | 2020-03-31 21:03 | 2020-03-31 21:09 |  |  | Rel-16 | 26.445 | 16.0.0 | EVS_codec |  |  | F
S4-200539 | CR on Domain Model for Uplink Streaming | Qualcomm India Pvt Ltd | FG: moved to 8.6 | Imed Bouazizi | 84417 | CR |  |  |  | 13 | 8.6 |  | available |  | CRs to completed features in Release 16 | 0 | available | 2020-03-30 15:29 | 2020-03-31 18:07 |  |  | Rel-16 | 26.501 | 16.3.1 | 5GMSA | 0013 |  | F
S4-200541 | Corrections to Stage 2 Ingest Configuration Procedures | Qualcomm India Pvt Ltd | FG: moved to 8.6 | Imed Bouazizi | 84417 | CR |  |  |  | 13 | 8.6 |  | available |  | CRs to completed features in Release 16 | 0 | available | 2020-03-30 15:51 | 2020-03-31 18:07 |  |  | Rel-16 | 26.501 | 16.3.1 | 5GMSA | 0014 |  | F
S4-200503 | The Acoustics Research Institute | VoiceAge Corporation |  | Piotr Majdak | 86790 | discussion | Information | This document provides a brief introduction of the Acoustics Research Institute of the Austrian Academy of Sciences |  | 15 | 7.6 |  | available |  | IVAS_Codec (EVS Codec Extension for Immersive Voice and Audio Services) | 0 | available | 2020-03-25 18:04 | 2020-03-31 11:16
S4-200529 | Discussions on the IVAS Standardization Process | EVS SWG Chairman |  | Imre Varga | 16587 | discussion | Information |  |  | 15 | 7.6 |  | available |  | IVAS_Codec (EVS Codec Extension for Immersive Voice and Audio Services) | 0 | available | 2020-03-30 13:11 | 2020-03-30 13:15
S4-200599 | On the potential public collaboration for IVAS standardization | Nokia Corporation |  | Lasse Laaksonen | 45550 | discussion | Discussion |  |  | 15 | 7.6 |  | available |  | IVAS_Codec (EVS Codec Extension for Immersive Voice and Audio Services) | 0 | available | 2020-03-31 18:09 | 2020-03-31 19:55
S4-200544 | Draft TR proposal for Edge Media Processing | Qualcomm India Pvt Ltd | FG: low priority. to be triggered when time allows. | Imed Bouazizi | 84417 | discussion |  |  |  | 29 | 8.10 |  | available |  | FS_EMSA (Feasibility Study on Streaming Architecture extensions For Edge processing) | 0 | available | 2020-03-30 15:59 | 2020-03-31 21:46
S4-200545 | Timeplan Proposal for Edge Media Processing | Qualcomm India Pvt Ltd | FG: Late | Imed Bouazizi | 84417 | discussion |  |  |  | 29 | 8.10 |  | available |  | FS_EMSA (Feasibility Study on Streaming Architecture extensions For Edge processing) | 0 | available | 2020-03-30 16:14 | 2020-03-31 22:09
S4-200596 | Edge Computing for Content Hosting and Caching | KPN N.V. | FG: low priority. to be triggered when time allows. | Jan Willem Kleinrouweler | 79278 | discussion | Agreement |  |  | 29 | 8.10 |  | available |  | FS_EMSA (Feasibility Study on Streaming Architecture extensions For Edge processing) | 0 | available | 2020-03-31 17:25 | 2020-03-31 17:27
S4-200512 | Add sample percentage to 5GMSA stage 2 Consumption Reporting | BBC | FG: revised before submission deadline | Richard Bradbury | 82569 | draftCR | Agreement | • Reduce impact of consumption reporting mechanism on the network. • Harmonisation of consumption reporting design with QoE metrics reporting. |  | 25 | 8.6 |  | revised |  | CRs to completed features in Release 16 | 0 | revised | 2020-03-27 19:30 | 2020-03-30 16:34 |  | S4-200594 | Rel-16 | 26.501 | 16.3.0 | 5GMSA |  |  | C
S4-200568 | Rename Ingest Session Configuration as Content Hosting Configuration | BBC | FG: revised before submission deadline | Richard Bradbury | 82569 | draftCR | Agreement | Align name of configuration in the domain model with stage 2 feature name. Textual modification and replacement figure. |  | 25 | 8.6 |  | revised |  | CRs to completed features in Release 16 | 0 | revised | 2020-03-31 11:11 | 2020-03-31 11:32 |  | S4-200597 | Rel-16 | 26.501 | 16.3.1 | 5GMSA |  |  | D
S4-200572 | Correction of Provisioning Session Concept | Ericsson LM, BBC | FG: high priority. To be triggered. | Frederic Gabin | 18030 | draftCR | Agreement |  |  | 25 | 8.6 |  | available |  | CRs to completed features in Release 16 | 0 | available | 2020-03-31 13:38 | 2020-03-31 19:55 |  |  | Rel-16 | 26.501 | 16.3.1 | 5GMSA
S4-200575 | Discussion of Multi-MNO Distribution Scenario | Ericsson LM | FG: high priority. To be triggered. | Frederic Gabin | 18030 | discussion | Agreement |  |  | 25 | 8.6 |  | available |  | CRs to completed features in Release 16 | 0 | available | 2020-03-31 13:38 | 2020-03-31 19:55 | [5 empty] | 5GMSA
S4-200576 | Collaboration Model: Multi-MNO Distribution | Ericsson LM | FG: high priority. To be triggered. | Frederic Gabin | 18030 | draftCR | Agreement |  |  | 25 | 8.6 |  | available |  | CRs to completed features in Release 16 | 0 | available | 2020-03-31 13:38 | 2020-03-31 19:55 |  |  | Rel-16 | 26.501 | 16.3.1 | 5GMSA
S4-200579 | Correction on xMB for MCData | Ericsson LM | FG: high priority. To be triggered 02/04 am | Frederic Gabin | 18030 | draftCR | Agreement |  |  | 25 | 8.6 |  | available |  | CRs to completed features in Release 16 | 0 | available | 2020-03-31 13:38 | 2020-03-31 19:55 |  |  | Rel-16 | 26.348 | 16.3.0 | MC_XMB
S4-200580 | Correction on Annex L.4 (MBMS Download Profile) | Ericsson LM | FG: high priority. To be triggered 02/04 am | Frederic Gabin | 18030 | draftCR | Agreement |  |  | 25 | 8.6 |  | available |  | CRs to completed features in Release 16 | 0 | available | 2020-03-31 13:38 | 2020-03-31 19:55 |  |  | Rel-16 | 26.346 | 16.4.1 | TEI16
S4-200590 | Corrections on network slicing | Tencent | FG: high priority. To be triggered. | Zhuoyun Zhang | 78278 | CR | Approval |  |  | 25 | 8.6 |  | available |  | CRs to completed features in Release 16 | 0 | available | 2020-03-31 14:45 | 2020-03-31 15:51 |  |  | Rel-16 | 26.501 | 16.3.1 | 5GMSA | 0015 |  | F
S4-200594 | Add sample percentage to 5GMSA stage 2 Consumption Reporting | BBC | FG: high priority. To be triggered. | Richard Bradbury | 82569 | draftCR | Agreement | • Reduce impact of consumption reporting mechanism on the network. • Harmonisation of consumption reporting design with QoE metrics reporting. |  | 25 | 8.6 |  | available |  | CRs to completed features in Release 16 | 0 | available | 2020-03-31 15:43 | 2020-03-31 15:49 | S4-200512 |  | Rel-16 | 26.501 | 16.3.1 | 5GMSA |  |  | C
S4-200597 | Rename Ingest Session Configuration as Content Hosting Configuration | BBC | FG: high priority. To be triggered. | Richard Bradbury | 82569 | draftCR | Agreement | Align name of configuration in the domain model with stage 2 feature name. Textual modifications to various clauses and replacement Figure 5.3.1-1. |  | 25 | 8.6 |  | available |  | CRs to completed features in Release 16 | 0 | available | 2020-03-31 17:45 | 2020-03-31 18:04 | S4-200568 |  | Rel-16 | 26.501 | 16.3.1 | 5GMSA |  |  | D
S4-200601 | 5GMSA Network Assistance | Sony Europe B.V. | FG: high priority. To be triggered. | Paul Szucs | 82030 | draftCR | Agreement |  |  | 25 | 8.6 |  | available |  | CRs to completed features in Release 16 | 0 | available | 2020-03-31 18:21 | 2020-03-31 19:29 |  |  | Rel-16 | 26.501 | 16.3.1 | 5GMSA |  |  | F
S4-200602 | 5GMSA Remote Control | Sony Europe B.V., Ericsson LM | FG: high priority. To be triggered. | Paul Szucs | 82030 | draftCR | Agreement |  |  | 25 | 8.6 |  | available |  | CRs to completed features in Release 16 | 0 | available | 2020-03-31 18:28 | 2020-03-31 19:29 |  |  | Rel-16 | 26.501 | 16.3.1 | 5GMSA |  |  | C
S4-200509 | Draft TS 26.512 5G Media Streaming (5GMS); Protocols | Ericsson Japan K.K. | FG: high priority. To be triggered. FG: triggered by email 02/04 16:20 CEST. Deadline 03/04 1200 CEST. To be agreed as basis for further work | Thorsten Lohmar | 59317 | draft TS |  |  |  | 26 | 8.7 | 03APR 1200 | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-27 14:16 | 2020-03-27 14:24 |  |  | Rel-16 | 26.512 | 1.0.1 | 5GMS3
S4-200510 | Draft TR 26.511 5GMS Profiles, Codecs and Formats v1.2.0 | Orange | FG: high priority. To be triggered. FG: triggered by email 02/04 16:26 CEST. Deadline 03/04 1200 CEST. To be agreed as basis for further work | Gilles Teniou | 41772 | draft TR | Agreement | Draft TR implementing the agreements from the MBS SWG teleconference. To be considered as the starting point for SA4#108-e |  | 26 | 8.7 | 03APR 1200 | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-27 17:26 | 2020-03-27 17:30 |  |  | Rel-16 | 26.511 | 1.2.0 | 5GMS3
S4-200511 | 5GMSA Domain Model and API Design Principles | BBC | FG: high priority. To be triggered. | Richard Bradbury | 82569 | discussion | Agreement | - Update to 5G Media Streaming domain model for review and discussion. - Modified proposal for RESTful API resource hierarchy at interface M1d, for agreement. |  | 26 | 8.7 |  | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-27 19:09 | 2020-03-30 16:54 |  |  | Rel-16 |  |  | 5GMSA
S4-200513 | Renaming entities in the 5GMS Provisioning API | BBC | FG: high priority. To be triggered. | Richard Bradbury | 82569 | pCR | Agreement | The names of some entities in the object model are confusing. This change aligns the terminology with that of the phase 2 architecture. TS 26.501 defines a high-level feature called "Content Hosting", so the object model should follow suit. |  | 26 | 8.7 |  | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-27 19:49 | 2020-03-30 17:15 |  |  | Rel-16 | 26.512 | 1.0.1 | 5GMS3
S4-200514 | Additional clauses to specify procedures for manipulating Ingest Protocols, Content Preparation Templates and Server Certificates | BBC | FG: high priority. To be triggered. | Richard Bradbury | 82569 | pCR | Agreement | Document procedures for manipulating M1d RESTful resources describing Ingest Protocols, Content Preparation Templates and Server Certificates. |  | 26 | 8.7 |  | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-27 19:57 | 2020-03-30 17:25 |  |  | Rel-16 | 26.512 | 1.0.1 | 5GMS3
S4-200522 | 5GMS3: Video Codec Support | Huawei Technologies Co. Ltd.; Samsung Electronics Co. Ltd. | FG: high priority. To be triggered. | Yidan Teng | 86794 | discussion |  |  |  | 26 | 8.7 |  | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-30 07:48 | 2020-03-31 02:32
S4-200540 | RAN Signaling-based Network Assistance | Qualcomm India Pvt Ltd | FG: high priority. To be triggered. | Imed Bouazizi | 84417 | pCR | Agreement |  |  | 26 | 8.7 |  | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-30 15:34 | 2020-03-31 21:44 |  |  | Rel-16 | 26.512 | 1.0.0 | 5GMS3
S4-200542 | Dynamic Policy Configuration Procedures | Qualcomm India Pvt Ltd | FG: high priority. To be triggered. | Imed Bouazizi | 84417 | pCR |  |  |  | 26 | 8.7 |  | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-30 15:53 | 2020-03-31 20:50 |  |  | Rel-16 | 26.512 | 1.0.0 | 5GMS3
S4-200553 | Client APIs for 5GMS | Qualcomm Incorporated | FG: high priority. To be triggered. | Thomas Stockhammer | 60397 | pCR | Agreement |  |  | 26 | 8.7 |  | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-31 04:32 | 2020-03-31 21:55 |  |  | Rel-16 | 26.512 | 1.0.0 | 5GMS3
S4-200554 | DASH/CMAF in 5GMS | Qualcomm Incorporated | FG: high priority. To be triggered. | Thomas Stockhammer | 60397 | pCR | Agreement |  |  | 26 | 8.7 |  | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-31 04:32 | 2020-03-31 21:45 |  |  | Rel-16 | 26.512 | 1.0.0 | 5GMS3
S4-200555 | Proposed Updates to TV Video Profiles | Qualcomm Incorporated | FG: high priority. To be triggered. | Thomas Stockhammer | 60397 | pCR | Agreement |  |  | 26 | 8.7 |  | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-31 04:32 | 2020-03-31 19:40 |  |  | Rel-16 | 26.511 | 1.1.0 | 5GMS3
S4-200556 | Proposed Updates to Subtitles | Qualcomm Incorporated | FG: high priority. To be triggered. | Thomas Stockhammer | 60397 | pCR | Agreement |  |  | 26 | 8.7 |  | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-31 04:32 | 2020-03-31 18:33 |  |  | Rel-16 | 26.511 | 1.1.0 | 5GMS3
S4-200557 | Proposed General Updates | Qualcomm Incorporated | FG: high priority. To be triggered. | Thomas Stockhammer | 60397 | pCR | Agreement |  |  | 26 | 8.7 |  | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-31 04:32 | 2020-03-31 19:45 |  |  | Rel-16 | 26.511 | 1.1.0 | 5GMS3
S4-200573 | Review of N5 / N33 parameters and discussion of Policy Template realizations | Ericsson LM | FG: high priority. To be triggered. | Frederic Gabin | 18030 | discussion | Agreement |  |  | 26 | 8.7 |  | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-31 13:38 | 2020-03-31 19:55 | [5 empty] | 5GMS3
S4-200574 | M1d Procedure for Dynamic Policy Provisioning | Ericsson LM | FG: high priority. To be triggered. | Frederic Gabin | 18030 | pCR | Agreement |  |  | 26 | 8.7 |  | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-31 13:38 | 2020-03-31 19:55 |  |  | Rel-16 | 26.512 | 1.0.1 | 5GMS3
S4-200577 | API for Service Access information aquisition | Ericsson LM | FG: high priority. To be triggered. | Frederic Gabin | 18030 | pCR | Agreement |  |  | 26 | 8.7 |  | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-31 13:38 | 2020-03-31 19:55 |  |  | Rel-16 | 26.512 | 1.0.1 | 5GMS3
S4-200588 | Consumption Reporting Procedure API- M1d and M5d | ENENSYS | FG: high priority. To be triggered. | Cedric THIENOT | 82595 | draftCR | Agreement |  |  | 26 | 8.7 |  | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-31 14:19 | 2020-03-31 15:53 |  |  | Rel-16 | 26.512 | 1.0.1 | 5GMS3
S4-200600 | 5GMS3 Work Plan V0.10 | Sony Europe B.V. | FG: high priority. To be triggered. FG: triggered by email 02/04 16:34 CEST. Deadline 03/04 1200 CEST. To be agreed as basis for further work | Paul Szucs | 82030 | Work Plan | Agreement |  |  | 26 | 8.7 | 03APR 1200 | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-31 18:15 | 2020-03-31 19:29 |  |  | Rel-16 |  |  | 5GMS3
S4-200611 | Procedure for the OpenAPI implementation of the 5GMS APIs | Qualcomm India Pvt Ltd | FG: high priority. To be triggered. | Imed Bouazizi | 84417 | discussion |  |  |  | 26 | 8.7 |  | available |  | 5GMS3 (5G Media Streaming stage 3) | 0 | available | 2020-03-31 21:04 | 2020-03-31 21:07
S4-200598 | Proposed Work Plan for FS_5GMS_Multicast | TELUS | FG: low priority. to be triggered when time allows. | PENG TAN | 82945 | Work Plan | Agreement | In this contribution, the work plan for FS_5GMS_Multicast is proposed. |  | 27 | 8.8 |  | available |  | FS_5GMS_Multicast (Feasibility Study on Multicast Architecture Enhancements for 5GMSA) | 0 | available | 2020-03-31 17:54 | 2020-03-31 21:10 |  |  | Rel-17
S4-200612 | Proposed Skeleton TR26.802 Multicast Architecture Enhancement for 5G Media Streaming | TELUS | FG: low priority. to be triggered when time allows. | PENG TAN | 82945 | discussion | Agreement | A skeleton of TR 26.802 is proposed in this contribution. |  | 27 | 8.8 |  | available |  | FS_5GMS_Multicast (Feasibility Study on Multicast Architecture Enhancements for 5GMSA) | 0 | available | 2020-03-31 21:28 | 2020-03-31 21:35 |  |  | Rel-17
S4-200563 | Proposed Work Plan for FS_XRTraffic | Qualcomm Incorporated | FG: low priority. to be triggered when time allows. | Thomas Stockhammer | 60397 | Work Plan | Agreement |  |  | 28 | 8.9 |  | available |  | FS_XRTraffic (Feasibility Study on Typical Traffic Characteristics for XR Services and other Media) | 0 | available | 2020-03-31 04:32 | 2020-03-31 05:02 |  |  | Rel-17 |  |  | FS_XRTraffic
S4-200564 | Proposed Skeleton Draft CR XR Traffic | Qualcomm Incorporated | FG: low priority. to be triggered when time allows. | Thomas Stockhammer | 60397 | draftCR | Agreement |  |  | 28 | 8.9 |  | available |  | FS_XRTraffic (Feasibility Study on Typical Traffic Characteristics for XR Services and other Media) | 0 | available | 2020-03-31 04:32 | 2020-03-31 05:02 |  |  | Rel-17 | 26.925 | 16.0.0 | FS_XRTraffic
S4-200504 | Clarifying nature of headset requirements | Samsung Electronics Polska | FG: related to LS in 537. To be handled by SQ SWG | Kyunghun Jung | 38881 | CR | Approval |  |  | 39 | 9.4 |  | available |  | CRs to Features in Release 15 and earlier, and other contributions on terminal acoustics | 0 | available | 2020-03-26 06:12 | 2020-03-31 07:34 |  |  | Rel-16 | 26.131 | 16.0.0 | TEI16 | 0081 |  | F
S4-200505 | Handling insert-type headsets that not fitting ear simulators properly | Samsung Electronics Polska | FG: related to LS in 537. To be handled by SQ SWG | Kyunghun Jung | 38881 | CR | Approval |  |  | 39 | 9.4 |  | available |  | CRs to Features in Release 15 and earlier, and other contributions on terminal acoustics | 0 | available | 2020-03-26 06:19 | 2020-03-31 07:34 |  |  | Rel-16 | 26.132 | 16.2.0 | TEI16 | 0104 |  | F
S4-200606 | Comments to S4-200504 and S4-200505 on Headset Testing | Sony Corporation | FG: related to LS in 537 and proposals in 504 and 505. To be handled by SQ SWG | Peter Isberg | 82130 | discussion |  | Comments to draft CR:s to TS 26.131 and TS 26.132 on headset testing |  | 39 | 9.4 |  | available |  | CRs to Features in Release 15 and earlier, and other contributions on terminal acoustics | 0 | available | 2020-03-31 19:31 | 2020-03-31 20:09 |  |  | Rel-16
S4-200565 | Proposals for data collection of HaNTE – test methods | Qualcomm Incorporated | FG: high priority. | Andre Schevciw | 84573 | discussion | Agreement |  |  | 41 | 9.6 |  | available |  | HaNTE (Handsets Featuring Non-Traditional Earpieces) | 0 | available | 2020-03-31 04:51 | 2020-03-31 17:05 | [5 empty] | HaNTE
S4-200567 | WI summary for ANTeM | HEAD acoustics GmbH | FG: low priority. To be endorsed. | Jan Reimes | 47443 | WI summary | Endorsement |  |  | 42 | 9.7 |  | available |  | ANTeM (Ambient noise test methodology for evaluation of acoustic UE performance) | 0 | available | 2020-03-31 08:49 | 2020-03-31 14:10 |  |  | Rel-16 |  |  | ANTeM
S4-200614
S4-200615
S4-200617 | Reserved MBS SWG
S4-200618 | Reserved MBS SWG
S4-200619 | Reserved MBS SWG
S4-200620 | Reserved MBS SWG
S4-200621 | Reserved MBS SWG
S4-200622 | Reserved MBS SWG
S4-200623 | Reserved MBS SWG
S4-200624 | Reserved MBS SWG
S4-200625 | Reserved MBS SWG
S4-200626 | Reserved MBS SWG
S4-200627 | Reserved MBS SWG
S4-200628 | Reserved MBS SWG
S4-200629 | Reserved MBS SWG
S4-200630 | Reserved MBS SWG
S4-200631 | Reserved MBS SWG
S4-200632 | Reserved MBS SWG
S4-200633 | Reserved MBS SWG
S4-200634 | Reserved MBS SWG
S4-200635 | Reserved MBS SWG
S4-200636 | Reserved SQ SWG
S4-200637 | Reserved SQ SWG
S4-200638 | Reserved SQ SWG
S4-200639 | Reserved SQ SWG
S4-200640 | Reserved SQ SWG
S4-200641 | Reserved MTSI SWG
S4-200642 | Reserved MTSI SWG
S4-200643 | Reserved MTSI SWG
S4-200644 | Reserved MTSI SWG
S4-200645 | Reserved MTSI SWG
S4-200646 | Reserved MTSI SWG
S4-200647 | Reserved MTSI SWG
S4-200648 | Reserved MTSI SWG
S4-200649 | Reserved MTSI SWG
S4-200650 | Reserved MTSI SWG
S4-200651 | Reserved MTSI SWG
S4-200652 | Reserved MTSI SWG
S4-200653 | Reserved MTSI SWG
S4-200654 | Reserved MTSI SWG
S4-200655 | Reserved MTSI SWG
S4-200656 | Reserved MTSI SWG
S4-200657 | Reserved MTSI SWG
S4-200658 | Reserved MTSI SWG
S4-200659 | Reserved MTSI SWG
S4-200660 | Reserved MTSI SWG
Note on B1: Free text. Maximum length: 200 characters
Note on C1: Free text. Maximum length: 200 characters
Note on E1: Not used in import. Instead, Contact ID is used to uniquely identify the contact person of a TDoc
Note on F1: Contact ID is used to uniquely identify contact person of TDocs. At import time, if Empty, the contact person will be the person who performed the import.
Note on G1: Allowed values: agenda Work Plan LS in LS out pCR draftCR CR CR pack ToR WID new WID revised SID new SID revised WI status report WI exception request Ts or TR cover draft TS draft TR report discussion response other
Note on H1: Allowed values: Decision Agreement Approval Information Discussion Action Endorsement Presentation
Note on L1: Agenda item # is used to uniquely identify the meeting allocation of the TDoc. Make sure you use a valid agenda item, otherwise TDoc cannot be imported.
Note on N1: Allowed values: reserved available revised agreed conditionally agreed approved conditionally approved partially approved treated endorsed replied to merged not pursued postponed noted not concluded withdrawn reissued
Note on P1: Free text. Not used during import. The Agenda item is uniquely identified by its number.
Note on Q1: is used to order TDocs belonging to the same agenda item. This field is imported, make sure you use a numeric value
Note on R1: Allowed values: reserved available revised agreed conditionally agreed approved conditionally approved partially approved treated endorsed replied to merged not pursued postponed noted not concluded withdrawn reissued
Note on S1: is not imported. Reservation date of new TDocs is the date when the import will be performed
Note on T1: During import, if the cell is NOT empty, the TDoc will be considered available, in this case, make sure the TDoc is stored in the right place on FTP server, and is correctly named. At export time, the cell contains upload date.
Note on U1: Imported to identify the source TDoc. If the value is not a valid TDoc number, the TDoc cannot be imported. If source TDoc is new, make sure it is located above the current line.
Note on V1: is used to identify the TDoc(s) revision(s) of the current TDoc. This column is not imported.
Note on Z1: Related Wis are imported. Use UID or Acronym to identify WI. Several Wi can be imported if they are comma separated. Example: "UPCON, 570029, RSE"R

## CR_Packs_List
CR Pack TDoc | WG Tdoc | WG TDoc decision | CR Individual TSG decision | Spec | CR | CR revision | CR category | Release | Version | CR title

## Parameters (hidden)
Types of Tdocs | Possible statuses of Tdocs | Categories
agenda | reserved | A | Decision
Work Plan | available | B | Agreement
LS in | revised | C | Approval
LS out | agreed | D | Information
pCR | conditionally agreed | E | Discussion
draftCR | approved | F | Action
CR | conditionally approved |  | Endorsement
CR pack | partially approved |  | Presentation
ToR | treated
WID new | endorsed
WID revised | replied to
SID new | merged
SID revised | not pursued
WI status report | postponed
WI exception request | noted
TS or TR cover | not concluded
draft TS | withdrawn
draft TR | reissued
report | not treated
discussion
other
WI summary