## SA4#114-e_Status
3GPP SA4 WI/SI Status Update
Name | WI_Code | WI_ID | Release | Impact on other 3GPP WGs except SA4 | Target Completion Date | Completion %age till SA4#113-e | Completion %age till SA4#114-e | Specify whether Stage2 / Stage 3 | Name of the Rapporteur | Comments
Extension for headset interface tests of UE | HInT | 880012 | Rel-17 |  | 2021-09-10 | 60% | 70% | Stage 3 | Jan Reimes, Stéphane Ragot | Test specifications
Support of Immersive Teleconferencing and Telepresence for Remote Terminals | ITT4RT | 820003 | Rel-17 |  | 2022-03-18 | 70% | 75% | Stage 3 | Igor Curcio, Simon Gunkel
Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 830005 | Rel-17 |  | 2022-12-04 | 20% | 20% | Stage 3 | Stéphane Ragot, Stefan Bruhn | Test specifications
Handsets Featuring Non-Traditional Earpieces | HaNTE | 860012 | Rel-17 |  | 2020-09-15 | 55% | 70% | Stage 3 | Andre Schevciw | Test specifications
EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 770024 | Rel-17 |  | 2022-06-11 | 27% |  | Stage 3 | Imre Varga
Operation Points for 8K VR 360 Video over 5G | 8K_VR_5G | 890009 | Rel-17 |  | 2021-06-11 | 95% | 100% | Stage 3 | Ozgur Oyman, Thomas Stockhammer | completed during SA4#114-e
Study on 5G Glass-type AR/MR Devices | FS_5GSTAR | 880011 | Rel-17 |  | 2021-12-17 | 50% | 65% | Stage 3 | Hakju Ryan Lee
Study on Multicast Architecture Enhancements for 5G Media Streaming | FS_5GMS_Multicast | 870014 | Rel-17 |  | 2021-06-10 | 75% |  | Stage 2 | Peng Tan
Study on VR Streaming Conformance and Guidelines | FS_VR_CoGui | 850004 | Rel-17 |  | 2021-12-17 | 20% | 20% | Stage 3 | Igor Curcio
Study on 5G Video Codec Characteristics | FS_5GVideo | 870011 | Rel-17 |  | 2021-12-17 | 65% | 70% | Stage 3 | Thomas Stockhammer | excellent progress, but long way to go and also work item extended
Study on the use of NBMP in FLUS | FS_FLUS_NBMP | 870012 | Rel-17 |  | 2021-09-17 | 96% |  | Stage 3 | Iraj Sodagar
Study on Streaming Architecture extensions For Edge processing | FS_EMSA | 870015 | Rel-17 |  | 2021-06-11 | 90% |  | Stage 2 | Imed Bouazizi
Study on Typical Traffic Characteristics for XR Services and other Media | FS_XRTraffic | 870013 | Rel-17 |  | 2021-12-15 | 60% | 65% | Stage 3 | Thomas Stockhammer | little progress, but we will move based on PD
Study on 5G media streaming extensions | FS_5GMS_EXT | 900029 | Rel-17 |  | 2021-09-08 | 30% | 40% | Stage 2 | Thorsten Lohmar, Iraj Sodagar
Study on Media Production over 5G NPN | FS_5G_4_AVProd | 910001 | Rel-17 |  | 2022-03-22 | 5% | 15% |  | Thorsten Lohmar,
* Currently the Stage 3 Release Freeze has been planned to be shifted from Sep '21 (ASN.1 freeze: Dec.21) to Mar '22 (ASN.1 freeze: Sep.22) [RP-202111]
* In Bold are the WIs

## SA4#113-e_Status
3GPP SA4 WI/SI Status Update
Name | WI_Code | WI_ID | Release | Impact on other 3GPP WGs except SA4 | Target Completion Date | Completion %age till SA4#110-e | Completion %age till SA4#111-e | Completion %age till SA4#112-e | Completion %age till SA4#113-e | Specify whether Stage2 / Stage 3 | Name of the Rapporteur | Comments
Extension for headset interface tests of UE | HInT | 880012 | Rel-17 |  | 2021-09-10 | 10% | 25% | 50% | 60% | Stage 3 | Jan Reimes, Stéphane Ragot | Test specifications
Support of Immersive Teleconferencing and Telepresence for Remote Terminals | ITT4RT | 820003 | Rel-17 |  | 2021-06-11 | 50% | 55% | 60% | 70% | Stage 3 | Ozgur Oyman, Igor Curcio
Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 830005 | Rel-17 |  | 2022-12-04 | 15% | 20% | 20% | 20% | Stage 3 | Stéphane Ragot, Stefan Bruhn | Test specifications
Handsets Featuring Non-Traditional Earpieces | HaNTE | 860012 | Rel-17 |  | 2020-09-15 | 35% | 37% | 50% | 55% | Stage 3 | Andre Schevciw | Test specifications
EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 770024 | Rel-17 |  | 2022-06-11 | 27% | 27% | 27% | 27% | Stage 3 | Imre Varga
Operation Points for 8K VR 360 Video over 5G | 8K_VR_5G | 890009 | Rel-17 |  | 2021-06-11 | 0% | 25% | 85% | 95% | Stage 3 | Ozgur Oyman, Thomas Stockhammer
Study on 5G Glass-type AR/MR Devices | FS_5GSTAR | 880011 | Rel-17 |  | 17-Sep-21 | 5% | 10% | 20% | 50% | Stage 3 | Hakju Ryan Lee
Study on Multicast Architecture Enhancements for 5G Media Streaming | FS_5GMS_Multicast | 870014 | Rel-17 |  | 2021-06-10 | 10% | 20% | 60% | 75% | Stage 2 | Peng Tan
Study on VR Streaming Conformance and Guidelines | FS_VR_CoGui | 850004 | Rel-17 |  | 2021-06-21 | 10% | 20% | 20% | 20% | Stage 3 | Igor Curcio
Study on 5G Video Codec Characteristics | FS_5GVideo | 870011 | Rel-17 |  | 2021-09-17 | 30% | 45% | 55% | 65% | Stage 3 | Thomas Stockhammer
Study on the use of NBMP in FLUS | FS_FLUS_NBMP | 870012 | Rel-17 |  | 2021-06-21 | 20% | 30% | 40% | 70% | Stage 3 | Iraj Sodagar
Study on Streaming Architecture extensions For Edge processing | FS_EMSA | 870015 | Rel-17 |  | 2021-06-11 | 25% | 30% | 60% | 90% | Stage 2 | Imed Bouazizi
Study on Typical Traffic Characteristics for XR Services and other Media | FS_XRTraffic | 870013 | Rel-17 |  | 2021-09-17 | 25% | 40% | 55% | 60% | Stage 3 | Thomas Stockhammer
Traffic Models and Quality Evaluation Methods for Media and XR Services in 5G Systems |  |  |  |  | 2021-12-15
Study on 5G media streaming extensions | FS_5GMS_EXT | 900029 | Rel-17 |  | 2021-09-08 | NA | 0% | 5% | 15% |  | Thorsten Lohmar, Iraj Saudagar
Study on Media Production over 5G NPN | FS_5G_4_AVProd | 910001 | Rel-17 |  | 2022-03-22 |  |  | 0% | 5% |  | Thorsten Lohmar,
* Currently the Stage 3 Release Freeze has been planned to be shifted from Sep '21 (ASN.1 freeze: Dec.21) to Mar '22 (ASN.1 freeze: Sep.22) [RP-202111]
* In Bold are the WIs

## SA4#112-e_Status
3GPP SA4 WI/SI Status Update
Name | WI_Code | WI_ID | Release | Impact on other 3GPP WGs except SA4 | Target Completion Date | Completion %age till SA4#110-e | Completion %age till SA4#111-e | Completion %age till SA4#112-e | Specify whether Stage2 / Stage 3 | Name of the Rapporteur | Comments
Extension for headset interface tests of UE | HInT | 880012 | Rel-17 |  | 2021-09-10 | 10% | 25% | 50% | Stage 3 | Jan Reimes, Stéphane Ragot | Test specifications
Support of Immersive Teleconferencing and Telepresence for Remote Terminals | ITT4RT | 820003 | Rel-17 |  | 2020-12-18 | 50% | 55% | 60% | Stage 3 | Ozgur Oyman, Igor Curcio
Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 830005 | Rel-17 |  | 2022-12-04 | 15% | 20% | 20% | Stage 3 | Stéphane Ragot, Stefan Bruhn | Test specifications
Handsets Featuring Non-Traditional Earpieces | HaNTE | 860012 | Rel-17 |  | 2020-09-15 | 35% | 37% | 50% | Stage 3 | Andre Schevciw | Test specifications
EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 770024 | Rel-17 |  | 2021-06-11 | 27% | 27% | 27% | Stage 3 | Imre Varga
Operation Points for 8K VR 360 Video over 5G | 8K_VR_5G | 890009 | Rel-17 |  | 2021-03-12 | 0% | 25% | 85% | Stage 3 | Ozgur Oyman
Study on 5G Glass-type AR/MR Devices | FS_5GSTAR | 880011 | Rel-17 |  | 17-Sep-21 | 5% | 10% | 20% | Stage 3 | Hakju Ryan Lee
Study on Multicast Architecture Enhancements for 5G Media Streaming | FS_5GMS_Multicast | 870014 | Rel-17 |  | 2021-06-10 | 10% | 20% | 60% | Stage 2 | Peng Tan
Study on VR Streaming Conformance and Guidelines | FS_VR_CoGui | 850004 | Rel-17 |  | 2021-06-21 | 10% | 20% | 20% | Stage 3 | Igor Curcio
Study on 5G Video Codec Characteristics | FS_5GVideo | 870011 | Rel-17 |  | 2020-12-17 | 30% | 45% | 55% | Stage 3 | Thomas Stockhammer
Study on the use of NBMP in FLUS | FS_FLUS_NBMP | 870012 | Rel-17 |  | 2021-09-21 | 20% | 30% | 40% | Stage 3 | Iraj Sodagar
Study on Streaming Architecture extensions For Edge processing | FS_EMSA | 870015 | Rel-17 |  | 2021-06-11 | 25% | 30% | 60% | Stage 2 | Imed Bouazizi
Study on Typical Traffic Characteristics for XR Services and other Media | FS_XRTraffic | 870013 | Rel-17 |  | 2020-06-18 | 25% | 40% | 55% | Stage 3 | Thomas Stockhammer
Study on 5G media streaming extensions | FS_5GMS_EXT | 900029 | Rel-17 |  | 2021-09-08 | NA | 0% | 5% |  | Thorsten Lohmar, Iraj Saudagar
* Currently the Stage 3 Release Freeze has been planned to be shifted from Sep '21 (ASN.1 freeze: Dec.21) to Mar '22 (ASN.1 freeze: Sep.22) [RP-202111]
* In Bold are the WIs

## SA4#111-e_Status
3GPP SA4 WI/SI Status Update
Name | WI_Code | WI_ID | Release | Impact on other 3GPP WGs except SA4 | Target Completion Date | Completion %age till SA4#110-e | Completion %age till SA4#111-e | Specify whether Stage2 / Stage 3 | Name of the Rapporteur | Comments
Extension for headset interface tests of UE | HInT | 880012 | Rel-17 | None | 2021-09-10 | 10% | 25% | Stage 3 | Jan Reimes, Stéphane Ragot | Test specifications
Support of Immersive Teleconferencing and Telepresence for Remote Terminals | ITT4RT | 820003 | Rel-17 | None | 2020-12-18 | 50% | 55% | Stage 3 | Ozgur Oyman, Igor Curcio
Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS | 830005 | Rel-17 |  | 2022-12-04 | 15% | 20% | Stage 3 | Stéphane Ragot, Stefan Bruhn
Handsets Featuring Non-Traditional Earpieces | HaNTE | 860012 | Rel-17 |  | 2020-09-15 | 35% | 37% | Stage 3 | Andre Schevciw | Test specifications
EVS Codec Extension for Immersive Voice and Audio Services | IVAS_Codec | 770024 | Rel-18 |  | 2021-06-11 | 27% | 27% | Stage 3 | Imre Varga
Operation Points for 8K VR 360 Video over 5G | 8K_VR_5G | 890009 | Rel-17 | None | 2021-03-12 | 0% | 25% | Stage 3 | Ozgur Oyman
Study on 5G Glass-type AR/MR Devices | FS_5GSTAR | 880011 | Rel-17 | None | 2021-06-11 | 5% | 10% | Stage 3 | Hakju Ryan Lee
Study on Multicast Architecture Enhancements for 5G Media Streaming | FS_5GMS_Multicast | 870014 | Rel-17 |  | 2020-12-17 | 10% | 20% | Stage 2 | Peng Tan
Study on VR Streaming Conformance and Guidelines | FS_VR_CoGui | 850004 | Rel-17 | None | 2021-06-21 | 10% | 20% | Stage 3 | Igor Curcio
Study on 5G Video Codec Characteristics | FS_5GVideo | 870011 | Rel-17 |  | 2020-12-17 | 30% | 45% | Stage 3 | Thomas Stockhammer
Study on the use of NBMP in FLUS | FS_FLUS_NBMP | 870012 | Rel-17 |  | 2021-09-21 | 20% | 30% | Stage 3 | Iraj Sodagar
Study on Streaming Architecture extensions For Edge processing | FS_EMSA | 870015 | Rel-17 |  | 2020-12-17 | 25% | 30% | Stage 2 | Imed Bouazizi
Study on Typical Traffic Characteristics for XR Services and other Media | FS_XRTraffic | 870013 | Rel-17 |  | 2020-06-18 | 25% | 40% | Stage 3 | Thomas Stockhammer
* Currently the Stage 3 Release Freeze has been planned to be shifted from Sep '21 (ASN.1 freeze: Dec.21) to Mar '22 (ASN.1 freeze: Sep.22) [RP-202111]
* In Bold are the WIs