## Slide 1: SA4 Work and Study Items Status at the start of SA4#131
Frédéric Gabin, SA4 Chair (Dolby France SAS)
and all SA4 WID/SID Rapporteurs
(Agenda Item 5.1)

## Slide 2: Outline
Rel-19 Work Items
  Status at the end of SA#106 (and SA4#130)
  Rapporteur’s progress report since SA4#130
Study Items
  Status at the end of SA#106 (and SA4#130)
  Rapporteur’s progress report since SA4#130

## Slide 3: Overview of work progress Rel-19 Work Items – after SA#106 (SA4#130)
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
1030002 | Video Operating Points - Harmonization and Stereo MV-HEVC | VOPS | 6/6/2025 | 20% | SP-240060 | 45% | 
1030003 | Split Rendering over IMS | SR_IMS | 6/6/2025 | 25% | SP-240492 | 45% | 
1040021 | EVS Codec Extension for Immersive Voice and Audio Services, Phase 2 | IVAS_Codec_Ph2 | 9/9/2025 | 5% | SP-241000 | 20% | IVAS fixed-point Decoder and Renderer 90% delivery
1050113 | Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS_Ph2 | 9/9/2025 | - | SP-241314 | 5% | 
1060069 | Stage 2 for Advanced Media Delivery | AMD-ARCH-MED | 3/3/2025 | - | SP-241674 | - | New WID
1060022 | Diverse audio Capturing System for UEs | DaCAS | 9/9/2025 | - | SP-241673 | - | New WID
1060021 | 5G Real-time Transport Protocol Configurations, Phase 2 | 5G_RTP_Ph2 | 9/9/2025 | - | SP-241672 | - | New WID

## Slide 4: Video Operating Points - Harmonization and Stereo MV-HEVC (VOPS)
Rapporteur: Waqar Zia (waqar_zia (at) apple.com)
Progress since last SA4 meeting
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  There were no documents reported in Adhoc calls.
Any recommendations based on the agreements?
  None.
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Several input contributions available that are expected to progress the work forward reasonably.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030002 | Video Operating Points - Harmonization and Stereo MV-HEVC | VOPS | 6/6/2025 | 20% | SP-240060 | 45% | 

## Slide 5: Split Rendering over IMS (SR_IMS)
Rapporteur: He, Shane, Nokia Corporation, shane.he@nokia.com
Progress since last SA4 meeting
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  14 contributions received
    3 to Joint session with Audio SWG: S4aR250059 ,S4aR250060 , S4aR250054 were reviewed and noted, several key issues were clarified.
    6 agreed: S4aR250009 , S4aR250056 , S4aR250057 , S4aR250061, S4aR250069 , S4aR250062 it was agreed to add the details of functionalities, metadata format, delay adaptation based on QoE metric to TS 26.567.
    1 endorsed: S4aR250063 and 4 noted: S4aR250005 , S4aR250006 , S4aR250007 , S4aR250026
Any recommendations based on the agreements?
  None
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Discuss the submitted contributions and incorporate these into TS 26.567: S4-250089, S4-250101, S4-250157, S4-250159, S4-250197, S4-250198, S4-250199, S4-250200, S4-250226 (9 incl. updated draft TS 26.567 v0.4.1 )
  Progress the work on media codecs, configuration, metric format, MF capabilities for split rendering over IMS, etc.
  According to the time plan, expect to agree on TS 26.567 v1.0.0 (send to SA plenary for information)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030003 | Split Rendering over IMS | SR_IMS | 6/6/2025 | 25% | SP-240492 | 45% | 

## Slide 6: EVS Codec Extension for Immersive Voice and Audio Services, Phase 2 (IVAS_Codec_Ph2)
Rapporteur: Su, Huan-yu, Huawei Technologies Co Ltd., su.huanyu@huawei.com
Progress since last SA4 meeting
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Scheduled Audio SWG Adhoc call on 17 January 2025 did not take place due to the lack of input contribution
  Ittiam delivered fixed point Encoder v1 on 30 November, 2024 and fixed point Encoder v2 on 31 January, 2025
Any recommendations based on the agreements?
  N/A
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Due to the lack of complete verification results for v2 fixed point Encoder delivery, need to revise the timeplan taking into account the status
  Finalize the processing plan, IVAS-7b, and test plan, IVAS-8b, for the Characterization phase
  Decision on other logistics, e.g., NDA, test materials reuse, etc. for the Characterization tests
  Discussion and decision on WID revision to address the need of having a conformance test procedure for implementations based on floating point C-code
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1040021 | EVS Codec Extension for Immersive Voice and Audio Services, Phase 2 | IVAS_Codec_Ph2 | 9/9/2025 | 5% | SP-241000 | 20% | IVAS fixed-point Decoder and Renderer 90% delivery

## Slide 7: Terminal Audio quality performance and Test methods for Immersive Audio Services, Phase 2 (ATIAS_Ph2)
Rapporteur: Jan Reimes, HEAD acoustics GmbH, jan.reimes@head-acoustics.com
Progress since last SA4 meeting
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Inputs on test methods for sound scene capture (SA4aA250005) and test setup for complex UE types (SA4aA250003) noted; further work is anticipated here.
  Input on test method for motion-to-sound (M2S) latency (SA4aA250001) agreed.
Any recommendations based on the agreements?
  Test method for M2S to be integrated into PDoc ATIAS-2
  Delegates were invited to contribute for SA4#131 on various testing aspects regarding sound scene reproduction & loudspeaker arrays
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Discuss inputs on test setups for sound scene reproduction & send capture test methods (S4-250126, S4-250088, S4-250205)
  Review & progress on PDoc ATIAS-2 (S4-250082)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1050113 | Terminal Audio quality performance and Test methods for Immersive Audio Services | ATIAS_Ph2 | 9/9/2025 | - | SP-241314 | 5% | 

## Slide 8: Stage 2 for Advanced Media Delivery (AMD-ARCH-MED)
Rapporteur: Thomas Stockhammer, Qualcomm Incorporated, tsto@qti.qualcomm.com
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1060069 | Stage 2 for Advanced Media Delivery | AMD-ARCH-MED | 3/3/2025 | - | SP-241674 | - | New WID
Title | Lead | Latest Document and Status | Related spec and CR number | Completion | Input for this meeting
Common Client Metadata | Thomas Stockhammer, Qualcomm | S4aI250061 (n) | 26501-0101rev3 | 50% | S4-250021
Media delivery from multiple service endpoints/locations | Jason Cloud, Dolby | S4aI250062 (e) | 26501-0103rev3 | 50% | S4-250103
Multi-Access Media Delivery | Prakash Kolan, Samsung | S4aI250036 (e) | 26501-0107rev1 | 80% | 
Distributing encrypted and high-value content | Thomas Stockhammer, Qualcomm | S4aI250062 (n) | 26501-0102rev3 | 45% | S4-250022
In-session Unicast Repair for MBS Object Distribution | Thomas Stockhammer, Qualcomm | S4aI250068 (e) | 26502-0033rev4 | 50% | S4-250026
MBS User Service and Delivery Protocols for eMBMS | Thomas Stockhammer, Qualcomm | S4aI250040 (e) | 26502-0034rev2 | 50% | S4-250020
Selected MBMS Functionalities not supported in MBS | Thomas Stockhammer, Qualcomm | S4aI250057 (n) | 26502-0035rev2 | 40% | S4-250019
Improved QoS support for Media Streaming services | Qi Pan, Huawei | S4aI250042 (e) | 26501-0104rev1 | 70% | S4-250146
Media Streaming aspects of Network Slicing | Prakash Kolan, Samsung | S4-242016 (e) | 26501-0098rev2 | 80% | 
Overall progress |  |  |  | 57% | 
S4-250023 [AMD-ARCH-MED] Time and Work Plan for Stage 2 for Advanced Media Delivery
S4-250027 [AMD-ARCH-MED] Work Item Summary for Stage 2 for Advanced Media Delivery
S4-250106 [AMD-ARCH-MED] Draft LS on Advanced Media Delivery
S4-250218 [AMD-ARCH-MED] Review of 5G and 5GMS Terminology
Goal for meeting: Complete work item with 80% to initiate stage-3 work

## Slide 9: Diverse audio Capturing System for UEs (DaCAS)
Rapporteur: Wang Bin, Xiaomi Technology, wangbin23@xiaomi.com
Progress since last SA4 meeting
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  None
Any recommendations based on the agreements?
  None
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  8 contributions in the meeting, we will discuss the workplan, requirements/templates for target device or target device type and database, solution proposals.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1060022 | Diverse audio Capturing System for UEs | DaCAS | 9/9/2025 | - | SP-241673 | - | New WID

## Slide 10: 5G Real-time Transport Protocol Configurations, Phase 2 (5G_RTP_Ph2)
Rapporteur: Igor Curcio, Nokia Corporation, igor.curcio@nokia.com
Progress since last SA4 meeting
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Agreed corrections to TR 26.822
  Agreed contribution on RTCP messages to better support XR services in 5G
  Endorsed PSI Guidelines for HEVC tiles
  Endorsed RTP Header Extension for Dynamically Changing Traffic Characteristics
  Endorsed Guidelines for PDU Set Marking of Multiplexed Streams
  Agreed On the draft LS on Application-Layer FEC Awareness at RAN
Any recommendations based on the agreements?
  Continue to review and discuss the contributions submitted at this meeting
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Review and discuss the input contributions submitted at this meeting
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1060021 | 5G Real-time Transport Protocol Configurations, Phase 2 | 5G_RTP_Ph2 | 9/9/2025 | - | SP-241672 | - | New WID

## Slide 11: Overview of work progress Study Items – after SA#106 (SA4#130)
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950011 | Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media | FS_AI4Media | 6/6/2025 | 78% | SP-220328 | 82% | 
1000019 | Feasibility Study on Avatars for Real-Time Communication | FS_AVATAR | 3/3/2025 | 55% | SP-230544 | 60% | 
1030004 | Study on Media enerGy consumption exposuRE and EvaluatioN framework | FS_MediaEnergyGREEN | 3/3/2025 | 30% | SP-240481 | 60% | 
1030005 | Study on Media Messaging | FS_MeMe | 3/3/2025 | 30% | SP-240477 | 60% | 
1030006 | Study on Advanced Media Delivery | FS_AMD | 3/3/2025 | 60% | SP-241011 | 75% | 
1030008 | Study on Beyond 2D Video | FS_Beyond2D | 6/6/2025 | 17% | SP-240479 | 28% | 
1030009 | Study on Audio Codec APIs | FS_ACAPI | 6/6/2025 | 10% | SP-240480 | 20% | 
1040020 | Study on Haptics in 5G Media Services | FS_HapticsMedia | 3/3/2025 | 15% | SP-241121 | 60% | 
1040022 | Study on Spatial Computing for AR Services | FS_ARSpatial | 6/6/2025 | 10% | SP-240927 | 25% | 
1050037 | Study on immersive Real-Time Communication for WebRTC, Phase 2 | FS_iRTCW_Ph2 | 6/6/2025 | 0% | SP-241374 | 15% | 

## Slide 12: Feasibility Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media (FS_AI4Media)
Rapporteur: Eric Yip, eric.yip@samsung.com
Progress since last SA4 meeting
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  None
Any recommendations based on the agreements?
  None
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Clean up TR 26.927 and TR 26.847 to send to SA for information
  Continue discussion on conclusions
  Related to conclusions, discuss future AI/ML activities in 5G-A and 6G
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
950011 | Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media | FS_AI4Media | 6/6/2025 | 78% | SP-220328 | 82% | 

## Slide 13: Feasibility Study on Avatars for Real-Time Communication (FS_AVATAR)
Rapporteur: Bouazizi, Imed, Qualcomm Incorporated, bouazizi AT qti DOT qualcomm DOT com
Progress since last SA4 meeting
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Avatar related topics were discussed in one Video AHG call
  One contribution was agreed into the TR, which was agreed before but was not properly integrated into the TR
  Other contributions on IMS architecture and call flows were not agreed as SA2 specifications are not finalized
Any recommendations based on the agreements?
  Finalize the IMS mapping based on the SA2 final specifications
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Conclude the FS_AVATAR study and submit TR for approval
  Start normative work in Rel-19 to implement basic support for Avatars in AR Calls
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1000019 | Feasibility Study on Avatars for Real-Time Communication | FS_AVATAR | 3/3/2025 | 55% | SP-230544 | 60% | 

## Slide 14: Study on Media enerGy consumption exposuRE and EvaluatioN framework (FS_MediaEnergyGREEN)
Rapporteur: Julien Lemotheux, Orange, julien.lemotheux@orange.com
Progress since last SA4 meeting
6 contributions agreed during the MBS Adhoc calls: Solution#1: Update to Potential solution to Key Issue #1: Energy-related information exposure from UE (S4aI250007), Additional background information (S4aI250018), Complement on KI3 (S4aI250038), Potential solution to KI1 based Energy related information from the UE, network and other entities provided to an App (S4aI250043), Abbreviations and introductions (S4aI250048), Potential solution to Key Issue #2: QMC-based monitoring and measurement (S4aI250066).
This has been integrated in new v1.0.1 of TR 26.942, and a new v1.0.2 has been uploaded with editorial corrections.
For the meeting, 10 contributions have been submitted. The goal is to add some text references, add or improve potential solutions and agree on the conclusions.
At the end of this meeting, the plan is to complete the study and present TR 26.942 v2.0.0 to SA for approval.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030004 | Study on Media enerGy consumption exposuRE and EvaluatioN framework | FS_MediaEnergyGREEN | 3/3/2025 | 30% | SP-240481 | 60% | 

## Slide 15: Study on Media Messaging (FS_MeMe)
Rapporteur: Thomas Stockhammer, Qualcomm Incorporated, tsto@qti.qualcomm.com
Progress since last SA4 meeting
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  No input documents for the Adhoc group calls
Any recommendations based on the agreements?
  None
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Review the time plan and discuss the transition from Study to normative work  Proposal is to shift start of normative only after SA4#132.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030005 | Study on Media Messaging | FS_MeMe | 3/3/2025 | 30% | SP-240477 | 60% | 
S4-250036 | [FS_MeMe] IETF MIMI and 3GPP Messaging
S4-250038 | [FS_MeMe] Time and Work Plan for Media Messaging
S4-250151 | [FS_MeMe] Proposed Updates to TR 26.841

## Slide 16: Study on Advanced Media Delivery (FS_AMD)
Rapporteur:
Thomas Stockhammer, Qualcomm Incorporated, tsto@qti.qualcomm.com
Progress since last SA4 meeting
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  Updated time plan and two documents related to MBS
  Time was short as stage-2 normative work was prioritized
Any recommendations based on the agreements?
  None
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Dispose the documents and complete the study.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030006 | Study on Advanced Media Delivery | FS_AMD | 3/3/2025 | 60% | SP-241011 | 75% | 
S4-250016 | [FS_AMD] Time and Work Plan for Advanced Media Delivery
S4-250017 | [FS_AMD] Selective Unicast Requests in MBS/MBMS
S4-250018 | [FS_AMD] Generic Application Service
S4-250024 | Overview Slides on Advanced Media Delivery for 5G-MAG
S4-250145 | Update of NOTE for MBS User Service over eMBMS
S4-250209 | [FS-AMD WT 3b]: Documenting future work with multi-access media delivery

## Slide 17: Study on Beyond 2D Video (FS_Beyond2D)
Rapporteur:
Jiayi Xu, xujiayi@chinamobile.com
Progress since last SA4 meeting
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  During the Adhoc meeting, 2 documents were agreed,
    Dynamic mesh representation format (S4aV250011), was agreed for PD,
    Editoral updates, the relocation of clause 7.3.8.3.2 to Annex B, was agreed on TR (S4aV250012).
Any recommendations based on the agreements?
  Agree the updated time plan in S4-250078.
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Progress the work on the representation format and scenarios, update TR and prepare TR 26.956 for submission for information to SA plenary.
  Potential new permanent document on B2D format characterization.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030008 | Study on Beyond 2D Video | FS_Beyond2D | 6/6/2025 | 17% | SP-240479 | 28% | 

## Slide 18: Study on Audio Codec APIs (FS_ACAPI)
Rapporteur:
Stefan Döhla (stefan DOT doehla AT iis DOT fraunhofer DOT de)
Progress since last SA4 meeting
Little progress during Audio SWG calls, no contributions
Two contributions to this meeting:
  S4-250211 - W3C RTPTransport for 3GPP codecs in WebRTC
  S4-250216 - Codec support in WebRTC libraries
SI at a critical point
  Sufficient input for Objectives 2 and 3 to draft conclusions (objective 4, 5)
  Objective 1 has seen no input so far
  Timeline challenging without sufficient input, should decide how to progress / conclude the SI by 6/6/2025
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1030009 | Study on Audio Codec APIs | FS_ACAPI | 6/6/2025 | 20% | SP-240480 | 40% | 

## Slide 19: Study on Haptics in 5G Media Services (FS_HapticsMed)
Rapporteur:
Gaëlle Martin-Cocher, InterDigital (Gaelle.Martin-Cocher@InterDigital.com)
Progress since last SA4 meeting
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  In support of the integration of Haptics media in 3GPP services: Scene Description (S4aR250011), Messaging services (S4-250053), OpenXR API description (S4aR250012)
  Refined text and editorial changes (S4aR250013), use case (S4-250053), codec performances (S4-250055)
  Provided information on QoS, QoE (S4-250056)
Any recommendations based on the agreements?
  Agree TR V1.0.1 as basis to progress the work.
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Address the 13 input contributions (scope, gap, conclusion, improvement to existing sections)
  Conclude the TR.
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1040020 | Study on Haptics in 5G Media Services | FS_HapticsMedia | 3/3/2025 | 15% | SP-241121 | 60% | 
FS_HapticsMed

## Slide 20: Study on Spatial Computing for AR Services (FS_ARSpatial)
Rapporteur:
Hamza, Ahmed, InterDigital Canada, <Ahmed.Hamza@InterDigital.com>
Progress since last SA4 meeting
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  No progress during ad-hoc calls
Any recommendations based on the agreements?
  None
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Discuss 3 contributions
    1 contribution with updates to related work (S4-250183)
    2 contributions on architecture mapping and call flows (S4-250193, S4-250194)
  Update time and work plan
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1040022 | Study on Spatial Computing for AR Services | FS_ARSpatial | 6/6/2025 | 10% | SP-240927 | 25% | 

## Slide 21: Study on immersive Real-Time Communication for WebRTC, Phase 2 (FS_iRTCW_Ph2)
Rapporteur:
Hakju Ryan Lee, Samsung Electronics, CO., LTD, hakju00.lee@samsung.com
Progress since last SA4 meeting
What happened during the Adhoc calls, i.e., which key issues & documents were agreed?
  No input
Any recommendations based on the agreements?
  None
Plans for the meeting based on the input contributions that have been reviewed by the rapporteur
  Agreements on KI#1 (Media capability for RTC system)
  Discussion of way forward for metadata and signalling
UID | Name | Acronym | Target (mm/yyyy) | Old % | WID | New % | Change or comment
1050037 | Study on immersive Real-Time Communication for WebRTC, Phase 2 | FS_iRTCW_Ph2 | 6/6/2025 | 0% | SP-241374 | 15% |