3GPP TSG-SA WG4 Meeting #132	S4-251047

Japan, Fukuoka, 19 – 23 May 2025	Revision of S4-250918

# Source:	Fraunhofer IIS (Rapporteur)

# Title:	[FS_ACAPI] Updated Time Plan

# Document for:	Agreement

# Agenda Item:	7.8

# Proposed Time and Work Plan

| Meeting |  | Completion Status |
| --- | --- | --- |
| SA4#127 (29 January - 2 February 2024, Sophia Antipolis, FR) | - Endorse work item in S4-240511 | Target 0% |
| SA4-SA4 AH Telco on Rel-19 | - Agree work item in S4-240528 |  |
| SA#103 (March 19 - 22 2023, Maastricht, NL) | - Approve work item in SP-240064 |  |
| SA4#127bis-e (8 - 12 April 2024, Online) | - Agree on Work Plan in S4-240605 | Target 5% |
| SA4#128 (20 – 24 May 2024, Jeju Island, KR) | - Agree on Initial Draft (Skeleton) for TR 26.858 - Start to identify potential gaps in the 3GPP and W3C specifications to enable and simplify the use of the codecs in TS 26.114 and TS 26.117 in WebCodecs and WebRTC - Start to identify common APIs for the relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, that are useable to expose the identified interfaces. | Target 25% |
| SA#104 (18 – 21 June 2024, China) | - No actions |  |
| SA4#129-e (19 – 23 August 2024, online) | - Start to identify relevant interfaces on hardware/firmware platforms to the (supported) relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, and characterize signal (including control signal and metadata) flows on these interfaces. - Continue to identify potential gaps in the 3GPP and W3C specifications to enable and simplify the use of the codecs in TS 26.114 and TS 26.117 in WebCodecs and WebRTC - Continue to identify common APIs for the relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, that are useable to expose the identified interfaces. - Progress TR - Potentially communicate with external organizations, on need basis | Target 50% |
| SA#105 (10– 13 September 2024, Melbourne, AU) | - No action |  |
| SA4#130 (18 – 22 November 2024, Orlando, FL, US) | - Continue to identify potential gaps in the 3GPP and W3C specifications to enable and simplify the use of the codecs in TS 26.114 and TS 26.117 in WebCodecs and WebRTC - Copntinue to identify common APIs for the relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, that are useable to expose the identified interfaces. | Target 30% |
| SA#106 (10 – 13 December 2024, Madrid, ES) | - No Action |  |
| Telco on FS_ACAPI | - Continue to identify relevant interfaces on hardware/firmware platforms to the (supported) relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, and characterize signal (including control signal and metadata) flows on these interfaces. - Continue to identify potential gaps in the 3GPP and W3C specifications to enable and simplify the use of the codecs in TS 26.114 and TS 26.117 in WebCodecs and WebRTC - Continue to identify common APIs for the relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, that are useable to expose the identified interfaces. |  |
| SA4#131 (17-21 February 2025, Geneva, CH) | - Progress to identify potential gaps in the 3GPP and W3C specifications to enable and simplify the use of the codecs in TS 26.114 and TS 26.117 in WebCodecs and WebRTC - Progress to identify common APIs for the relevant codecs defined in TS 26.114 and TS 26.117. | Target 50% Actual: 40% |
| Audio SWG Call (21st March, 14:00 -16:00) | - Progress on relevant interfaces on hardware/firmware platforms to the (supported) relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, and characterize signal (including control signal and metadata) flows on these interfaces. - Progress on common APIs for the relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, that are useable to expose the identified interfaces. - Provide draft recommendations for interfaces and adapters to WebRTC and WebCodec. - Provide draft recommendations for potential normative work in 3GPP and/or other organizations, for example W3C and IETF. |  |
| SA4#131-bis-e (11-17 April, 2025) | - Progress to identify relevant interfaces on hardware/firmware platforms to the (supported) relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, and characterize signal (including control signal and metadata) flows on these interfaces. - Progress to identify potential gaps in the 3GPP and W3C specifications to enable and simplify the use of the codecs in TS 26.114 and TS 26.117 in WebCodecs and WebRTC - Progress to identify common APIs for the relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, that are useable to expose the identified interfaces. - Provide recommendations for interfaces and adapters to WebRTC and WebCodec. - Provide recommendations for potential normative work in 3GPP and/or other organizations, for example W3C and IETF. - Potentially communicate with external organizations, on need basis | Target 60% Actual: 42% |
| SA4#132 (19 – 23 May 2025, Fukuoka, JP) | - Progress to identify relevant interfaces on hardware/firmware platforms to the (supported) relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, and characterize signal (including control signal and metadata) flows on these interfaces. - Progress to identify potential gaps in the 3GPP and W3C specifications to enable and simplify the use of the codecs in TS 26.114 and TS 26.117 in WebCodecs and WebRTC - Progress to identify common APIs for the relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, that are useable to expose the identified interfaces. - Potentially communicate with external organizations, on need basis | Target 70% Actual: 47% |
| SA4#133-e (21 – 27 July 2025, online) | - Progress to identify relevant interfaces on hardware/firmware platforms to the (supported) relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, and characterize signal (including control signal and metadata) flows on these interfaces. - Progress to identify potential gaps in the 3GPP and W3C specifications to enable and simplify the use of the codecs in TS 26.114 and TS 26.117 in WebCodecs and WebRTC - Progress to identify common APIs for the relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, that are useable to expose the identified interfaces. - Provide recommendations for interfaces and adapters to WebRTC and WebCodec. - Provide recommendations for potential normative work in 3GPP and/or other organizations, for example W3C and IETF. - Potentially communicate with external organizations, on need basis | Target 60% |
| Ad-hoc call | - Progress to identify relevant interfaces on hardware/firmware platforms to the (supported) relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, and characterize signal (including control signal and metadata) flows on these interfaces. - Progress to identify potential gaps in the 3GPP and W3C specifications to enable and simplify the use of the codecs in TS 26.114 and TS 26.117 in WebCodecs and WebRTC - Progress to identify common APIs for the relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, that are useable to expose the identified interfaces. - Provide recommendations for interfaces and adapters to WebRTC and WebCodec. - Provide recommendations for potential normative work in 3GPP and/or other organizations, for example W3C and IETF. - Potentially communicate with external organizations, on need basis | Target 80% |
| SA#109 (16-19 September 2025, Beijing, CN) | - Present TR for Information |  |
| SA4#132 (11 – 17 November 2025, Dallas, US) | - Complete to identify relevant interfaces on hardware/firmware platforms to the (supported) relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, and characterize signal (including control signal and metadata) flows on these interfaces. - Complete to identify potential gaps in the 3GPP and W3C specifications to enable and simplify the use of the codecs in TS 26.114 and TS 26.117 in WebCodecs and WebRTC - Complete to identify common APIs for the relevant codecs defined in TS 26.114 and TS 26.117 and other common pre- and postprocessing blocks, including capture front end and renderer, that are useable to expose the identified interfaces. - Provide recommendations for interfaces and adapters to WebRTC and WebCodec. - Provide recommendations for potential normative work in 3GPP and/or other organizations, for example W3C and IETF. - Potentially communicate with external organizations, on need basis | Target 100% |
| SA#110 (9-12 December 2025, Baltimore, US) | - Present TR for approval |  |