Source:	IVAS Rapporteur

Title:	IVAS Permanent document IVAS-2b: IVAS_Codec_Ph2 Project Plan, v.1.4.0

Agenda Item:	7.5

- Introduction

The IVAS_Codec_Ph2 work item has been approved at the SA plenary #104 in document SP-241000, and further revised and approved at SA#107 in SP-250262. The work item has the following objectives:

- A fixed-point C-code to be part of TS 26.251 having:

  - Same functionalities and equivalent performance as the floating-point C-code in TS 26.258.

  - Full interoperability with floating-point C-code in TS 26.258.

  - Comparable complexity as the floating-point C-code in TS 26.258.

This includes verification of 3rd party delivered code and necessary adaptation to the latest version of TS 	26.258. This might include some alignment of floating-point C-code in TS 26.258.

- Test vectors for bit-exact conformance testing of IVAS fixed-point implementations based on the fixed-point C-code to be part of TS 26.252.

- Evaluate the decoder robustness to (undetected) corrupted bit streams and address arising issues.

- Characterization of the IVAS codec based on the floating-point and fixed-point C-codes, and documentation of characterization results into TR 26.997.

- Enhancements to codec conformance test procedures and criteria. Under this objective, a conformance process (including tools and test vectors) of IVAS for non-bit-exact floating-point implementations shall be developed, aligned with the conclusions of TR 26.843. More specifically, this work includes the following steps:

  - Specification of tools and conformance test vectors suitable for performing IVAS conformance testing.

  - Definition of relevant testing processes and criteria, based on the latest IVAS floating-point reference code.

    - The conformance testing processes and criteria shall be tight enough to ensure equivalent quality and interoperability with

      - implementation of the floating-point reference code that meets the bit-exact conformance requirements for this code specified in TS 26.252 and

      - implementation of the fixed-point reference code that meets the bit-exact conformance requirements for this code specified in TS 26.252.

    - At the same time, the coverage of the conformance testing processes and criteria shall be sufficient to avoid interoperability issues between implementations found conformant based on the non-bit-exact criteria and conformant implementations based on the bit-exact criteria.

  - Investigation on the applicability of the testing processes and criteria, which includes:

    - Robustness testing with validation that inadequate optimizations are properly detected while adequate optimizations still pass the criteria.

  - Definition of a mandatory non-bit-exact IVAS conformance testing process to be included in TS 26.252 using the tools, conformance criteria and conformance test vectors developed under this work item objective.

- Investigate potential applicability of a similar non-bit exact conformance testing procedures for IVAS fixed-point implementations.

- Definition of relevant tiers of functionality to be implementable on a wide range of UEs with different capabilities, balancing user experience and implementation complexity/cost.

- Enhancements to the RTP payload format and SDP negotiation, including split rendering operation.

- Update relevant system and service specifications.

- Timeplan

The timeplan for the execution of the IVAS_Codec_Ph2 work item objectives is in the following table.

| Meeting | Objectives |
| --- | --- |
| TSG SA#104 (18th – 21st June 2024) | - IVAS_Codec_Ph2 Work Item approved by SA Plenary |
| SA4#129-e (16th – 23rd August 2024, online) | - Agree on initial time plan |
| 31st August 2024 | - Delivery of IVAS fixed-point Decoder and Renderer by Ittiam to SA4, fulfilling the FL-to-FX requirements |
| Audio SWG call (13th September 2024) | - Review progress of the fixed-point code conversion |
| 30th September 2024 | - Delivery of IVAS fixed-point Encoder by Ittiam to SA4, fulfilling the FL-to-FX requirements, covering the following operation modes: - Mono (EVS) - ISM (core coder) - Stereo - MCT |
| Audio SWG call (18th October 2024) | - Review progress of the fixed-point code conversion |
| 31st October 2024 | - Delivery of IVAS fixed-point Encoder by Ittiam to SA4, fulfilling the FL-to-FX requirements, covering the following operation modes: - MASA - SBA - Parametric modes |
| Audio SWG call, TBD | - Review progress of the fixed-point code conversion |
| SA4#130 (18th – 22nd November 2024) | - Verification and Agreement by SA4 on Delivery by Ittiam of IVAS fixed-point Decoder and Renderer, fulfilling the FL-to-FX requirements - Agreement on definition of IVAS Levels |
| 30th November 2024 | - Delivery of IVAS fixed-point Encoder v1 to SA4, targeting fulfilment of FL-to-FX requirements |
| Audio SWG call, TBD | - Review progress of the fixed-point code conversion |
| TSG SA#106 (10th – 12th December 2024) | - Approval by TSG SA (SA#106) of Delivery of IVAS fixed-point Decoder and Renderer, fulfilling the FL-to-FX requirements, based on agreement in SA4 (SP-241766) |
| Audio SWG call, (17th January 2025, 12:00-15:00 CET) (Canceled) | - Review progress of the fixed-point code conversion |
| 31st January 2025 | - Delivery of the fixed point Encoder v2, targeting fulfilment of FL-to-FX requirements, as basis for subjective verification |
| SA4#131 (17th – 21st February 2025) | - Review the timeplan taking into account the status of fixed-point development |
| March 7th | - Delivery of Encoder v2.1 |
| TSG SA#107 (12th – 14th March 2025) |  |
| Email confirmation 14th March 2025 | - Pre-verification of Encoder v2.1 to assess if it is ready for subjective verification Conclusion: it is ready for subjective verification for some operating points |
| Audio SWG call (21st March, 14:00-16:00) Submission deadline: March 20th, 14:00, Host : Ericsson (cancelled) | - Progress IVAS_Codec_Ph2 |
| SA4#131-bis-e (11th – 17th April 2025) | - Progress IVAS_Codec_Ph2 |
| SA4#132 (19th – 23rd May 2025) | - Verification by TSG SA WG 4 (SA4) on Encoder v2.1 (with potential additional bugfixes) - Delivery of the fixed point Encoder v3 (addressing most severe issues identified by the verification) – Determined to be unnecessary - Agreement by TSG SA WG 4 (SA4) on Delivery of Encoder, fulfilling FL-to-FX requirements – Agreed to be at 90% - Finalization of IVAS characterization permanent documents, including: - IVAS-7b Processing Plan for Characterization Phase - IVAS-8b Test Plan for Characterization Phase - Agree on CR for enhancements to the RTP payload format and SDP negotiation, including split rendering operation - Start investigating IVAS non-be conformance criteria and testing procedure - Start identifying potential tools for non-be conformance - Gather data based on test runs on various platforms and compilers |
| TSG SA#108 (10th-13th June, 2025) | - Approval by TSG SA of Delivery of Encoder, fulfilling FL-to-FX requirements, based on agreement in SA4 |
| 18th July, 2025 | - Delivery of Maintenance (further corrections and optimizations) to IVAS fixed-point Encoder/Decoder/Renderer |
| Audio SWG call (17 June, 2025 14-16 CEST), Submission deadline 16 June, 2025 14:00 CEST, Host: Ericsson | - Progress IVAS fixed point code development - Progress IVAS characterization test planning - Continue to investigate IVAS non-be conformance criteria and testing - Identification of suitable tools for non-be conformance - Gather data based on test runs on various platforms and compilers |
| SA4#133-e (18th -25th July, 2025) | - Finalization of IVAS characterization permanent documents, including: - IVAS-7b Processing Plan for Characterization Phase - IVAS-8b Test Plan for Characterization Phase - Agreement by TSG SA WG 4 (SA4) on Delivery of Maintenance (further corrections and optimizations) to IVAS fixed-point Encoder/Decoder/Renderer - Decision on launching characterization tests - Continue to investigate IVAS non-be conformance criteria and testing procedure - Gather data based on test runs on various platforms and compilers |
| Audio SWG call on IVAS_Codec_Ph2 (8th September 2025), 14:00-16:00 CEST. Submission deadline: 4th September, 2025, 14:00 CEST, Host: Ericsson | - Finalizing IVAS-7b - Finalizing IVAS-8b SA4 power to agree updates to IVAS-7b (processing plan) and IVAS-8b (test plan) for IVAS characterization test |
| September – November 2025 | - IVAS characterization testing |
| TSG SA#109 (16th-19th September, 2025) | - Approval on Delivery of Maintenance (further corrections and optimizations) to IVAS fixed-point Encoder/Decoder/Renderer |
| SA4#134 (17th – 21st Nov 2025) | - Verification of IVAS fixed-point C-code for TS 26.251 having - Same functionalities and equivalent performance as the floating-point C-code in TS 26.258. - Full interoperability with floating-point C-code in TS 26.258. - Comparable complexity as the floating-point C-code in TS 26.258. - Note: This includes necessary adaptation to the latest version of TS 26.258 on top of the delivery by Ittiam and might include some adaptation of the floating-point C-code in TS 26.258. - Agreement on TS 26.251 (IVAS fixed-point C-code) based on the verification reports. - Agreement on related CR to TS 26.249, moving ISAR fixed-point code to TS 26.251. - Agreement on CR to TS 26.258 on alignment between floating-point code and fixed-point code in TS 26.251 - Agreement on relevant CRs for: - Test sequences for bitexact testing of TS 26.251 (TS 26.252) - Agreement on CRs for update of relevant system and service specifications (26.114, 26.117, 26.119) - Characterization test results available for analysis - Agreement on characterization test results to be incorporated into TR 26.997 - Evaluate the decoder robustness to (undetected) corrupted bit streams and address arising issues - Agree on enhanced conformance procedures and criteria, including tools and test vectors of IVAS for non-bit-exact floating-point implementations, aligned with the conclusions of TR 26.843. - Define IVAS non-be conformance criteria and testing procedure |
| TSG SA#110 (9th-12th December, 2025) | - CR to TR 26.997 on IVAS Codec characterization, for approval - CR to TS 26.252 on enhanced conformance procedures and criteria, for approval - TS 26.251 (IVAS fixed-point C-code), for approval - CR to TS 26.252 on Test sequences for TS 26.251, for approval - CR to TS 26.249, moving ISAR fixed-point code to 26.251, for approval - CR to TS 26.258 on alignment between floating-point code and fixed-point code in TS 26.251, for approval - CR to TS 26.253 on corrections corresponding to TS 26.258 - CR to TS 26.114 on enhanced support for the IVAS Codec, for approval - CR to TS 26.117 with reference to TS 26.251, for approval - CR to TS 26.119 on enhanced support for the IVAS Codec, for approval |

- Revision history

| Date | Meeting | Subject/Comment | Old | New |
| --- | --- | --- | --- | --- |
| 2025-02-19 | SA4#131 | Initial version based on S4-250085 and edits during SA4#131 |  | 0.1.0 |
| 2025-04-08 | SA4#131-bis-e | Update prior to SA4#131-bis-e meeting | 0.1.0 | 1.1.1 |
| 2025-04-16 | SA4#131-bis-e | Update during the meeting to address comments received | 1.1.1 | 1.2.0 |
| 2025-05-22 | SA4#132 | Update during the meeting including adding time-plan for non-BE conformance | 1.2.0 | 1.3.0 |
| 2025-07-21 | SA4#133-e | Update during the meeting | 1.3.0 | 1.4.0 |

Huan-yu Su, Huawei; email: su.huanyu@huawei.com