## Slide 1: Rel-20 SA5 Work Planning SA5#162, Goteborg, Sweden, 25 - 29 August 2025
Zou Lan, 3GPP SA5 Chair, HUAWEI
Thomas Tovinger, 3GPP SA5 Vice-Chair, ERICSSON
Anatoly Andrianov, 3GPP SA5 Vice-Chair, NOKIA
Gerald Görmer, SA5 Charging SWG Chair, MATRIXX Software

## Slide 2: Content
Release 20
  3GPP SA background information
  3GPP SA5 general information
  SA5 time plan
    5GA
    6G
  TU planning

## Slide 3: SA#108 information: Rel-20 5GA timeline (ref:SP-250890)

## Slide 4: SA#108 information: Release 20 (FS) 6G timeline (ref:SP-250890)

## Slide 5: SA#108 information: Overall 6G Workplan

## Slide 6: Selecting release for Charging/OAM aspects proposals endorsed in SA#108
Selecting the Release for Charging/OAM aspects (SP-250888): 4 proposals are endorsed. (details in SA report section 5.1) Action1: Request SA5 companies to follow the endorsed guidelines for future SA5 work.
SA#108 report in: https://www.3gpp.org/ftp/tsg_sa/TSG_SA/TSGS_108_Prague_2025-06/Report

## Slide 7: Content
Release 20
  3GPP SA background information
  3GPP SA5 general information
  SA5 time plan
    5GA
    6G
  TU planning

## Slide 8: Rel-19~21 timelines with SA5
(updated SA5 based on SP-250420)
SA5 Rel-20 5GA study/norm
SA5 6G study(ies)
SA5 Rel-19 5GA study/norm
or

## Slide 9: Detailed Rel-20 time plan with 5GA/6G
Overall Plan:
Start of Rel-20: Jun.2025 (SA#108/SA5#161)
End of Rel-20 (TBD) : Mar.2027 (SA#115/SA5#171) or Jun.2027 (SA#116/SA5#172)
5GA Rel-20:
OAM/CH prime feature:
It’s recommended to take max 6~9 months for study phase if normative work is planned for Rel-20.
Start of Rel-20 prime study: right after Jun.2025 (SA#108/SA5#161)
End of Rel-20 prime normative: Dec.2026 (SA#114/SA5#170)
OAM/CH supporting to network feature(SA5 is ready to support network features pending the availability of inputs from other WGs)
All supporting studies/normative WIDs to be agreed no later than May.2026 (SA5#167) and target for approval in Jun.2026 (SA#112).
Start of Rel-20 supporting study (if needed): right after Jun.2026 (SA#112/SA5#167)
End of Rel-20 supporting normative: Mar.2027 (SA#115/SA5#171)
6G SI Rel-20:
Start of Rel-20 study: Sep.2025 (SA#109/SA5#163)
End of Rel-20 study: Mar.2027 (SA#115/SA5#171) or Jun.2027 (SA#116/SA5#172)
Note: Check point on Mar. 2026(SA#111/SA5#165) for 6G end time and future 6G workplan

## Slide 10: SA5 Rel-20 Capacity Summary
SA5 capacity :
  Max TUs : 124 (OAM) / 80 (Charging)
    Additional buffer TUs: 61(OAM)/40(CH)
  Max number of SIs/WIs: 10~15 (OAM) / 6~10 (Charging)
    Note: one feature made up of SI+WI is counted as one item
  Max TUs per Feature: 12~8 TU
  Adopt 1:1 on TU allocation portion of 5GA part/6G part in Rel-20
Assumptions
  Start: Jun 2025, End: Mar 2027 (21 months)
  One track for OAM and One track for Charging
  Number of meetings: 10
  Expected total TUs per meeting (for all releases)(with Q5 included): 18.5 (OAM) / 12 (Charging)
  Total TUs (for all releases): 185 (OAM) / 120 (Charging)
  TUs for maintenance of past releases: 35 (OAM) / 20 (Charging)
Note: detailed TU calculation see slides 22~27

## Slide 11
Expectation of SA5 rapporteur role:
  Actively contribute and facilitate the progress of the WI/SI, coordinate the discussion within SA5 and with external groups if necessary
  Prepare tdoc sequence list and tdoc grouping suggestion before the meeting
  Provide inputs to TU planning/TU consumption for each meeting.
  Provide timely progress report in NWM before closing plenary with clear highlights for external readers with references to the WID/SID objectives.
  Implement any necessary draftCR/draft TR/draft TS and facilitate the email approval of draftCR/draft TR/draft TS
  Moderate the breakout sessions/offline calls and provide summary report
  Refer to TR 21.900 clause 6.3.2 for Role of the work item rapporteur and 4.1.2 Role of the specification rapporteur
  Be familiar with 3GPP drafting rules as specified in TR 21.801.
If you agree with the expectation above, please provide the nomination for the new WIDs/SIDs (one company one email please send the nominee’s name for Rel-20 SID/WID directly to SA5 chair and SA Chair, rather than sharing it on the SA reflector):
  Please consider the guidance (bullet 2/3/4/5) provided in Rel-19 Rapporteurship document SP-230746 from SA.
  Indicate if the nomination is for the role of Primary Rapporteur.
  Indicate if the nomination is for the role of Secondary Rapporteur.
  The work responsibility of Primary/Secondary Rapporteurs shall be clearly described if there are proposals for co-rapporteurs.
  Note： While operating in Rapporteurs roles, delegates are expected to carry out their assigned duties with impartiality and in the interests of 3GPP, and regular participation to SA5 f2f meeting is a must for commitment to the rapporteur role
Expectation of SA5 rapporteur role

## Slide 12: Content
Release 20
  3GPP SA background information
  3GPP SA5 general information
  SA5 time plan
    5GA
    6G
  TU planning

## Slide 13
Release 20 5GA timeline with SA5
(updated SA5 based on SP-250890)
Now
SA5 (5GA OAM/CH Prime) management St.+Norm Stage1/2/3
OAM/CH Prime
SID def.
①
②
SA5 (OAM/CH Stage 2/Stage3 supporting) SA&RAN (SA5)
OAM/CH Supporting
SID def.(if needed)
Workshops 5GA SA5
3GPP SA5
Timeline
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
TSGs
SA1 5GA SID definition
100%
SA1 5GA Studies + Norm 80%
100%
St. 2 (SA2, SA6, …) 5GA St.+Norm 80%
Stage 3 5GA St + Norm
#113
Sep.
#114
Dec.
#115
Mar.
Jun
RAN1
RAN Completion (RAN2/3/4core)
#116
RAN4 C.def.
RAN4 Perf
RP Content def.
2025
2026
2027
5GA ASN.1 & Open APIs
St.3 SID def. TBD
Release 20 5GA timeline
Note: All starting dates are indicative
Workshops
5GA RAN & SA
RAN WG SID def.
St.2 SID def.
OAM/CH prime feature:
It’s recommended to take max 6~9 months for study phase if normative work is planned for Rel-20.
Start of Rel-20 prime study: right after Jun.2025 (SA#108/SA5#161)
End of Rel-20 prime normative:
Dec.2026 (SA#114/SA5#170)
OAM/CH supporting to network feature(SA5 is ready to support network features pending the availability of inputs from other WGs)
All supporting studies/normative WIDs to be agreed no later than May.2026 (SA5#167) and target for approval in Jun.2026 (SA#112).
Start of Rel-20 supporting study (if needed): right after Jun.2026 (SA#112/SA5#167)
End of Rel-20 supporting normative: Mar.2027 (SA#115/SA5#171)
①
②

## Slide 14: SA5 Rel-20 5GA Content Definition steps
Following SA content definition steps guidance in SP-241738 :
Discussion and Guidance for Rel-20 5GA Scope: The content proposals for SA5 Rel-20 5GA being discussed during the SA5 Rel-20 5GA Workshop in January and February.
  The potential topics include a list of prime and supporting topics for SA5 Rel-20 5GA.
  Maximum total number of SID/WID for OAM/CH Rel-20 is 15/10 and 1:1 TU allocation portion of 5GA part/6G part in Rel-20 estimates will be taken into account.
    Number of 5GA topics for OAM
      Maximum 62 TUs available (e.g. roughly max 8 with TU allocation per topic 8 TUs)
      46 TUs for OAM Prime, 16 TUs for network supporting based on Rel-19 TU usage experience (consumed TU ratio of prime and supporting are around 3:1)
    Number of 5GA topics for CH
      Maximum 40 TUs available (e.g. max 5 with TU allocation per topic 8 TUs)
    All the topics shall be technically ready before Tuesday 20 May, 2025 (SA5#161) to be in the list for prioritization.
    Prioritization is targeted to be done in SA5#161 if needed.
  Note1: One feature made up of SI+WI is counted as one item
  Note2: Small network support features (mini WIDs) are not counted in the maximum number. One Mini WID will allocate maximum 2 TUs.
Moderated Email Discussions: Moderated Email Discussions to develop SID/WID details corresponding to the Rel-20 5GA topics identified in the prime/supporting feature list. The focus will be on defining technical objectives, work tasks, and estimated budgets for each task. These discussions are planned to start after SA5#159. Further prioritization, if necessary, will be handled in SA5#160/SA5#161 (for the first package) and SA5#166/ SA5#167(for the second package) .
Approval of Selected Rel-20 5GA SID/WID (first package): Companies may submit the SID/WID to SA5#160/#161 for WG agreement. SA5 targets to submit WID/SIs to SA#108 for approval. Ideally, the Rel-20 5GA SID/WID for approval at this step should have no dependencies on Rel-20 work in RAN and SA. SID/WID for approval should follow the guidance on Rapporteurship (see SP-230746). Part of WG capacity will be allocated during the first step approval process.
WG commences Rel-20 5GA SI/WI Work: After the approval of the SID/WID at SA#108, SA5 will start working on the approved SID/WID during Q3 meetings.
Final Approval of Rel-20 5GA SID/WID (second package): This represents the second and final step in the approval process for the Rel-20 5GA content definition. Companies may submit additional SID/WID to SA5#166/#167 for WG agreement. SA5 targets to submit the second package of WID/SIs to SA#112 for approval. The Rel-20 5GA SID/WID for approval at this step should be mainly the network support features to Rel-20 work in RAN and SA. SID/WID for approval should follow the guidance on Rapporteurship (see SP-230746).

## Slide 15
Ongoing SA5 Rel-20 5GA topics
Unique_ID | Name | Acronym | Start | Finish | %Complete | Hyperlink | WI rapporteur name | Impacted TSs and TRs
1080012 | Study on AIML management phase 3 | FS_AIML_MGT_Ph3 | Thu 05/06/25 | Tue 03/03/26 | 0% | SP-250867 | Hassan Al-Kanani (NEC), | 28.882
1080005 | Study on energy efficiency and energy saving aspects of 5G Advanced | FS_Energy_Ph4_OAM | Thu 05/06/25 | Tue 03/03/26 | 0% | SP-250860 | Srilakshmi S (Nokia), | 28.885
1080006 | Study on intent driven management services for mobile network phase 4 | FS_IDMS_MN_Ph4 | Thu 05/06/25 | Tue 03/03/26 | 0% | SP-250861 | Ruiyue Xu (Huawei), | 28.881
1080007 | Study on Management Data Analytics (MDA) phase 4 | FS_eMDAS_Ph4 | Thu 05/06/25 | Tue 03/03/26 | 0% | SP-250862 | Brendan T Hassett (Huawei), | 28.886
1080008 | Study on Service Based Management Architecture enhancement phase 4 | FS_SBMA_Ph4 | Thu 05/06/25 | Tue 03/03/26 | 0% | SP-250863 | Kai Zhang (Huawei), | 28.884
1080009 | Study on Enhanced exposure of management services | FS_EnExpo | Thu 05/06/25 | Tue 03/03/26 | 0% | SP-250864 | Winnie Nakimuli (Nokia) | 28.888
1080010 | Study for Data management phase 3 | FS_MADCOL_Ph3 | Thu 05/06/25 | Tue 03/03/26 | 0% | SP-250865 | Sreekumar PK (Nokia), | 28.887
1080011 | Study on management aspects of Network Digital Twins phase 2 | FS_NDT_Ph2 | Thu 05/06/25 | Tue 03/03/26 | 0% | SP-250866 | Xian Zhao (Huawei), | 28.883
1080013 | Study on Closed Control Loop Management phase 2 | FS_CCLM_Ph2 | Thu 05/06/25 | Tue 03/03/26 | 0% | SP-250868 | Deepanshu Gautam (Samsung), | 28.889
1080015 | 5G performance measurements/KPIs and Trace/MDT/QoE | PM_KPI_Trace_MDT_QoE-OAM | Thu 05/06/25 | Wed 09/09/26 | 0% | SP-250879 | XiuMin Chen (China Telecom), | 28.552/28.554/28.532/28.558/32.404/32.421/32.422/32.423/28.404/28.405/28.406/28.622/28.623/28.541
1080017 | Management Aspects related to NWDAF phase 3 | NWDAF_Ph3-OAM | Thu 05/06/25 | Sat 06/06/26 | 0% | SP-250881 | Song Zhao (China Telecom), | 28.541/28.552/28.554/
1080018 | 5G Advanced NRM features phase 4 | AdNRM_Ph4-OAM | Thu 05/06/25 | Sat 12/12/26 | 0% | SP-250882 | Sean Sun (Nokia) | 28.540/28.541/28.622/28.623/32.160
1080016 | OAM support for Extended Reality and Media service (XRM) phase 2 | XRM_Ph2-OAM | Thu 05/06/25 | Sat 06/06/26 | 0% | SP-250880 | Xie Pengxiang (ZTE) | 28.540; 28.541; 28.552; 28.554
1080014 | Study on Charging Aspects of CAPIF phase 3 | FS_CAPIF_Ph3_CH | Thu 05/06/25 | Tue 03/03/26 | 0% | SP-250869 | João Rodrigues (Nokia) | 28.891

## Slide 16
SA5 Rel-20 5GA topics (TU Budget)
OAM | Rel-20 5GA topics | Planned TU
1 | Intent driven management enhancement | 8
2 | AIML management enhancement | 8
3 | NDT enhancement | 4
4 | SBMA enhancement | 8
5 | Energy efficiency enhancement | 5
6 | MDA enhancement | 4
7 | Data Management enhancement | 4
8 | MExpo enhancement | 4
9 | CCL enhancement | 4
10 | AdNRM | 4
11 | PM/KPI/Trace/MDT/QoE/SON enhancement | 5
12 | NWDAFM | 2
13 | XR management | 2
Total TU |  | 62
CH | Rel-20 5GA topics | Planned TU
1 | Charging Aspects of CAPIF | 1

## Slide 17: Content
Release 20
  3GPP SA background information
  3GPP SA5 general information
  SA5 time plan
    5GA
    6G
  TU planning

## Slide 18
Release 20 6G timeline with SA5
(updated SA5 based on SP-250890)
Now
SA5 6G SID def.
SA5 6G Study(ies)
3GPP SA5
Timeline
Workshops 6G SA5
or
Check point 6G SA5
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
TSGs
Workshop 6G TSGs
CT & St. 3 6G SID def.
#113
Sep.
#114
Dec.
#115
Mar.
Jun
Workshop SA1 on IMT-2030 use cases
#116
SA1 6G Study(ies)
SA1 6G SID def.
RP IMT-2030 disc.
RP ITU Study
RP 6G Study(ies)
RAN1 6G Study(ies)
SA2 6G Study(ies)
Stage 3 6G Study(ies)
2025
2026
2027
SA2 & RAN WGs 6G SID def.
SA3/4/5/6 6G SID def. TBD
RAN2/3/4 6G Study(ies)
Release 20 (FS) 6G timeline
or
TBD
Note: All starting dates are indicative
SA3/4/5/6 6G Study(ies)TBD
SA5 6G SI Rel-20:
Start of Rel-20 study: Sep.2025 (SA#109/SA5#163)
End of Rel-20 study: Mar.2027 (SA#115/SA5#171) or Jun.2027 (SA#116/SA5#172)
Note: Check point on Mar. 2026(SA#111/SA5#165) for 6G end time and future 6G workplan

## Slide 19: SA5 Rel-20 6G Content Definition steps
Following SA content definition steps guidance in SP-241738 :
Discussion and Guidance for Rel-20 6G Scope: The content proposals for SA5 Rel-20 6G being discussed during the SA5 Rel-20 6G Workshop in June.
  The potential topics should be categorized by prime and supporting topics.
  Maximum 62 TUs available for OAM, Maximum 40 TUs available for CH
  The study of 6G should start with 1 study item for OAM and 1 study item for CH.
  Moderator:
    OAM Moderator: Wang Zhao Ning (China Unicom)
    Charging Moderator: Mo Zhi wei (China Telecom)
Moderated Email Discussions: Moderated Email Discussions to develop SID details corresponding to the Rel-20 6G topics identified in the prime/supporting feature list. The focus will be on defining technical objectives, work tasks, and estimated budgets for each task. These discussions are planned to start after SA5#161.
Approval of Selected Rel-20 6G SID: Companies may submit the SID to SA5#162 for WG agreement. SA5 targets to submit SIs to SA#109 for approval. Ideally, the Rel-20 6G SID for approval at this step should have no dependencies on Rel-20 work in RAN and SA. SID for approval should follow the guidance on Rapporteurship (see SP-230746).
WG commences Rel-20 6G SI Work: After the approval of the SID at SA#109, SA5 will start working on the approved SID during Q4 meetings.
1
Mar.2025 SA
3GPP 6G Workshop
2
Jun~Aug. 2025
SA5 NWM/Email discussion for SID proposal
3
Aug.2025 SA5#162
Target to endorse SID proposal
4
Oct. 2025 SA5 6G studies start
5
6
Jun.25~26 2025 SA5 3GPP 6G Workshop
Sep. 2025 SA#109
Target to approve SID proposal
Aug.7 2025 SA5#161.2 rapporteur call
Rel-20 6G study preparation status

## Slide 20: Rel-20 Source of 6G Requirements
SA5 – Management, Orchestration and Charging
3GPP SA1
NGMN/ GSMA OPG&WSOLU/ TMF
Verticals (5G-ACIA, AECC…)
SA2/RAN2/RAN3
SA5 contributions
Management
/Charging support requirements
3GPP Service management/ Charging requirements
Management/Charging
Prime & support requirements
Operational/
Charging requirements
Management exposure requirements

## Slide 21: Content
Release 20
  3GPP SA background information
  3GPP SA5 general information
  SA5 time plan
    5GA
    6G
  TU planning

## Slide 22: SA5 calendar with OAM TU (one track)
Time | Monday | Tuesday | Wednesday | Thursday | Friday (Closing plenary)
Q0 (8:00~8:55) (If needed) | NA | Breakout (opt.) | Breakout (opt.) | Breakout (opt.) | Closing plenary Start at 8:30am (may change depends on the host restriction)
Q1 (9:00 - 10:30) | Plenary Session#1 (1TU) [Single Stream] | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
10:30 - 11:00 | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break
Q2 (11:00 - 12:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
12:30 - 14:00 | Lunch | Lunch | Lunch | Lunch | Lunch
Q3 (14:00 - 15:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
15:30 - 16:00 | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break
Q4 (16:00 - 17:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
17:30 - 17:40 | Break | Break | Break | Break | Break
Q5 (17:40 – 19:10) | Stream#1 (1TU) | Stream#1 (0.5 TU) Stop around 18:45 Social evening | Stream#1 (1TU) | Revision session | 
Assumption:
Every day = 5 sessions (TUs), total TU in 1 ordinary meeting (exclude closing plenary TUs) = 18.5 TUs

## Slide 23: TU Budget for SA5 OAM
Assumptions for SA5 OAM :
  6 ordinary meeting per year.
  Rel-20 spans 21 months for SA5 (with early start of studies) = 10 meetings
  1 Session = 1.5 hour time window
  Max 5 sessions per meeting day
  1 Stream = 1 TU (Time Unit)
  1 TU is time (i.e., 1.5 hours) spent to discuss/handle technical contributions.
  Revisions/Drafting/offline conference call are not counted for the TU estimates.
  OAM revision sessions normally planned to be in Thursday Q4 and Q5 (initial assump.)
  Statistics:
    1 parallel (OAM) stream per session => 18.5 TUs per meeting (incl. 2 TUs as buffer) = 185
    Assume Maintenance + Buffer = 33% => ~ 61 TU
    Resulting total TUs avail. f. SI/WI: 10 meetings x 18.5 sessions = 185 TU minus 61 => 124 TU
    With 15 SI/WI => Average 8 TU per SI/WI (0.8/meeting).

## Slide 24: SA5 Rel-20 OAM TU planning (Jan.2025~Mar.2027)
 | Maintenance+R18/R19 | R19 | R20 | R21 preparation | Buffer (revision session)
Jan.2025~Jun.2025: SA5#159~#161 (3 meetings) (5GA OAM/CH Prime SID def.) | 1.5 TU*3 meetings= 4.5 TU (CRs) | 13 TU*3 meetings= 39 TU | 2 TU*3 meetings = 6 TU | NA | 2 TU*3=6 TU
Jun.2025~Sep.2025: SA5#162 (1 meeting) (Rel-19 stage-3 freeze, first meeting for Rel-20 6G OAM/CH SID def.) | 1.5 TU (CRs) | 13 TU | 2 TU | NA | 2 TU
Oct.2025~Dec.2026: SA5#163~#169 (7 meetings) (OAM/CH Prime stage-3 freeze) SA5#165~#167 (3 meetings) (5GA OAM/CH Supporting SID def.) | 2.5 TU*7 meetings= 17.5 TU (CRs) | NA | 14 TU*7 meetings = 98 TU | NA | 2 TU*7=14 TU
Jan. 2027~Mar.2027: SA5#170~#171 (2 meetings) (5GA OAM/CH Supporting stage-3 freeze) (6G study completion) | 1.5 TU*2 meetings = 3 TU (CRs) | NA | 12 TU*2 meetings = 24 TU | 3 TU*2 meetings = 6 TU | 2 TU*2=4 TU
Total=185 TU | 22 TU | 13 TU | 124 TU | 6TU | 20 TU
Assumptions:
Every meeting day = 5 quarters (= 5 TUs)
Total TUs per meeting = 18.5 TUs
  Buffer = 2 TUs
  OAM = 16.5 TUs
    Maintenance CRs + remaining Rel-19 work (TU allocation will decrease over time )
    Rel-21 preparation work (TU allocation will be zero at the beginning and will increase over time )
    All remaining time is available for Rel-20 SIDs / WIDs
Total TUs allocated to Rel-20 SIDs / WIDs = 124 TUs

## Slide 25: SA5 calendar with CH TU (one track)
Time | Monday | Tuesday | Wednesday | Thursday | Friday (Closing plenary)
Q0 (8:00~8:55) (If needed) |  | Breakout (opt.) | Breakout (opt.) |  | Closing plenary Start at 8:30am (may change depends on the host restriction)
Q1 (9:00 - 10:30) | Plenary Session#1 (1TU) [Single Stream] | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
10:30 - 11:00 | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break
Q2 (11:00 - 12:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
12:30 - 14:00 | Lunch | Lunch | Lunch | Lunch | Lunch
Q3 (14:00 - 15:30) | Stream#1 (1TU) | Stream#1 (1TU) | Offline session | CH Closing | Closing plenary
15:30 - 16:00 | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break
Q4 (16:00 - 17:30) | Stream#1 (1TU) | Stream#1 (1TU) | Offline session | CH Closing | Closing plenary
17:30 - 17:40 | Break | Break | Break | Break | Break
Q5 (17:40 – 19:10) | Stream#1 (1TU) | Social evening | Offline session (Opt.) | CH Closing(Opt.) | 
Assumption:
Every day = 5 sessions (TUs), total TU in 1 ordinary meeting (exclude closing plenary and offline TUs) = 12 TUs

## Slide 26: TU Budget for SA5 CH
Assumptions for SA5 CH :
  6 ordinary meeting per year.
  Rel-20 spans 21 months for SA5 (with early start of studies) = 10 meetings
  1 Session = 1.5 hour time window
  Max 5 sessions per meeting day
  1 Stream = 1 TU (Time Unit)
  1 TU is time (i.e., 1.5 hours) spent to discuss/handle technical contributions.
  Revisions/Drafting/offline conference call are not counted for the TU estimates.
  CH revision sessions normally planned to be in Thursday Q1 and Q2 (initial assump.),CH closing plenary planned to be in Thursday Q3 and Q4.
  Detail statistics:
    1 (CH) stream per session => 12 TUs per meeting (incl. 2 TUs as buffer) = 120
    Assume Maintenance + Buffer = 33% as in SA2 => ~ 40 TU
    Resulting total TUs avail. f. SI/WI: 10 meetings x 10 sessions = 120 TU minus 40 => 80 TU
    With 10 SI/WI => Average 8 TU per SI/WI (0.8/meeting).
  Note: TU capacity for CH could be extended if more topics are proposed.

## Slide 27: SA5 Rel-20 CH TU planning (Jan.2025~Mar.2027)
Assumptions:
Every meeting day = 5 quarters (= 5 TUs)
Total TUs per meeting = 12 TUs
  Buffer = 2 TUs
  CH = 10 TUs
    Maintenance CRs + remaining Rel-19 work (TU allocation will decrease over time )
    Rel-21 preparation work (TU allocation will be zero at the beginning and will increase over time )
    All remaining time is available for Rel-20 SIDs / WIDs
Total TUs allocated to Rel-20 SIDs / WIDs = 80 TUs
 | Maintenance+R18/R19 | R19 | R20 | R21 preparation | Buffer (revision session)
Jan.2025~Jun.2025: SA5#159~#161 (3 meetings) (5GA OAM/CH Prime SID def.) | 1.5 TU*3 meetings= 4.5 TU (CRs) | 7.5 TU*3 meetings= 22.5 TU | 1 TU*3 meetings = 3 TU | NA | 2 TU*3=6 TU
Jun.2025~Sep.2025: SA5#162 (1 meeting) (Rel-19 stage-3 freeze, first meeting for Rel-20 6G OAM/CH SID def.) | 1.5 TU (CRs) | 6.5 TU | 2 TU | NA | 2 TU
Oct.2025~Dec.2026: SA5#163~#169 (7 meetings) (OAM/CH Prime stage-3 freeze) SA5#165~#167 (3 meetings) (5GA OAM/CH Supporting SID def.) | 1.5 TU*2 meetings+ 1 TU*5 meetings = 8 TU (CRs) | NA | 8.5 TU*2 meetings + 9 TU *5 meetings = 62 TU | NA | 2 TU*2=4 TU
Jan. 2027~Mar.2027: SA5#170~#171 (2 meetings) (5GA OAM/CH Supporting stage-3 freeze) (6G study completion) | 1 TU*2 meetings = 2 TU (CRs) | NA | 8 TU*2 meetings = 16 TU | 1 TU*2 meetings = 2 TU | 2 TU*2=4 TU
Total=120 TU | 11.5 TU | 6.5 TU | 80 TU | 2 TU | 20 TU

## Slide 28: Thank you!

## Slide 29: Sample of OAM TU planning and statistics
TU planning: to be proposed by rapporteurs and agreed by the group
TU statistics: to be filled by chair based on the time consumed after each meeting
This is an example to illustrate TU planning and statistics

## Slide 30
SA5 Rel-20 5GA candidate topics (NWM Links)
No | Topic | Topic moderator | NWM Link
1 | AIML management enhancement | Hassan Al-kanani (NEC) yizhi(Intel) | 9047
2 | Energy efficiency enhancement | Srilakshmi (Nokia) | 9027
3 | Intent driven management enhancement | Xu Ruiyue (Huawei), Mark Scott (Ericsson) | 9063
4 | NDT enhancement | Yushuang Hu (CMCC) | 9052
5 | CCL enhancement | Deepanshu Gautam (Samsung) /Stephen(Nokia) | 9040
6 | SBMA enhancement | Kai Zhang (Huawei) | 9037
7 | Cloud-native management and orchestration | Guangjing Cao (CMCC) | 9051
8 | MDA enhancement | Brendan Hassett (Huawei) | 9036
9 | Knowledge-assisted management / Semantics – Based Network Management | Zhaoning Wang (China Unicom) /Deepanshu(Samsung) | 9034
10 | Mexpo enhancement | Winnie Nakimuli (Nokia) | 9044
11 | MADCOL/Data Management | Sreekumar Pothera Kalloor (Nokia) | 9046
12 | Trace/MDT/QoE/SON enhancement | Robert Petersen (Ericsson) | 9029
13 | Security Monitoring | Balazs Lengyel (Ericsson) | 9059
No | Topic | Topic Moderator | NWM Link
14 | ISAC management | Bangqiu Ruan (ZTE) | 9054
15 | NWDAFM | Zhen Li (China Telecommunications) | 9049
16 | AdNRM | Sean(Nokia) | 9053
17 | XR management | Xiepengxiang (ZTE) | 9138
18 | PM/KPI | Chenxiumin (China Telecom) | 9139
No | Topic | Topic Moderator | NWM Link
19 | Charging reliability enhancement (failure handling) | Yimeng Deng (Huawei) | 9057
No | Topic | Topic Moderator | NWM Link
20 | CAPCH | João Rodrigues (Nokia) | 9062
Rel-20 5GA OAM Prime topics
Rel-20 5GA OAM Support topics
Rel-20 5GA CH Prime topics
Rel-20 5GA CH Support topics