## Slide 1: SA6#47-e Work Plan Review
Suresh Chitturi
SA6 Chair
SAMSUNG

## Slide 2: Overview: Ongoing Studies
Study Item | WI Code | SID Approved | SA#94-e | SA6#47-e | Target Completion | Remarks
Study on Mission Critical Services support over 5G System | FS_MCOver5GS | SA#80 (06/2018) | 91% | TBD | SA#96 (06/2022) | 
Study of Interconnection and Migration Aspects for Railways | FS_IRail | SA#88 (06/2020) | 85% | TBD | SA#94 (12/2021) | TR for approval at SA#95-e
Study on Network Slice Capability Exposure for Application Layer Enablement | FS_NSCALE | SA#91 (03/2021) | 55% | TBD | SA#96 (06/2022) | TR for information at SA#95-e
Study on application enablement aspects for subscriber-aware NB API access | FS_SNAAPP | SA#92 (06/2021) | 65% | TBD | SA#96 (06/2022) | Revised SID at SA6#47-e (Target completion: 06/2022)
Study on Application Capability Exposure for IoT Platforms | FS_ACE_IOT | SA#92 (06/2021) | 40% | TBD | SA#97 (09/2022) | Revised SID at SA6#47-e (Target completion: 09/2022)

## Slide 3: Overview: Ongoing Studies
Study Item | WI Code | SID Approved | SA#94-e | SA6#47-e | Target Completion | Remarks
Study on enhanced Application Architecture for enabling Edge Applications | FS_eEDGEAPP | SA#92 (06/2021) | 45% | TBD | SA#96 (06/2022) | TR for information at SA#95-e?
Study on 5G-enabled fused location service capability exposure | FS_5GFLS | SA#92 (06/2021) | 40% | TBD | SA#97 (09/2022) | Revised SID at SA6#47-e (Target Completion: – Sep 2022, Change in Rapporteur)
Study on enhanced architecture for UAS Applications | FS_eUASAPP | SA#93 (09/2021) | 10% | TBD | SA#97 (09/2022) | Revised SID at SA6#47-e (Alignment with SA2 SID)
Study on SEAL data delivery enabler for vertical applications | FS_SEALDD | SA#93 (09/2021) | 30% | TBD | SA#96 (06/2022) | Target date realistic?
Study on enhancements to application layer support for V2X services; Phase 2 | FS_eV2XAPP2 | SA#93 (09/2021) | 30% | TBD | SA#96 (06/2022) | Target date realistic?

## Slide 4: Overview: Ongoing Studies
Study Item | WI Code | SID Approved | SA#94-e | SA6#47-e | Target Completion | Remarks
Study on Application Data Analytics Enablement Service | FS_ADAES | SA#94 (12/2021) | 0% | TBD | SA#97 (09/2022) | 
Study on Application layer support for Personal IoT and Residential Networks | FS_PIRatesAPP | SA#94 (12/2021) | 0% | TBD | SA#97 (09/2022) | Revised SID at SA6#47-e (Alignment with SA2 SID)
Study on sharing of administrative configuration between interconnected MC service systems | FS_MCShAC | SA#94 (12/2021) | 0% | TBD | SA#99 (03/2023) | 
Study on Mission Critical Ad hoc Group Communications Support for Mission Critical Services | FS_MCAHGC | SA#94 (12/2021) | 0% | TBD | SA#97 (09/2022) | 

## Slide 5: Overview: Rel-18 Work-Items
Study Item | WI Code | WID Approved | SA#94-e | SA6#47-e | Target Completion | Remarks
Mission Critical Services over 5MBS | MCOver5MBS | SA#93 (09/2021) | 30% | TBD | SA#95 (03/2022) | Target completion? Revised WID not needed.
Gateway UE function for Mission Critical Communication | MCGWUE | SA#93 (09/2021) | 50% | TBD | SA#96 (06/2022) | 
Application layer support for Factories of the Future (FF) | FFAPP | SA#93 (09/2021) | 15% | TBD | SA#98 (12/2022) | 
Enhanced Service Enabler Architecture Layer for Verticals Phase 2 | eSEAL2 | SA#94 (12/2021) | 0% | TBD | SA#98 (12/2022) | 
Enhanced Mission Critical Push-to-talk architecture phase 4 | enh4MCPTT | SA#94 (12/2021) | 0% | TBD | SA#99 (03/2023) | 
Mission Critical Services over 5GProSe | MCOver5GProSe | SA#94 (12/2021) | 0% | TBD | SA#99 (03/2023) | 

## Slide 6: Conference calls and other items
Pre-SA6#48-e conference calls
  eEDGEAPP – 2 (date TBD)
  5GFLS/SNAAPP – 1(date TBD)
  MC – 1 (date TBD)
2024 calendar to be prepared
Rapporteurs to make the draft TRs/TSs available within one week!
All pre-agreed/approved revisions MUST be in the inbox folder!
Rapporteurs to provide inputs to Rel-17 WI summaries (TR 21.917)

## Slide 7: SA6 Vice-chair Election
Elections to SA6 Vice-chair position to be held in SA6#48-e meeting
  The VC position is vacant due to election of Mr. Alan Soloway (previously VC) to the Chair position
  Announcement will be made on the SA6 list with further details

## Slide 8: Thank You!