## Slide 1: eLSAPP (SID/WID) Work Plan and TU Tracking
Meeting | TUs Planned |  | Work Planned | TUs Consumed | Work Completed
 | SID | WID |  |  | 
SA6#55 (May-23) | - | - | SID Approval | - | SID Approval completed
SA6#56 (Aug-23) | 0.5TU | - | Skeleton, Scope, Key Issues | 0.5 TU | Finish Skeleton, Scope and 2 key issues
SA6#57 (Oct-23) | 1.0 TU | - | Key Issues, Architecture Requirements, Solutions | 1.0 TU | Finish Architecture Requirements, 2 KI, 3 Solutions
SA6#58 (Nov-23) | 1.0 TU | - | Key Issues, Solutions | 1.0 TU | Finish 1 Solutions, update 3 solutions
SA6#59 (Feb-24) | 1.0 TU |  | Key Issues, Solutions | 0.5 TU | Finish 2 Solutions, update 2 solutions, 1 new KI
SA6#60 (Apr-24) | 1.0 TU | - | Key Issues(Freeze), Solutions, Start Solution Evaluation. |  | 
SA6#61 (May-24) | 0.5 TU | - | Solutions(Freeze), Start Solution Conclusions. Send for Approval, WID Approval |  | 
SA6#62-Adhoc-e (Jul-24) (TBC) | 0.5 TU | 0.5 TUs | Finish Solution Evaluation and Conclusions. Begin Normative work |  | 
SA6#62 (Aug-24) | - | 1.0 TUs | Architecture and Solutions |  | 
SA6#63 (Oct-24) | - | 1.0 TUs | Architecture and Solutions |  | 
SA6#64 (Nov24) | - | 1.0 TUs | Complete unfinished work, Send for Approval. |  | 
Total | 5.5 TUs | 3.5 TUs |  | 3 TUs |