3GPP TSG-SA6 Meeting #66	S6-251023

# Stor-Göteborg, Sweden, 7th Apr 2025 - 11th Apr 2025

Source:	Airbus

Title:	Schedule for Rel-20 MCLOG_Ph2 and MCDISC_Ph2

Spec:	TR 23.700-37, TR 23.700-39, all SA6 MC TSs

Agenda item:	9.1, 9.2

Document for:	Discussion

Contact:	Jukka Vialen (jukka.vialen@airbus.com)

Abstract:

This document provides the overal schedule and status for the Rel-20 SA6 study items and work items related to Recording and Discreet monitoring.

The schedule and target dates are for the SA6 work but status of related SIs/WIs in SA3, SA1 and CT1 is also included.

This document will be updated after every SA6 meeting until the recording and discreet monitoring work items are 100% ready.

The colour coding is: (Green: completed  /  Yellow: ongoing  / No highlight: not yet started)

# Rel-20 overall time plan for Recording and Discreet monitoring

- Feb 17-21

  - SA6#65

    - For agreement: SIDs - agreed

    - For discussion: TR templates, initial review of TR 23.784 for MCLOG_Ph2 - noted

  - SA3#120

    - MC WID proposal from Motorola - S3-250348 – postponed

  - CT1#153

    - Discussion paper from Motorola – C1-250066 -   noted

  - SA1#109

    - nothing

- Mar 12-14 SA plenary#107:

    - SA6 SIDs for approval - SP-250184, SP-250185 - approved

- April 7-11 SA6#66, SA3#121, CT1#154

  - For discussion: Final review of TR 23.784 for MCLOG_Ph2

  - For discussion/information: Initial review of TR 23.784 for MCDISC_Ph2

  - For discussion/action: Review of SA1 requirements -> LS to SA1 if needed

  - For approval (pCRs):

    - TR skeletons + basic clauses to the new TRs

    - First scenarios and key issues ?

- May 19-23 SA6#67, SA3#122, SA1#110

  - For discussion: Final review of TR 23.784 for MCDISC

  - For approval: More scenarios, KIs, solutions, (solution evaluations)

- June 10-13 SA plenary#108		- SA3 Rel-20 MC WID for approval?

- Aug 25-29 SA6#68, SA3#123, SA1#111     - KIs, solutions, solution evaluations

- Sep 16-19 SA#109		- SA6 TR(s) for information (optional), SA6 WI(s) for approval

- Oct 13-17 SA6#69, SA3#124	- Last meeting for solutions/solution evaluations (target: both SIs min 90% complete)

- Nov 17-21 SA6#70, SA3#125, SA1#112	- SA6 SIs 100% complete, First normative CRs based on the agreed solutions

- Dec 9-12 SA plenary#109		- TRs for approval

- Feb 9-13 (2026) SA6#71	- Last normative CRs based on agreed solutions, WIs 100% complete

- Mar 9-13 (2026) SA plenary#110			- WIs declared 100% complete

- April 13-17 (2026) SA6#72		- available for delayed topics and/or corrections

- May 18-22 (2026) SA6#73		- available for delayed topics and/or corrections

- June XX-YY (2026) SA plenary#111	 - Final 3GPP deadline for SA6 Rel-20 5GA work items