## Slide 1: SA6#66 Work Plan Review
Atle Monrad (InterDigital)
SA6 Chair
3GPP TSG-SA WG6 Meeting #66 S6-251489
Gothenburg, Sweden, 7th – 11th April 2025

## Slide 2: Overview: Rel-20 Studies
Study Item | WI Code | SID Approved | SA6#65 | SA6#66 | Target Completion | Remarks
Study on Discreet listening and monitoring of mission critical services, Phase 2 | FS_MCDISC_Ph2 | SA#107 (03/2025) | - | 5% | SA#111 (03/2026) | 
Study on Logging and recording of mission critical services, Phase 2 | FS_MCLOG_Ph2 | SA#107 (03/2025) | - | 5% | SA#111 (03/2026) | 
Study on Service Enabler Architecture Layer (SEAL) Phase 4 | FS_SEAL_Ph4 | SA#105 (09/2024) | 40% | 65% | SA#110 (12/2025) | 
Study on Stage 2 for AI/ML service Phase 2 | FS_AIML_App_Ph2 | SA#107 (03/2025) | - | 20% | SA#110 (12/2025) | 
Study on Application enabler for XR Services Phase 3 | FS_XRM_Ph3_APP | SA#107 (03/2025) | - | 20% | SA#110 (12/2025) | 
Study on Stage 2 for MMTel Phase 2 | FS_MMTel_Ph2_APP | SA#107 (03/2025) | - | 20% | SA#111 (03/2026) | 
Study on SEAL data delivery Phase 3 | FS_SEALDD_Ph3 | SA#107 (03/2025) | - | 25% | SA#110 (12/2025) | 

## Slide 3: Overview: Rel-20 Work-Items
Work Item | WI Code | WID Approved | SA6#65 | SA6-#66 | Target Completion | Remarks
Stage 2 for Enhanced Mission Critical Services Architecture Phase 2 | enhMC_Ph2-MC | SA#107 (03/2025) | - | 5% | SA#112 (06/2026) | 
Stage 2 for FRMCS Phase 6 | FRMCS_Ph6 | SA#107 (03/2025) | - | 15% | SA#112 (06/2026) | 
Stage 2 for Mission Critical Services for UE-to-UE and UE-to-Network over multi-hop relay | MultiHop-MC | SA#107 (03/2025) | - | 75% | SA#111 (03/2026) | 
Stage 2 for mobile metaverse services Phase 2 | Metaverse_Ph2-APP | SA#107 (03/2025) | - | 10% | SA#110 (12/2025) | 

## Slide 4: Conference calls and other items
Rapporteurs to make the draft TRs/TSs available Wednesday April 16th 23:00 UTC
All documents must be uploaded before End-of-Meeting
Pre-SA6#67 conference calls (Dates are TBD) – Maximum 2 hours/call and 1 hour/topic
  Potential Topics
    May 6 (2 hrs) remote device disable / lawful intercept
    Sensing SID (1 hr)
    Cocoa / capif_ph4 (2 hrs)
  Date Exclusions
    ??

## Slide 5: Planning of Rel-20 6G-study phase
At SA#107 the estimated split of the Rel-20 work between 5GA and 6G-study was set to 50/50 for the meetings between Oct-25 and Aug-26.
At SA#107, SA-chair asked for the planning of the SA6-component of the 6G-study for Rel-20.
  Proposed timeline for SA6 Rel-20 6G-study planning :
    No discussions on 6G-study SID(s) in Q2, but 6G-proposals can be provided to SA6#67 for information.
    Discussion and presentation of Rel-20 SID(s) for 6G-study will take place during Q3-25. Similar approach as for Q1-25 on 5GA-work:
      A virtual workshop (June 25-26) on Rel-20 6G SID(s) where companies express their view.
      SA6#68 in August where Rel-20 6G-SID(s) are discussed and agreed.
    Target to have approval of Rel-20 6G SID(s) at SA#109. SA6 can then start the work on Rel-20 6G SID(s) in Q4-25.
    The Rel-20 6G study item completion date is still not decided, Tentative completion is Q4-26 or Q1-27.
Should SA6 revisit the estimated 50/50 split of the Rel-20 work between 5GA and 6G-study?
Should SA6 have the same estimated 50/50 split for features on mission critical and application enablement?

## Slide 6: SA6 meeting schedule
Meeting | Date | Location
2025 |  | 
SA6#66 | 7 – 11 April 2025 | Gothenburg, Sweden
SA6#67 | 19 – 23 May 2025 | Fukuoka, Japan
SA6#68 | 25 – 29 August 2025 | Gothenburg, Sweden
SA6#69 | 13 – 17 October 2025 | China, Location TBC
SA6#70 | 17 – 21 November 2025 | Dallas (TX), USA
2026 |  | 
SA6#71 | 9 – 13 Feb 2025 | India, Location TBC
SA6#72 | 13 – 17 April 2025 | EU, Location TBC
SA6#73 | 18 – 22 May 2025 | Japan, Location TBC
SA6#74 | 24 – 28 August 2025 | EU, Location TBC
SA6#75 | 12 – 16 October 2025 | EU, Location TBC
SA6#76 | 16 – 20 November 2025 | North America, Location TBC

## Slide 7: Thank You!